## Read_Me
CE725 Topic 5: Manual validation workbook
Plain Excel formulas only. Excel recalculates everything here independently of the Python tool.
Colour legend
Yellow cells | Fill in: your hand calculations (paper or calculator) and tool values from scripts/export_validation_values.py
Blue numbers | Inputs typed in (benchmark ranges, finance inputs, activity data)
Green text | Links to another sheet
Black | Formulas: do not overwrite
Order of work
1. T1_PERT | Do the PERT means by hand on paper first, type them in the yellow column, then compare with Excel and the tool.
2. T2_CPM | Do the forward and backward pass by hand for the most-likely case, then compare.
3. T3_MonteCarlo | 5,000-run simulation in Excel with RAND() and BETAINV. Press F9 to re-run; results move slightly each time, which is why tolerances are used.
4. T4_Correlated | Optional: B and D correlated at 0.6 using a hand-built 2x2 Cholesky step. Checks the tool's correlation method.
5. Fin_Inputs + Fin_Activities | Paste your verified finance inputs and activity data (same values as the tool's data folder).
6. Fin_CashFlow | Monthly cash flow, debt, NPV and IRR. Compare with the tool. Then do the hand checks at the bottom by calculator.
7. Scenarios | Set cost multiplier to 1.10 for the flat-10% test (T20), then delay days to 60 for the delay test (T21). Reset to 1 and 0 afterwards.
8. Summary | All results in one place. Copy each into the Validation tab of the tracking workbook, with cause and fix for any Fail.
Updating tool values | After any data change run: python scripts/export_validation_values.py and copy results/validation_tool_values.csv values into the yellow Tool value cells (they are pre-filled for the data the workbook was built with).
Independence | The tool and this workbook were both written with AI help (log this). The hand calculations in the yellow columns are what make this a genuine manual check, so do them yourselves before looking at the Excel column.
Speed | The two simulation sheets recalculate on every edit. If Excel feels slow: Formulas > Calculation Options > Manual, then press F9 when you want to recalculate.

## Summary
Validation summary
Copy each row into the Validation tab of the tracking workbook. Finance rows show the scenario currently set in Fin_Inputs.
Finance scenario now: | Plan
Test | What | Excel | Tool | Difference | Tolerance | Result
T01A | Simulated mean of A vs PERT mean | 4 | 3.9985 | 0.0014951 | 0.02 | Pass
T01B | Simulated mean of B vs PERT mean | 5.3333 | 5.3371 | 0.0037861 | 0.02 | Pass
T01C | Simulated mean of C vs PERT mean | 5.6667 | 5.6653 | 0.0013849 | 0.02 | Pass
T01D | Simulated mean of D vs PERT mean | 5.3333 | 5.3341 | 0.00072969 | 0.02 | Pass
T01E | Simulated mean of E vs PERT mean | 4.3333 | 4.3336 | 0.00027745 | 0.02 | Pass
T01F | Simulated mean of F vs PERT mean | 2 | 2.0001 | 0.00010427 | 0.02 | Pass
T02 | Project duration, most-likely (days) | 16 | 16 | 0 | 0.001 | Pass
T03 | Project duration, PERT on one critical path (days) | 16.6667 | 16.6667 | 0 | 0.001 | Pass
T04 | Mean project duration | 17.1207 | 17.1224 | 0.0017562 | 0.1 | Pass
T05b | P50 project duration | 17.1169 | 17.0981 | 0.018801 | 0.15 | Pass
T05 | P80 project duration | 18.301 | 18.3081 | 0.0070937 | 0.15 | Pass
T05c | P90 project duration | 18.9499 | 18.9447 | 0.0052751 | 0.2 | Pass
T06 | Criticality index of B (share of runs A-B-D-F is longest) | 0.6322 | 0.63011 | 0.00209 | 0.03 | Pass
T09 | Rank correlation of B and D (CORREL of their uniforms) | 0.5841 | 0.5826 | 0.0015003 | 0.03 | Pass
T09b | Mean project duration | 17.2286 | 17.2125 | 0.016079 | 0.1 | Pass
T09c | P80 project duration | 18.5809 | 18.5305 | 0.050409 | 0.15 | Pass
T21a | Project duration (days) [current finance scenario] | 700 | 700 | 0 | 0.0001 | Pass
T15a | Construction cost incl. overheads (Rs lakh) [current finance scenario] | 3777.85 | 3777.85 | 0 | 0.01 | Pass
T15 | Project NPV (Rs lakh) [current finance scenario] | 613.9657 | 613.9657 | 0 | 0.01 | Pass
T15b | Equity NPV (Rs lakh) [current finance scenario] | 313.4826 | 313.4826 | 0 | 0.01 | Pass
T16 | Project IRR (annual) [current finance scenario] | 0.19708 | 0.19708 | 3.0809e-15 | 0.0001 | Pass
T16b | Equity IRR (annual) [current finance scenario] | 0.2062 | 0.2062 | 0 | 0.0001 | Pass
T18 | Interest during construction (Rs lakh) [current finance scenario] | 84.1208 | 84.1208 | 0 | 0.01 | Pass
T18b | Total interest (Rs lakh) [current finance scenario] | 94.1761 | 94.1761 | 0 | 0.01 | Pass
T19 | Peak debt (Rs lakh) [current finance scenario] | 842.6108 | 842.6108 | 0 | 0.01 | Pass
T21b | Compensation to buyers (Rs lakh) [current finance scenario] | 0 | 0 | 0 | 0.01 | Pass
T15c | Undiscounted profit (Rs lakh) [current finance scenario] | 1951.15 | 1951.15 | 0 | 0.01 | Pass
| Pass | 27
| Fail | 0
| Pending | 0

## T1_PERT
T01: PERT means and simulated means (6-activity benchmark)
PERT mean = (O + 4M + P)/6. Fill the yellow hand column from paper BEFORE looking at the Excel column.
Activity | Predecessors | O (days) | M (days) | P (days) | alpha | beta | PERT mean (Excel) | SD (Excel) | Your hand PERT mean | Hand vs Excel | Tool simulated mean | Tool vs Excel | Tolerance | Result
A |  | 2 | 4 | 6 | 3 | 3 | 4 | 0.66667 |  |  | 3.9985 | 0.0014951 | 0.02 | Pass
B | A | 3 | 5 | 9 | 2.3333 | 3.6667 | 5.3333 | 1 |  |  | 5.3371 | 0.0037861 | 0.02 | Pass
C | A | 2 | 6 | 8 | 3.6667 | 2.3333 | 5.6667 | 1 |  |  | 5.6653 | 0.0013849 | 0.02 | Pass
D | B | 4 | 5 | 8 | 2 | 4 | 5.3333 | 0.66667 |  |  | 5.3341 | 0.00072969 | 0.02 | Pass
E | C | 3 | 4 | 7 | 2 | 4 | 4.3333 | 0.66667 |  |  | 4.3336 | 0.00027745 | 0.02 | Pass
F | D;E | 1 | 2 | 3 | 3 | 3 | 2 | 0.33333 |  |  | 2.0001 | 0.00010427 | 0.02 | Pass
Tool values: 200,000 iterations, seed 42, from scripts/export_validation_values.py.

## T2_CPM
T02-T03: Critical path by hand (forward and backward pass)
Network: A first; B then D, and C then E, run in parallel; F needs both D and E.
Most-likely durations
Activity | Duration | ES | EF | LS | LF | Float | Critical?
A | 4 | 0 | 4 | 0 | 4 | 0 | Yes
B | 5 | 4 | 9 | 4 | 9 | 0 | Yes
C | 6 | 4 | 10 | 4 | 10 | 0 | Yes
D | 5 | 9 | 14 | 9 | 14 | 0 | Yes
E | 4 | 10 | 14 | 10 | 14 | 0 | Yes
F | 2 | 14 | 16 | 14 | 16 | 0 | Yes
PERT mean durations
Activity | Duration | ES | EF | LS | LF | Float | Critical?
A | 4 | 0 | 4 | 0 | 4 | 0 | Yes
B | 5.3333 | 4 | 9.3333 | 4 | 9.3333 | 0 | Yes
C | 5.6667 | 4 | 9.6667 | 4.6667 | 10.3333 | 0.66667 | No
D | 5.3333 | 9.3333 | 14.6667 | 9.3333 | 14.6667 | 0 | Yes
E | 4.3333 | 9.6667 | 14 | 10.3333 | 14.6667 | 0.66667 | No
F | 2 | 14.6667 | 16.6667 | 14.6667 | 16.6667 | 0 | Yes
Checks
Test | What | Excel | Your hand value | Tool value | Tolerance | Hand vs Excel | Result
T02 | Project duration, most-likely (days) | 16 |  | 16 | 0.001 |  | Pass
T03 | Project duration, PERT on one critical path (days) | 16.6667 |  | 16.6667 | 0.001 |  | Pass
With most-likely values both paths take 16 days, so every activity is critical. With PERT means, path A-B-D-F is longer. The simulation mean (T3) is higher than both: that gap is merge bias.

## T3_MonteCarlo
T04-T06: Monte Carlo in plain Excel (5,000 runs, activities independent)
Each row is one run: BETAINV(RAND(), alpha, beta, O, P) per activity. Press F9 to re-run.
Test | Measure | Excel (5,000 runs) | Tool (200,000 runs) | Difference | Tolerance | Result
T04 | Mean project duration | 17.1207 | 17.1224 | 0.0017562 | 0.1 | Pass
T05b | P50 project duration | 17.1169 | 17.0981 | 0.018801 | 0.15 | Pass
T05 | P80 project duration | 18.301 | 18.3081 | 0.0070937 | 0.15 | Pass
T05c | P90 project duration | 18.9499 | 18.9447 | 0.0052751 | 0.2 | Pass
T06 | Criticality index of B (share of runs A-B-D-F is longest) | 0.6322 | 0.63011 | 0.00209 | 0.03 | Pass
| Standard deviation of project duration | 1.3982 |  | Excel mean of each activity vs PERT mean (extra check): |  |  | Columns F and G should agree within about 0.05
| Standard error of the Excel mean | 0.019774 |  | A | 3.9999 | 4
| PERT single-path answer (T2) | 16.6667 |  | B | 5.3411 | 5.3333
| Merge bias: simulated mean minus PERT | 0.45399 |  | C | 5.6895 | 5.6667
|  |  |  | D | 5.3384 | 5.3333
|  |  |  | E | 4.3237 | 4.3333
|  |  |  | F | 1.9961 | 2
Run | A | B | C | D | E | F | Path A-B-D-F | Path A-C-E-F | Project | B critical (1/0)
1 | 3.4989 | 4.3526 | 5.0993 | 5.103 | 4.6344 | 1.9399 | 14.8943 | 15.1724 | 15.1724 | 0
2 | 3.6313 | 3.7994 | 3.1344 | 5.8341 | 5.7598 | 1.9619 | 15.2268 | 14.4873 | 15.2268 | 1
3 | 3.7679 | 5.9882 | 6.6829 | 4.3204 | 4.852 | 2.2694 | 16.3459 | 17.5722 | 17.5722 | 0
4 | 4.2957 | 5.041 | 4.5589 | 4.5743 | 5.31 | 2.0228 | 15.9338 | 16.1874 | 16.1874 | 0
5 | 4.4225 | 6.233 | 7.7116 | 5.5373 | 4.2062 | 2.6916 | 18.8844 | 19.0319 | 19.0319 | 0
6 | 4.4389 | 4.4808 | 7.0051 | 5.8753 | 4.3613 | 1.7031 | 16.4981 | 17.5083 | 17.5083 | 0
7 | 3.8198 | 3.2582 | 3.7662 | 4.6593 | 4.108 | 2.0284 | 13.7658 | 13.7224 | 13.7658 | 1
8 | 4.3408 | 4.3871 | 3.7426 | 5.6688 | 3.6857 | 1.8602 | 16.257 | 13.6294 | 16.257 | 1
9 | 3.096 | 6.7556 | 4.8129 | 4.9208 | 5.1956 | 2.0424 | 16.8147 | 15.1469 | 16.8147 | 1
10 | 3.9207 | 3.9056 | 4.0706 | 5.8148 | 4.7994 | 2.5553 | 16.1964 | 15.346 | 16.1964 | 1
11 | 4.0763 | 6.3417 | 3.0366 | 5.8228 | 4.0415 | 1.9332 | 18.1741 | 13.0878 | 18.1741 | 1
12 | 5.1107 | 4.6754 | 3.9562 | 5.158 | 4.7303 | 2.5686 | 17.5127 | 16.3658 | 17.5127 | 1
13 | 3.3727 | 4.7931 | 6.8452 | 5.1549 | 3.9519 | 1.6749 | 14.9955 | 15.8447 | 15.8447 | 0
14 | 3.6622 | 4.2509 | 7.5254 | 4.575 | 5.4753 | 1.3974 | 13.8855 | 18.0602 | 18.0602 | 0
15 | 4.1593 | 5.0822 | 7.0261 | 5.337 | 3.3376 | 2.6416 | 17.2201 | 17.1645 | 17.2201 | 1
16 | 3.8968 | 3.799 | 3.8167 | 4.7203 | 4.0284 | 2.123 | 14.5391 | 13.865 | 14.5391 | 1
17 | 4.1372 | 5.0768 | 7.239 | 5.7957 | 5.1904 | 2.0248 | 17.0344 | 18.5913 | 18.5913 | 0
18 | 3.6224 | 6.4585 | 4.6251 | 4.8653 | 4.9434 | 1.2666 | 16.2129 | 14.4575 | 16.2129 | 1
19 | 3.2745 | 5.6966 | 7.008 | 5.5862 | 4.7857 | 1.5535 | 16.1108 | 16.6216 | 16.6216 | 0
20 | 4.3552 | 4.8957 | 5.4295 | 4.8691 | 4.4014 | 2.0921 | 16.2121 | 16.2782 | 16.2782 | 0
21 | 3.3506 | 3.9578 | 5.1376 | 6.4678 | 4.773 | 1.727 | 15.5032 | 14.9882 | 15.5032 | 1
22 | 4.4119 | 4.9202 | 6.4793 | 5.0267 | 5.5998 | 1.8784 | 16.2373 | 18.3695 | 18.3695 | 0
23 | 4.0533 | 5.9984 | 5.2205 | 5.3172 | 4.8379 | 1.8443 | 17.2132 | 15.956 | 17.2132 | 1
24 | 3.2577 | 5.4586 | 4.7936 | 4.935 | 4.9035 | 2.6487 | 16.3 | 15.6035 | 16.3 | 1
25 | 4.7048 | 5.0592 | 3.9973 | 4.4769 | 3.2492 | 2.2379 | 16.4788 | 14.1891 | 16.4788 | 1
26 | 2.877 | 5.8343 | 5.3728 | 4.7776 | 3.5329 | 2.6406 | 16.1295 | 14.4233 | 16.1295 | 1
27 | 5.3062 | 3.9925 | 6.7262 | 6.1953 | 4.4283 | 2.7131 | 18.2071 | 19.1738 | 19.1738 | 0
28 | 3.326 | 3.9225 | 7.0108 | 4.5422 | 4.6779 | 1.6976 | 13.4882 | 16.7122 | 16.7122 | 0
29 | 3.613 | 3.169 | 6.4806 | 4.9714 | 4.8824 | 1.3892 | 13.1425 | 16.3651 | 16.3651 | 0
30 | 2.3861 | 4.8517 | 6.1768 | 5.1108 | 5.111 | 2.4521 | 14.8007 | 16.126 | 16.126 | 0
31 | 3.6574 | 7.0418 | 5.3531 | 5.5109 | 5.0243 | 1.8965 | 18.1067 | 15.9313 | 18.1067 | 1
32 | 3.8399 | 6.778 | 7.6753 | 4.8583 | 3.5181 | 1.7069 | 17.1831 | 16.7403 | 17.1831 | 1
33 | 5.2117 | 5.0822 | 5.3146 | 4.5066 | 4.1603 | 2.4399 | 17.2405 | 17.1267 | 17.2405 | 1
34 | 3.2765 | 5.2791 | 5.8606 | 4.419 | 3.7506 | 1.7594 | 14.734 | 14.647 | 14.734 | 1
35 | 3.6534 | 6.7365 | 6.9916 | 6.868 | 3.5001 | 1.4822 | 18.7401 | 15.6274 | 18.7401 | 1
36 | 3.3077 | 5.614 | 7.1629 | 5.0134 | 4.0086 | 1.6769 | 15.612 | 16.1561 | 16.1561 | 0
37 | 3.0078 | 3.6356 | 5.9486 | 5.2672 | 5.4973 | 2.5023 | 14.4128 | 16.9559 | 16.9559 | 0
38 | 2.9846 | 3.5821 | 7.0409 | 5.0229 | 5.6127 | 1.74 | 13.3296 | 17.3783 | 17.3783 | 0
39 | 3.3049 | 6.1349 | 6.5697 | 5.204 | 3.3787 | 2.1494 | 16.7932 | 15.4027 | 16.7932 | 1
40 | 4.1694 | 5.1613 | 6.2407 | 5.1737 | 4.8207 | 1.9089 | 16.4133 | 17.1397 | 17.1397 | 0
41 | 2.5552 | 4.5806 | 5.1096 | 5.5481 | 6.1788 | 1.5817 | 14.2657 | 15.4253 | 15.4253 | 0
42 | 3.8781 | 5.459 | 5.7242 | 4.8449 | 5.5236 | 1.5425 | 15.7246 | 16.6685 | 16.6685 | 0
43 | 4.09 | 6.5233 | 6.7367 | 5.859 | 3.409 | 1.634 | 18.1063 | 15.8696 | 18.1063 | 1
44 | 3.3292 | 5.4673 | 4.2707 | 5.1445 | 5.9888 | 1.8763 | 15.8173 | 15.465 | 15.8173 | 1
45 | 4.2676 | 6.4489 | 4.2875 | 5.2961 | 4.1392 | 2.0236 | 18.0362 | 14.718 | 18.0362 | 1
46 | 3.0067 | 6.1059 | 3.365 | 5.5302 | 4.024 | 2.3563 | 16.999 | 12.7519 | 16.999 | 1
47 | 3.4651 | 4.2861 | 6.3794 | 4.7025 | 3.7129 | 1.822 | 14.2757 | 15.3794 | 15.3794 | 0
48 | 3.266 | 5.7209 | 6.5352 | 7.121 | 3.3486 | 1.9806 | 18.0885 | 15.1303 | 18.0885 | 1
49 | 2.52 | 6.3727 | 5.8128 | 4.8821 | 4.6152 | 2.5806 | 16.3555 | 15.5286 | 16.3555 | 1
50 | 2.3306 | 6.2302 | 4.7679 | 5.1842 | 4.7975 | 2.0913 | 15.8362 | 13.9872 | 15.8362 | 1
51 | 3.55 | 4.8946 | 4.8054 | 5.3106 | 3.9331 | 1.8029 | 15.5581 | 14.0914 | 15.5581 | 1
52 | 3.7286 | 5.984 | 5.202 | 4.954 | 5.9133 | 1.5974 | 16.264 | 16.4414 | 16.4414 | 0
53 | 5.202 | 3.6063 | 3.6157 | 6.1554 | 4.9758 | 1.9174 | 16.881 | 15.7109 | 16.881 | 1
54 | 4.8527 | 5.563 | 7.5337 | 6.2878 | 4.041 | 2.0558 | 18.7592 | 18.4832 | 18.7592 | 1
55 | 4.3614 | 6.207 | 4.6476 | 5.494 | 4.7342 | 2.5832 | 18.6456 | 16.3264 | 18.6456 | 1
56 | 3.2548 | 5.6068 | 4.957 | 4.4608 | 4.2033 | 2.0175 | 15.3399 | 14.4327 | 15.3399 | 1
57 | 3.774 | 6.6099 | 6.8254 | 6.208 | 5.6742 | 2.1383 | 18.7303 | 18.4119 | 18.7303 | 1
58 | 3.1336 | 4.9053 | 5.2319 | 6.3212 | 5.226 | 1.8392 | 16.1993 | 15.4307 | 16.1993 | 1
59 | 4.4572 | 5.8388 | 7.2221 | 4.1444 | 3.6958 | 1.5741 | 16.0144 | 16.9491 | 16.9491 | 0
60 | 3.0523 | 5.8104 | 6.072 | 4.2269 | 3.6806 | 2.0966 | 15.1862 | 14.9016 | 15.1862 | 1
61 | 4.385 | 3.8619 | 5.1043 | 6.2118 | 4.2891 | 1.7041 | 16.1628 | 15.4824 | 16.1628 | 1
62 | 4.332 | 6.2047 | 5.7196 | 6.1825 | 4.5994 | 2.2865 | 19.0057 | 16.9374 | 19.0057 | 1
63 | 3.8493 | 5.2088 | 4.5775 | 5.3126 | 4.0456 | 1.4934 | 15.8641 | 13.9658 | 15.8641 | 1
64 | 4.8673 | 4.8233 | 5.0461 | 5.3117 | 4.0205 | 2.2201 | 17.2225 | 16.154 | 17.2225 | 1
65 | 5.1406 | 4.2024 | 4.2454 | 5.6049 | 3.099 | 1.8582 | 16.8061 | 14.3432 | 16.8061 | 1
66 | 3.7806 | 6.3544 | 5.1344 | 4.8422 | 4.2468 | 1.6615 | 16.6387 | 14.8233 | 16.6387 | 1
67 | 4.0776 | 4.6159 | 7.2648 | 5.6864 | 4.1415 | 2.5841 | 16.964 | 18.068 | 18.068 | 0
68 | 3.6885 | 6.2465 | 6.3151 | 4.661 | 3.9184 | 1.7855 | 16.3814 | 15.7075 | 16.3814 | 1
69 | 4.3671 | 4.3832 | 6.3186 | 5.6951 | 4.9066 | 1.5549 | 16.0003 | 17.1472 | 17.1472 | 0
70 | 4.2037 | 4.3 | 5.0384 | 6.5675 | 3.5015 | 2.1793 | 17.2504 | 14.9228 | 17.2504 | 1
71 | 5.0791 | 6.0341 | 5.8727 | 5.7638 | 3.4837 | 2.2836 | 19.1606 | 16.7192 | 19.1606 | 1
72 | 3.782 | 3.6856 | 4.8833 | 5.9775 | 5.2479 | 2.2467 | 15.6919 | 16.1599 | 16.1599 | 0
73 | 3.1743 | 5.1849 | 6.8049 | 4.4926 | 3.4042 | 2.0016 | 14.8535 | 15.3851 | 15.3851 | 0
74 | 3.9306 | 6.0705 | 5.9805 | 4.5413 | 4.7628 | 2.3024 | 16.8448 | 16.9763 | 16.9763 | 0
75 | 3.691 | 3.397 | 6.4791 | 5.618 | 3.4323 | 1.2579 | 13.964 | 14.8604 | 14.8604 | 0
76 | 3.6742 | 6.7369 | 6.2367 | 4.4373 | 4.1402 | 2.1374 | 16.9858 | 16.1885 | 16.9858 | 1
77 | 3.6172 | 4.6101 | 6.731 | 6.3496 | 3.4967 | 1.9933 | 16.5702 | 15.8381 | 16.5702 | 1
78 | 2.9494 | 5.7623 | 4.0598 | 6.5674 | 3.623 | 1.4137 | 16.6928 | 12.0458 | 16.6928 | 1
79 | 3.036 | 6.6779 | 6.6612 | 7.2715 | 4.6488 | 1.6856 | 18.671 | 16.0316 | 18.671 | 1
80 | 3.4514 | 4.7619 | 7.0132 | 5.0354 | 4.7993 | 2.527 | 15.7757 | 17.7909 | 17.7909 | 0
81 | 3.8618 | 6.2473 | 5.2797 | 5.0547 | 5.3231 | 2.1349 | 17.2989 | 16.5997 | 17.2989 | 1
82 | 5.1741 | 6.4769 | 6.658 | 6.5427 | 5.9511 | 1.8951 | 20.0886 | 19.6783 | 20.0886 | 1
83 | 5.2947 | 5.2907 | 6.0907 | 4.7933 | 3.4903 | 1.8283 | 17.2071 | 16.7041 | 17.2071 | 1
84 | 4.0243 | 4.4495 | 4.8544 | 5.8815 | 3.4274 | 2.5602 | 16.9154 | 14.8663 | 16.9154 | 1
85 | 4.6613 | 6.3376 | 6.7448 | 4.1719 | 4.1711 | 2.268 | 17.4389 | 17.8452 | 17.8452 | 0
86 | 3.3116 | 6.237 | 4.5831 | 4.3396 | 4.5066 | 2.0759 | 15.9641 | 14.4772 | 15.9641 | 1
87 | 3.6221 | 4.3911 | 7.2936 | 5.2595 | 3.7442 | 2.6557 | 15.9285 | 17.3157 | 17.3157 | 0
88 | 2.3726 | 6.6483 | 4.6284 | 4.6593 | 4.0582 | 1.31 | 14.9902 | 12.3692 | 14.9902 | 1
89 | 4.8637 | 4.1705 | 6.6124 | 6.5237 | 3.8216 | 1.7683 | 17.3261 | 17.066 | 17.3261 | 1
90 | 3.6812 | 4.8132 | 4.7557 | 5.7282 | 4.3986 | 2.0508 | 16.2734 | 14.8862 | 16.2734 | 1
91 | 3.9342 | 6.8248 | 7.229 | 4.8848 | 3.443 | 1.199 | 16.8428 | 15.8052 | 16.8428 | 1
92 | 3.9188 | 7.1147 | 4.0644 | 5.4376 | 5.6126 | 1.3166 | 17.7877 | 14.9124 | 17.7877 | 1
93 | 3.4381 | 5.3354 | 5.7949 | 5.2004 | 3.8184 | 2.0246 | 15.9985 | 15.076 | 15.9985 | 1
94 | 3.7641 | 5.5132 | 7.0699 | 6.0418 | 3.2862 | 2.4125 | 17.7317 | 16.5328 | 17.7317 | 1
95 | 4.0172 | 4.0722 | 5.6059 | 6.472 | 4.2698 | 2.1745 | 16.7359 | 16.0673 | 16.7359 | 1
96 | 4.8561 | 4.4475 | 7.1962 | 5.319 | 4.4564 | 2.2258 | 16.8484 | 18.7345 | 18.7345 | 0
97 | 4.3936 | 5.2683 | 6.6727 | 5.019 | 3.704 | 1.6004 | 16.2813 | 16.3707 | 16.3707 | 0
98 | 4.2485 | 4.1297 | 3.9265 | 4.292 | 3.8341 | 2.0601 | 14.7303 | 14.0692 | 14.7303 | 1
99 | 3.4217 | 3.175 | 5.4821 | 4.2922 | 4.4565 | 2.1628 | 13.0517 | 15.5231 | 15.5231 | 0
100 | 3.5921 | 4.7147 | 6.3054 | 6.5693 | 3.1999 | 1.6014 | 16.4775 | 14.6988 | 16.4775 | 1
101 | 4.8618 | 4.8627 | 4.9403 | 5.3587 | 3.5123 | 2.3325 | 17.4158 | 15.6469 | 17.4158 | 1
102 | 4.8837 | 7.0233 | 5.5311 | 4.9771 | 4.268 | 2.527 | 19.4111 | 17.2098 | 19.4111 | 1
103 | 3.6658 | 5.6014 | 6.5126 | 4.2848 | 3.9508 | 1.9613 | 15.5133 | 16.0906 | 16.0906 | 0
104 | 3.8768 | 7.3956 | 5.7546 | 4.6813 | 4.1802 | 2.2382 | 18.1918 | 16.0497 | 18.1918 | 1
105 | 4.8342 | 6.6373 | 4.0023 | 5.8467 | 5.7308 | 1.9716 | 19.2898 | 16.5388 | 19.2898 | 1
106 | 4.0811 | 7.6618 | 5.5967 | 5.7034 | 3.338 | 1.8734 | 19.3198 | 14.8892 | 19.3198 | 1
107 | 4.1952 | 6.8218 | 3.3156 | 5.4039 | 4.3428 | 2.558 | 18.9788 | 14.4115 | 18.9788 | 1
108 | 4.8134 | 5.8346 | 6.1064 | 5.082 | 3.4471 | 2.6838 | 18.4138 | 17.0506 | 18.4138 | 1
109 | 4.5549 | 6.136 | 5.7067 | 5.6542 | 4.6004 | 2.1292 | 18.4743 | 16.9912 | 18.4743 | 1
110 | 2.7958 | 4.5922 | 5.5546 | 4.5785 | 3.6112 | 1.9478 | 13.9143 | 13.9094 | 13.9143 | 1
111 | 4.8032 | 4.7313 | 4.3807 | 4.503 | 5.8135 | 1.4996 | 15.5371 | 16.497 | 16.497 | 0
112 | 3.7955 | 6.0761 | 6.0735 | 4.4697 | 3.8788 | 1.5721 | 15.9135 | 15.3198 | 15.9135 | 1
113 | 4.1171 | 4.0154 | 3.7227 | 4.9222 | 3.1709 | 1.4278 | 14.4825 | 12.4385 | 14.4825 | 1
114 | 2.5392 | 3.3285 | 6.1236 | 4.4637 | 4.7485 | 2.1413 | 12.4728 | 15.5526 | 15.5526 | 0
115 | 3.2111 | 4.9772 | 5.7964 | 6.0727 | 4.769 | 1.7247 | 15.9856 | 15.5012 | 15.9856 | 1
116 | 3.9263 | 5.4028 | 6.6166 | 4.737 | 4.3782 | 1.8449 | 15.911 | 16.766 | 16.766 | 0
117 | 3.8212 | 6.9456 | 6.1629 | 4.9632 | 4.5574 | 2.3236 | 18.0536 | 16.865 | 18.0536 | 1
118 | 4.125 | 5.6686 | 3.7573 | 6.4386 | 3.5654 | 1.2558 | 17.488 | 12.7035 | 17.488 | 1
119 | 2.5624 | 4.6189 | 6.5808 | 5.3132 | 3.3864 | 2.6222 | 15.1166 | 15.1517 | 15.1517 | 0
120 | 4.4619 | 5.8329 | 5.6866 | 5.2381 | 4.1617 | 1.7288 | 17.2617 | 16.039 | 17.2617 | 1
121 | 3.4444 | 5.8972 | 6.5168 | 5.673 | 4.0166 | 1.6378 | 16.6524 | 15.6156 | 16.6524 | 1
122 | 4.7473 | 4.3027 | 3.7225 | 4.0373 | 3.9717 | 2.1647 | 15.2519 | 14.6061 | 15.2519 | 1
123 | 4.8499 | 4.1674 | 5.9051 | 4.9494 | 5.4705 | 2.1216 | 16.0882 | 18.347 | 18.347 | 0
124 | 4.8156 | 4.739 | 7.0633 | 7.0563 | 4.5317 | 2.8644 | 19.4753 | 19.2751 | 19.4753 | 1
125 | 3.0642 | 5.3277 | 6.0266 | 5.1131 | 4.9799 | 2.3769 | 15.8819 | 16.4476 | 16.4476 | 0
126 | 2.613 | 5.7801 | 4.3823 | 4.8008 | 4.7917 | 1.5113 | 14.7052 | 13.2982 | 14.7052 | 1
127 | 3.1312 | 5.6379 | 7.5746 | 5.6677 | 4.0692 | 1.317 | 15.7538 | 16.092 | 16.092 | 0
128 | 5.2475 | 5.0785 | 6.1076 | 5.8004 | 5.9589 | 1.4346 | 17.561 | 18.7486 | 18.7486 | 0
129 | 5.1701 | 4.7718 | 3.933 | 4.3848 | 4.5476 | 1.9175 | 16.2442 | 15.5681 | 16.2442 | 1
130 | 3.3805 | 4.5175 | 6.5812 | 5.5275 | 3.8657 | 2.4282 | 15.8538 | 16.2557 | 16.2557 | 0
131 | 4.6439 | 4.1771 | 6.4469 | 5.2377 | 3.5776 | 1.6469 | 15.7056 | 16.3153 | 16.3153 | 0
132 | 3.8583 | 4.9428 | 7.3896 | 6.1604 | 3.8654 | 2.4504 | 17.4119 | 17.5636 | 17.5636 | 0
133 | 4.0313 | 3.5109 | 7.0084 | 6.644 | 4.3399 | 2.44 | 16.6262 | 17.8196 | 17.8196 | 0
134 | 4.6445 | 3.2755 | 5.6802 | 4.3546 | 3.7558 | 1.4332 | 13.7078 | 15.5137 | 15.5137 | 0
135 | 4.4875 | 5.3182 | 6.0691 | 5.6166 | 4.1672 | 1.3795 | 16.8018 | 16.1032 | 16.8018 | 1
136 | 3.4855 | 3.6703 | 5.1204 | 4.7111 | 3.2196 | 2.022 | 13.8889 | 13.8477 | 13.8889 | 1
137 | 3.3463 | 5.9987 | 6.1042 | 5.8223 | 4.0171 | 1.5408 | 16.7082 | 15.0084 | 16.7082 | 1
138 | 3.0819 | 6.2759 | 5.9933 | 5.065 | 4.0633 | 1.5485 | 15.9713 | 14.687 | 15.9713 | 1
139 | 3.5894 | 6.474 | 5.3525 | 5.9183 | 4.2345 | 2.6449 | 18.6266 | 15.8213 | 18.6266 | 1
140 | 3.2246 | 5.1784 | 4.4579 | 6.1456 | 3.8143 | 2.4216 | 16.9702 | 13.9184 | 16.9702 | 1
141 | 2.7191 | 5.7477 | 6.013 | 4.39 | 4.5353 | 2.0408 | 14.8976 | 15.3082 | 15.3082 | 0
142 | 4.8476 | 5.0199 | 5.2053 | 5.5127 | 4.6569 | 2.2417 | 17.6219 | 16.9515 | 17.6219 | 1
143 | 3.5936 | 4.2409 | 6.626 | 4.9173 | 3.2151 | 2.267 | 15.0188 | 15.7017 | 15.7017 | 0
144 | 4.0802 | 5.8951 | 5.9488 | 4.9638 | 5.7211 | 2.0792 | 17.0183 | 17.8293 | 17.8293 | 0
145 | 2.9064 | 5.884 | 5.6055 | 4.7889 | 4.1606 | 2.1798 | 15.7591 | 14.8523 | 15.7591 | 1
146 | 4.6308 | 3.6885 | 5.2738 | 4.6877 | 4.7326 | 2.2535 | 15.2605 | 16.8906 | 16.8906 | 0
147 | 4.4879 | 4.1621 | 5.7916 | 5.1369 | 4.1285 | 2.01 | 15.7969 | 16.418 | 16.418 | 0
148 | 3.8409 | 6.6338 | 4.2917 | 5.1619 | 3.1666 | 2.7416 | 18.3783 | 14.0408 | 18.3783 | 1
149 | 4.9764 | 6.4272 | 6.9462 | 5.6007 | 3.2149 | 1.2218 | 18.2262 | 16.3593 | 18.2262 | 1
150 | 4.492 | 5.1727 | 6.5775 | 4.2782 | 5.0801 | 1.5762 | 15.5192 | 17.7258 | 17.7258 | 0
151 | 4.4858 | 6.0804 | 4.6508 | 5.369 | 4.2728 | 2.7929 | 18.728 | 16.2023 | 18.728 | 1
152 | 4.1286 | 5.0347 | 6.2867 | 4.4521 | 4.6811 | 2.3173 | 15.9327 | 17.4136 | 17.4136 | 0
153 | 2.9121 | 5.3276 | 3.9298 | 4.9373 | 4.6392 | 2.1025 | 15.2796 | 13.5837 | 15.2796 | 1
154 | 4.0776 | 3.8533 | 5.8374 | 4.939 | 4.0481 | 1.4434 | 14.3134 | 15.4066 | 15.4066 | 0
155 | 4.7173 | 5.7495 | 4.3126 | 4.9985 | 5.524 | 1.4132 | 16.8784 | 15.967 | 16.8784 | 1
156 | 4.8901 | 6.6245 | 5.614 | 5.5827 | 3.8384 | 2.0568 | 19.1541 | 16.3992 | 19.1541 | 1
157 | 3.578 | 3.6302 | 7.2213 | 6.3084 | 3.91 | 1.752 | 15.2685 | 16.4613 | 16.4613 | 0
158 | 4.1331 | 6.0851 | 4.6208 | 7.1788 | 5.1952 | 1.6514 | 19.0484 | 15.6004 | 19.0484 | 1
159 | 4.6212 | 7.8766 | 5.2049 | 4.4116 | 3.8061 | 1.6342 | 18.5436 | 15.2664 | 18.5436 | 1
160 | 2.6011 | 5.0239 | 6.8229 | 4.9023 | 3.878 | 2.08 | 14.6073 | 15.382 | 15.382 | 0
161 | 3.5837 | 6.6215 | 6.0219 | 5.2523 | 5.8834 | 1.6758 | 17.1333 | 17.1648 | 17.1648 | 0
162 | 2.5753 | 5.6295 | 6.0657 | 5.7895 | 5.1237 | 1.6869 | 15.6812 | 15.4517 | 15.6812 | 1
163 | 4.3361 | 4.9593 | 3.4811 | 5.2163 | 3.4464 | 2.0591 | 16.5708 | 13.3227 | 16.5708 | 1
164 | 3.2054 | 5.7473 | 4.0095 | 5.4085 | 3.8074 | 1.9869 | 16.3481 | 13.0092 | 16.3481 | 1
165 | 3.3547 | 5.8884 | 5.7651 | 5.7412 | 4.82 | 2.0503 | 17.0347 | 15.9901 | 17.0347 | 1
166 | 5.3825 | 6.4525 | 7.383 | 4.6102 | 4.2071 | 2.1664 | 18.6116 | 19.139 | 19.139 | 0
167 | 3.1061 | 7.5847 | 5.937 | 4.8346 | 3.5968 | 1.8002 | 17.3257 | 14.4402 | 17.3257 | 1
168 | 4.4258 | 4.5013 | 4.5916 | 5.952 | 4.5531 | 2.1807 | 17.0598 | 15.7511 | 17.0598 | 1
169 | 3.1473 | 5.2922 | 5.0642 | 5.4742 | 5.4627 | 1.7008 | 15.6145 | 15.375 | 15.6145 | 1
170 | 4.1809 | 5.7812 | 7.1979 | 4.1378 | 5.3337 | 2.0479 | 16.1478 | 18.7605 | 18.7605 | 0
171 | 3.6088 | 7.1516 | 5.4983 | 4.2673 | 5.507 | 2.4207 | 17.4484 | 17.0348 | 17.4484 | 1
172 | 3.0974 | 3.4859 | 5.3571 | 5.2142 | 4.3304 | 2.5531 | 14.3507 | 15.3381 | 15.3381 | 0
173 | 3.0325 | 6.5622 | 6.8777 | 7.3928 | 4.3398 | 2.5871 | 19.5746 | 16.8371 | 19.5746 | 1
174 | 3.504 | 4.3844 | 6.4884 | 4.28 | 3.7473 | 1.6704 | 13.8388 | 15.4102 | 15.4102 | 0
175 | 3.8563 | 6.5446 | 3.3506 | 5.1063 | 3.9297 | 2.3553 | 17.8626 | 13.4919 | 17.8626 | 1
176 | 4.0336 | 5.3008 | 3.7523 | 4.5653 | 5.1987 | 1.9106 | 15.8103 | 14.8952 | 15.8103 | 1
177 | 2.7169 | 6.3424 | 4.9415 | 5.2052 | 4.8232 | 2.3997 | 16.6642 | 14.8814 | 16.6642 | 1
178 | 3.7373 | 4.0681 | 4.6246 | 5.5148 | 4.0073 | 2.1174 | 15.4376 | 14.4866 | 15.4376 | 1
179 | 2.9431 | 7.4527 | 4.3024 | 5.7335 | 5.5503 | 1.2573 | 17.3866 | 14.0531 | 17.3866 | 1
180 | 3.4433 | 4.0526 | 4.9045 | 4.8943 | 4.0233 | 2.4352 | 14.8255 | 14.8064 | 14.8255 | 1
181 | 4.3842 | 6.4748 | 3.3434 | 4.2376 | 3.7149 | 1.8441 | 16.9407 | 13.2866 | 16.9407 | 1
182 | 2.5854 | 4.3003 | 5.8368 | 5.3561 | 3.9972 | 1.6076 | 13.8495 | 14.0271 | 14.0271 | 0
183 | 3.4064 | 5.1369 | 6.6027 | 5.2578 | 4.4145 | 1.6222 | 15.4232 | 16.0458 | 16.0458 | 0
184 | 3.5128 | 5.7301 | 7.1549 | 4.2885 | 4.2764 | 2.4131 | 15.9446 | 17.3572 | 17.3572 | 0
185 | 4.2658 | 4.0977 | 6.1189 | 4.5622 | 5.5591 | 1.9073 | 14.8329 | 17.8511 | 17.8511 | 0
186 | 3.9751 | 5.0721 | 4.2765 | 4.7142 | 4.6925 | 2.0276 | 15.789 | 14.9717 | 15.789 | 1
187 | 3.5771 | 5.8103 | 6.2233 | 5.7344 | 4.6905 | 2.2775 | 17.3993 | 16.7684 | 17.3993 | 1
188 | 4.4323 | 5.7124 | 5.1343 | 5.5718 | 4.3057 | 1.8585 | 17.5749 | 15.7307 | 17.5749 | 1
189 | 5.1687 | 4.5587 | 6.6057 | 5.6444 | 4.667 | 2.1175 | 17.4894 | 18.559 | 18.559 | 0
190 | 5.2946 | 5.1152 | 7.3177 | 4.5279 | 4.6201 | 2.2405 | 17.1781 | 19.4729 | 19.4729 | 0
191 | 3.3111 | 3.8158 | 2.6791 | 4.6452 | 3.0368 | 2.4417 | 14.2136 | 11.4686 | 14.2136 | 1
192 | 3.8742 | 8.2498 | 7.1903 | 5.031 | 4.5536 | 1.7786 | 18.9337 | 17.3968 | 18.9337 | 1
193 | 4.2198 | 5.8366 | 5.2727 | 4.8876 | 4.258 | 1.6761 | 16.62 | 15.4266 | 16.62 | 1
194 | 3.6908 | 5.3026 | 6.211 | 4.4676 | 5.1801 | 1.9276 | 15.3886 | 17.0095 | 17.0095 | 0
195 | 2.611 | 6.2262 | 7.3415 | 5.0602 | 5.569 | 1.976 | 15.8735 | 17.4974 | 17.4974 | 0
196 | 3.1897 | 5.0734 | 5.3439 | 6.047 | 3.3637 | 1.5369 | 15.847 | 13.4343 | 15.847 | 1
197 | 4.9 | 3.8061 | 5.0799 | 4.4741 | 3.4853 | 1.8491 | 15.0293 | 15.3143 | 15.3143 | 0
198 | 4.3032 | 5.2045 | 7.0741 | 6.2173 | 3.1609 | 1.4267 | 17.1517 | 15.9649 | 17.1517 | 1
199 | 3.3866 | 6.7905 | 4.2576 | 5.9184 | 3.527 | 1.4492 | 17.5447 | 12.6204 | 17.5447 | 1
200 | 3.7229 | 5.8323 | 5.391 | 5.1168 | 3.3784 | 1.6258 | 16.2977 | 14.1181 | 16.2977 | 1
201 | 4.0709 | 6.804 | 7.0641 | 5.0129 | 5.7595 | 1.6117 | 17.4995 | 18.5062 | 18.5062 | 0
202 | 3.9537 | 5.2745 | 6.2601 | 5.7176 | 4.0898 | 1.8625 | 16.8083 | 16.1661 | 16.8083 | 1
203 | 4.531 | 6.9736 | 3.8115 | 5.2079 | 5.0773 | 2.1288 | 18.8414 | 15.5487 | 18.8414 | 1
204 | 3.6697 | 5.1268 | 4.2689 | 6.4136 | 3.6924 | 2.0837 | 17.2938 | 13.7147 | 17.2938 | 1
205 | 5.2503 | 6.8017 | 7.3114 | 6.0238 | 6.2253 | 1.8989 | 19.9747 | 20.6859 | 20.6859 | 0
206 | 4.3157 | 5.201 | 5.3715 | 4.855 | 3.3268 | 2.0455 | 16.4173 | 15.0596 | 16.4173 | 1
207 | 3.6211 | 4.7982 | 5.1633 | 5.6389 | 3.8991 | 1.9621 | 16.0202 | 14.6455 | 16.0202 | 1
208 | 2.7686 | 6.4224 | 5.3182 | 5.8236 | 3.4561 | 1.693 | 16.7077 | 13.2359 | 16.7077 | 1
209 | 5.5254 | 4.1732 | 5.6788 | 5.2439 | 4.832 | 2.1016 | 17.0441 | 18.1378 | 18.1378 | 0
210 | 3.1566 | 4.5656 | 5.0802 | 4.655 | 4.7949 | 1.8825 | 14.2596 | 14.9142 | 14.9142 | 0
211 | 4.9238 | 7.0625 | 6.6666 | 4.1848 | 4.1254 | 2.1004 | 18.2716 | 17.8162 | 18.2716 | 1
212 | 3.3741 | 5.0156 | 5.9087 | 4.9951 | 4.0899 | 2.1483 | 15.533 | 15.521 | 15.533 | 1
213 | 4.74 | 4.1554 | 6.9046 | 5.5107 | 3.9741 | 2.2481 | 16.6542 | 17.8668 | 17.8668 | 0
214 | 4.8659 | 5.9896 | 4.3768 | 5.4545 | 4.7582 | 2.0551 | 18.3651 | 16.0559 | 18.3651 | 1
215 | 4.2469 | 5.0111 | 5.5631 | 4.9509 | 5.2956 | 1.6798 | 15.8888 | 16.7854 | 16.7854 | 0
216 | 3.1995 | 5.0427 | 6.1187 | 5.2791 | 3.1812 | 2.348 | 15.8694 | 14.8474 | 15.8694 | 1
217 | 4.5276 | 5.2415 | 7.3059 | 5.1161 | 3.6815 | 2.1852 | 17.0704 | 17.7003 | 17.7003 | 0
218 | 5.0954 | 6.3724 | 4.5053 | 6.0986 | 3.6762 | 2.1854 | 19.7518 | 15.4623 | 19.7518 | 1
219 | 4.5031 | 6.2133 | 3.2318 | 5.4442 | 4.1461 | 1.9962 | 18.1568 | 13.8772 | 18.1568 | 1
220 | 4.8366 | 6.9921 | 5.0781 | 6.3164 | 3.6113 | 1.502 | 19.6472 | 15.028 | 19.6472 | 1
221 | 3.1109 | 5.1421 | 5.8442 | 4.1993 | 4.3113 | 2.3369 | 14.7892 | 15.6032 | 15.6032 | 0
222 | 3.374 | 5.6888 | 5.2261 | 5.5694 | 4.3403 | 2.0044 | 16.6365 | 14.9448 | 16.6365 | 1
223 | 4.3015 | 5.7205 | 3.5328 | 6.1105 | 5.9171 | 2.0365 | 18.1691 | 15.7879 | 18.1691 | 1
224 | 4.3628 | 5.7444 | 6.7019 | 5.9178 | 3.5657 | 2.1053 | 18.1302 | 16.7357 | 18.1302 | 1
225 | 4.8776 | 5.1461 | 6.0619 | 4.766 | 5.1111 | 1.6063 | 16.3961 | 17.6569 | 17.6569 | 0
226 | 2.9837 | 4.8704 | 7.6373 | 6.0115 | 4.9692 | 2.3887 | 16.2542 | 17.9789 | 17.9789 | 0
227 | 4.3665 | 6.6055 | 5.9225 | 6.1838 | 3.9625 | 1.9013 | 19.0571 | 16.1528 | 19.0571 | 1
228 | 4.3542 | 4.7197 | 7.6823 | 5.3557 | 4.9816 | 1.6091 | 16.0387 | 18.6272 | 18.6272 | 0
229 | 3.8602 | 3.9152 | 5.6857 | 4.3963 | 4.1667 | 2.5915 | 14.7632 | 16.3041 | 16.3041 | 0
230 | 4.1416 | 4.9594 | 7.011 | 6.1674 | 3.2729 | 1.9203 | 17.1887 | 16.3459 | 17.1887 | 1
231 | 4.2028 | 6.7576 | 7.0182 | 5.7246 | 3.7436 | 2.42 | 19.105 | 17.3846 | 19.105 | 1
232 | 2.8816 | 5.1283 | 5.853 | 6.8095 | 4.2639 | 2.041 | 16.8604 | 15.0395 | 16.8604 | 1
233 | 4.9635 | 6.7121 | 7.2444 | 4.5099 | 4.5523 | 2.4116 | 18.5971 | 19.1717 | 19.1717 | 0
234 | 2.7912 | 5.7795 | 4.0738 | 6.0989 | 3.4372 | 1.6223 | 16.292 | 11.9245 | 16.292 | 1
235 | 3.8201 | 7.1331 | 3.8947 | 5.2083 | 4.3618 | 2.1706 | 18.3321 | 14.2472 | 18.3321 | 1
236 | 3.556 | 6.3084 | 3.5188 | 4.2809 | 4.2025 | 1.3508 | 15.496 | 12.628 | 15.496 | 1
237 | 3.7917 | 7.2524 | 6.4766 | 5.1943 | 5.9192 | 1.8044 | 18.0429 | 17.992 | 18.0429 | 1
238 | 4.531 | 5.1126 | 7.1664 | 4.738 | 4.537 | 1.8621 | 16.2437 | 18.0965 | 18.0965 | 0
239 | 4.7319 | 5.333 | 6.4777 | 6.5559 | 3.7159 | 2.0628 | 18.6836 | 16.9883 | 18.6836 | 1
240 | 4.8781 | 6.2752 | 6.0225 | 4.9527 | 3.9325 | 2.5162 | 18.6222 | 17.3494 | 18.6222 | 1
241 | 4.121 | 4.2337 | 5.9379 | 4.7523 | 3.5491 | 1.4491 | 14.5561 | 15.0571 | 15.0571 | 0
242 | 3.7068 | 6.8508 | 4.3141 | 4.9019 | 3.4418 | 1.4947 | 16.9541 | 12.9573 | 16.9541 | 1
243 | 2.9965 | 4.2914 | 4.4177 | 5.9259 | 3.454 | 1.9722 | 15.1859 | 12.8404 | 15.1859 | 1
244 | 5.4734 | 4.647 | 4.7226 | 5.8532 | 3.9243 | 1.483 | 17.4566 | 15.6034 | 17.4566 | 1
245 | 4.4635 | 7.3167 | 6.9626 | 6.2819 | 3.7312 | 1.6795 | 19.7417 | 16.8369 | 19.7417 | 1
246 | 5.4877 | 6.7899 | 5.2937 | 4.185 | 3.1846 | 2.4115 | 18.8741 | 16.3775 | 18.8741 | 1
247 | 5.6199 | 5.2139 | 6.8318 | 4.7659 | 4.9651 | 1.7223 | 17.322 | 19.1391 | 19.1391 | 0
248 | 3.7073 | 6.1167 | 5.7412 | 4.8373 | 4.4688 | 1.4219 | 16.0832 | 15.3392 | 16.0832 | 1
249 | 4.3225 | 7.3117 | 4.4378 | 4.7637 | 3.4811 | 2.3364 | 18.7342 | 14.5777 | 18.7342 | 1
250 | 5.1222 | 5.1898 | 6.1882 | 6.3632 | 4.0735 | 1.9273 | 18.6024 | 17.3112 | 18.6024 | 1
251 | 3.9066 | 5.9822 | 4.8782 | 4.4113 | 5.0231 | 1.207 | 15.5071 | 15.0149 | 15.5071 | 1
252 | 4.9706 | 6.4854 | 7.031 | 4.3911 | 3.6515 | 2.476 | 18.3231 | 18.1291 | 18.3231 | 1
253 | 3.7217 | 6.8472 | 4.4761 | 4.8393 | 4.3675 | 1.9669 | 17.3751 | 14.5321 | 17.3751 | 1
254 | 2.8727 | 5.929 | 6.2272 | 4.9539 | 3.8747 | 2.3413 | 16.0969 | 15.3158 | 16.0969 | 1
255 | 4.4864 | 5.5313 | 4.9498 | 5.1225 | 3.9902 | 2.452 | 17.5922 | 15.8783 | 17.5922 | 1
256 | 5.3881 | 4.8801 | 6.3988 | 5.6282 | 3.2664 | 1.7424 | 17.6388 | 16.7957 | 17.6388 | 1
257 | 4.0352 | 3.8924 | 6.0681 | 5.8639 | 4.1165 | 1.7632 | 15.5547 | 15.983 | 15.983 | 0
258 | 3.8288 | 4.8464 | 5.4014 | 5.2981 | 4.9323 | 1.6706 | 15.6438 | 15.833 | 15.833 | 0
259 | 3.4183 | 4.7247 | 5.5888 | 4.1689 | 5.3908 | 1.6637 | 13.9757 | 16.0615 | 16.0615 | 0
260 | 4.6795 | 4.9123 | 6.8609 | 6.9386 | 3.7451 | 2.6859 | 19.2163 | 17.9714 | 19.2163 | 1
261 | 4.575 | 6.2952 | 6.9456 | 5.8615 | 4.1816 | 1.194 | 17.9257 | 16.8962 | 17.9257 | 1
262 | 3.9027 | 4.0084 | 4.9458 | 4.9071 | 3.8571 | 2.374 | 15.1922 | 15.0796 | 15.1922 | 1
263 | 4.9665 | 5.8653 | 6.2919 | 5.1514 | 4.2147 | 2.3402 | 18.3233 | 17.8133 | 18.3233 | 1
264 | 3.8734 | 5.4373 | 5.916 | 4.9153 | 3.8164 | 2.0888 | 16.3148 | 15.6946 | 16.3148 | 1
265 | 4.3131 | 6.8424 | 4.7951 | 6.1962 | 5.3734 | 1.8292 | 19.1809 | 16.3107 | 19.1809 | 1
266 | 3.5532 | 6.091 | 3.9783 | 5.3529 | 3.3903 | 2.2177 | 17.2149 | 13.1395 | 17.2149 | 1
267 | 3.2308 | 5.4958 | 4.9178 | 4.3033 | 4.1935 | 2.1306 | 15.1605 | 14.4728 | 15.1605 | 1
268 | 4.7547 | 5.7567 | 5.0192 | 4.9138 | 3.7614 | 2.2124 | 17.6377 | 15.7478 | 17.6377 | 1
269 | 2.9224 | 4.5507 | 5.9219 | 5.8045 | 6.3868 | 1.8646 | 15.1422 | 17.0957 | 17.0957 | 0
270 | 4.5458 | 4.287 | 3.9448 | 4.17 | 4.3113 | 1.4582 | 14.4611 | 14.2601 | 14.4611 | 1
271 | 3.6218 | 4.4526 | 3.4665 | 5.2454 | 4.5851 | 1.5469 | 14.8668 | 13.2203 | 14.8668 | 1
272 | 4.6882 | 5.8471 | 5.1215 | 5.7799 | 4.9077 | 1.7348 | 18.05 | 16.4522 | 18.05 | 1
273 | 4.7493 | 4.6773 | 6.2491 | 7.4439 | 4.9746 | 1.655 | 18.5255 | 17.6279 | 18.5255 | 1
274 | 3.2683 | 4.8276 | 7.4247 | 5.0102 | 4.1124 | 1.834 | 14.9402 | 16.6395 | 16.6395 | 0
275 | 4.4527 | 4.2627 | 3.3493 | 5.001 | 3.393 | 1.9339 | 15.6503 | 13.1289 | 15.6503 | 1
276 | 5.4607 | 3.888 | 5.9323 | 6.0225 | 4.5377 | 2.2037 | 17.5748 | 18.1344 | 18.1344 | 0
277 | 4.1159 | 5.8436 | 6.7003 | 4.908 | 3.5604 | 1.8957 | 16.7632 | 16.2724 | 16.7632 | 1
278 | 2.9953 | 6.2453 | 6.842 | 5.4147 | 3.7176 | 1.3901 | 16.0454 | 14.9451 | 16.0454 | 1
279 | 4.8163 | 5.9943 | 4.7572 | 5.4565 | 3.6073 | 1.9209 | 18.188 | 15.1016 | 18.188 | 1
280 | 4.1784 | 4.481 | 5.3054 | 5.8906 | 4.8763 | 1.5688 | 16.1189 | 15.9289 | 16.1189 | 1
281 | 3.7533 | 5.7986 | 7.2555 | 4.705 | 3.4357 | 1.8012 | 16.0582 | 16.2458 | 16.2458 | 0
282 | 3.7274 | 7.1728 | 2.9618 | 5.3601 | 3.2721 | 2.2816 | 18.5419 | 12.2428 | 18.5419 | 1
283 | 4.6685 | 4.9897 | 6.3618 | 4.9438 | 4.4768 | 2.088 | 16.69 | 17.5952 | 17.5952 | 0
284 | 2.869 | 5.6907 | 4.8784 | 5.4969 | 5.6481 | 1.9043 | 15.9608 | 15.2997 | 15.9608 | 1
285 | 4.461 | 4.5477 | 6.0853 | 6.4242 | 3.7336 | 2.1775 | 17.6104 | 16.4574 | 17.6104 | 1
286 | 2.7412 | 6.1891 | 6.8345 | 4.2569 | 5.3257 | 1.9943 | 15.1815 | 16.8957 | 16.8957 | 0
287 | 3.0296 | 8.0005 | 5.2597 | 5.2471 | 3.6643 | 2.378 | 18.6553 | 14.3317 | 18.6553 | 1
288 | 4.1734 | 3.2726 | 6.6322 | 4.5061 | 4.6451 | 2.3068 | 14.2589 | 17.7576 | 17.7576 | 0
289 | 3.5754 | 5.6864 | 6.7818 | 4.6494 | 4.1285 | 1.8725 | 15.7837 | 16.3583 | 16.3583 | 0
290 | 4.1221 | 5.273 | 6.9984 | 4.9109 | 4.7324 | 2.0219 | 16.3279 | 17.8748 | 17.8748 | 0
291 | 4.9717 | 4.3602 | 6.2862 | 4.4601 | 4.2469 | 2.1209 | 15.9129 | 17.6258 | 17.6258 | 0
292 | 3.5113 | 5.8568 | 7.6781 | 6.0532 | 4.261 | 1.8196 | 17.2409 | 17.27 | 17.27 | 0
293 | 2.7651 | 5.3451 | 6.2703 | 5.1714 | 4.2427 | 1.6656 | 14.9472 | 14.9437 | 14.9472 | 1
294 | 2.9529 | 4.2882 | 6.7728 | 4.4528 | 5.2031 | 1.9451 | 13.6391 | 16.874 | 16.874 | 0
295 | 3.7722 | 6.9805 | 5.1823 | 4.1027 | 4.2163 | 1.956 | 16.8113 | 15.1268 | 16.8113 | 1
296 | 3.5434 | 5.3976 | 3.7735 | 4.1451 | 6.3249 | 1.9877 | 15.0738 | 15.6295 | 15.6295 | 0
297 | 4.6471 | 7.5267 | 7.1011 | 6.8938 | 4.0475 | 2.234 | 21.3016 | 18.0296 | 21.3016 | 1
298 | 4.6892 | 4.8871 | 7.6345 | 5.0167 | 5.8826 | 2.3005 | 16.8934 | 20.5067 | 20.5067 | 0
299 | 3.5196 | 5.7892 | 6.5688 | 4.5249 | 4.3126 | 1.7956 | 15.6292 | 16.1966 | 16.1966 | 0
300 | 4.2213 | 5.5634 | 4.6922 | 5.4311 | 3.7443 | 2.004 | 17.2198 | 14.6618 | 17.2198 | 1
301 | 3.6171 | 4.9187 | 3.4721 | 6.3763 | 4.309 | 2.566 | 17.4781 | 13.9642 | 17.4781 | 1
302 | 3.4226 | 5.1215 | 7.2921 | 5.4218 | 4.7359 | 1.5006 | 15.4665 | 16.9513 | 16.9513 | 0
303 | 3.4959 | 5.5439 | 7.0787 | 6.4506 | 4.2291 | 1.8462 | 17.3367 | 16.65 | 17.3367 | 1
304 | 4.1952 | 4.3484 | 6.4344 | 4.8673 | 5.4333 | 2.5334 | 15.9442 | 18.5963 | 18.5963 | 0
305 | 4.6138 | 4.9474 | 3.3923 | 4.768 | 4.2596 | 2.1286 | 16.4578 | 14.3943 | 16.4578 | 1
306 | 4.0218 | 6.3969 | 4.6957 | 4.9601 | 4.7241 | 2.3669 | 17.7458 | 15.8085 | 17.7458 | 1
307 | 3.6442 | 4.4841 | 4.2386 | 5.1884 | 3.3459 | 1.7538 | 15.0705 | 12.9825 | 15.0705 | 1
308 | 4.4871 | 4.7432 | 5.8016 | 5.4578 | 4.4064 | 2.3057 | 16.9937 | 17.0007 | 17.0007 | 0
309 | 4.6398 | 5.1071 | 4.1572 | 4.7616 | 3.3544 | 2.5526 | 17.0611 | 14.704 | 17.0611 | 1
310 | 4.6067 | 6.7403 | 4.3145 | 4.3214 | 3.6553 | 1.5866 | 17.255 | 14.1631 | 17.255 | 1
311 | 3.9691 | 3.8454 | 6.8565 | 4.9005 | 3.8429 | 1.7857 | 14.5007 | 16.4543 | 16.4543 | 0
312 | 5.0551 | 5.7841 | 5.982 | 6.4914 | 3.9515 | 2.188 | 19.5187 | 17.1766 | 19.5187 | 1
313 | 2.5549 | 6.1063 | 7.2946 | 5.0503 | 4.3116 | 2.2935 | 16.005 | 16.4545 | 16.4545 | 0
314 | 2.6133 | 4.3422 | 5.1809 | 4.2254 | 4.939 | 1.9862 | 13.1671 | 14.7194 | 14.7194 | 0
315 | 3.7787 | 4.9282 | 7.4617 | 4.3659 | 3.7977 | 2.0924 | 15.1652 | 17.1305 | 17.1305 | 0
316 | 4.1265 | 3.3888 | 5.6649 | 5.179 | 4.9109 | 1.2907 | 13.985 | 15.993 | 15.993 | 0
317 | 4.6062 | 7.4713 | 4.7454 | 4.6805 | 3.494 | 1.2327 | 17.9907 | 14.0783 | 17.9907 | 1
318 | 3.7994 | 7.0978 | 5.348 | 6.368 | 5.082 | 1.3452 | 18.6103 | 15.5746 | 18.6103 | 1
319 | 5.0626 | 4.5991 | 5.4783 | 5.0334 | 4.4851 | 1.7698 | 16.465 | 16.7959 | 16.7959 | 0
320 | 4.8089 | 4.1281 | 7.4212 | 6.2716 | 4.8264 | 2.0209 | 17.2296 | 19.0774 | 19.0774 | 0
321 | 4.9426 | 4.5502 | 6.094 | 6.0269 | 4.41 | 2.3584 | 17.8781 | 17.805 | 17.8781 | 1
322 | 5.1096 | 3.7503 | 3.7809 | 4.7315 | 4.19 | 2.6796 | 16.271 | 15.7601 | 16.271 | 1
323 | 3.8474 | 4.2469 | 7.3142 | 5.1573 | 3.1871 | 1.2456 | 14.4972 | 15.5943 | 15.5943 | 0
324 | 3.155 | 6.0741 | 3.9308 | 5.258 | 4.5631 | 2.3742 | 16.8613 | 14.023 | 16.8613 | 1
325 | 2.9654 | 4.397 | 6.2509 | 4.2999 | 3.7597 | 1.6418 | 13.3041 | 14.6178 | 14.6178 | 0
326 | 3.5406 | 6.9832 | 3.6848 | 5.7184 | 3.9052 | 2.3732 | 18.6154 | 13.5038 | 18.6154 | 1
327 | 3.3415 | 3.7891 | 4.6246 | 4.6643 | 4.7049 | 2.6657 | 14.4607 | 15.3367 | 15.3367 | 0
328 | 3.244 | 3.9519 | 6.1773 | 6.7371 | 4.9036 | 2.7743 | 16.7073 | 17.0993 | 17.0993 | 0
329 | 3.3067 | 6.1493 | 6.7633 | 4.7659 | 6.0265 | 1.8197 | 16.0416 | 17.9161 | 17.9161 | 0
330 | 3.1846 | 4.9822 | 6.1556 | 5.4408 | 3.3564 | 2.2603 | 15.8679 | 14.9569 | 15.8679 | 1
331 | 2.8194 | 5.3683 | 4.9323 | 5.9937 | 5.1245 | 1.9908 | 16.1721 | 14.867 | 16.1721 | 1
332 | 4.8094 | 5.1448 | 5.6412 | 4.1872 | 3.2696 | 1.8595 | 16.0009 | 15.5796 | 16.0009 | 1
333 | 4.6035 | 4.3884 | 4.2212 | 4.8892 | 4.3122 | 1.3482 | 15.2293 | 14.4851 | 15.2293 | 1
334 | 4.62 | 6.9608 | 6.5669 | 5.0033 | 3.3516 | 2.4727 | 19.0568 | 17.0112 | 19.0568 | 1
335 | 2.4123 | 4.2456 | 4.2025 | 4.8036 | 5.8213 | 2.0427 | 13.5043 | 14.4789 | 14.4789 | 0
336 | 3.3204 | 3.6999 | 5.3619 | 4.3582 | 3.3993 | 1.7364 | 13.115 | 13.818 | 13.818 | 0
337 | 4.0163 | 4.6088 | 6.2354 | 4.6359 | 4.9014 | 2.1724 | 15.4333 | 17.3255 | 17.3255 | 0
338 | 3.4458 | 7.7315 | 7.0056 | 4.4927 | 4.4806 | 1.4281 | 17.0981 | 16.3601 | 17.0981 | 1
339 | 2.9616 | 6.2562 | 5.9308 | 5.126 | 4.9215 | 1.8874 | 16.2313 | 15.7014 | 16.2313 | 1
340 | 4.8153 | 4.4592 | 6.8328 | 5.2192 | 4.9025 | 2.6714 | 17.1651 | 19.222 | 19.222 | 0
341 | 3.6996 | 5.2583 | 3.9403 | 4.7464 | 4.5413 | 2.013 | 15.7173 | 14.1943 | 15.7173 | 1
342 | 4.7572 | 5.1177 | 3.7109 | 4.6385 | 4.0218 | 2.3592 | 16.8726 | 14.8491 | 16.8726 | 1
343 | 4.4655 | 3.7695 | 7.6374 | 4.4951 | 4.4686 | 2.4587 | 15.1887 | 19.0301 | 19.0301 | 0
344 | 3.693 | 6.1039 | 7.0096 | 6.0006 | 4.4114 | 1.1936 | 16.991 | 16.3075 | 16.991 | 1
345 | 2.9234 | 8.0659 | 6.3602 | 6.1316 | 5.0522 | 2.4227 | 19.5437 | 16.7584 | 19.5437 | 1
346 | 4.5746 | 5.2508 | 3.7711 | 5.651 | 4.7055 | 1.4046 | 16.8811 | 14.4559 | 16.8811 | 1
347 | 3.51 | 4.6006 | 7.0364 | 5.556 | 4.5859 | 1.5348 | 15.2014 | 16.6671 | 16.6671 | 0
348 | 5.3189 | 5.2207 | 6.1889 | 5.0735 | 3.8858 | 2.0915 | 17.7045 | 17.4851 | 17.7045 | 1
349 | 5.0989 | 3.6584 | 6.8186 | 4.8873 | 4.4046 | 1.2598 | 14.9044 | 17.5818 | 17.5818 | 0
350 | 3.5863 | 6.0316 | 6.5617 | 5.9989 | 5.3349 | 1.9203 | 17.5371 | 17.4033 | 17.5371 | 1
351 | 3.5952 | 4.6634 | 6.8124 | 4.5434 | 4.3149 | 2.4638 | 15.2658 | 17.1862 | 17.1862 | 0
352 | 4.3627 | 5.3254 | 4.6335 | 4.8626 | 4.4515 | 2.3702 | 16.9209 | 15.818 | 16.9209 | 1
353 | 4.2399 | 5.4164 | 5.4894 | 4.6268 | 4.3038 | 2.2566 | 16.5397 | 16.2897 | 16.5397 | 1
354 | 4.7438 | 6.9441 | 6.1185 | 5.782 | 3.8801 | 2.2583 | 19.7283 | 17.0007 | 19.7283 | 1
355 | 5.8196 | 6.0808 | 7.6536 | 5.4039 | 4.1026 | 2.5555 | 19.8598 | 20.1312 | 20.1312 | 0
356 | 5.0567 | 5.009 | 5.3069 | 5.6134 | 3.1881 | 1.5288 | 17.2079 | 15.0805 | 17.2079 | 1
357 | 2.9111 | 6.082 | 4.8451 | 4.5717 | 4.5864 | 1.7695 | 15.3344 | 14.1121 | 15.3344 | 1
358 | 4.1493 | 4.0581 | 5.8127 | 4.381 | 3.5699 | 2.1069 | 14.6952 | 15.6387 | 15.6387 | 0
359 | 3.9254 | 4.938 | 6.4211 | 6.8762 | 3.9661 | 1.9199 | 17.6595 | 16.2326 | 17.6595 | 1
360 | 4.9747 | 5.5076 | 7.3156 | 4.5614 | 4.5096 | 2.5594 | 17.6031 | 19.3593 | 19.3593 | 0
361 | 3.5208 | 6.4756 | 5.9485 | 5.1108 | 3.7789 | 1.7521 | 16.8592 | 15.0003 | 16.8592 | 1
362 | 5.5408 | 5.2085 | 5.1064 | 4.5358 | 3.4816 | 1.8728 | 17.1579 | 16.0015 | 17.1579 | 1
363 | 3.9823 | 5.3808 | 6.824 | 6.499 | 4.3001 | 1.3096 | 17.1717 | 16.4161 | 17.1717 | 1
364 | 3.4052 | 6.0597 | 6.7182 | 5.2364 | 3.6978 | 2.1838 | 16.8851 | 16.0051 | 16.8851 | 1
365 | 4.3209 | 3.6215 | 5.4598 | 5.6282 | 4.2673 | 2.0616 | 15.6321 | 16.1095 | 16.1095 | 0
366 | 4.5022 | 6.7774 | 4.4722 | 5.1599 | 4.8523 | 2.147 | 18.5865 | 15.9738 | 18.5865 | 1
367 | 3.5947 | 5.2865 | 5.8795 | 4.2667 | 4.76 | 2.1553 | 15.3033 | 16.3895 | 16.3895 | 0
368 | 4.9048 | 4.4025 | 7.2165 | 4.822 | 4.7216 | 2.5573 | 16.6866 | 19.4002 | 19.4002 | 0
369 | 5.019 | 4.7641 | 3.9185 | 7.1759 | 3.3399 | 2.0495 | 19.0084 | 14.3268 | 19.0084 | 1
370 | 3.0695 | 6.8143 | 5.0478 | 4.7724 | 4.1449 | 2.6341 | 17.2902 | 14.8963 | 17.2902 | 1
371 | 4.6589 | 4.4584 | 6.666 | 5.8926 | 3.7835 | 1.3305 | 16.3405 | 16.439 | 16.439 | 0
372 | 4.7818 | 5.0258 | 4.3951 | 4.9753 | 3.9418 | 1.9624 | 16.7453 | 15.0812 | 16.7453 | 1
373 | 3.7425 | 5.6529 | 6.1283 | 4.7021 | 3.3345 | 1.795 | 15.8926 | 15.0003 | 15.8926 | 1
374 | 3.5094 | 4.8812 | 7.402 | 4.684 | 5.7301 | 1.8641 | 14.9386 | 18.5055 | 18.5055 | 0
375 | 4.209 | 4.0424 | 7.1269 | 4.506 | 4.897 | 2.4264 | 15.1837 | 18.6592 | 18.6592 | 0
376 | 4.3283 | 6.4163 | 4.5044 | 4.5355 | 3.9482 | 1.6843 | 16.9644 | 14.4653 | 16.9644 | 1
377 | 2.5429 | 4.3628 | 5.1389 | 4.9471 | 3.9074 | 1.346 | 13.1988 | 12.9352 | 13.1988 | 1
378 | 3.8773 | 7.5096 | 6.7732 | 4.8765 | 3.1566 | 2.3212 | 18.5846 | 16.1283 | 18.5846 | 1
379 | 3.0233 | 6.2367 | 6.1997 | 5.5931 | 3.3716 | 1.7307 | 16.5838 | 14.3252 | 16.5838 | 1
380 | 4.8222 | 3.4882 | 4.3427 | 5.9225 | 4.9976 | 2.2389 | 16.4718 | 16.4014 | 16.4718 | 1
381 | 3.3539 | 3.9357 | 7.7047 | 4.7238 | 3.5467 | 1.988 | 14.0014 | 16.5934 | 16.5934 | 0
382 | 4.8664 | 5.427 | 6.2396 | 5.6414 | 3.2678 | 1.7351 | 17.6699 | 16.1089 | 17.6699 | 1
383 | 3.2056 | 5.0331 | 6.9833 | 6.0703 | 5.0466 | 2.4192 | 16.7283 | 17.6547 | 17.6547 | 0
384 | 4.0032 | 4.9064 | 6.5939 | 6.0043 | 4.7541 | 2.8851 | 17.799 | 18.2363 | 18.2363 | 0
385 | 4.8857 | 4.3994 | 4.2148 | 5.1439 | 4.5517 | 2.2382 | 16.6672 | 15.8905 | 16.6672 | 1
386 | 3.3015 | 4.1465 | 6.244 | 4.9881 | 5.2031 | 1.7105 | 14.1466 | 16.4591 | 16.4591 | 0
387 | 3.6466 | 6.1832 | 7.1256 | 5.4715 | 3.6508 | 2.2173 | 17.5186 | 16.6403 | 17.5186 | 1
388 | 3.819 | 5.304 | 4.9621 | 6.1622 | 4.0604 | 1.5191 | 16.8043 | 14.3607 | 16.8043 | 1
389 | 4.1166 | 7.1233 | 5.4365 | 4.4822 | 3.3943 | 1.7361 | 17.4582 | 14.6835 | 17.4582 | 1
390 | 4.4893 | 4.8726 | 6.0844 | 5.7522 | 4.335 | 2.0454 | 17.1595 | 16.9541 | 17.1595 | 1
391 | 2.9905 | 4.712 | 5.3079 | 5.4378 | 5.3245 | 2.0557 | 15.196 | 15.6787 | 15.6787 | 0
392 | 3.7264 | 6.5257 | 6.0392 | 4.5198 | 3.4893 | 2.2986 | 17.0705 | 15.5536 | 17.0705 | 1
393 | 2.594 | 6.8288 | 4.6894 | 5.1936 | 5.2995 | 2.1233 | 16.7396 | 14.7062 | 16.7396 | 1
394 | 4.2448 | 6.6033 | 6.7848 | 5.3776 | 3.9384 | 1.6256 | 17.8513 | 16.5936 | 17.8513 | 1
395 | 5.7367 | 4.2025 | 4.1006 | 7.1584 | 5.3446 | 2.4018 | 19.4993 | 17.5836 | 19.4993 | 1
396 | 4.1254 | 7.3945 | 7.6508 | 4.982 | 4.903 | 2.3715 | 18.8734 | 19.0507 | 19.0507 | 0
397 | 3.5464 | 5.0009 | 5.2532 | 6.4179 | 4.237 | 2.1699 | 17.135 | 15.2064 | 17.135 | 1
398 | 5.0485 | 5.8388 | 6.6803 | 6.5223 | 4.4939 | 2.4078 | 19.8174 | 18.6305 | 19.8174 | 1
399 | 3.229 | 6.3776 | 7.7068 | 4.7394 | 4.7883 | 2.9255 | 17.2715 | 18.6496 | 18.6496 | 0
400 | 4.4702 | 6.0286 | 5.9417 | 4.0535 | 4.1651 | 1.6526 | 16.2049 | 16.2295 | 16.2295 | 0
401 | 4.8361 | 6.6083 | 6.1488 | 4.4875 | 4.5595 | 2.5678 | 18.4998 | 18.1122 | 18.4998 | 1
402 | 4.5924 | 5.2404 | 5.3178 | 4.3872 | 4.2582 | 2.4878 | 16.7078 | 16.6563 | 16.7078 | 1
403 | 3.8598 | 5.8305 | 5.184 | 5.2097 | 4.9605 | 2.1239 | 17.0239 | 16.1282 | 17.0239 | 1
404 | 2.9809 | 6.5543 | 5.6202 | 5.7625 | 5.4754 | 1.8563 | 17.1541 | 15.9329 | 17.1541 | 1
405 | 4.2906 | 4.0422 | 6.8249 | 4.5696 | 5.3258 | 2.4015 | 15.3039 | 18.8428 | 18.8428 | 0
406 | 4.1053 | 7.1535 | 6.937 | 5.2759 | 5.3847 | 1.9101 | 18.4448 | 18.3371 | 18.4448 | 1
407 | 4.2277 | 7.6484 | 7.097 | 4.9834 | 4.0118 | 2.3503 | 19.2099 | 17.6869 | 19.2099 | 1
408 | 4.6562 | 4.81 | 6.0971 | 6.4853 | 3.9193 | 2.1991 | 18.1505 | 16.8716 | 18.1505 | 1
409 | 3.0022 | 6.6341 | 6.4842 | 6.2645 | 4.3755 | 1.8098 | 17.7106 | 15.6718 | 17.7106 | 1
410 | 4.0355 | 5.4068 | 5.8193 | 5.1855 | 3.4345 | 1.7711 | 16.399 | 15.0604 | 16.399 | 1
411 | 3.5863 | 5.1923 | 2.6543 | 4.3908 | 4.502 | 2.2152 | 15.3847 | 12.9579 | 15.3847 | 1
412 | 4.3851 | 5.3553 | 6.7968 | 7.3484 | 5.7665 | 2.0192 | 19.1079 | 18.9675 | 19.1079 | 1
413 | 4.994 | 7.1177 | 3.6756 | 4.8726 | 3.6292 | 2.0871 | 19.0712 | 14.3858 | 19.0712 | 1
414 | 3.6873 | 3.6449 | 4.6455 | 4.4697 | 6.3179 | 1.9599 | 13.7619 | 16.6107 | 16.6107 | 0
415 | 4.7708 | 6.9849 | 5.6474 | 5.1181 | 4.5905 | 1.3892 | 18.2629 | 16.3979 | 18.2629 | 1
416 | 3.8168 | 3.7199 | 6.8232 | 6.3436 | 4.1175 | 2.5463 | 16.4266 | 17.3038 | 17.3038 | 0
417 | 5.4863 | 6.001 | 6.2525 | 5.3428 | 5.595 | 1.7454 | 18.5755 | 19.0792 | 19.0792 | 0
418 | 4.8874 | 5.2267 | 5.5141 | 5.3108 | 3.8033 | 2.0412 | 17.4661 | 16.246 | 17.4661 | 1
419 | 2.5702 | 4.685 | 5.8432 | 6.1171 | 5.2821 | 2.1376 | 15.5099 | 15.8332 | 15.8332 | 0
420 | 5.0391 | 3.646 | 5.7118 | 5.4668 | 6.2972 | 1.7831 | 15.9351 | 18.8313 | 18.8313 | 0
421 | 4.7144 | 5.2359 | 7.4908 | 5.0611 | 4.0759 | 1.7163 | 16.7277 | 17.9974 | 17.9974 | 0
422 | 4.2511 | 5.6738 | 3.6954 | 5.2137 | 5.1915 | 2.302 | 17.4405 | 15.44 | 17.4405 | 1
423 | 2.7734 | 5.7376 | 4.628 | 5.7041 | 4.4467 | 2.1183 | 16.3334 | 13.9664 | 16.3334 | 1
424 | 4.4193 | 3.4796 | 6.073 | 5.0998 | 3.9035 | 2.0896 | 15.0884 | 16.4856 | 16.4856 | 0
425 | 4.4119 | 4.3467 | 7.7965 | 6.04 | 3.3704 | 1.1603 | 15.9589 | 16.7391 | 16.7391 | 0
426 | 5.1394 | 5.6139 | 6.2018 | 5.2789 | 4.0396 | 1.5422 | 17.5744 | 16.923 | 17.5744 | 1
427 | 4.369 | 5.9349 | 6.9083 | 6.1505 | 4.56 | 1.8928 | 18.3472 | 17.7301 | 18.3472 | 1
428 | 4.2862 | 6.9664 | 5.0301 | 4.7667 | 4.199 | 1.4066 | 17.4259 | 14.9219 | 17.4259 | 1
429 | 4.4844 | 5.1934 | 5.1361 | 5.1308 | 4.0133 | 2.0145 | 16.823 | 15.6483 | 16.823 | 1
430 | 3.7789 | 3.3683 | 6.5824 | 6.6076 | 3.086 | 2.3446 | 16.0995 | 15.792 | 16.0995 | 1
431 | 3.7772 | 6.6161 | 5.9964 | 5.9303 | 4.4183 | 1.4433 | 17.767 | 15.6351 | 17.767 | 1
432 | 4.2283 | 6.4609 | 6.9796 | 5.6588 | 4.1025 | 1.5071 | 17.855 | 16.8175 | 17.855 | 1
433 | 3.4389 | 4.6395 | 7.2 | 4.5564 | 3.9697 | 1.9213 | 14.556 | 16.5298 | 16.5298 | 0
434 | 5.0396 | 5.0987 | 6.5658 | 5.2314 | 5.1243 | 1.9243 | 17.2939 | 18.6539 | 18.6539 | 0
435 | 3.0094 | 6.6961 | 3.6783 | 4.6056 | 3.0861 | 2.1475 | 16.4585 | 11.9213 | 16.4585 | 1
436 | 3.6398 | 5.5299 | 4.0555 | 5.6026 | 4.1061 | 2.275 | 17.0474 | 14.0765 | 17.0474 | 1
437 | 3.4077 | 6.8398 | 5.8252 | 5.8526 | 3.8224 | 1.5559 | 17.6559 | 14.6112 | 17.6559 | 1
438 | 3.3773 | 3.6475 | 5.3492 | 7.1124 | 5.7232 | 1.6788 | 15.8159 | 16.1285 | 16.1285 | 0
439 | 4.4179 | 6.812 | 4.7241 | 4.9636 | 3.7926 | 2.3464 | 18.5399 | 15.281 | 18.5399 | 1
440 | 5.1402 | 3.8305 | 5.7886 | 6.0185 | 3.5897 | 2.0357 | 17.0249 | 16.5542 | 17.0249 | 1
441 | 3.3826 | 4.9626 | 4.4831 | 6.1115 | 5.6945 | 2.3934 | 16.8501 | 15.9535 | 16.8501 | 1
442 | 4.6073 | 4.785 | 6.297 | 5.0923 | 3.2903 | 2.1544 | 16.6391 | 16.349 | 16.6391 | 1
443 | 5.2631 | 6.8661 | 4.0101 | 6.8937 | 5.0624 | 2.1883 | 21.2113 | 16.5239 | 21.2113 | 1
444 | 3.2641 | 4.0535 | 5.0751 | 4.6538 | 4.1538 | 2.0504 | 14.0218 | 14.5435 | 14.5435 | 0
445 | 4.658 | 4.627 | 6.8687 | 5.0496 | 3.8995 | 2.0136 | 16.3482 | 17.4397 | 17.4397 | 0
446 | 3.3721 | 5.3174 | 3.6042 | 4.7499 | 4.2943 | 1.8935 | 15.3328 | 13.1641 | 15.3328 | 1
447 | 3.9986 | 4.0095 | 6.8993 | 5.8105 | 4.8378 | 2.0763 | 15.895 | 17.8121 | 17.8121 | 0
448 | 4.7287 | 3.9628 | 4.7007 | 6.2478 | 4.8069 | 1.9524 | 16.8918 | 16.1887 | 16.8918 | 1
449 | 3.5481 | 4.2054 | 5.622 | 4.9955 | 4.0003 | 1.977 | 14.7259 | 15.1474 | 15.1474 | 0
450 | 4.3508 | 4.3198 | 3.2356 | 5.8401 | 3.6395 | 1.1591 | 15.6698 | 12.385 | 15.6698 | 1
451 | 3.2181 | 4.4979 | 6.5945 | 5.6291 | 3.9133 | 2.3036 | 15.6488 | 16.0296 | 16.0296 | 0
452 | 4.3321 | 5.6471 | 5.9389 | 4.8648 | 4.3103 | 1.4363 | 16.2803 | 16.0177 | 16.2803 | 1
453 | 3.1404 | 6.752 | 6.5782 | 5.239 | 3.919 | 2.1133 | 17.2446 | 15.7509 | 17.2446 | 1
454 | 3.014 | 4.1488 | 4.3336 | 5.1255 | 3.861 | 1.3986 | 13.6869 | 12.6072 | 13.6869 | 1
455 | 2.3284 | 6.9548 | 7.7184 | 5.1589 | 4.0055 | 2.1649 | 16.6071 | 16.2172 | 16.6071 | 1
456 | 5.069 | 6.0185 | 6.1352 | 4.5076 | 5.1342 | 2.0409 | 17.636 | 18.3794 | 18.3794 | 0
457 | 4.1722 | 6.0398 | 6.0646 | 5.7087 | 3.1371 | 2.6699 | 18.5906 | 16.0438 | 18.5906 | 1
458 | 4.2389 | 5.9531 | 7.1632 | 4.9785 | 3.4394 | 2.4338 | 17.6043 | 17.2754 | 17.6043 | 1
459 | 3.9989 | 6.334 | 4.2269 | 4.9271 | 4.7998 | 2.4176 | 17.6776 | 15.4431 | 17.6776 | 1
460 | 4.8378 | 5.4627 | 6.3979 | 6.2179 | 5.3263 | 1.6769 | 18.1952 | 18.2388 | 18.2388 | 0
461 | 3.7239 | 5.8043 | 6.9003 | 5.7081 | 3.3865 | 2.2447 | 17.481 | 16.2554 | 17.481 | 1
462 | 3.7637 | 6.7479 | 6.0106 | 4.5568 | 4.135 | 1.9483 | 17.0167 | 15.8577 | 17.0167 | 1
463 | 3.6969 | 4.0952 | 7.3371 | 5.058 | 3.6066 | 1.4213 | 14.2714 | 16.062 | 16.062 | 0
464 | 4.7885 | 6.8249 | 7.2381 | 4.7109 | 5.3127 | 2.159 | 18.4833 | 19.4983 | 19.4983 | 0
465 | 4.0933 | 5.2505 | 7.6395 | 4.7974 | 4.7667 | 1.2482 | 15.3895 | 17.7477 | 17.7477 | 0
466 | 4.7415 | 4.959 | 7.0612 | 5.7552 | 3.888 | 1.6954 | 17.1511 | 17.3861 | 17.3861 | 0
467 | 4.7657 | 4.9913 | 6.5503 | 6.1901 | 4.742 | 2.1864 | 18.1335 | 18.2444 | 18.2444 | 0
468 | 3.5557 | 6.6496 | 4.9188 | 6.6375 | 4.6457 | 1.8709 | 18.7138 | 14.9912 | 18.7138 | 1
469 | 4.7699 | 5.5448 | 5.8263 | 5.1663 | 4.0945 | 1.7371 | 17.2181 | 16.4277 | 17.2181 | 1
470 | 3.4933 | 4.1899 | 7.0539 | 4.4296 | 4.0505 | 1.633 | 13.7459 | 16.2308 | 16.2308 | 0
471 | 3.8368 | 3.6449 | 5.7098 | 4.6288 | 4.5783 | 1.8293 | 13.9399 | 15.9543 | 15.9543 | 0
472 | 3.4124 | 3.2611 | 5.9642 | 6.575 | 4.8071 | 2.0905 | 15.3389 | 16.2742 | 16.2742 | 0
473 | 3.4443 | 6.138 | 4.2509 | 4.7508 | 3.4212 | 2.1553 | 16.4884 | 13.2716 | 16.4884 | 1
474 | 4.9962 | 5.8224 | 6.0164 | 5.6066 | 3.99 | 1.7396 | 18.1648 | 16.7422 | 18.1648 | 1
475 | 3.9192 | 4.6041 | 6.8016 | 6.2207 | 4.198 | 1.3905 | 16.1344 | 16.3092 | 16.3092 | 0
476 | 3.0391 | 5.288 | 4.6454 | 5.466 | 5.2161 | 1.5211 | 15.3141 | 14.4216 | 15.3141 | 1
477 | 2.665 | 6.9148 | 5.6676 | 4.6465 | 5.2582 | 2.2665 | 16.4927 | 15.8573 | 16.4927 | 1
478 | 3.4968 | 4.8985 | 5.5517 | 4.3217 | 5.4423 | 1.4512 | 14.1681 | 15.9419 | 15.9419 | 0
479 | 4.7504 | 5.9282 | 6.4451 | 6.4507 | 3.3916 | 2.2339 | 19.3632 | 16.821 | 19.3632 | 1
480 | 4.0612 | 5.4927 | 6.1624 | 5.7862 | 3.5201 | 1.7474 | 17.0875 | 15.491 | 17.0875 | 1
481 | 3.1319 | 3.6111 | 6.0378 | 6.695 | 4.0677 | 1.7325 | 15.1704 | 14.9699 | 15.1704 | 1
482 | 3.1885 | 6.1485 | 7.5595 | 6.5637 | 3.2217 | 1.7195 | 17.6202 | 15.6891 | 17.6202 | 1
483 | 5.0468 | 4.2087 | 4.1243 | 5.6378 | 3.5497 | 2.3969 | 17.2903 | 15.1178 | 17.2903 | 1
484 | 4.6729 | 6.9056 | 5.5259 | 5.6041 | 3.4914 | 2.1643 | 19.3469 | 15.8545 | 19.3469 | 1
485 | 2.625 | 6.0126 | 6.6607 | 6.5788 | 5.6541 | 2.6454 | 17.8618 | 17.5853 | 17.8618 | 1
486 | 3.0204 | 3.304 | 6.8222 | 6.4823 | 4.2768 | 2.4604 | 15.2672 | 16.5798 | 16.5798 | 0
487 | 4.6186 | 3.6798 | 4.6475 | 6.0603 | 4.7633 | 2.3284 | 16.687 | 16.3578 | 16.687 | 1
488 | 3.619 | 4.1999 | 3.9937 | 4.3832 | 4.273 | 2.3099 | 14.512 | 14.1956 | 14.512 | 1
489 | 5.2014 | 3.115 | 4.4395 | 5.0792 | 3.7907 | 2.318 | 15.7136 | 15.7497 | 15.7497 | 0
490 | 5.3396 | 5.7955 | 7.4347 | 6.2312 | 4.0447 | 2.3853 | 19.7517 | 19.2043 | 19.7517 | 1
491 | 5.1745 | 4.9103 | 7.014 | 4.6619 | 4.269 | 2.9076 | 17.6544 | 19.3652 | 19.3652 | 0
492 | 5.1173 | 5.6265 | 5.9439 | 4.1897 | 3.4384 | 1.8315 | 16.7651 | 16.3312 | 16.7651 | 1
493 | 3.9233 | 6.9366 | 4.3302 | 4.3813 | 5.0783 | 1.6533 | 16.8945 | 14.9851 | 16.8945 | 1
494 | 3.8468 | 4.6873 | 4.6146 | 6.5882 | 3.3467 | 2.4442 | 17.5664 | 14.2522 | 17.5664 | 1
495 | 4.1503 | 5.6633 | 7.4288 | 6.4962 | 3.7361 | 2.4148 | 18.7245 | 17.7299 | 18.7245 | 1
496 | 3.7337 | 4.6974 | 5.6855 | 5.0272 | 5.5036 | 1.5997 | 15.0581 | 16.5225 | 16.5225 | 0
497 | 2.2211 | 5.1514 | 6.3747 | 4.6251 | 3.5643 | 2.007 | 14.0046 | 14.167 | 14.167 | 0
498 | 3.0727 | 5.6534 | 7.7984 | 5.4228 | 3.9674 | 2.3586 | 16.5074 | 17.197 | 17.197 | 0
499 | 3.9056 | 5.4972 | 6.645 | 5.2476 | 3.7648 | 2.0896 | 16.7399 | 16.405 | 16.7399 | 1
500 | 4.3687 | 5.5236 | 4.0541 | 5.0214 | 3.7602 | 1.6012 | 16.5148 | 13.7842 | 16.5148 | 1
501 | 4.0439 | 5.0338 | 4.8931 | 5.6809 | 4.669 | 2.4765 | 17.2351 | 16.0825 | 17.2351 | 1
502 | 3.2787 | 6.0876 | 6.0233 | 5.2745 | 3.2348 | 1.958 | 16.5988 | 14.4948 | 16.5988 | 1
503 | 3.8577 | 4.1153 | 4.8503 | 6.0082 | 5.1604 | 2.4235 | 16.4047 | 16.292 | 16.4047 | 1
504 | 4.2787 | 7.6819 | 2.8094 | 5.2444 | 3.9174 | 2.051 | 19.256 | 13.0565 | 19.256 | 1
505 | 5.2464 | 4.8522 | 4.5338 | 4.1124 | 3.32 | 1.8494 | 16.0604 | 14.9496 | 16.0604 | 1
506 | 3.4912 | 4.5788 | 5.8599 | 4.7267 | 4.8652 | 2.2664 | 15.0631 | 16.4827 | 16.4827 | 0
507 | 3.4023 | 4.899 | 6.7099 | 4.4419 | 3.1245 | 1.7843 | 14.5276 | 15.021 | 15.021 | 0
508 | 3.5019 | 4.3531 | 4.3912 | 5.6533 | 4.0312 | 1.6101 | 15.1185 | 13.5344 | 15.1185 | 1
509 | 5.3933 | 5.7112 | 4.9072 | 6.3933 | 4.6188 | 2.0906 | 19.5884 | 17.01 | 19.5884 | 1
510 | 3.5011 | 6.2077 | 4.1056 | 4.9077 | 4.0033 | 1.6502 | 16.2667 | 13.2602 | 16.2667 | 1
511 | 3.1579 | 4.8792 | 5.2213 | 5.2518 | 4.4813 | 1.5596 | 14.8484 | 14.4201 | 14.8484 | 1
512 | 2.8352 | 4.5753 | 6.1239 | 6.759 | 4.9235 | 2.2372 | 16.4068 | 16.1198 | 16.4068 | 1
513 | 4.0254 | 7.5458 | 5.5656 | 6.1224 | 4.1356 | 1.7981 | 19.4918 | 15.5247 | 19.4918 | 1
514 | 4.5024 | 7.8867 | 6.9349 | 5.3483 | 3.5714 | 1.9599 | 19.6973 | 16.9686 | 19.6973 | 1
515 | 2.6742 | 4.7478 | 3.8955 | 4.9184 | 3.5286 | 1.692 | 14.0323 | 11.7902 | 14.0323 | 1
516 | 4.4662 | 4.0807 | 7.1418 | 5.5666 | 5.2193 | 2.5169 | 16.6303 | 19.3442 | 19.3442 | 0
517 | 4.1361 | 3.7572 | 6.1805 | 4.8882 | 3.5318 | 1.8094 | 14.5909 | 15.6577 | 15.6577 | 0
518 | 4.045 | 4.04 | 4.5076 | 6.2563 | 4.3411 | 1.7374 | 16.0788 | 14.6312 | 16.0788 | 1
519 | 2.9126 | 4.0924 | 3.8812 | 5.0328 | 5.5671 | 1.4755 | 13.5134 | 13.8364 | 13.8364 | 0
520 | 3.914 | 6.2003 | 7.6722 | 4.7165 | 6.3446 | 2.1598 | 16.9905 | 20.0906 | 20.0906 | 0
521 | 4.5639 | 5.2784 | 5.2715 | 4.8729 | 3.714 | 2.348 | 17.0632 | 15.8973 | 17.0632 | 1
522 | 4.3701 | 6.5057 | 3.9334 | 4.8938 | 3.643 | 1.8224 | 17.5919 | 13.7689 | 17.5919 | 1
523 | 3.7506 | 4.1466 | 6.6867 | 4.7845 | 5.9813 | 2.1536 | 14.8353 | 18.5723 | 18.5723 | 0
524 | 4.6034 | 3.8072 | 5.2252 | 6.7346 | 3.403 | 1.7227 | 16.8679 | 14.9543 | 16.8679 | 1
525 | 4.0749 | 4.3437 | 4.6331 | 5.0625 | 5.6334 | 2.663 | 16.1441 | 17.0045 | 17.0045 | 0
526 | 4.3336 | 5.58 | 6.2706 | 4.6036 | 4.4006 | 2.045 | 16.5621 | 17.0497 | 17.0497 | 0
527 | 4.6113 | 3.8844 | 5.7572 | 5.8164 | 3.6009 | 1.7567 | 16.0688 | 15.7262 | 16.0688 | 1
528 | 3.7538 | 6.0612 | 6.9076 | 5.561 | 6.0007 | 2.2358 | 17.6119 | 18.898 | 18.898 | 0
529 | 3.4133 | 4.4727 | 4.2252 | 4.8493 | 4.5785 | 1.6665 | 14.4018 | 13.8835 | 14.4018 | 1
530 | 3.3301 | 3.5432 | 6.4588 | 5.2546 | 4.2798 | 2.8158 | 14.9437 | 16.8845 | 16.8845 | 0
531 | 3.9436 | 5.3274 | 4.955 | 5.5985 | 3.9945 | 1.7913 | 16.6608 | 14.6845 | 16.6608 | 1
532 | 3.5257 | 5.1281 | 5.6901 | 5.7769 | 4.4446 | 1.5165 | 15.9472 | 15.1769 | 15.9472 | 1
533 | 2.4203 | 6.9336 | 5.3146 | 4.1914 | 3.9764 | 1.9498 | 15.4951 | 13.6611 | 15.4951 | 1
534 | 3.9148 | 4.7969 | 5.5434 | 4.1376 | 3.8633 | 2.0356 | 14.8848 | 15.357 | 15.357 | 0
535 | 2.6561 | 5.7263 | 5.4157 | 5.0846 | 4.9196 | 2.1305 | 15.5975 | 15.1219 | 15.5975 | 1
536 | 4.0819 | 4.8534 | 7.3158 | 5.7259 | 3.6035 | 1.701 | 16.3622 | 16.7022 | 16.7022 | 0
537 | 3.2666 | 5.8026 | 2.8767 | 5.8791 | 3.383 | 2.4635 | 17.4117 | 11.9898 | 17.4117 | 1
538 | 3.3433 | 4.7584 | 4.5821 | 5.6681 | 3.3337 | 2.1001 | 15.8699 | 13.3592 | 15.8699 | 1
539 | 4.2322 | 6.4187 | 4.6395 | 4.624 | 4.3236 | 1.3252 | 16.6002 | 14.5206 | 16.6002 | 1
540 | 4.335 | 5.0677 | 7.1917 | 4.9131 | 4.7901 | 1.9548 | 16.2707 | 18.2717 | 18.2717 | 0
541 | 3.679 | 5.4973 | 4.7296 | 5.8162 | 5.0098 | 2.4017 | 17.3941 | 15.8201 | 17.3941 | 1
542 | 3.6121 | 4.3369 | 6.6355 | 6.6956 | 4.862 | 2.5735 | 17.2181 | 17.6832 | 17.6832 | 0
543 | 4.6289 | 4.7331 | 6.0019 | 6.107 | 3.325 | 2.2418 | 17.7107 | 16.1975 | 17.7107 | 1
544 | 2.6616 | 3.9289 | 6.0803 | 5.9545 | 3.9127 | 2.41 | 14.955 | 15.0646 | 15.0646 | 0
545 | 3.8246 | 5.4675 | 7.2649 | 4.3142 | 3.7576 | 1.6026 | 15.2089 | 16.4497 | 16.4497 | 0
546 | 4.0051 | 4.5079 | 7.2741 | 6.887 | 4.116 | 1.9578 | 17.3577 | 17.353 | 17.3577 | 1
547 | 5.4393 | 6.4479 | 3.3755 | 6.4348 | 3.6544 | 1.7465 | 20.0684 | 14.2156 | 20.0684 | 1
548 | 3.8111 | 5.6953 | 4.322 | 6.1537 | 4.0211 | 2.4794 | 18.1394 | 14.6336 | 18.1394 | 1
549 | 2.8643 | 4.4277 | 4.4935 | 4.2463 | 3.6813 | 1.8674 | 13.4057 | 12.9065 | 13.4057 | 1
550 | 3.1191 | 6.7544 | 5.1956 | 6.404 | 4.6576 | 1.142 | 17.4196 | 14.1144 | 17.4196 | 1
551 | 3.9219 | 5.9292 | 7.1366 | 4.655 | 4.5963 | 1.8709 | 16.377 | 17.5257 | 17.5257 | 0
552 | 4.7949 | 3.0617 | 4.1103 | 5.0846 | 4.6423 | 1.3558 | 14.297 | 14.9033 | 14.9033 | 0
553 | 3.5965 | 4.1044 | 6.0945 | 4.9514 | 4.1538 | 1.6169 | 14.2693 | 15.4618 | 15.4618 | 0
554 | 3.6562 | 5.9154 | 5.5054 | 5.7075 | 4.2433 | 1.4774 | 16.7566 | 14.8824 | 16.7566 | 1
555 | 2.9342 | 6.2725 | 6.3359 | 6.9243 | 5.7141 | 1.9935 | 18.1245 | 16.9777 | 18.1245 | 1
556 | 3.9 | 4.7206 | 7.3646 | 4.8828 | 4.9236 | 1.2591 | 14.7626 | 17.4473 | 17.4473 | 0
557 | 4.22 | 5.33 | 7.0382 | 5.4471 | 4.1315 | 1.4244 | 16.4216 | 16.8141 | 16.8141 | 0
558 | 5.0976 | 4.9942 | 5.5609 | 6.5365 | 5.0972 | 1.7406 | 18.3688 | 17.4962 | 18.3688 | 1
559 | 4.1764 | 5.1241 | 7.1946 | 5.5667 | 3.9093 | 1.4182 | 16.2854 | 16.6986 | 16.6986 | 0
560 | 4.838 | 5.5829 | 6.6636 | 5.2813 | 3.8444 | 1.6703 | 17.3725 | 17.0164 | 17.3725 | 1
561 | 3.441 | 4.4169 | 5.1808 | 5.4361 | 3.6323 | 1.9665 | 15.2605 | 14.2205 | 15.2605 | 1
562 | 3.2803 | 4.3781 | 6.5479 | 4.7149 | 3.44 | 2.1223 | 14.4956 | 15.3905 | 15.3905 | 0
563 | 4.6496 | 4.6658 | 5.108 | 6.2858 | 4.1714 | 1.2766 | 16.8777 | 15.2056 | 16.8777 | 1
564 | 3.135 | 4.0085 | 6.9035 | 6.4226 | 5.0464 | 1.4063 | 14.9724 | 16.4912 | 16.4912 | 0
565 | 2.9448 | 4.8438 | 6.5418 | 5.7917 | 3.9572 | 1.7166 | 15.2969 | 15.1604 | 15.2969 | 1
566 | 4.3371 | 4.4379 | 3.0694 | 4.823 | 3.9177 | 2.4182 | 16.0161 | 13.7424 | 16.0161 | 1
567 | 2.7965 | 5.0098 | 5.3839 | 5.9968 | 5.4337 | 1.6516 | 15.4548 | 15.2658 | 15.4548 | 1
568 | 3.3256 | 5.2413 | 5.9445 | 6.9826 | 4.51 | 2.0672 | 17.6167 | 15.8474 | 17.6167 | 1
569 | 2.8734 | 6.5411 | 4.7989 | 6.0552 | 4.2255 | 1.3318 | 16.8016 | 13.2297 | 16.8016 | 1
570 | 2.3891 | 6.0447 | 7.2622 | 4.5115 | 4.1767 | 2.3032 | 15.2485 | 16.1312 | 16.1312 | 0
571 | 3.777 | 5.644 | 5.1902 | 5.8551 | 4.1122 | 1.9158 | 17.1919 | 14.9952 | 17.1919 | 1
572 | 4.0068 | 5.3844 | 5.709 | 4.9748 | 4.8613 | 1.2191 | 15.585 | 15.7962 | 15.7962 | 0
573 | 3.6322 | 4.9193 | 5.6782 | 4.1105 | 5.9528 | 2.2349 | 14.8968 | 17.498 | 17.498 | 0
574 | 3.7233 | 3.6258 | 6.8516 | 4.0912 | 4.1728 | 2.2088 | 13.649 | 16.9564 | 16.9564 | 0
575 | 4.4481 | 6.3296 | 6.5098 | 5.2685 | 3.2344 | 1.8239 | 17.8701 | 16.0161 | 17.8701 | 1
576 | 3.7017 | 4.9087 | 5.0276 | 5.2858 | 3.9023 | 1.4014 | 15.2976 | 14.033 | 15.2976 | 1
577 | 3.3883 | 6.1214 | 4.7141 | 5.7025 | 4.8991 | 1.969 | 17.1812 | 14.9704 | 17.1812 | 1
578 | 2.2518 | 6.4239 | 4.0706 | 4.928 | 5.2868 | 1.8815 | 15.4852 | 13.4907 | 15.4852 | 1
579 | 3.8653 | 4.5854 | 4.8573 | 5.846 | 4.8097 | 1.4895 | 15.7861 | 15.0218 | 15.7861 | 1
580 | 4.0815 | 5.546 | 3.8736 | 5.3651 | 4.8469 | 1.8609 | 16.8534 | 14.6629 | 16.8534 | 1
581 | 4.6438 | 5.0284 | 5.1963 | 5.2146 | 4.0856 | 1.5956 | 16.4824 | 15.5212 | 16.4824 | 1
582 | 3.5601 | 4.8835 | 6.5377 | 4.1977 | 5.2167 | 2.1485 | 14.7899 | 17.4631 | 17.4631 | 0
583 | 4.85 | 5.834 | 7.5873 | 7.3755 | 3.707 | 2.0615 | 20.121 | 18.2059 | 20.121 | 1
584 | 5.731 | 5.1135 | 5.4863 | 4.6686 | 5.4486 | 2.271 | 17.7842 | 18.9369 | 18.9369 | 0
585 | 4.7425 | 5.2838 | 6.4668 | 6.1617 | 5.4679 | 2.1209 | 18.3089 | 18.798 | 18.798 | 0
586 | 4.7496 | 6.797 | 2.8619 | 5.1615 | 4.4663 | 1.7557 | 18.4638 | 13.8335 | 18.4638 | 1
587 | 3.838 | 4.3563 | 4.9015 | 5.0965 | 3.7714 | 2.1919 | 15.4828 | 14.7028 | 15.4828 | 1
588 | 2.9646 | 6.7397 | 3.5898 | 5.075 | 4.646 | 2.0691 | 16.8483 | 13.2695 | 16.8483 | 1
589 | 3.6105 | 7.1244 | 3.0159 | 4.4288 | 5.3166 | 1.9305 | 17.0941 | 13.8735 | 17.0941 | 1
590 | 3.3578 | 4.7352 | 5.6337 | 4.2239 | 4.3621 | 1.4299 | 13.7468 | 14.7834 | 14.7834 | 0
591 | 3.5586 | 7.7121 | 4.1078 | 5.1534 | 5.0022 | 2.0906 | 18.5147 | 14.7592 | 18.5147 | 1
592 | 3.3817 | 4.6014 | 6.3361 | 4.952 | 4.0056 | 1.2978 | 14.233 | 15.0212 | 15.0212 | 0
593 | 4.7972 | 4.9177 | 4.9165 | 5.9228 | 4.5098 | 2.0694 | 17.707 | 16.2929 | 17.707 | 1
594 | 4.8623 | 4.6014 | 5.5547 | 5.3667 | 5.8671 | 1.2476 | 16.078 | 17.5317 | 17.5317 | 0
595 | 5.4712 | 4.9556 | 4.8555 | 4.1079 | 5.3012 | 1.4072 | 15.9419 | 17.035 | 17.035 | 0
596 | 5.113 | 5.6639 | 4.0242 | 4.9253 | 4.9725 | 1.931 | 17.6332 | 16.0407 | 17.6332 | 1
597 | 4.3753 | 6.1048 | 3.7455 | 4.737 | 4.5104 | 1.3695 | 16.5865 | 14.0007 | 16.5865 | 1
598 | 5.305 | 5.1564 | 6.4793 | 6.3092 | 4.3738 | 2.1163 | 18.8869 | 18.2744 | 18.8869 | 1
599 | 3.2167 | 5.7891 | 4.0541 | 6.0359 | 3.405 | 2.3425 | 17.3843 | 13.0184 | 17.3843 | 1
600 | 4.6127 | 5.481 | 6.8327 | 5.9646 | 3.7895 | 2.0601 | 18.1184 | 17.2951 | 18.1184 | 1
601 | 3.3426 | 5.5801 | 5.5332 | 4.3695 | 4.9378 | 1.5344 | 14.8265 | 15.3478 | 15.3478 | 0
602 | 4.3454 | 4.5493 | 5.0372 | 5.1603 | 3.366 | 2.1945 | 16.2495 | 14.9431 | 16.2495 | 1
603 | 4.3676 | 5.6543 | 6.0857 | 4.9839 | 3.6605 | 2.1705 | 17.1763 | 16.2844 | 17.1763 | 1
604 | 3.668 | 5.7653 | 5.8466 | 6.0268 | 4.6501 | 2.0471 | 17.5072 | 16.2119 | 17.5072 | 1
605 | 4.7824 | 6.3122 | 6.2729 | 4.4757 | 4.9763 | 1.5147 | 17.085 | 17.5463 | 17.5463 | 0
606 | 5.8922 | 3.5203 | 5.7882 | 5.2842 | 4.1094 | 2.6304 | 17.327 | 18.4201 | 18.4201 | 0
607 | 2.8886 | 5.4817 | 4.3563 | 4.9716 | 4.5046 | 2.2359 | 15.5778 | 13.9854 | 15.5778 | 1
608 | 5.0831 | 5.2943 | 6.6477 | 5.6527 | 3.4345 | 1.5069 | 17.537 | 16.6722 | 17.537 | 1
609 | 3.4773 | 5.0522 | 4.2295 | 6.5652 | 5.3298 | 2.523 | 17.6178 | 15.5597 | 17.6178 | 1
610 | 5.4459 | 3.9453 | 5.584 | 5.7087 | 4.9087 | 2.0678 | 17.1677 | 18.0064 | 18.0064 | 0
611 | 4.1999 | 3.7958 | 5.2807 | 7.0743 | 3.8134 | 2.3553 | 17.4253 | 15.6493 | 17.4253 | 1
612 | 4.2957 | 8.1968 | 6.4514 | 6.4176 | 4.1867 | 1.4727 | 20.3828 | 16.4065 | 20.3828 | 1
613 | 2.7452 | 4.7418 | 4.7993 | 6.1927 | 4.5616 | 2.3711 | 16.0509 | 14.4773 | 16.0509 | 1
614 | 4.6422 | 6.2153 | 7.0627 | 4.738 | 4.36 | 2.3435 | 17.9388 | 18.4083 | 18.4083 | 0
615 | 4.4061 | 5.4291 | 7.1242 | 6.0975 | 4.9627 | 2.2989 | 18.2317 | 18.7919 | 18.7919 | 0
616 | 4.2585 | 5.407 | 6.1824 | 5.8069 | 3.7965 | 2.1704 | 17.6429 | 16.4078 | 17.6429 | 1
617 | 2.765 | 5.7131 | 3.9951 | 5.9392 | 3.3694 | 2.1278 | 16.5451 | 12.2574 | 16.5451 | 1
618 | 3.4266 | 3.4083 | 6.3887 | 5.8571 | 5.3077 | 2.1435 | 14.8355 | 17.2665 | 17.2665 | 0
619 | 3.5795 | 3.165 | 7.4554 | 4.7393 | 4.3482 | 1.6313 | 13.1151 | 17.0144 | 17.0144 | 0
620 | 4.1094 | 5.8437 | 6.5558 | 4.9777 | 3.9104 | 1.9174 | 16.8482 | 16.493 | 16.8482 | 1
621 | 3.8772 | 6.6769 | 7.3449 | 5.3813 | 4.1996 | 1.7761 | 17.7116 | 17.1978 | 17.7116 | 1
622 | 4.6097 | 7.7909 | 4.7056 | 5.3218 | 3.4276 | 2.1776 | 19.8999 | 14.9204 | 19.8999 | 1
623 | 3.5646 | 6.8219 | 5.8859 | 5.6533 | 4.7246 | 2.1787 | 18.2185 | 16.3538 | 18.2185 | 1
624 | 5.2429 | 5.9131 | 7.1971 | 4.7903 | 5.1975 | 2.4219 | 18.3681 | 20.0593 | 20.0593 | 0
625 | 3.8147 | 4.7535 | 5.0503 | 5.9198 | 5.8083 | 2.445 | 16.933 | 17.1183 | 17.1183 | 0
626 | 3.5743 | 7.537 | 4.9722 | 4.4135 | 6.0373 | 2.2968 | 17.8215 | 16.8806 | 17.8215 | 1
627 | 3.5146 | 6.0219 | 3.2048 | 5.867 | 5.6481 | 1.5802 | 16.9837 | 13.9477 | 16.9837 | 1
628 | 4.1982 | 3.4854 | 6.426 | 5.9609 | 4.2922 | 2.1409 | 15.7854 | 17.0573 | 17.0573 | 0
629 | 3.9483 | 5.7957 | 6.5811 | 4.4267 | 4.3608 | 1.4887 | 15.6594 | 16.3789 | 16.3789 | 0
630 | 3.4257 | 5.6755 | 6.0255 | 5.4078 | 4.8047 | 2.2291 | 16.7381 | 16.485 | 16.7381 | 1
631 | 4.7435 | 5.8153 | 7.117 | 5.9982 | 3.2513 | 2.3351 | 18.8921 | 17.4469 | 18.8921 | 1
632 | 3.4023 | 4.7572 | 5.1657 | 4.8155 | 4.9079 | 2.0681 | 15.0432 | 15.544 | 15.544 | 0
633 | 2.7372 | 4.2439 | 4.9712 | 5.2269 | 5.2676 | 2.0219 | 14.2299 | 14.998 | 14.998 | 0
634 | 2.9445 | 3.5724 | 6.6766 | 4.6764 | 3.3069 | 1.1739 | 12.3672 | 14.1019 | 14.1019 | 0
635 | 5.231 | 5.388 | 6.791 | 6.8826 | 4.263 | 1.5945 | 19.0961 | 17.8795 | 19.0961 | 1
636 | 3.768 | 4.4966 | 4.0075 | 5.1588 | 4.4722 | 1.8978 | 15.3213 | 14.1456 | 15.3213 | 1
637 | 3.9572 | 5.4461 | 6.274 | 4.851 | 4.1223 | 2.2237 | 16.4779 | 16.5772 | 16.5772 | 0
638 | 4.3243 | 3.8595 | 6.5208 | 4.972 | 4.2912 | 2.1116 | 15.2674 | 17.248 | 17.248 | 0
639 | 3.4796 | 4.8497 | 5.9792 | 6.5514 | 3.8484 | 2.6742 | 17.5548 | 15.9814 | 17.5548 | 1
640 | 4.9648 | 3.7748 | 6.8761 | 5.5805 | 5.2829 | 2.5656 | 16.8856 | 19.6894 | 19.6894 | 0
641 | 2.606 | 4.5286 | 5.3843 | 4.8425 | 5.4208 | 2.2749 | 14.252 | 15.6859 | 15.6859 | 0
642 | 3.4103 | 3.3202 | 7.4297 | 6.6866 | 3.9872 | 2.0981 | 15.5151 | 16.9253 | 16.9253 | 0
643 | 4.1134 | 5.2302 | 6.4184 | 5.0582 | 5.3521 | 1.8224 | 16.2242 | 17.7064 | 17.7064 | 0
644 | 5.5908 | 6.0832 | 3.0112 | 4.7628 | 3.1982 | 2.5764 | 19.0133 | 14.3766 | 19.0133 | 1
645 | 5.1102 | 5.2481 | 4.7209 | 5.956 | 3.2828 | 1.4467 | 17.761 | 14.5605 | 17.761 | 1
646 | 5.0678 | 7.7724 | 6.0611 | 5.0421 | 4.0989 | 2.1907 | 20.073 | 17.4185 | 20.073 | 1
647 | 4.6798 | 4.4335 | 3.5672 | 4.8485 | 4.5294 | 2.5798 | 16.5415 | 15.3561 | 16.5415 | 1
648 | 3.4723 | 4.5322 | 6.7821 | 5.4762 | 3.8001 | 1.867 | 15.3476 | 15.9214 | 15.9214 | 0
649 | 2.6988 | 5.2958 | 5.8566 | 4.3392 | 3.9615 | 2.1153 | 14.4492 | 14.6323 | 14.6323 | 0
650 | 3.5525 | 5.3629 | 5.6712 | 5.2742 | 3.7562 | 2.0846 | 16.2743 | 15.0646 | 16.2743 | 1
651 | 4.9661 | 7.5037 | 5.7403 | 6.1487 | 4.7767 | 2.5931 | 21.2115 | 18.0762 | 21.2115 | 1
652 | 3.5009 | 6.3186 | 6.153 | 5.5579 | 4.1418 | 1.9193 | 17.2966 | 15.715 | 17.2966 | 1
653 | 3.0397 | 3.9585 | 6.6241 | 5.747 | 3.8495 | 2.431 | 15.1762 | 15.9444 | 15.9444 | 0
654 | 4.0249 | 5.8075 | 6.299 | 4.7912 | 3.3757 | 2.36 | 16.9836 | 16.0595 | 16.9836 | 1
655 | 4.1978 | 4.8002 | 4.8649 | 6.3695 | 4.8128 | 2.2163 | 17.5839 | 16.0919 | 17.5839 | 1
656 | 4.8661 | 4.3961 | 3.5151 | 4.1808 | 3.7439 | 1.9674 | 15.4104 | 14.0924 | 15.4104 | 1
657 | 4.7554 | 6.0519 | 6.5168 | 4.2969 | 4.4762 | 2.6706 | 17.7749 | 18.419 | 18.419 | 0
658 | 3.7427 | 4.4637 | 5.8901 | 4.3613 | 4.8564 | 2.007 | 14.5748 | 16.4962 | 16.4962 | 0
659 | 4.5665 | 4.0355 | 5.9503 | 6.2202 | 4.0132 | 2.4359 | 17.2581 | 16.9659 | 17.2581 | 1
660 | 4.4698 | 7.4027 | 6.1189 | 4.0906 | 5.4341 | 2.2133 | 18.1765 | 18.2362 | 18.2362 | 0
661 | 3.9072 | 3.8587 | 5.0646 | 5.7068 | 4.2879 | 1.698 | 15.1707 | 14.9577 | 15.1707 | 1
662 | 4.2997 | 5.4438 | 4.5672 | 5.6072 | 4.2818 | 2.1387 | 17.4894 | 15.2874 | 17.4894 | 1
663 | 3.5546 | 4.4212 | 5.5735 | 6.167 | 3.8338 | 1.5932 | 15.736 | 14.5551 | 15.736 | 1
664 | 4.1826 | 4.1219 | 6.4943 | 6.6952 | 4.8795 | 1.9309 | 16.9307 | 17.4874 | 17.4874 | 0
665 | 5.0165 | 6.2293 | 5.5476 | 4.6449 | 3.9561 | 2.7291 | 18.6197 | 17.2493 | 18.6197 | 1
666 | 3.3742 | 7.9528 | 5.7935 | 6.9086 | 5.1644 | 2.4102 | 20.6458 | 16.7423 | 20.6458 | 1
667 | 4.6033 | 3.7572 | 7.1746 | 6.3378 | 3.7832 | 1.7472 | 16.4454 | 17.3083 | 17.3083 | 0
668 | 3.8251 | 4.642 | 3.4665 | 4.9365 | 3.334 | 1.5092 | 14.9128 | 12.1349 | 14.9128 | 1
669 | 2.8101 | 3.672 | 6.4123 | 5.3096 | 3.6526 | 2.4871 | 14.2788 | 15.3621 | 15.3621 | 0
670 | 4.2958 | 7.9056 | 5.7801 | 4.9269 | 3.5772 | 1.879 | 19.0073 | 15.5321 | 19.0073 | 1
671 | 3.9068 | 5.9975 | 3.9769 | 4.6613 | 4.32 | 2.1794 | 16.745 | 14.3831 | 16.745 | 1
672 | 4.7101 | 5.2869 | 5.6229 | 6.4351 | 3.8327 | 1.8122 | 18.2444 | 15.9779 | 18.2444 | 1
673 | 3.8865 | 5.2457 | 4.4386 | 5.4082 | 5.3684 | 1.7188 | 16.2592 | 15.4123 | 16.2592 | 1
674 | 4.5531 | 4.0889 | 3.5955 | 4.355 | 4.9137 | 2.1302 | 15.1272 | 15.1924 | 15.1924 | 0
675 | 4.1303 | 4.5638 | 4.1426 | 4.8881 | 4.1804 | 1.4684 | 15.0506 | 13.9217 | 15.0506 | 1
676 | 3.052 | 5.6631 | 7.4448 | 5.472 | 4.0958 | 2.2607 | 16.4478 | 16.8533 | 16.8533 | 0
677 | 4.6519 | 7.3036 | 4.2244 | 5.6707 | 4.0027 | 1.8344 | 19.4606 | 14.7133 | 19.4606 | 1
678 | 2.551 | 5.3011 | 6.0046 | 4.1472 | 4.3631 | 2.2769 | 14.2763 | 15.1956 | 15.1956 | 0
679 | 4.8096 | 4.1493 | 5.7262 | 5.427 | 5.1461 | 2.4316 | 16.8175 | 18.1135 | 18.1135 | 0
680 | 4.466 | 3.9459 | 6.5815 | 5.8421 | 3.4676 | 1.5156 | 15.7696 | 16.0307 | 16.0307 | 0
681 | 3.7328 | 5.0605 | 3.7707 | 6.5455 | 3.7094 | 1.7163 | 17.0551 | 12.9292 | 17.0551 | 1
682 | 4.8765 | 5.8444 | 4.7753 | 5.2479 | 4.504 | 2.0946 | 18.0634 | 16.2504 | 18.0634 | 1
683 | 4.1605 | 5.2961 | 5.6761 | 5.3398 | 5.9086 | 1.633 | 16.4294 | 17.3783 | 17.3783 | 0
684 | 3.8946 | 6.8772 | 6.0454 | 4.1219 | 3.8585 | 2.0014 | 16.8951 | 15.8 | 16.8951 | 1
685 | 3.243 | 4.3285 | 6.9837 | 5.5646 | 4.6339 | 1.9695 | 15.1056 | 16.8301 | 16.8301 | 0
686 | 3.7107 | 4.8489 | 6.5896 | 5.4059 | 3.6904 | 2.2653 | 16.2308 | 16.256 | 16.256 | 0
687 | 4.6296 | 5.5839 | 6.1519 | 5.8245 | 5.2097 | 2.138 | 18.1761 | 18.1292 | 18.1761 | 1
688 | 2.6225 | 4.8909 | 6.0718 | 5.792 | 3.717 | 2.6525 | 15.9579 | 15.0639 | 15.9579 | 1
689 | 3.7846 | 5.7162 | 4.9571 | 4.4321 | 5.3916 | 1.7606 | 15.6935 | 15.894 | 15.894 | 0
690 | 3.573 | 4.7018 | 7.6811 | 4.7544 | 3.1247 | 2.0165 | 15.0457 | 16.3953 | 16.3953 | 0
691 | 2.6934 | 4.7163 | 6.2106 | 5.5672 | 5.5387 | 1.3546 | 14.3315 | 15.7974 | 15.7974 | 0
692 | 3.8209 | 6.0787 | 5.5912 | 5.2994 | 3.6856 | 1.9371 | 17.136 | 15.0347 | 17.136 | 1
693 | 2.9733 | 8.2252 | 5.232 | 4.8886 | 5.2792 | 2.0458 | 18.1328 | 15.5303 | 18.1328 | 1
694 | 3.0314 | 5.7819 | 6.6834 | 5.626 | 4.4671 | 1.813 | 16.2523 | 15.9949 | 16.2523 | 1
695 | 4.0526 | 4.904 | 4.5109 | 4.9347 | 4.9594 | 1.3721 | 15.2634 | 14.8949 | 15.2634 | 1
696 | 5.2082 | 8.1669 | 4.4699 | 4.8402 | 4.9174 | 2.914 | 21.1292 | 17.5095 | 21.1292 | 1
697 | 4.6232 | 3.7083 | 5.7308 | 4.3767 | 4.3867 | 1.9893 | 14.6975 | 16.73 | 16.73 | 0
698 | 2.3849 | 4.6946 | 4.2055 | 6.5599 | 4.4372 | 1.3638 | 15.0032 | 12.3913 | 15.0032 | 1
699 | 4.0672 | 4.9487 | 3.9373 | 6.013 | 5.4854 | 2.6338 | 17.6628 | 16.1238 | 17.6628 | 1
700 | 4.7581 | 7.77 | 4.6909 | 5.0011 | 3.6786 | 1.9223 | 19.4515 | 15.0499 | 19.4515 | 1
701 | 5.0031 | 5.6546 | 6.2152 | 5.842 | 3.7193 | 1.4784 | 17.9781 | 16.416 | 17.9781 | 1
702 | 4.9603 | 5.7248 | 6.0978 | 4.8347 | 4.8199 | 1.7491 | 17.269 | 17.6271 | 17.6271 | 0
703 | 3.5586 | 4.7763 | 2.9484 | 5.1894 | 5.599 | 2.3424 | 15.8667 | 14.4483 | 15.8667 | 1
704 | 4.5066 | 4.0184 | 4.8797 | 4.2431 | 5.822 | 1.3311 | 14.0993 | 16.5395 | 16.5395 | 0
705 | 3.7928 | 4.5194 | 4.9304 | 4.5958 | 4.9353 | 1.3416 | 14.2496 | 15.0001 | 15.0001 | 0
706 | 3.3674 | 4.0923 | 7.3913 | 5.9735 | 4.6061 | 2.3396 | 15.7728 | 17.7043 | 17.7043 | 0
707 | 4.0353 | 4.2976 | 5.2148 | 5.8099 | 3.6726 | 2.277 | 16.4198 | 15.1997 | 16.4198 | 1
708 | 3.6723 | 6.0817 | 6.4486 | 4.7546 | 4.872 | 2.195 | 16.7037 | 17.188 | 17.188 | 0
709 | 4.2255 | 4.0456 | 4.4034 | 4.2034 | 5.4004 | 2.4792 | 14.9537 | 16.5086 | 16.5086 | 0
710 | 3.5205 | 3.9082 | 5.5157 | 6.1189 | 5.003 | 1.382 | 14.9296 | 15.4212 | 15.4212 | 0
711 | 3.6248 | 6.4049 | 6.6614 | 6.5835 | 3.417 | 1.4629 | 18.0761 | 15.1661 | 18.0761 | 1
712 | 3.8713 | 6.8541 | 5.6865 | 4.9404 | 3.459 | 2.0918 | 17.7576 | 15.1085 | 17.7576 | 1
713 | 4.0374 | 6.6064 | 4.4135 | 4.9502 | 4.5137 | 1.9322 | 17.5262 | 14.8969 | 17.5262 | 1
714 | 3.308 | 4.5304 | 7.2938 | 4.2866 | 4.6732 | 1.9146 | 14.0396 | 17.1896 | 17.1896 | 0
715 | 3.8133 | 3.4998 | 7.2632 | 5.0101 | 4.0771 | 1.9566 | 14.2798 | 17.1102 | 17.1102 | 0
716 | 5.7833 | 4.8746 | 3.9287 | 4.7342 | 3.3845 | 2.1986 | 17.5906 | 15.295 | 17.5906 | 1
717 | 3.0136 | 3.6124 | 3.9562 | 4.8813 | 5.4785 | 1.4747 | 12.9819 | 13.923 | 13.923 | 0
718 | 3.6235 | 6.6345 | 6.6919 | 5.8638 | 5.9753 | 2.0574 | 18.1792 | 18.3481 | 18.3481 | 0
719 | 4.5356 | 4.4419 | 7.6668 | 5.1347 | 4.709 | 1.7938 | 15.906 | 18.7052 | 18.7052 | 0
720 | 3.4559 | 4.8758 | 7.7829 | 4.7948 | 4.6186 | 1.1456 | 14.2721 | 17.003 | 17.003 | 0
721 | 2.7912 | 3.861 | 6.7949 | 5.3385 | 5.0746 | 1.6727 | 13.6634 | 16.3333 | 16.3333 | 0
722 | 2.9118 | 4.9631 | 6.3439 | 4.4489 | 3.893 | 2.1644 | 14.4882 | 15.3131 | 15.3131 | 0
723 | 5.1231 | 4.2416 | 6.2052 | 5.5237 | 4.1559 | 1.6412 | 16.5295 | 17.1254 | 17.1254 | 0
724 | 3.4513 | 6.2997 | 6.8673 | 4.2188 | 4.9371 | 2.4949 | 16.4646 | 17.7505 | 17.7505 | 0
725 | 5.6074 | 8.5472 | 6.0117 | 5.7502 | 5.5957 | 2.6812 | 22.5859 | 19.896 | 22.5859 | 1
726 | 4.5291 | 3.9097 | 5.5704 | 6.4633 | 3.1248 | 1.7548 | 16.6568 | 14.9791 | 16.6568 | 1
727 | 5.3982 | 4.4015 | 7.0608 | 5.4855 | 4.3754 | 2.1567 | 17.4419 | 18.9911 | 18.9911 | 0
728 | 5.3262 | 6.1534 | 4.6048 | 4.7073 | 4.4706 | 1.5706 | 17.7575 | 15.9722 | 17.7575 | 1
729 | 3.7057 | 6.64 | 5.8491 | 5.1763 | 5.7727 | 1.7543 | 17.2763 | 17.0818 | 17.2763 | 1
730 | 4.4242 | 4.354 | 4.9527 | 4.1676 | 3.344 | 2.1943 | 15.1401 | 14.9152 | 15.1401 | 1
731 | 4.0222 | 6.2914 | 4.3582 | 5.2192 | 5.0348 | 2.437 | 17.9698 | 15.8522 | 17.9698 | 1
732 | 4.438 | 4.9847 | 7.3296 | 4.7325 | 5.0269 | 2.6512 | 16.8063 | 19.4457 | 19.4457 | 0
733 | 3.8132 | 5.0803 | 7.538 | 5.0842 | 4.7044 | 1.7308 | 15.7086 | 17.7865 | 17.7865 | 0
734 | 3.951 | 4.2022 | 7.1968 | 5.791 | 3.4363 | 2.1225 | 16.0667 | 16.7066 | 16.7066 | 0
735 | 4.2752 | 5.8107 | 4.1903 | 5.0361 | 4.5133 | 2.8321 | 17.9541 | 15.811 | 17.9541 | 1
736 | 4.2566 | 4.3813 | 6.1614 | 4.5682 | 3.5133 | 2.2381 | 15.4442 | 16.1693 | 16.1693 | 0
737 | 3.1164 | 4.6842 | 6.2273 | 4.2803 | 3.7248 | 1.6283 | 13.7092 | 14.6967 | 14.6967 | 0
738 | 3.2 | 6.2944 | 4.0505 | 4.9614 | 3.74 | 1.9266 | 16.3825 | 12.9171 | 16.3825 | 1
739 | 3.7714 | 8.3894 | 5.1881 | 5.1309 | 5.4964 | 1.4456 | 18.7374 | 15.9016 | 18.7374 | 1
740 | 4.6385 | 6.0924 | 6.8205 | 4.4661 | 3.5873 | 1.564 | 16.7611 | 16.6104 | 16.7611 | 1
741 | 4.5517 | 5.2731 | 6.6737 | 5.0578 | 3.6283 | 1.535 | 16.4176 | 16.3888 | 16.4176 | 1
742 | 3.3582 | 4.3026 | 4.6359 | 5.0582 | 3.8266 | 2.2366 | 14.9557 | 14.0573 | 14.9557 | 1
743 | 4.5811 | 5.7418 | 5.6813 | 5.6714 | 5.8845 | 1.7272 | 17.7215 | 17.8741 | 17.8741 | 0
744 | 4.0759 | 5.0844 | 5.182 | 4.4498 | 4.6387 | 1.5707 | 15.1808 | 15.4672 | 15.4672 | 0
745 | 4.0649 | 3.7767 | 6.7431 | 4.6834 | 3.6162 | 1.2309 | 13.7559 | 15.6552 | 15.6552 | 0
746 | 3.9745 | 3.8564 | 5.9554 | 6.5019 | 4.8414 | 2.0839 | 16.4167 | 16.8551 | 16.8551 | 0
747 | 2.8985 | 6.0925 | 6.9734 | 4.6404 | 5.2271 | 2.2081 | 15.8396 | 17.3071 | 17.3071 | 0
748 | 3.0844 | 5.5473 | 6.4304 | 5.6305 | 3.7075 | 2.3955 | 16.6577 | 15.6179 | 16.6577 | 1
749 | 4.3644 | 6.9765 | 4.6875 | 5.4472 | 3.6602 | 1.4816 | 18.2697 | 14.1937 | 18.2697 | 1
750 | 3.2678 | 5.0926 | 5.0902 | 6.5716 | 3.3824 | 2.5264 | 17.4585 | 14.2668 | 17.4585 | 1
751 | 3.6335 | 3.9517 | 6.6253 | 5.3766 | 4.9899 | 1.2994 | 14.2612 | 16.5481 | 16.5481 | 0
752 | 4.6564 | 4.2496 | 5.2316 | 5.5147 | 3.9702 | 2.4088 | 16.8295 | 16.2671 | 16.8295 | 1
753 | 3.3565 | 4.8473 | 4.1547 | 4.7142 | 4.4045 | 2.2066 | 15.1246 | 14.1222 | 15.1246 | 1
754 | 4.0178 | 6.2666 | 4.4143 | 6.4905 | 6.2634 | 2.111 | 18.8858 | 16.8065 | 18.8858 | 1
755 | 4.4016 | 4.8098 | 5.0471 | 4.2576 | 4.405 | 2.4886 | 15.9575 | 16.3423 | 16.3423 | 0
756 | 4.6307 | 4.9717 | 7.2617 | 4.5049 | 4.3454 | 2.0538 | 16.1612 | 18.2917 | 18.2917 | 0
757 | 3.4303 | 3.4279 | 7.7177 | 5.8255 | 3.2623 | 1.5949 | 14.2787 | 16.0052 | 16.0052 | 0
758 | 3.4086 | 6.2637 | 6.6046 | 6.358 | 4.0622 | 2.3665 | 18.3967 | 16.4419 | 18.3967 | 1
759 | 3.2914 | 4.1681 | 5.8361 | 5.6959 | 3.3473 | 2.1323 | 15.2876 | 14.6071 | 15.2876 | 1
760 | 3.5752 | 4.4552 | 7.4238 | 4.8095 | 4.4229 | 2.3363 | 15.1762 | 17.7583 | 17.7583 | 0
761 | 4.2484 | 4.5602 | 6.2458 | 5.828 | 3.4989 | 2.8887 | 17.5253 | 16.8818 | 17.5253 | 1
762 | 3.1472 | 7.4733 | 6.3225 | 5.4826 | 3.061 | 1.7483 | 17.8515 | 14.279 | 17.8515 | 1
763 | 3.9783 | 3.8089 | 6.4001 | 4.9425 | 4.8751 | 2.4703 | 15.2 | 17.7238 | 17.7238 | 0
764 | 3.0516 | 4.6004 | 5.0775 | 5.1945 | 3.2031 | 1.8804 | 14.7269 | 13.2126 | 14.7269 | 1
765 | 4.6782 | 4.5487 | 4.8376 | 4.5808 | 4.3099 | 1.2851 | 15.0929 | 15.1108 | 15.1108 | 0
766 | 3.5802 | 6.4159 | 5.9057 | 5.0527 | 4.4592 | 2.5372 | 17.586 | 16.4822 | 17.586 | 1
767 | 4.641 | 3.5645 | 5.3599 | 5.2215 | 3.4592 | 1.6178 | 15.0448 | 15.0779 | 15.0779 | 0
768 | 4.1555 | 3.5612 | 7.451 | 5.0696 | 4.3535 | 1.3143 | 14.1006 | 17.2742 | 17.2742 | 0
769 | 3.5217 | 4.0586 | 4.9013 | 4.9081 | 4.8835 | 1.996 | 14.4845 | 15.3025 | 15.3025 | 0
770 | 4.9703 | 3.2526 | 4.4969 | 5.5024 | 3.3536 | 1.6951 | 15.4203 | 14.5158 | 15.4203 | 1
771 | 5.3206 | 4.7955 | 7.3063 | 5.3081 | 4.3776 | 2.1221 | 17.5461 | 19.1264 | 19.1264 | 0
772 | 3.5042 | 3.7317 | 5.6369 | 4.5867 | 3.8781 | 1.189 | 13.0116 | 14.2082 | 14.2082 | 0
773 | 4.0927 | 5.1721 | 5.2984 | 6.162 | 3.4524 | 1.9094 | 17.3361 | 14.7529 | 17.3361 | 1
774 | 3.6657 | 3.6533 | 7.0754 | 5.0959 | 3.8768 | 1.8231 | 14.238 | 16.441 | 16.441 | 0
775 | 5.0022 | 4.9576 | 7.1468 | 4.2706 | 5.1519 | 1.9721 | 16.2025 | 19.2731 | 19.2731 | 0
776 | 4.29 | 5.7651 | 5.8235 | 5.0482 | 3.4584 | 1.5389 | 16.6422 | 15.1107 | 16.6422 | 1
777 | 3.4529 | 4.8119 | 5.5592 | 5.0479 | 4.1294 | 1.6198 | 14.9324 | 14.7612 | 14.9324 | 1
778 | 3.0409 | 6.5953 | 5.8061 | 5.8575 | 4.3685 | 1.3537 | 16.8474 | 14.5692 | 16.8474 | 1
779 | 3.4669 | 4.2066 | 5.5545 | 5.1564 | 3.9225 | 2.1819 | 15.0117 | 15.1257 | 15.1257 | 0
780 | 4.7291 | 5.0324 | 4.7357 | 5.326 | 4.0186 | 2.0673 | 17.1548 | 15.5507 | 17.1548 | 1
781 | 5.012 | 5.4174 | 6.219 | 4.4772 | 4.0082 | 2.4679 | 17.3745 | 17.7071 | 17.7071 | 0
782 | 3.4078 | 5.449 | 6.1597 | 5.7954 | 5.1237 | 2.1968 | 16.849 | 16.888 | 16.888 | 0
783 | 4.881 | 5.0703 | 6.8932 | 6.2124 | 4.2658 | 1.8946 | 18.0583 | 17.9346 | 18.0583 | 1
784 | 3.8307 | 5.1199 | 5.9006 | 5.0101 | 3.5127 | 2.4967 | 16.4574 | 15.7407 | 16.4574 | 1
785 | 3.9087 | 6.3106 | 7.7389 | 5.5363 | 3.5568 | 2.4381 | 18.1937 | 17.6425 | 18.1937 | 1
786 | 4.6038 | 4.6361 | 5.751 | 4.9536 | 3.4413 | 2.0178 | 16.2113 | 15.8138 | 16.2113 | 1
787 | 4.8524 | 4.1038 | 6.82 | 6.0538 | 4.8302 | 2.1711 | 17.181 | 18.6737 | 18.6737 | 0
788 | 4.307 | 7.2818 | 6.5711 | 5.6514 | 4.141 | 1.9116 | 19.1518 | 16.9307 | 19.1518 | 1
789 | 4.033 | 5.9077 | 6.9257 | 5.856 | 3.9342 | 1.4018 | 17.1984 | 16.2946 | 17.1984 | 1
790 | 4.1551 | 6.7992 | 5.3089 | 4.8863 | 3.8375 | 1.7658 | 17.6063 | 15.0672 | 17.6063 | 1
791 | 4.8228 | 4.452 | 6.0196 | 5.9109 | 4.9518 | 1.9147 | 17.1004 | 17.7089 | 17.7089 | 0
792 | 3.8869 | 5.5633 | 6.179 | 4.4548 | 4.3433 | 2.3565 | 16.2615 | 16.7658 | 16.7658 | 0
793 | 3.9802 | 6.5716 | 7.1383 | 5.0372 | 5.4761 | 2.7019 | 18.2909 | 19.2965 | 19.2965 | 0
794 | 3.042 | 5.7324 | 6.3477 | 6.5721 | 4.0248 | 1.8404 | 17.1869 | 15.2549 | 17.1869 | 1
795 | 4.5643 | 6.3357 | 6.0316 | 5.6141 | 5.3122 | 2.1241 | 18.6383 | 18.0323 | 18.6383 | 1
796 | 4.1615 | 5.7212 | 6.8258 | 6.2239 | 4.2372 | 2.3419 | 18.4485 | 17.5664 | 18.4485 | 1
797 | 5.1429 | 5.8954 | 3.4049 | 5.3717 | 5.4529 | 2.2738 | 18.6838 | 16.2745 | 18.6838 | 1
798 | 3.2128 | 6.4198 | 7.7044 | 4.912 | 4.124 | 2.057 | 16.6016 | 17.0983 | 17.0983 | 0
799 | 3.0562 | 5.3264 | 4.1019 | 6.4934 | 4.4419 | 2.2436 | 17.1197 | 13.8436 | 17.1197 | 1
800 | 3.4813 | 5.7214 | 7.266 | 6.0336 | 4.4171 | 2.1867 | 17.423 | 17.351 | 17.423 | 1
801 | 4.4397 | 6.2201 | 4.8737 | 6.1112 | 4.363 | 2.4404 | 19.2113 | 16.1168 | 19.2113 | 1
802 | 3.6212 | 3.4749 | 6.1032 | 5.7115 | 4.3007 | 1.8206 | 14.6281 | 15.8457 | 15.8457 | 0
803 | 5.1472 | 6.0312 | 5.1197 | 4.5613 | 3.2323 | 2.5737 | 18.3134 | 16.0729 | 18.3134 | 1
804 | 4.2096 | 8.1162 | 5.2911 | 4.0464 | 5.2448 | 2.6819 | 19.0541 | 17.4275 | 19.0541 | 1
805 | 3.2797 | 6.2972 | 5.8513 | 6.6402 | 4.0329 | 2.4254 | 18.6425 | 15.5893 | 18.6425 | 1
806 | 3.2556 | 6.1245 | 5.4309 | 4.8047 | 4.2485 | 2.0622 | 16.2469 | 14.9972 | 16.2469 | 1
807 | 4.387 | 4.4082 | 5.6041 | 4.2357 | 5.0359 | 1.6632 | 14.6941 | 16.6902 | 16.6902 | 0
808 | 4.5006 | 6.4568 | 6.4659 | 5.7714 | 4.8165 | 2.4341 | 19.1628 | 18.2171 | 19.1628 | 1
809 | 4.746 | 4.1145 | 5.8972 | 4.7482 | 4.9397 | 1.6373 | 15.2459 | 17.2201 | 17.2201 | 0
810 | 3.0905 | 4.6051 | 5.8123 | 5.3654 | 5.1184 | 2.2672 | 15.3282 | 16.2884 | 16.2884 | 0
811 | 3.9242 | 3.3315 | 5.0273 | 5.0736 | 5.5394 | 1.9644 | 14.2937 | 16.4554 | 16.4554 | 0
812 | 3.6308 | 6.4059 | 6.2006 | 5.0577 | 3.8316 | 2.7265 | 17.8208 | 16.3895 | 17.8208 | 1
813 | 4.741 | 6.333 | 3.1968 | 6.5802 | 3.8159 | 1.8401 | 19.4942 | 13.5938 | 19.4942 | 1
814 | 4.6608 | 5.3728 | 5.6446 | 4.2178 | 4.6418 | 2.6665 | 16.918 | 17.6138 | 17.6138 | 0
815 | 3.2188 | 6.0683 | 4.999 | 5.4995 | 4.8019 | 2.6336 | 17.4201 | 15.6533 | 17.4201 | 1
816 | 2.933 | 3.5594 | 4.3088 | 5.3427 | 3.3398 | 1.9901 | 13.8252 | 12.5717 | 13.8252 | 1
817 | 3.005 | 5.7625 | 4.5035 | 6.0667 | 5.0801 | 1.3929 | 16.2271 | 13.9815 | 16.2271 | 1
818 | 4.5738 | 4.1121 | 6.2505 | 6.0737 | 5.8286 | 2.7557 | 17.5154 | 19.4087 | 19.4087 | 0
819 | 2.8521 | 7.2829 | 5.9276 | 4.8098 | 3.8281 | 1.9449 | 16.8897 | 14.5527 | 16.8897 | 1
820 | 3.3979 | 5.5241 | 5.9093 | 6.2842 | 3.9513 | 1.9959 | 17.2021 | 15.2544 | 17.2021 | 1
821 | 3.4776 | 3.7757 | 3.7516 | 5.6502 | 5.0171 | 2.3874 | 15.291 | 14.6337 | 15.291 | 1
822 | 3.3361 | 5.6111 | 6.1846 | 4.8068 | 3.1798 | 1.6679 | 15.4219 | 14.3684 | 15.4219 | 1
823 | 4.7748 | 5.7113 | 3.8032 | 4.6707 | 3.5903 | 2.5267 | 17.6834 | 14.695 | 17.6834 | 1
824 | 3.2639 | 4.0743 | 5.7128 | 5.4159 | 3.9102 | 2.2225 | 14.9766 | 15.1094 | 15.1094 | 0
825 | 3.2227 | 4.3028 | 5.6687 | 6.343 | 3.8672 | 1.9404 | 15.809 | 14.699 | 15.809 | 1
826 | 2.9228 | 6.8378 | 6.242 | 6.5343 | 3.8886 | 1.406 | 17.701 | 14.4594 | 17.701 | 1
827 | 4.657 | 3.1785 | 4.6091 | 4.1407 | 4.4145 | 2.3669 | 14.3431 | 16.0475 | 16.0475 | 0
828 | 4.6541 | 6.1398 | 4.0174 | 4.4846 | 5.4322 | 1.6877 | 16.9662 | 15.7914 | 16.9662 | 1
829 | 3.2462 | 5.9093 | 6.4704 | 5.81 | 3.3251 | 1.4279 | 16.3934 | 14.4696 | 16.3934 | 1
830 | 4.7648 | 6.9568 | 6.0086 | 4.5329 | 5.5983 | 1.9146 | 18.1691 | 18.2863 | 18.2863 | 0
831 | 4.1237 | 5.2805 | 4.8496 | 4.099 | 3.8772 | 2.588 | 16.0912 | 15.4385 | 16.0912 | 1
832 | 3.874 | 5.3322 | 6.7329 | 6.1132 | 4.8617 | 2.0004 | 17.3198 | 17.469 | 17.469 | 0
833 | 3.7371 | 6.3567 | 6.7221 | 5.252 | 5.1965 | 1.781 | 17.1268 | 17.4367 | 17.4367 | 0
834 | 4.312 | 4.8659 | 7.1787 | 4.2678 | 5.6989 | 2.288 | 15.7337 | 19.4776 | 19.4776 | 0
835 | 5.1208 | 7.5308 | 4.7812 | 5.3815 | 5.3974 | 2.5468 | 20.5798 | 17.8462 | 20.5798 | 1
836 | 3.4703 | 4.5874 | 6.6896 | 6.2067 | 3.0845 | 2.7433 | 17.0077 | 15.9877 | 17.0077 | 1
837 | 4.8647 | 4.3715 | 6.6209 | 5.0414 | 5.6758 | 1.8162 | 16.0938 | 18.9776 | 18.9776 | 0
838 | 4.2795 | 4.6471 | 5.7927 | 5.3849 | 5.122 | 1.9851 | 16.2966 | 17.1792 | 17.1792 | 0
839 | 3.8736 | 5.0326 | 5.8274 | 6.6517 | 4.4537 | 2.4722 | 18.0302 | 16.6269 | 18.0302 | 1
840 | 4.219 | 4.7399 | 6.9898 | 5.0572 | 3.8125 | 2.3118 | 16.3279 | 17.3331 | 17.3331 | 0
841 | 4.7176 | 5.1853 | 4.0274 | 5.6851 | 3.5584 | 1.6956 | 17.2836 | 13.999 | 17.2836 | 1
842 | 3.0498 | 5.4382 | 4.2031 | 4.2197 | 3.5723 | 1.8536 | 14.5613 | 12.6787 | 14.5613 | 1
843 | 3.0204 | 3.671 | 6.8969 | 4.2053 | 3.6866 | 1.6393 | 12.5361 | 15.2433 | 15.2433 | 0
844 | 3.3155 | 4.4643 | 7.3291 | 4.9057 | 4.4656 | 2.3403 | 15.0258 | 17.4505 | 17.4505 | 0
845 | 5.0599 | 4.5609 | 6.4695 | 5.5664 | 4.3205 | 2.4391 | 17.6263 | 18.289 | 18.289 | 0
846 | 3.3194 | 5.5838 | 6.5024 | 6.0328 | 4.0851 | 1.4286 | 16.3647 | 15.3355 | 16.3647 | 1
847 | 4.2338 | 3.6827 | 4.1538 | 5.7494 | 3.0273 | 1.6799 | 15.3458 | 13.0948 | 15.3458 | 1
848 | 3.0621 | 6.2922 | 6.5306 | 5.9618 | 5.6389 | 2.331 | 17.6472 | 17.5626 | 17.6472 | 1
849 | 3.844 | 4.2698 | 6.8927 | 5.6372 | 4.7207 | 1.9696 | 15.7206 | 17.427 | 17.427 | 0
850 | 3.2043 | 4.7789 | 4.0597 | 5.173 | 4.4955 | 2.1313 | 15.2875 | 13.8908 | 15.2875 | 1
851 | 3.5286 | 5.7781 | 3.9429 | 6.8516 | 4.7368 | 1.1845 | 17.3428 | 13.3928 | 17.3428 | 1
852 | 3.6612 | 5.9995 | 7.0476 | 5.2585 | 3.5656 | 1.7764 | 16.6956 | 16.0509 | 16.6956 | 1
853 | 4.6709 | 5.5068 | 5.6867 | 5.4512 | 4.4508 | 1.2152 | 16.8441 | 16.0237 | 16.8441 | 1
854 | 4.1463 | 5.4307 | 6.054 | 5.8218 | 4.1611 | 1.4576 | 16.8564 | 15.819 | 16.8564 | 1
855 | 3.6172 | 5.6669 | 6.0414 | 4.4164 | 4.8655 | 2.8709 | 16.5715 | 17.395 | 17.395 | 0
856 | 3.1234 | 5.5549 | 5.5887 | 5.8249 | 4.0797 | 1.9653 | 16.4686 | 14.7572 | 16.4686 | 1
857 | 2.6 | 7.1643 | 6.9595 | 5.1612 | 4.513 | 2.2839 | 17.2094 | 16.3564 | 17.2094 | 1
858 | 5.6575 | 5.3572 | 6.6027 | 4.6504 | 4.0997 | 2.2745 | 17.9396 | 18.6343 | 18.6343 | 0
859 | 3.6388 | 4.7819 | 5.0506 | 5.7217 | 3.5161 | 1.7584 | 15.9009 | 13.964 | 15.9009 | 1
860 | 2.9304 | 5.4918 | 6.1599 | 4.9075 | 4.3351 | 2.776 | 16.1056 | 16.2014 | 16.2014 | 0
861 | 4.3055 | 5.4024 | 7.6073 | 5.6137 | 5.3362 | 2.0034 | 17.325 | 19.2525 | 19.2525 | 0
862 | 3.9031 | 5.6639 | 7.5183 | 4.8549 | 4.6265 | 1.53 | 15.9519 | 17.578 | 17.578 | 0
863 | 4.4875 | 3.539 | 5.927 | 6.0779 | 3.9927 | 1.866 | 15.9704 | 16.2733 | 16.2733 | 0
864 | 4.0251 | 5.1001 | 5.8463 | 6.0477 | 5.5035 | 2.4779 | 17.6508 | 17.8528 | 17.8528 | 0
865 | 4.2478 | 6.2892 | 5.5545 | 4.4175 | 3.8928 | 1.5334 | 16.488 | 15.2285 | 16.488 | 1
866 | 4.1171 | 4.9725 | 5.6832 | 4.7346 | 4.9926 | 2.739 | 16.5632 | 17.5318 | 17.5318 | 0
867 | 5.5336 | 5.4239 | 5.7607 | 6.1655 | 5.6445 | 1.9786 | 19.1016 | 18.9173 | 19.1016 | 1
868 | 5.7452 | 5.1825 | 5.2374 | 5.3005 | 4.0713 | 2.5979 | 18.8261 | 17.6518 | 18.8261 | 1
869 | 3.6902 | 6.127 | 7.2391 | 4.8582 | 4.0564 | 1.6582 | 16.3336 | 16.6438 | 16.6438 | 0
870 | 4.4168 | 4.1422 | 6.0826 | 5.4344 | 4.3817 | 2.0105 | 16.0039 | 16.8915 | 16.8915 | 0
871 | 3.2986 | 5.053 | 4.4289 | 5.7235 | 3.7341 | 2.2482 | 16.3234 | 13.7098 | 16.3234 | 1
872 | 3.7422 | 5.5009 | 7.0489 | 5.1574 | 3.2726 | 1.7419 | 16.1423 | 15.8055 | 16.1423 | 1
873 | 3.0972 | 3.451 | 4.9887 | 4.4496 | 3.3042 | 2.0251 | 13.0228 | 13.4151 | 13.4151 | 0
874 | 3.4502 | 6.2787 | 7.3442 | 5.6904 | 4.4988 | 2.0354 | 17.4547 | 17.3286 | 17.4547 | 1
875 | 3.5928 | 6.4993 | 7.4341 | 6.6897 | 3.8933 | 1.5792 | 18.3611 | 16.4994 | 18.3611 | 1
876 | 4.3606 | 3.8057 | 5.2807 | 4.9629 | 3.8512 | 1.1309 | 14.26 | 14.6234 | 14.6234 | 0
877 | 3.2044 | 6.3555 | 6.7988 | 5.6586 | 3.7656 | 1.756 | 16.9744 | 15.5248 | 16.9744 | 1
878 | 4.6015 | 3.7835 | 4.6761 | 5.5866 | 4.8215 | 2.2468 | 16.2185 | 16.3459 | 16.3459 | 0
879 | 4.2177 | 4.405 | 7.2506 | 4.5257 | 4.0567 | 2.0843 | 15.2328 | 17.6094 | 17.6094 | 0
880 | 4.7509 | 3.9255 | 5.1998 | 6.6981 | 4.4126 | 1.6524 | 17.0269 | 16.0157 | 17.0269 | 1
881 | 4.5975 | 6.1695 | 4.751 | 4.5722 | 5.4748 | 1.4426 | 16.7818 | 16.2659 | 16.7818 | 1
882 | 3.0249 | 5.5809 | 5.7249 | 5.3556 | 4.0059 | 1.7834 | 15.7448 | 14.539 | 15.7448 | 1
883 | 4.0549 | 4.2343 | 6.205 | 5.616 | 4.433 | 1.3031 | 15.2083 | 15.996 | 15.996 | 0
884 | 3.8346 | 5.9189 | 5.6406 | 5.4454 | 3.3831 | 1.6658 | 16.8647 | 14.5241 | 16.8647 | 1
885 | 5.3467 | 3.7402 | 4.503 | 5.6243 | 5.4665 | 1.7588 | 16.4701 | 17.0751 | 17.0751 | 0
886 | 4.6445 | 5.3167 | 6.1256 | 6.5754 | 3.4867 | 2.2601 | 18.7967 | 16.517 | 18.7967 | 1
887 | 4.1436 | 3.9499 | 6.8954 | 6.8137 | 4.1058 | 1.4734 | 16.3807 | 16.6183 | 16.6183 | 0
888 | 3.8715 | 5.1083 | 5.7855 | 4.3454 | 3.7467 | 1.9472 | 15.2723 | 15.3508 | 15.3508 | 0
889 | 4.1898 | 7.4307 | 6.8539 | 4.8693 | 3.7792 | 2.1955 | 18.6854 | 17.0184 | 18.6854 | 1
890 | 4.0117 | 3.7457 | 5.7504 | 4.9336 | 3.3663 | 2.1148 | 14.8059 | 15.2432 | 15.2432 | 0
891 | 3.7636 | 4.5495 | 7.4944 | 6.2297 | 4.2277 | 2.7165 | 17.2593 | 18.2022 | 18.2022 | 0
892 | 4.4914 | 6.8951 | 4.3955 | 7.0013 | 5.3658 | 2.2761 | 20.664 | 16.5288 | 20.664 | 1
893 | 3.4155 | 6.0087 | 6.1049 | 4.0323 | 4.5908 | 1.7115 | 15.168 | 15.8227 | 15.8227 | 0
894 | 4.6949 | 4.912 | 5.5301 | 4.7562 | 3.7361 | 1.6435 | 16.0067 | 15.6047 | 16.0067 | 1
895 | 4.9454 | 5.4746 | 2.9465 | 4.0156 | 4.7561 | 1.7179 | 16.1535 | 14.3659 | 16.1535 | 1
896 | 5.0711 | 3.8032 | 6.7798 | 4.665 | 5.3043 | 2.7494 | 16.2886 | 19.9045 | 19.9045 | 0
897 | 3.138 | 3.7507 | 6.69 | 4.9065 | 3.8065 | 1.8324 | 13.6277 | 15.4669 | 15.4669 | 0
898 | 3.0501 | 4.1306 | 6.9575 | 5.1287 | 5.0804 | 1.5828 | 13.8922 | 16.6708 | 16.6708 | 0
899 | 5.1586 | 5.5644 | 7.1012 | 5.4975 | 3.4718 | 2.2415 | 18.4619 | 17.9731 | 18.4619 | 1
900 | 3.5527 | 4.3392 | 5.8543 | 4.5402 | 3.6142 | 2.0654 | 14.4975 | 15.0865 | 15.0865 | 0
901 | 4.6227 | 4.1752 | 6.5011 | 6.0847 | 4.3001 | 2.0279 | 16.9105 | 17.4518 | 17.4518 | 0
902 | 2.4612 | 7.6593 | 4.6824 | 5.3787 | 3.9768 | 1.3711 | 16.8702 | 12.4915 | 16.8702 | 1
903 | 4.2123 | 6.134 | 4.9528 | 4.8206 | 3.8332 | 2.0785 | 17.2454 | 15.0767 | 17.2454 | 1
904 | 3.2241 | 4.05 | 5.2784 | 5.2867 | 4.6281 | 1.6476 | 14.2083 | 14.7781 | 14.7781 | 0
905 | 3.786 | 3.7471 | 7.5768 | 4.4567 | 3.6222 | 2.0245 | 14.0143 | 17.0094 | 17.0094 | 0
906 | 3.9262 | 6.2265 | 7.2323 | 5.2573 | 5.1189 | 1.6911 | 17.1011 | 17.9685 | 17.9685 | 0
907 | 3.4841 | 4.9747 | 6.7144 | 4.7797 | 3.3657 | 2.0828 | 15.3213 | 15.647 | 15.647 | 0
908 | 3.0963 | 6.9958 | 4.0875 | 6.5362 | 3.5676 | 1.2117 | 17.8399 | 11.963 | 17.8399 | 1
909 | 4.3717 | 6.1297 | 7.6016 | 6.7089 | 3.6698 | 1.479 | 18.6893 | 17.1222 | 18.6893 | 1
910 | 3.3595 | 6.6153 | 6.1327 | 6.6887 | 4.0761 | 2.6276 | 19.291 | 16.1958 | 19.291 | 1
911 | 3.1712 | 5.2704 | 5.9203 | 4.3467 | 5.2035 | 2.4573 | 15.2456 | 16.7523 | 16.7523 | 0
912 | 2.4226 | 6.0504 | 6.4133 | 5.2342 | 5.2719 | 1.7244 | 15.4316 | 15.8322 | 15.8322 | 0
913 | 4.0803 | 4.4296 | 6.1873 | 4.8641 | 5.6056 | 1.492 | 14.8661 | 17.3652 | 17.3652 | 0
914 | 3.5912 | 7.1204 | 5.7585 | 4.4313 | 3.3748 | 2.0207 | 17.1636 | 14.7452 | 17.1636 | 1
915 | 2.9786 | 4.4519 | 4.5506 | 5.476 | 4.2997 | 2.0607 | 14.9673 | 13.8896 | 14.9673 | 1
916 | 4.1959 | 4.7726 | 5.4951 | 5.3868 | 3.2547 | 1.5452 | 15.9005 | 14.4909 | 15.9005 | 1
917 | 2.4983 | 6.522 | 5.3285 | 5.2538 | 5.0529 | 1.5522 | 15.8263 | 14.4319 | 15.8263 | 1
918 | 5.4359 | 5.0215 | 6.0074 | 5.773 | 4.7847 | 1.575 | 17.8054 | 17.803 | 17.8054 | 1
919 | 4.6126 | 4.2815 | 6.3699 | 4.8448 | 4.1916 | 2.285 | 16.0239 | 17.459 | 17.459 | 0
920 | 4.0263 | 5.1559 | 7.1094 | 5.5871 | 4.7008 | 2.3516 | 17.1209 | 18.1881 | 18.1881 | 0
921 | 2.7782 | 6.4723 | 7.468 | 4.835 | 4.8352 | 2.1107 | 16.1962 | 17.1921 | 17.1921 | 0
922 | 4.5041 | 6.7793 | 4.7969 | 5.4427 | 4.241 | 2.1819 | 18.9079 | 15.7239 | 18.9079 | 1
923 | 4.2813 | 3.3991 | 6.2176 | 4.8265 | 3.7911 | 2.1441 | 14.651 | 16.4341 | 16.4341 | 0
924 | 3.5788 | 7.2607 | 6.7167 | 5.2456 | 3.7614 | 1.7601 | 17.8452 | 15.8171 | 17.8452 | 1
925 | 3.3694 | 5.1228 | 6.663 | 5.2976 | 4.1783 | 2.3401 | 16.1298 | 16.5508 | 16.5508 | 0
926 | 4.9883 | 5.5665 | 6.2222 | 5.8339 | 5.3236 | 1.9405 | 18.3293 | 18.4747 | 18.4747 | 0
927 | 4.8265 | 3.4234 | 7.3358 | 4.6061 | 5.0142 | 2.4838 | 15.3398 | 19.6603 | 19.6603 | 0
928 | 4.2488 | 5.9385 | 5.4743 | 4.4674 | 4.5558 | 2.4461 | 17.1007 | 16.725 | 17.1007 | 1
929 | 4.1802 | 6.0563 | 5.363 | 5.9528 | 3.7057 | 1.5399 | 17.7292 | 14.7888 | 17.7292 | 1
930 | 4.5521 | 4.9997 | 4.5876 | 5.5383 | 4.1008 | 1.9921 | 17.0822 | 15.2326 | 17.0822 | 1
931 | 4.2604 | 5.4929 | 5.2056 | 5.958 | 5.5397 | 2.2332 | 17.9445 | 17.2388 | 17.9445 | 1
932 | 2.9792 | 4.5616 | 6.6145 | 5.7515 | 4.6231 | 1.8374 | 15.1297 | 16.0542 | 16.0542 | 0
933 | 4.614 | 5.6086 | 6.5923 | 4.1625 | 5.1759 | 2.1456 | 16.5306 | 18.5277 | 18.5277 | 0
934 | 4.0903 | 5.4643 | 5.5903 | 5.4148 | 3.8645 | 2.4539 | 17.4233 | 15.999 | 17.4233 | 1
935 | 2.8743 | 6.9144 | 5.6236 | 4.963 | 3.8282 | 2.2335 | 16.9851 | 14.5596 | 16.9851 | 1
936 | 3.9391 | 5.9201 | 7.1148 | 5.3138 | 3.8947 | 2.4728 | 17.6458 | 17.4214 | 17.6458 | 1
937 | 4.8948 | 6.6053 | 4.718 | 4.4218 | 3.9722 | 2.1233 | 18.0452 | 15.7083 | 18.0452 | 1
938 | 4.8162 | 7.1098 | 6.1103 | 5.289 | 5.2851 | 2.383 | 19.598 | 18.5946 | 19.598 | 1
939 | 5.5613 | 4.1576 | 7.0066 | 6.0195 | 3.9644 | 1.4272 | 17.1656 | 17.9595 | 17.9595 | 0
940 | 3.4208 | 5.0096 | 6.0513 | 5.455 | 4.1083 | 1.8777 | 15.7631 | 15.4582 | 15.7631 | 1
941 | 4.3819 | 5.1221 | 7.2689 | 4.7826 | 5.7111 | 2.1112 | 16.3979 | 19.4732 | 19.4732 | 0
942 | 3.5346 | 4.5028 | 6.0951 | 5.4827 | 4.5367 | 2.1424 | 15.6624 | 16.3087 | 16.3087 | 0
943 | 4.3691 | 4.0716 | 7.3097 | 4.7383 | 4.8793 | 1.471 | 14.65 | 18.0291 | 18.0291 | 0
944 | 4.3007 | 6.5599 | 6.9591 | 6.0346 | 4.6971 | 1.9296 | 18.8249 | 17.8865 | 18.8249 | 1
945 | 3.5668 | 3.5441 | 5.9387 | 4.6256 | 4.3346 | 2.4298 | 14.1664 | 16.2699 | 16.2699 | 0
946 | 3.4553 | 6.1108 | 4.4694 | 6.0616 | 4.8789 | 1.9902 | 17.6178 | 14.7939 | 17.6178 | 1
947 | 4.2927 | 4.5823 | 4.6884 | 4.1647 | 5.5931 | 2.0358 | 15.0755 | 16.6101 | 16.6101 | 0
948 | 3.837 | 5.4287 | 5.1276 | 6.2159 | 6.4053 | 2.3974 | 17.879 | 17.7672 | 17.879 | 1
949 | 3.6068 | 4.9237 | 6.4376 | 5.1872 | 5.3292 | 1.4806 | 15.1983 | 16.8543 | 16.8543 | 0
950 | 4.2718 | 4.2571 | 6.7607 | 5.4861 | 3.734 | 2.5165 | 16.5315 | 17.283 | 17.283 | 0
951 | 3.9552 | 3.9852 | 7.6513 | 6.0815 | 4.0782 | 2.0937 | 16.1156 | 17.7784 | 17.7784 | 0
952 | 3.0751 | 6.3419 | 4.7849 | 5.3312 | 4.2266 | 2.238 | 16.9863 | 14.3245 | 16.9863 | 1
953 | 4.5669 | 4.4985 | 5.4148 | 4.199 | 4.0499 | 2.0325 | 15.2969 | 16.0641 | 16.0641 | 0
954 | 3.9375 | 3.6778 | 4.8651 | 5.0967 | 4.1598 | 1.6591 | 14.3711 | 14.6215 | 14.6215 | 0
955 | 4.9348 | 4.3892 | 3.4791 | 4.3322 | 4.863 | 2.3928 | 16.0489 | 15.6696 | 16.0489 | 1
956 | 4.5912 | 4.0196 | 7.1674 | 6.3309 | 4.846 | 2.3241 | 17.2658 | 18.9287 | 18.9287 | 0
957 | 5.1709 | 5.7261 | 5.7102 | 5.1197 | 4.3922 | 2.7275 | 18.7442 | 18.0009 | 18.7442 | 1
958 | 3.0532 | 6.4458 | 3.5209 | 4.9936 | 3.9446 | 1.4435 | 15.936 | 11.9622 | 15.936 | 1
959 | 3.2466 | 4.3916 | 5.5276 | 4.6562 | 4.5689 | 2.0372 | 14.3317 | 15.3804 | 15.3804 | 0
960 | 3.4635 | 4.5569 | 6.0492 | 4.6837 | 4.0547 | 2.1752 | 14.8793 | 15.7426 | 15.7426 | 0
961 | 4.52 | 6.1208 | 5.6116 | 4.1382 | 4.7735 | 2.3099 | 17.0889 | 17.215 | 17.215 | 0
962 | 4.7533 | 6.3521 | 6.7012 | 5.4872 | 3.3038 | 2.641 | 19.2336 | 17.3993 | 19.2336 | 1
963 | 2.3096 | 3.6315 | 5.5839 | 6.288 | 5.3586 | 1.9243 | 14.1534 | 15.1764 | 15.1764 | 0
964 | 4.5 | 5.1467 | 3.0477 | 6.2973 | 3.7245 | 2.5621 | 18.5061 | 13.8343 | 18.5061 | 1
965 | 3.6279 | 4.6861 | 6.6245 | 5.1328 | 5.2199 | 1.5785 | 15.0253 | 17.0507 | 17.0507 | 0
966 | 2.8141 | 5.7767 | 4.6515 | 5.017 | 3.8322 | 2.5392 | 16.147 | 13.8369 | 16.147 | 1
967 | 2.5765 | 3.9581 | 7.5968 | 4.6823 | 5.5817 | 1.7784 | 12.9954 | 17.5334 | 17.5334 | 0
968 | 3.8361 | 5.5228 | 5.3081 | 5.1184 | 5.1628 | 2.6619 | 17.1392 | 16.9689 | 17.1392 | 1
969 | 4.2098 | 5.0955 | 6.7561 | 5.5505 | 3.9366 | 1.8666 | 16.7224 | 16.7691 | 16.7691 | 0
970 | 4.8856 | 5.6532 | 5.5998 | 5.9258 | 3.9156 | 2.1512 | 18.6158 | 16.5521 | 18.6158 | 1
971 | 4.4942 | 4.0956 | 5.7084 | 5.6327 | 3.3618 | 1.3703 | 15.5927 | 14.9347 | 15.5927 | 1
972 | 3.3384 | 5.7392 | 5.742 | 6.1777 | 4.2601 | 1.6911 | 16.9464 | 15.0317 | 16.9464 | 1
973 | 4.6359 | 6.4247 | 7.3738 | 5.0025 | 4.9681 | 2.0576 | 18.1207 | 19.0353 | 19.0353 | 0
974 | 3.5359 | 4.7783 | 4.6857 | 5.0718 | 5.1811 | 1.7574 | 15.1433 | 15.16 | 15.16 | 0
975 | 3.9888 | 5.1134 | 5.937 | 4.9602 | 4.0997 | 1.4586 | 15.5209 | 15.4841 | 15.5209 | 1
976 | 5.3152 | 4.1667 | 6.6762 | 6.4044 | 5.5238 | 1.367 | 17.2533 | 18.8822 | 18.8822 | 0
977 | 4.4989 | 8.8059 | 4.0484 | 4.7843 | 3.7055 | 2.0024 | 20.0915 | 14.2552 | 20.0915 | 1
978 | 3.1721 | 4.4161 | 4.2308 | 5.1862 | 4.2973 | 2.0238 | 14.7982 | 13.724 | 14.7982 | 1
979 | 4.4796 | 5.1388 | 5.1971 | 4.9615 | 3.3143 | 2.2795 | 16.8595 | 15.2705 | 16.8595 | 1
980 | 3.0969 | 4.8691 | 6.0194 | 4.8912 | 3.3483 | 1.7976 | 14.6548 | 14.2622 | 14.6548 | 1
981 | 2.3543 | 4.7598 | 7.7298 | 6.9273 | 5.2369 | 1.9249 | 15.9663 | 17.2459 | 17.2459 | 0
982 | 3.0066 | 4.0553 | 5.0776 | 5.4693 | 3.907 | 2.2475 | 14.7786 | 14.2387 | 14.7786 | 1
983 | 3.6471 | 4.6376 | 6.7808 | 5.5453 | 4.257 | 2.3177 | 16.1477 | 17.0026 | 17.0026 | 0
984 | 4.3942 | 5.2146 | 7.1735 | 5.1696 | 3.4359 | 1.8863 | 16.6647 | 16.8899 | 16.8899 | 0
985 | 3.6655 | 5.4672 | 5.7506 | 6.7518 | 4.0151 | 1.9355 | 17.82 | 15.3667 | 17.82 | 1
986 | 4.3704 | 3.3092 | 5.9278 | 5.6403 | 5.0868 | 2.3962 | 15.7162 | 17.7812 | 17.7812 | 0
987 | 3.4612 | 5.8904 | 3.9536 | 4.9167 | 4.0012 | 1.8178 | 16.0861 | 13.2339 | 16.0861 | 1
988 | 2.607 | 5.3071 | 4.9948 | 4.6906 | 3.6166 | 2.4075 | 15.0123 | 13.626 | 15.0123 | 1
989 | 2.7185 | 5.6317 | 4.9011 | 6.0853 | 4.6825 | 2.4542 | 16.8897 | 14.7562 | 16.8897 | 1
990 | 2.96 | 4.2977 | 5.711 | 4.3907 | 4.6908 | 2.5095 | 14.1579 | 15.8714 | 15.8714 | 0
991 | 3.9435 | 7.1839 | 2.4342 | 5.3614 | 3.477 | 2.5077 | 18.9965 | 12.3625 | 18.9965 | 1
992 | 3.7099 | 3.2872 | 6.0055 | 5.4756 | 4.5804 | 2.5797 | 15.0524 | 16.8755 | 16.8755 | 0
993 | 2.1127 | 5.8264 | 5.9496 | 7.2075 | 4.7129 | 1.7438 | 16.8904 | 14.519 | 16.8904 | 1
994 | 5.1234 | 7.3079 | 6.6899 | 5.0989 | 4.1644 | 1.9229 | 19.4531 | 17.9005 | 19.4531 | 1
995 | 5.2302 | 6.0078 | 6.8665 | 5.0925 | 4.2124 | 2.2033 | 18.5338 | 18.5124 | 18.5338 | 1
996 | 4.2436 | 5.081 | 5.292 | 5.52 | 4.8779 | 2.1996 | 17.0442 | 16.6131 | 17.0442 | 1
997 | 3.2264 | 6.1483 | 5.5361 | 5.5591 | 3.3327 | 2.0048 | 16.9385 | 14.1 | 16.9385 | 1
998 | 3.8916 | 4.9694 | 5.6696 | 6.2006 | 3.5724 | 1.8591 | 16.9207 | 14.9927 | 16.9207 | 1
999 | 3.6915 | 4.7284 | 5.0371 | 5.5283 | 5.0228 | 1.6989 | 15.6471 | 15.4503 | 15.6471 | 1
1000 | 4.3257 | 4.5027 | 6.1963 | 5.5332 | 4.2262 | 1.2386 | 15.6002 | 15.9868 | 15.9868 | 0
1001 | 4.5438 | 3.8169 | 6.5562 | 6.4171 | 5.251 | 1.903 | 16.6808 | 18.2539 | 18.2539 | 0
1002 | 4.424 | 7.7003 | 6.3893 | 5.8883 | 4.1205 | 2.1011 | 20.1138 | 17.035 | 20.1138 | 1
1003 | 4.2732 | 6.0468 | 5.5067 | 5.3481 | 3.9422 | 1.8576 | 17.5257 | 15.5796 | 17.5257 | 1
1004 | 4.3602 | 7.0324 | 4.3399 | 5.888 | 4.58 | 2.4802 | 19.7608 | 15.7603 | 19.7608 | 1
1005 | 3.8261 | 4.8774 | 5.0058 | 6.7596 | 3.4764 | 2.2136 | 17.6766 | 14.5218 | 17.6766 | 1
1006 | 3.2214 | 6.6957 | 5.0685 | 5.0705 | 3.215 | 2.3318 | 17.3193 | 13.8367 | 17.3193 | 1
1007 | 3.5837 | 5.5531 | 7.4529 | 5.8585 | 5.0056 | 1.9915 | 16.9867 | 18.0337 | 18.0337 | 0
1008 | 5.7761 | 6.2199 | 6.8484 | 4.7125 | 5.7268 | 2.2235 | 18.932 | 20.5748 | 20.5748 | 0
1009 | 3.4197 | 3.3418 | 4.6938 | 5.672 | 4.6257 | 2.3356 | 14.769 | 15.0748 | 15.0748 | 0
1010 | 4.023 | 5.9306 | 6.0851 | 5.806 | 4.1744 | 2.5455 | 18.3051 | 16.828 | 18.3051 | 1
1011 | 3.5827 | 5.22 | 4.4831 | 5.0092 | 3.7742 | 2.0578 | 15.8697 | 13.8979 | 15.8697 | 1
1012 | 4.3759 | 3.6158 | 5.2826 | 5.2108 | 3.5792 | 1.9379 | 15.1404 | 15.1756 | 15.1756 | 0
1013 | 4.9669 | 6.45 | 4.7379 | 5.4577 | 4.331 | 1.5714 | 18.446 | 15.6072 | 18.446 | 1
1014 | 4.4598 | 4.5167 | 4.0314 | 4.8728 | 3.8796 | 2.228 | 16.0772 | 14.5987 | 16.0772 | 1
1015 | 3.1969 | 5.7965 | 5.0338 | 5.7098 | 3.8647 | 2.0066 | 16.7098 | 14.102 | 16.7098 | 1
1016 | 4.2378 | 3.6311 | 7.1184 | 5.0755 | 3.3591 | 1.6437 | 14.588 | 16.359 | 16.359 | 0
1017 | 2.3972 | 4.4318 | 5.6069 | 5.1122 | 3.6402 | 1.5784 | 13.5197 | 13.2227 | 13.5197 | 1
1018 | 2.7774 | 6.0862 | 5.8229 | 6.125 | 3.9656 | 1.846 | 16.8346 | 14.412 | 16.8346 | 1
1019 | 5.408 | 5.9979 | 5.1432 | 4.3621 | 3.487 | 1.9179 | 17.6859 | 15.956 | 17.6859 | 1
1020 | 4.1232 | 4.8161 | 6.1051 | 5.9427 | 3.9249 | 1.9442 | 16.8262 | 16.0975 | 16.8262 | 1
1021 | 5.0096 | 3.7723 | 6.6612 | 6.3839 | 4.6047 | 1.884 | 17.0498 | 18.1595 | 18.1595 | 0
1022 | 4.5074 | 7.2205 | 4.9659 | 5.8783 | 4.1279 | 2.1996 | 19.8058 | 15.8007 | 19.8058 | 1
1023 | 3.505 | 6.2202 | 4.9769 | 5.4802 | 4.2014 | 1.78 | 16.9853 | 14.4632 | 16.9853 | 1
1024 | 4.925 | 4.3487 | 6.8917 | 5.8631 | 3.2683 | 1.705 | 16.8418 | 16.79 | 16.8418 | 1
1025 | 3.4599 | 5.4325 | 4.5196 | 5.0306 | 3.597 | 1.7695 | 15.6924 | 13.346 | 15.6924 | 1
1026 | 4.5462 | 4.0816 | 6.8035 | 6.3245 | 3.2602 | 2.4169 | 17.3692 | 17.0268 | 17.3692 | 1
1027 | 5.1531 | 5.1306 | 7.6238 | 4.7307 | 3.3581 | 1.9525 | 16.9669 | 18.0875 | 18.0875 | 0
1028 | 4.2404 | 5.1707 | 6.5762 | 4.7477 | 3.7988 | 1.5045 | 15.6633 | 16.1199 | 16.1199 | 0
1029 | 4.5693 | 6.0741 | 6.3505 | 4.882 | 5.6437 | 2.0091 | 17.5345 | 18.5725 | 18.5725 | 0
1030 | 4.3974 | 3.5345 | 4.8381 | 5.2288 | 3.6153 | 1.8829 | 15.0437 | 14.7337 | 15.0437 | 1
1031 | 3.827 | 4.5059 | 3.3655 | 4.3644 | 3.9819 | 1.718 | 14.4153 | 12.8923 | 14.4153 | 1
1032 | 4.2837 | 5.5628 | 5.6818 | 4.3356 | 3.9278 | 1.62 | 15.8022 | 15.5133 | 15.8022 | 1
1033 | 3.4336 | 5.3777 | 6.8335 | 6.5227 | 5.4989 | 2.3247 | 17.6587 | 18.0907 | 18.0907 | 0
1034 | 5.1344 | 5.429 | 5.0677 | 6.0537 | 3.8898 | 2.3233 | 18.9405 | 16.4152 | 18.9405 | 1
1035 | 3.9585 | 3.9967 | 5.3292 | 4.35 | 4.3215 | 1.6736 | 13.9789 | 15.2829 | 15.2829 | 0
1036 | 5.0069 | 4.3618 | 6.5298 | 5.2946 | 3.772 | 2.1657 | 16.829 | 17.4745 | 17.4745 | 0
1037 | 3.9607 | 3.7046 | 5.2959 | 5.1189 | 4.6466 | 2.2495 | 15.0337 | 16.1526 | 16.1526 | 0
1038 | 3.4363 | 3.8886 | 6.0776 | 7.435 | 3.5855 | 1.6979 | 16.4579 | 14.7973 | 16.4579 | 1
1039 | 3.8441 | 4.8345 | 4.6026 | 5.0229 | 5.0492 | 2.1183 | 15.8199 | 15.6142 | 15.8199 | 1
1040 | 5.7231 | 5.3435 | 5.0949 | 6.0844 | 4.3039 | 1.7142 | 18.8652 | 16.8361 | 18.8652 | 1
1041 | 2.8543 | 6.3822 | 3.4597 | 5.1223 | 5.2489 | 1.8584 | 16.2172 | 13.4213 | 16.2172 | 1
1042 | 4.0233 | 5.8613 | 4.1185 | 5.9709 | 4.1818 | 1.4403 | 17.2958 | 13.7639 | 17.2958 | 1
1043 | 4.0899 | 4.5896 | 7.0969 | 4.2894 | 4.7556 | 1.7272 | 14.6961 | 17.6696 | 17.6696 | 0
1044 | 4.7319 | 4.8498 | 6.1555 | 5.0246 | 3.6039 | 1.8523 | 16.4586 | 16.3436 | 16.4586 | 1
1045 | 3.2248 | 5.0766 | 4.7288 | 4.4331 | 4.9133 | 1.9186 | 14.6531 | 14.7856 | 14.7856 | 0
1046 | 4.1416 | 4.8763 | 5.6897 | 5.3324 | 4.0628 | 1.681 | 16.0312 | 15.5751 | 16.0312 | 1
1047 | 3.5987 | 6.368 | 6.5656 | 5.0958 | 3.8818 | 2.1374 | 17.1999 | 16.1835 | 17.1999 | 1
1048 | 4.1562 | 6.1921 | 5.7366 | 4.7728 | 4.5466 | 2.0648 | 17.1859 | 16.5042 | 17.1859 | 1
1049 | 2.6064 | 7.053 | 6.3679 | 4.1403 | 5.47 | 2.152 | 15.9517 | 16.5963 | 16.5963 | 0
1050 | 4.0543 | 5.7991 | 6.5428 | 5.5903 | 4.407 | 1.385 | 16.8287 | 16.3891 | 16.8287 | 1
1051 | 4.2434 | 6.7398 | 4.6987 | 4.7997 | 3.2971 | 2.0369 | 17.8198 | 14.2761 | 17.8198 | 1
1052 | 4.3905 | 4.7476 | 6.361 | 4.4212 | 4.4718 | 1.5703 | 15.1296 | 16.7936 | 16.7936 | 0
1053 | 3.3794 | 6.9575 | 6.5705 | 4.5901 | 5.3657 | 2.5281 | 17.455 | 17.8436 | 17.8436 | 0
1054 | 4.426 | 5.3383 | 4.9568 | 5.7893 | 4.3633 | 1.3411 | 16.8945 | 15.0871 | 16.8945 | 1
1055 | 4.1262 | 5.6343 | 7.128 | 5.3407 | 4.8977 | 2.4523 | 17.5536 | 18.6042 | 18.6042 | 0
1056 | 3.9003 | 6.8417 | 5.3838 | 6.3741 | 5.0552 | 2.2473 | 19.3634 | 16.5865 | 19.3634 | 1
1057 | 5.2207 | 8.0796 | 4.5944 | 4.7672 | 5.2097 | 2.1393 | 20.2068 | 17.164 | 20.2068 | 1
1058 | 3.104 | 7.3607 | 6.0267 | 5.0205 | 4.6057 | 2.2872 | 17.7724 | 16.0235 | 17.7724 | 1
1059 | 3.9933 | 4.7904 | 7.0571 | 4.9074 | 3.4705 | 1.8397 | 15.5309 | 16.3606 | 16.3606 | 0
1060 | 3.1983 | 3.9858 | 7.3675 | 4.9541 | 4.4195 | 2.1483 | 14.2865 | 17.1337 | 17.1337 | 0
1061 | 3.4091 | 7.3081 | 5.6785 | 4.4549 | 3.5372 | 2.2625 | 17.4346 | 14.8873 | 17.4346 | 1
1062 | 4.7534 | 5.4242 | 5.8346 | 4.1393 | 4.4628 | 1.7882 | 16.1051 | 16.8389 | 16.8389 | 0
1063 | 3.6038 | 4.7733 | 7.4429 | 5.0327 | 3.9018 | 1.827 | 15.2367 | 16.7754 | 16.7754 | 0
1064 | 5.1519 | 4.9936 | 4.5311 | 4.5282 | 4.1642 | 2.585 | 17.2588 | 16.4322 | 17.2588 | 1
1065 | 4.0643 | 6.2339 | 6.5057 | 5.339 | 6.341 | 1.4229 | 17.06 | 18.3338 | 18.3338 | 0
1066 | 3.6088 | 4.2589 | 6.4765 | 6.1671 | 4.5825 | 1.5674 | 15.6023 | 16.2352 | 16.2352 | 0
1067 | 4.088 | 3.505 | 5.4498 | 5.4305 | 4.4278 | 1.7973 | 14.8208 | 15.7629 | 15.7629 | 0
1068 | 3.7877 | 5.3024 | 6.9879 | 6.4792 | 3.4596 | 2.3233 | 17.8926 | 16.5584 | 17.8926 | 1
1069 | 4.8596 | 6.1883 | 5.1376 | 4.5678 | 3.6228 | 1.5993 | 17.2151 | 15.2194 | 17.2151 | 1
1070 | 4.8618 | 6.0449 | 5.5608 | 5.6791 | 3.4262 | 1.7456 | 18.3314 | 15.5945 | 18.3314 | 1
1071 | 3.901 | 5.2934 | 6.9174 | 4.9926 | 4.2396 | 1.4492 | 15.6363 | 16.5072 | 16.5072 | 0
1072 | 4.0281 | 4.8103 | 7.0482 | 5.5332 | 4.062 | 1.4118 | 15.7834 | 16.55 | 16.55 | 0
1073 | 3.8128 | 6.0835 | 5.4953 | 5.7626 | 3.3825 | 2.3476 | 18.0065 | 15.0381 | 18.0065 | 1
1074 | 3.9083 | 7.2111 | 4.253 | 5.0601 | 3.7297 | 1.942 | 18.1215 | 13.8331 | 18.1215 | 1
1075 | 3.305 | 5.9325 | 6.203 | 6.0932 | 3.4827 | 1.847 | 17.1777 | 14.8377 | 17.1777 | 1
1076 | 5.24 | 5.3138 | 6.9665 | 6.5962 | 4.1429 | 2.752 | 19.902 | 19.1014 | 19.902 | 1
1077 | 3.3861 | 5.1604 | 5.7797 | 6.6826 | 5.3304 | 2.2176 | 17.4468 | 16.7139 | 17.4468 | 1
1078 | 2.9847 | 7.8204 | 5.9398 | 6.0484 | 4.8779 | 2.2235 | 19.0769 | 16.0259 | 19.0769 | 1
1079 | 4.3243 | 5.4257 | 6.6236 | 6.6327 | 3.9642 | 1.9749 | 18.3577 | 16.887 | 18.3577 | 1
1080 | 3.908 | 4.5107 | 7.3699 | 6.35 | 5.4542 | 2.1633 | 16.932 | 18.8954 | 18.8954 | 0
1081 | 4.6944 | 5.951 | 4.171 | 5.6344 | 4.5382 | 1.5105 | 17.7903 | 14.914 | 17.7903 | 1
1082 | 3.2767 | 5.4407 | 7.8327 | 4.3455 | 5.1376 | 2.6201 | 15.6828 | 18.867 | 18.867 | 0
1083 | 3.5139 | 4.611 | 6.9307 | 6.1702 | 4.3958 | 2.3698 | 16.665 | 17.2102 | 17.2102 | 0
1084 | 2.6448 | 5.8376 | 6.1388 | 6.6762 | 3.4216 | 2.3207 | 17.4793 | 14.526 | 17.4793 | 1
1085 | 3.9196 | 3.8359 | 5.2223 | 7.1359 | 3.924 | 2.1395 | 17.031 | 15.2055 | 17.031 | 1
1086 | 5.0895 | 5.142 | 5.9016 | 5.3981 | 3.6817 | 1.3228 | 16.9525 | 15.9957 | 16.9525 | 1
1087 | 3.8134 | 6.1904 | 5.2622 | 6.1978 | 5.1899 | 1.9882 | 18.1898 | 16.2537 | 18.1898 | 1
1088 | 3.2647 | 5.1402 | 5.8571 | 5.4518 | 5.4484 | 1.5157 | 15.3725 | 16.0859 | 16.0859 | 0
1089 | 3.4167 | 5.3051 | 5.5647 | 4.9401 | 4.6555 | 2.1773 | 15.8392 | 15.8141 | 15.8392 | 1
1090 | 3.7937 | 4.3924 | 6.2902 | 6.3227 | 4.8602 | 1.7788 | 16.2876 | 16.7229 | 16.7229 | 0
1091 | 4.4667 | 6.1374 | 5.2666 | 5.2766 | 3.7225 | 2.2914 | 18.1722 | 15.7472 | 18.1722 | 1
1092 | 5.6502 | 7.1971 | 6.705 | 5.508 | 3.9912 | 1.5396 | 19.895 | 17.8861 | 19.895 | 1
1093 | 4.2334 | 6.603 | 4.6096 | 5.5751 | 4.0401 | 1.8195 | 18.231 | 14.7026 | 18.231 | 1
1094 | 3.9888 | 4.2792 | 7.4974 | 5.336 | 5.0629 | 2.0247 | 15.6287 | 18.5739 | 18.5739 | 0
1095 | 4.8497 | 5.3468 | 5.4073 | 7.256 | 3.6138 | 1.7338 | 19.1863 | 15.6047 | 19.1863 | 1
1096 | 3.5194 | 6.0123 | 6.2046 | 4.3412 | 3.6975 | 2.1452 | 16.0181 | 15.5668 | 16.0181 | 1
1097 | 4.461 | 3.8238 | 5.5739 | 4.8349 | 3.2149 | 1.9993 | 15.1191 | 15.2492 | 15.2492 | 0
1098 | 4.4417 | 5.698 | 4.8676 | 5.7125 | 5.5637 | 2.7374 | 18.5897 | 17.6104 | 18.5897 | 1
1099 | 4.8782 | 5.7082 | 5.1642 | 6.0161 | 4.0642 | 1.4658 | 18.0683 | 15.5724 | 18.0683 | 1
1100 | 4.8468 | 5.0345 | 4.4626 | 6.35 | 5.0753 | 2.307 | 18.5383 | 16.6918 | 18.5383 | 1
1101 | 4.6701 | 4.946 | 5.0439 | 5.6172 | 3.8898 | 2.4501 | 17.6834 | 16.0538 | 17.6834 | 1
1102 | 3.2477 | 4.7935 | 7.3862 | 4.8109 | 4.1322 | 2.2418 | 15.0939 | 17.0079 | 17.0079 | 0
1103 | 3.8346 | 5.7592 | 5.8447 | 5.6725 | 6.1751 | 1.3112 | 16.5775 | 17.1656 | 17.1656 | 0
1104 | 3.0765 | 5.8126 | 5.3656 | 6.4393 | 6.0518 | 2.7594 | 18.0878 | 17.2533 | 18.0878 | 1
1105 | 2.5129 | 7.0092 | 5.0513 | 5.628 | 4.2441 | 1.8143 | 16.9643 | 13.6225 | 16.9643 | 1
1106 | 5.2914 | 3.8951 | 5.5503 | 4.95 | 4.1606 | 2.1809 | 16.3174 | 17.1832 | 17.1832 | 0
1107 | 3.6991 | 5.8609 | 4.4453 | 4.9469 | 5.5649 | 2.5064 | 17.0133 | 16.2156 | 17.0133 | 1
1108 | 2.6923 | 4.5991 | 5.4301 | 4.6508 | 4.6647 | 2.4939 | 14.4361 | 15.281 | 15.281 | 0
1109 | 5.4877 | 4.7604 | 6.2293 | 5.4861 | 4.9167 | 1.9904 | 17.7246 | 18.6241 | 18.6241 | 0
1110 | 3.1788 | 3.5265 | 5.3595 | 5.6892 | 4.1985 | 2.482 | 14.8765 | 15.2189 | 15.2189 | 0
1111 | 3.0585 | 6.0053 | 6.5978 | 4.6647 | 5.7515 | 2.7713 | 16.4998 | 18.1791 | 18.1791 | 0
1112 | 4.8917 | 6.5081 | 6.4099 | 5.337 | 4.2503 | 1.369 | 18.1058 | 16.9208 | 18.1058 | 1
1113 | 3.5644 | 4.5943 | 5.3147 | 6.3529 | 4.8014 | 1.4595 | 15.9711 | 15.1401 | 15.9711 | 1
1114 | 4.7433 | 6.3039 | 2.9801 | 4.7066 | 4.7966 | 2.6498 | 18.4036 | 15.1697 | 18.4036 | 1
1115 | 5.169 | 4.0942 | 7.0899 | 4.3358 | 3.9142 | 1.5672 | 15.1662 | 17.7402 | 17.7402 | 0
1116 | 4.7952 | 4.992 | 5.6691 | 5.1497 | 3.7856 | 2.1644 | 17.1013 | 16.4143 | 17.1013 | 1
1117 | 3.5293 | 4.0542 | 6.4821 | 5.9323 | 4.4222 | 2.5068 | 16.0225 | 16.9404 | 16.9404 | 0
1118 | 4.4405 | 6.0145 | 5.8702 | 6.6443 | 4.7969 | 1.9478 | 19.047 | 17.0553 | 19.047 | 1
1119 | 3.8386 | 4.7653 | 4.8277 | 5.1784 | 4.625 | 1.9871 | 15.7695 | 15.2784 | 15.7695 | 1
1120 | 3.4563 | 5.3391 | 4.335 | 5.919 | 4.5367 | 1.8314 | 16.5458 | 14.1595 | 16.5458 | 1
1121 | 4.7865 | 6.1559 | 4.902 | 4.5775 | 4.1837 | 1.7742 | 17.2942 | 15.6465 | 17.2942 | 1
1122 | 4.036 | 4.7714 | 4.6899 | 5.1256 | 4.0974 | 2.3375 | 16.2704 | 15.1608 | 16.2704 | 1
1123 | 4.2025 | 4.9497 | 5.0906 | 4.7276 | 4.5532 | 2.0175 | 15.8973 | 15.8639 | 15.8973 | 1
1124 | 3.6775 | 3.2811 | 5.087 | 6.4293 | 4.0504 | 1.8355 | 15.2233 | 14.6504 | 15.2233 | 1
1125 | 3.0874 | 5.9218 | 3.6486 | 4.6855 | 3.9673 | 1.9221 | 15.6168 | 12.6254 | 15.6168 | 1
1126 | 4.4984 | 7.161 | 5.0011 | 5.3774 | 4.732 | 1.5416 | 18.5783 | 15.773 | 18.5783 | 1
1127 | 3.2495 | 3.6871 | 3.9082 | 5.5297 | 4.1669 | 2.1648 | 14.631 | 13.4894 | 14.631 | 1
1128 | 4.3446 | 4.7918 | 5.2211 | 5.4813 | 3.9271 | 2.1778 | 16.7955 | 15.6705 | 16.7955 | 1
1129 | 4.6262 | 5.5956 | 5.3032 | 6.5517 | 4.501 | 1.7683 | 18.5418 | 16.1986 | 18.5418 | 1
1130 | 4.0823 | 5.0789 | 6.9982 | 5.122 | 3.8129 | 1.6843 | 15.9676 | 16.5778 | 16.5778 | 0
1131 | 4.1576 | 5.5274 | 4.5055 | 4.8395 | 3.6216 | 2.0196 | 16.5441 | 14.3043 | 16.5441 | 1
1132 | 4.5831 | 3.7564 | 7.6645 | 6.2729 | 4.0751 | 1.6528 | 16.2651 | 17.9755 | 17.9755 | 0
1133 | 4.8555 | 3.5999 | 7.1107 | 4.9802 | 4.4693 | 1.7554 | 15.1911 | 18.1909 | 18.1909 | 0
1134 | 5.4192 | 4.2217 | 6.2029 | 4.415 | 4.3714 | 2.3896 | 16.4455 | 18.3831 | 18.3831 | 0
1135 | 4.5936 | 3.7699 | 5.3531 | 5.5086 | 5.4951 | 2.4405 | 16.3126 | 17.8823 | 17.8823 | 0
1136 | 3.4792 | 6.2795 | 5.231 | 5.434 | 6.1741 | 2.1479 | 17.3406 | 17.0323 | 17.3406 | 1
1137 | 4.3776 | 6.1365 | 6.4531 | 5.3972 | 3.8173 | 1.8825 | 17.7938 | 16.5306 | 17.7938 | 1
1138 | 4.4892 | 5.959 | 5.5315 | 5.8943 | 5.8432 | 1.795 | 18.1375 | 17.6588 | 18.1375 | 1
1139 | 2.8599 | 5.4675 | 6.0432 | 5.234 | 4.0031 | 1.4927 | 15.0542 | 14.3989 | 15.0542 | 1
1140 | 3.7341 | 7.3126 | 6.028 | 6.5753 | 3.5568 | 2.4934 | 20.1155 | 15.8124 | 20.1155 | 1
1141 | 4.2801 | 7.1483 | 5.126 | 7.5596 | 3.8 | 2.0166 | 21.0047 | 15.2226 | 21.0047 | 1
1142 | 4.2341 | 5.8103 | 5.2999 | 4.5096 | 3.9268 | 2.3105 | 16.8644 | 15.7712 | 16.8644 | 1
1143 | 4.8986 | 5.1099 | 4.4944 | 6.6066 | 3.6875 | 1.9241 | 18.5394 | 15.0047 | 18.5394 | 1
1144 | 3.8786 | 7.2342 | 5.3888 | 4.9978 | 3.5786 | 1.8034 | 17.914 | 14.6494 | 17.914 | 1
1145 | 4.8406 | 7.0354 | 7.5511 | 4.7904 | 3.5367 | 1.403 | 18.0694 | 17.3314 | 18.0694 | 1
1146 | 4.448 | 4.0525 | 5.7665 | 6.595 | 4.5562 | 1.9633 | 17.0588 | 16.7341 | 17.0588 | 1
1147 | 4.2322 | 4.496 | 6.0732 | 5.3925 | 4.2063 | 1.9435 | 16.0642 | 16.4552 | 16.4552 | 0
1148 | 3.1989 | 4.1185 | 7.1475 | 6.3445 | 3.4148 | 1.7339 | 15.3957 | 15.4952 | 15.4952 | 0
1149 | 2.9857 | 6.6724 | 4.8958 | 6.2508 | 4.6428 | 2.1377 | 18.0465 | 14.662 | 18.0465 | 1
1150 | 3.4347 | 6.8432 | 6.5276 | 5.2226 | 3.9692 | 2.2834 | 17.7839 | 16.2148 | 17.7839 | 1
1151 | 3.615 | 5.5761 | 7.5284 | 4.7296 | 4.6187 | 1.8677 | 15.7883 | 17.6298 | 17.6298 | 0
1152 | 5.085 | 5.3831 | 4.0966 | 4.3749 | 3.2902 | 1.9454 | 16.7884 | 14.4171 | 16.7884 | 1
1153 | 5.1245 | 5.4983 | 6.0354 | 4.775 | 5.8258 | 2.3947 | 17.7926 | 19.3805 | 19.3805 | 0
1154 | 5.2242 | 4.1855 | 7.5642 | 4.6951 | 3.6255 | 2.1601 | 16.265 | 18.574 | 18.574 | 0
1155 | 3.3553 | 4.674 | 6.5901 | 5.4072 | 5.7655 | 1.4925 | 14.9289 | 17.2033 | 17.2033 | 0
1156 | 4.6514 | 5.5243 | 5.837 | 7.2151 | 4.0066 | 1.1195 | 18.5102 | 15.6144 | 18.5102 | 1
1157 | 4.3657 | 3.8891 | 3.9148 | 5.4506 | 3.8594 | 2.5379 | 16.2433 | 14.6778 | 16.2433 | 1
1158 | 3.5268 | 3.8475 | 4.9726 | 5.8321 | 3.2036 | 2.232 | 15.4385 | 13.935 | 15.4385 | 1
1159 | 5.2651 | 6.6614 | 3.8737 | 5.2425 | 4.0982 | 1.4225 | 18.5914 | 14.6594 | 18.5914 | 1
1160 | 5.5996 | 7.2291 | 5.186 | 6.2926 | 3.4205 | 1.8196 | 20.9409 | 16.0257 | 20.9409 | 1
1161 | 4.2572 | 7.7511 | 6.173 | 4.4025 | 3.8372 | 2.5574 | 18.9682 | 16.8248 | 18.9682 | 1
1162 | 5.3679 | 4.74 | 6.3551 | 5.1841 | 3.8755 | 1.3216 | 16.6136 | 16.9201 | 16.9201 | 0
1163 | 4.6842 | 5.8211 | 6.926 | 5.845 | 5.7929 | 2.3266 | 18.677 | 19.7297 | 19.7297 | 0
1164 | 4.5409 | 5.2737 | 6.7031 | 5.8945 | 5.5145 | 2.2685 | 17.9775 | 19.0269 | 19.0269 | 0
1165 | 4.1216 | 5.5469 | 7.6016 | 5.6529 | 5.061 | 1.6058 | 16.9272 | 18.39 | 18.39 | 0
1166 | 4.5805 | 7.5008 | 6.7541 | 6.355 | 4.7153 | 2.3669 | 20.8032 | 18.4168 | 20.8032 | 1
1167 | 2.9314 | 6.1027 | 6.7644 | 6.3651 | 4.753 | 2.224 | 17.6232 | 16.6728 | 17.6232 | 1
1168 | 2.6377 | 3.5892 | 5.3485 | 5.5555 | 4.2559 | 2.0545 | 13.8369 | 14.2966 | 14.2966 | 0
1169 | 3.3423 | 4.4292 | 3.9483 | 4.8305 | 4.6194 | 1.904 | 14.506 | 13.814 | 14.506 | 1
1170 | 3.609 | 4.349 | 5.9863 | 5.0099 | 3.8225 | 1.6398 | 14.6077 | 15.0575 | 15.0575 | 0
1171 | 3.5806 | 7.9869 | 7.2197 | 4.7085 | 3.6643 | 1.409 | 17.685 | 15.8735 | 17.685 | 1
1172 | 4.2532 | 4.8125 | 6.8211 | 5.9828 | 5.199 | 1.9337 | 16.9823 | 18.207 | 18.207 | 0
1173 | 3.8869 | 5.5398 | 5.5593 | 4.8541 | 4.5814 | 1.6546 | 15.9354 | 15.6822 | 15.9354 | 1
1174 | 3.2467 | 4.4501 | 6.5976 | 5.1326 | 4.5845 | 1.805 | 14.6345 | 16.2338 | 16.2338 | 0
1175 | 4.4686 | 5.6161 | 6.7457 | 5.8252 | 5.4111 | 1.4755 | 17.3854 | 18.101 | 18.101 | 0
1176 | 3.9789 | 4.7743 | 5.4853 | 6.31 | 3.9015 | 1.6524 | 16.7157 | 15.0181 | 16.7157 | 1
1177 | 2.9858 | 6.3258 | 5.9918 | 4.7454 | 3.2144 | 2.345 | 16.4019 | 14.5369 | 16.4019 | 1
1178 | 4.5827 | 4.7409 | 5.4827 | 5.5313 | 4.4334 | 1.7834 | 16.6383 | 16.2821 | 16.6383 | 1
1179 | 2.5974 | 5.2715 | 6.1645 | 6.9674 | 3.4384 | 1.8934 | 16.7296 | 14.0937 | 16.7296 | 1
1180 | 3.0228 | 4.3118 | 7.5208 | 5.7231 | 5.2712 | 1.4182 | 14.476 | 17.233 | 17.233 | 0
1181 | 3.9704 | 5.1097 | 5.47 | 4.7937 | 3.6594 | 1.1908 | 15.0646 | 14.2905 | 15.0646 | 1
1182 | 5.0267 | 4.2757 | 5.751 | 6.284 | 4.7303 | 1.6034 | 17.1898 | 17.1114 | 17.1898 | 1
1183 | 4.2757 | 6.5241 | 4.3844 | 6.5463 | 3.9809 | 1.4366 | 18.7827 | 14.0776 | 18.7827 | 1
1184 | 3.2009 | 4.3014 | 6.316 | 5.9067 | 3.1326 | 2.0505 | 15.4595 | 14.7 | 15.4595 | 1
1185 | 4.5251 | 6.7855 | 6.5425 | 5.3369 | 5.0309 | 1.8427 | 18.4903 | 17.9412 | 18.4903 | 1
1186 | 4.7518 | 6.1007 | 6.9896 | 4.8335 | 4.6442 | 1.6318 | 17.3178 | 18.0174 | 18.0174 | 0
1187 | 4.3847 | 3.7616 | 7.2168 | 4.3451 | 3.9653 | 1.9034 | 14.3949 | 17.4703 | 17.4703 | 0
1188 | 3.5393 | 4.9116 | 6.0269 | 7.5938 | 5.1136 | 2.1446 | 18.1893 | 16.8244 | 18.1893 | 1
1189 | 4.2257 | 6.1712 | 3.4807 | 4.4502 | 4.2018 | 1.5455 | 16.3927 | 13.4538 | 16.3927 | 1
1190 | 3.2156 | 5.0193 | 5.8709 | 4.4673 | 3.6089 | 2.5229 | 15.2251 | 15.2183 | 15.2251 | 1
1191 | 4.7182 | 7.9467 | 5.9235 | 5.9026 | 4.4473 | 2.5644 | 21.1319 | 17.6533 | 21.1319 | 1
1192 | 3.1961 | 5.1881 | 6.3427 | 6.0401 | 5.7476 | 1.2592 | 15.6835 | 16.5456 | 16.5456 | 0
1193 | 3.5558 | 4.6857 | 4.0877 | 4.4331 | 3.8326 | 2.1093 | 14.7839 | 13.5854 | 14.7839 | 1
1194 | 5.1007 | 6.5208 | 2.9489 | 5.012 | 3.9643 | 2.431 | 19.0644 | 14.4448 | 19.0644 | 1
1195 | 4.0829 | 7.4081 | 5.3037 | 6.484 | 4.7944 | 2.7046 | 20.6796 | 16.8856 | 20.6796 | 1
1196 | 4.5524 | 6.3523 | 4.5571 | 4.7962 | 4.1564 | 2.1618 | 17.8628 | 15.4277 | 17.8628 | 1
1197 | 3.0667 | 5.57 | 7.1827 | 6.7113 | 4.8882 | 2.3311 | 17.6792 | 17.4686 | 17.6792 | 1
1198 | 2.9463 | 3.8891 | 6.0576 | 6.4725 | 4.0176 | 1.3152 | 14.6232 | 14.3368 | 14.6232 | 1
1199 | 2.8167 | 4.0991 | 5.2892 | 5.4673 | 3.7717 | 2.0058 | 14.3888 | 13.8833 | 14.3888 | 1
1200 | 5.2876 | 3.7071 | 5.2849 | 4.5816 | 3.7627 | 2.321 | 15.8973 | 16.6562 | 16.6562 | 0
1201 | 5.5965 | 6.6337 | 4.9527 | 5.817 | 3.3976 | 1.5585 | 19.6057 | 15.5052 | 19.6057 | 1
1202 | 2.7085 | 6.0952 | 6.7475 | 6.0049 | 4.4587 | 2.2176 | 17.0263 | 16.1323 | 17.0263 | 1
1203 | 4.8102 | 7.6521 | 6.958 | 5.7424 | 4.6624 | 1.4637 | 19.6684 | 17.8943 | 19.6684 | 1
1204 | 2.7569 | 6.5571 | 7.6957 | 4.9102 | 5.2083 | 1.3115 | 15.5357 | 16.9724 | 16.9724 | 0
1205 | 4.4463 | 6.3739 | 4.3948 | 5.7883 | 4.1358 | 1.6563 | 18.2648 | 14.6332 | 18.2648 | 1
1206 | 3.8197 | 6.2863 | 6.6138 | 5.3259 | 3.2315 | 2.0477 | 17.4796 | 15.7127 | 17.4796 | 1
1207 | 4.1477 | 4.6884 | 5.4865 | 6.3068 | 3.4099 | 1.4395 | 16.5825 | 14.4837 | 16.5825 | 1
1208 | 2.5745 | 5.9411 | 7.0758 | 4.9424 | 4.0015 | 1.4842 | 14.9421 | 15.136 | 15.136 | 0
1209 | 2.6141 | 4.9232 | 3.5263 | 4.5987 | 4.8555 | 1.9534 | 14.0894 | 12.9493 | 14.0894 | 1
1210 | 2.5765 | 3.8992 | 7.0955 | 6.9575 | 4.6365 | 2.2215 | 15.6547 | 16.5299 | 16.5299 | 0
1211 | 5.2646 | 6.763 | 6.9906 | 5.5764 | 4.8198 | 2.2995 | 19.9035 | 19.3744 | 19.9035 | 1
1212 | 3.6328 | 6.6047 | 4.3907 | 5.0587 | 5.4461 | 2.3088 | 17.6049 | 15.7784 | 17.6049 | 1
1213 | 3.5705 | 7.7871 | 6.5946 | 4.2458 | 3.8894 | 1.5897 | 17.193 | 15.6441 | 17.193 | 1
1214 | 4.3718 | 4.0987 | 5.9957 | 5.0666 | 5.0016 | 2.1259 | 15.663 | 17.495 | 17.495 | 0
1215 | 3.3013 | 6.4455 | 6.1536 | 5.2316 | 3.6219 | 1.8136 | 16.792 | 14.8904 | 16.792 | 1
1216 | 5.701 | 6.4226 | 2.6579 | 5.8383 | 5.6296 | 1.4953 | 19.4571 | 15.4838 | 19.4571 | 1
1217 | 3.9585 | 5.7379 | 6.4851 | 5.0543 | 5.4048 | 1.8904 | 16.6411 | 17.7387 | 17.7387 | 0
1218 | 4.1285 | 4.5956 | 5.1964 | 5.7588 | 4.7476 | 2.2604 | 16.7433 | 16.3329 | 16.7433 | 1
1219 | 4.6418 | 7.0319 | 6.6221 | 4.96 | 3.4515 | 2.3703 | 19.004 | 17.0857 | 19.004 | 1
1220 | 2.8488 | 4.5513 | 5.4056 | 5.0293 | 3.77 | 2.0132 | 14.4425 | 14.0376 | 14.4425 | 1
1221 | 5.2073 | 7.1504 | 5.6531 | 5.4255 | 3.8859 | 1.9245 | 19.7077 | 16.6709 | 19.7077 | 1
1222 | 5.0794 | 5.8232 | 5.1346 | 4.2239 | 5.3562 | 2.6339 | 17.7605 | 18.2042 | 18.2042 | 0
1223 | 2.7178 | 4.2989 | 5.8724 | 4.823 | 5.3155 | 2.3636 | 14.2033 | 16.2693 | 16.2693 | 0
1224 | 3.5758 | 7.0611 | 5.5658 | 6.4637 | 4.307 | 2.3722 | 19.4727 | 15.8207 | 19.4727 | 1
1225 | 3.3566 | 3.4244 | 5.6413 | 4.9967 | 5.4593 | 1.6121 | 13.3898 | 16.0692 | 16.0692 | 0
1226 | 3.0631 | 6.3588 | 5.9866 | 5.0505 | 3.4155 | 1.8875 | 16.3598 | 14.3527 | 16.3598 | 1
1227 | 3.6909 | 3.7989 | 7.2045 | 4.7278 | 5.2552 | 2.4188 | 14.6364 | 18.5694 | 18.5694 | 0
1228 | 3.7265 | 4.4797 | 4.2559 | 4.8926 | 5.6367 | 1.9145 | 15.0134 | 15.5337 | 15.5337 | 0
1229 | 4.2358 | 5.1243 | 6.2646 | 4.8699 | 3.7503 | 1.726 | 15.956 | 15.9767 | 15.9767 | 0
1230 | 3.546 | 7.1248 | 4.4107 | 5.2718 | 3.7474 | 1.5933 | 17.536 | 13.2974 | 17.536 | 1
1231 | 4.3816 | 4.0689 | 6.5627 | 5.2333 | 3.7907 | 1.6907 | 15.3746 | 16.4258 | 16.4258 | 0
1232 | 4.3135 | 4.0656 | 6.0367 | 5.8004 | 3.4177 | 1.5378 | 15.7173 | 15.3057 | 15.7173 | 1
1233 | 4.7766 | 5.8166 | 6.5998 | 6.3347 | 3.6389 | 1.6026 | 18.5305 | 16.6179 | 18.5305 | 1
1234 | 4.6229 | 4.2729 | 7.4887 | 6.4884 | 4.4795 | 1.9685 | 17.3527 | 18.5596 | 18.5596 | 0
1235 | 4.5804 | 4.8037 | 6.1692 | 6.0736 | 4.7686 | 1.8437 | 17.3014 | 17.3619 | 17.3619 | 0
1236 | 3.7008 | 5.3617 | 3.3048 | 5.4841 | 3.1203 | 1.2181 | 15.7647 | 11.3441 | 15.7647 | 1
1237 | 2.6739 | 5.3125 | 4.4749 | 4.725 | 3.7351 | 1.7198 | 14.4313 | 12.6037 | 14.4313 | 1
1238 | 3.6342 | 6.1705 | 5.7581 | 5.5252 | 3.7248 | 2.3429 | 17.6729 | 15.46 | 17.6729 | 1
1239 | 3.301 | 4.9347 | 7.0332 | 4.3325 | 4.3213 | 1.9488 | 14.5169 | 16.6043 | 16.6043 | 0
1240 | 4.0929 | 4.6607 | 6.2918 | 6.453 | 4.7532 | 2.2265 | 17.4331 | 17.3644 | 17.4331 | 1
1241 | 3.9889 | 5.3024 | 4.7983 | 6.0414 | 3.3016 | 2.3271 | 17.6599 | 14.416 | 17.6599 | 1
1242 | 4.9714 | 4.6298 | 5.6481 | 5.3111 | 4.5661 | 1.293 | 16.2052 | 16.4785 | 16.4785 | 0
1243 | 5.058 | 7.3945 | 7.1528 | 5.2199 | 5.3155 | 1.9458 | 19.6182 | 19.4722 | 19.6182 | 1
1244 | 3.6456 | 7.6822 | 5.5656 | 5.0603 | 4.1761 | 2.5604 | 18.9486 | 15.9477 | 18.9486 | 1
1245 | 4.7915 | 5.4554 | 6.7233 | 6.1587 | 3.9683 | 2.2492 | 18.6547 | 17.7323 | 18.6547 | 1
1246 | 4.3469 | 6.7019 | 4.8021 | 4.6465 | 4.9392 | 2.8368 | 18.532 | 16.9249 | 18.532 | 1
1247 | 4.8591 | 7.0768 | 6.6424 | 4.6228 | 5.1421 | 2.2438 | 18.8025 | 18.8875 | 18.8875 | 0
1248 | 4.07 | 6.4829 | 4.7279 | 4.9198 | 4.4284 | 2.5257 | 17.9984 | 15.752 | 17.9984 | 1
1249 | 2.8079 | 7.3365 | 5.6128 | 6.8099 | 3.828 | 1.8345 | 18.7888 | 14.0833 | 18.7888 | 1
1250 | 3.4461 | 5.7462 | 5.5218 | 4.8506 | 3.0743 | 1.6204 | 15.6633 | 13.6626 | 15.6633 | 1
1251 | 3.6139 | 4.9989 | 3.6515 | 4.4708 | 4.8733 | 2.3033 | 15.3868 | 14.4419 | 15.3868 | 1
1252 | 4.4145 | 6.5 | 6.7048 | 5.6839 | 4.6366 | 1.8567 | 18.4551 | 17.6126 | 18.4551 | 1
1253 | 3.1902 | 5.995 | 6.8175 | 4.3731 | 3.6133 | 2.4313 | 15.9896 | 16.0523 | 16.0523 | 0
1254 | 3.1132 | 3.2863 | 4.8134 | 5.0134 | 3.518 | 1.4086 | 12.8215 | 12.8531 | 12.8531 | 0
1255 | 3.3726 | 4.2557 | 7.4545 | 5.1602 | 5.2513 | 2.1679 | 14.9564 | 18.2463 | 18.2463 | 0
1256 | 4.3725 | 6.0369 | 6.9837 | 5.2666 | 4.4855 | 2.3171 | 17.9932 | 18.1589 | 18.1589 | 0
1257 | 3.9295 | 5.1714 | 6.7305 | 5.2102 | 3.6326 | 2.5381 | 16.8492 | 16.8307 | 16.8492 | 1
1258 | 3.9332 | 4.5346 | 7.0708 | 5.8268 | 4.509 | 2.0921 | 16.3867 | 17.6051 | 17.6051 | 0
1259 | 3.8312 | 4.9372 | 4.909 | 5.3966 | 4.4744 | 2.4316 | 16.5966 | 15.6463 | 16.5966 | 1
1260 | 4.5455 | 3.3848 | 6.5767 | 4.5287 | 5.2786 | 1.911 | 14.37 | 18.3118 | 18.3118 | 0
1261 | 5.1033 | 7.0572 | 4.6463 | 6.1277 | 3.4753 | 1.7336 | 20.0218 | 14.9586 | 20.0218 | 1
1262 | 4.3362 | 4.8204 | 5.019 | 6.2406 | 3.3905 | 2.2528 | 17.65 | 14.9985 | 17.65 | 1
1263 | 4.1963 | 6.3588 | 6.5051 | 4.748 | 3.7237 | 2.5969 | 17.8999 | 17.022 | 17.8999 | 1
1264 | 4.6736 | 4.0921 | 6.2318 | 5.5191 | 3.9828 | 1.6277 | 15.9126 | 16.5159 | 16.5159 | 0
1265 | 3.9961 | 6.2663 | 6.9659 | 4.681 | 4.0099 | 2.659 | 17.6024 | 17.6309 | 17.6309 | 0
1266 | 3.5946 | 5.5689 | 4.5852 | 6.8421 | 4.3609 | 1.9996 | 18.0053 | 14.5403 | 18.0053 | 1
1267 | 4.9721 | 4.1087 | 5.7598 | 5.9749 | 3.4139 | 2.734 | 17.7896 | 16.8798 | 17.7896 | 1
1268 | 4.2232 | 5.324 | 5.2428 | 4.5832 | 4.2278 | 1.4569 | 15.5873 | 15.1507 | 15.5873 | 1
1269 | 3.8902 | 5.1042 | 7.0502 | 5.1819 | 3.6812 | 1.6 | 15.7763 | 16.2216 | 16.2216 | 0
1270 | 5.3752 | 4.1588 | 6.4172 | 5.5126 | 4.7739 | 2.5162 | 17.5628 | 19.0824 | 19.0824 | 0
1271 | 4.0429 | 4.5242 | 4.7819 | 5.5705 | 3.8832 | 2.5169 | 16.6546 | 15.225 | 16.6546 | 1
1272 | 4.509 | 4.9266 | 7.4623 | 4.7798 | 5.6124 | 1.8121 | 16.0275 | 19.3959 | 19.3959 | 0
1273 | 3.7359 | 5.3455 | 6.9628 | 6.2622 | 4.6998 | 2.569 | 17.9126 | 17.9675 | 17.9675 | 0
1274 | 4.3416 | 5.6865 | 6.5959 | 4.2738 | 4.7629 | 2.3741 | 16.676 | 18.0745 | 18.0745 | 0
1275 | 4.9249 | 3.9433 | 6.4946 | 6.0745 | 4.8371 | 1.6516 | 16.5943 | 17.9082 | 17.9082 | 0
1276 | 3.9458 | 5.3492 | 6.794 | 4.4643 | 3.5883 | 1.6677 | 15.4269 | 15.9958 | 15.9958 | 0
1277 | 4.8974 | 4.9296 | 6.6803 | 5.5399 | 3.2501 | 2.0025 | 17.3693 | 16.8303 | 17.3693 | 1
1278 | 3.5971 | 6.0406 | 7.1456 | 6.4028 | 3.6528 | 2.277 | 18.3175 | 16.6725 | 18.3175 | 1
1279 | 3.6804 | 4.5817 | 6.9043 | 4.3625 | 4.3223 | 2.5335 | 15.1582 | 17.4405 | 17.4405 | 0
1280 | 3.6038 | 6.5207 | 3.8405 | 5.5891 | 3.812 | 2.0552 | 17.7689 | 13.3116 | 17.7689 | 1
1281 | 5.092 | 6.3107 | 6.585 | 5.5742 | 4.1487 | 1.9939 | 18.9708 | 17.8196 | 18.9708 | 1
1282 | 4.1342 | 5.9504 | 5.4467 | 4.7719 | 4.5002 | 1.0713 | 15.9277 | 15.1523 | 15.9277 | 1
1283 | 4.7164 | 3.5094 | 5.837 | 4.8896 | 4.2313 | 1.3455 | 14.461 | 16.1302 | 16.1302 | 0
1284 | 4.9198 | 6.1497 | 5.4049 | 4.529 | 3.7787 | 2.0063 | 17.6048 | 16.1096 | 17.6048 | 1
1285 | 4.0231 | 6.6957 | 4.0832 | 4.9593 | 3.666 | 1.4829 | 17.161 | 13.2551 | 17.161 | 1
1286 | 4.9432 | 4.7059 | 6.3457 | 4.5444 | 4.2509 | 2.1821 | 16.3756 | 17.7219 | 17.7219 | 0
1287 | 4.0997 | 5.8348 | 4.0272 | 5.94 | 4.6751 | 1.5626 | 17.4371 | 14.3646 | 17.4371 | 1
1288 | 4.4249 | 4.3095 | 5.4095 | 5.1118 | 3.5573 | 2.2538 | 16.1 | 15.6454 | 16.1 | 1
1289 | 3.8049 | 8.1856 | 4.5609 | 4.6694 | 4.6246 | 2.3508 | 19.0107 | 15.3413 | 19.0107 | 1
1290 | 5.0615 | 6.2535 | 5.6919 | 5.3466 | 4.2981 | 1.2538 | 17.9153 | 16.3052 | 17.9153 | 1
1291 | 3.9555 | 5.3911 | 6.5462 | 5.6025 | 4.4161 | 2.0197 | 16.9688 | 16.9375 | 16.9688 | 1
1292 | 4.6723 | 4.8717 | 6.7125 | 4.2337 | 4.0291 | 2.3296 | 16.1074 | 17.7435 | 17.7435 | 0
1293 | 5.0252 | 6.3612 | 4.5857 | 5.5786 | 5.4856 | 2.2839 | 19.249 | 17.3805 | 19.249 | 1
1294 | 5.0266 | 5.8565 | 7.1248 | 5.7225 | 3.6785 | 2.2817 | 18.8873 | 18.1116 | 18.8873 | 1
1295 | 3.3226 | 7.2933 | 5.6194 | 5.0179 | 4.6635 | 1.6159 | 17.2497 | 15.2214 | 17.2497 | 1
1296 | 3.3595 | 4.3629 | 5.0656 | 6.1789 | 4.1261 | 2.5174 | 16.4187 | 15.0686 | 16.4187 | 1
1297 | 3.5693 | 6.6083 | 4.4643 | 5.0492 | 3.2648 | 2.1444 | 17.3711 | 13.4427 | 17.3711 | 1
1298 | 3.315 | 5.5512 | 7.4329 | 5.3346 | 3.4797 | 2.4489 | 16.6498 | 16.6765 | 16.6765 | 0
1299 | 4.1288 | 5.0713 | 4.207 | 4.4858 | 4.1861 | 1.6758 | 15.3617 | 14.1976 | 15.3617 | 1
1300 | 3.536 | 4.2803 | 2.9608 | 5.5851 | 3.8224 | 1.8828 | 15.2842 | 12.202 | 15.2842 | 1
1301 | 4.8775 | 4.4588 | 5.9324 | 5.2742 | 4.0783 | 1.298 | 15.9084 | 16.1862 | 16.1862 | 0
1302 | 3.6739 | 4.3007 | 5.2394 | 4.9349 | 5.3682 | 2.4882 | 15.3977 | 16.7697 | 16.7697 | 0
1303 | 3.8197 | 4.9171 | 4.6077 | 6.3566 | 4.6333 | 1.2421 | 16.3354 | 14.3028 | 16.3354 | 1
1304 | 4.6935 | 7.1146 | 4.2562 | 5.0798 | 3.7154 | 1.854 | 18.742 | 14.5191 | 18.742 | 1
1305 | 3.4864 | 4.5145 | 7.4833 | 6.4168 | 5.2688 | 1.9267 | 16.3445 | 18.1653 | 18.1653 | 0
1306 | 4.89 | 4.318 | 5.6893 | 5.2003 | 4.2461 | 2.1716 | 16.5799 | 16.997 | 16.997 | 0
1307 | 2.7526 | 6.7544 | 6.8925 | 4.9176 | 3.4405 | 2.0723 | 16.4968 | 15.1579 | 16.4968 | 1
1308 | 2.1605 | 4.3582 | 5.6522 | 6.5686 | 5.4191 | 1.4979 | 14.5852 | 14.7297 | 14.7297 | 0
1309 | 4.5718 | 4.8308 | 7.3262 | 5.2877 | 3.5412 | 2.6684 | 17.3586 | 18.1076 | 18.1076 | 0
1310 | 3.8651 | 4.6378 | 5.7031 | 6.1172 | 4.4221 | 1.8639 | 16.484 | 15.8542 | 16.484 | 1
1311 | 4.2155 | 6.5341 | 5.5382 | 6.3339 | 5.5333 | 2.317 | 19.4005 | 17.6041 | 19.4005 | 1
1312 | 4.7976 | 7.0865 | 7.2419 | 4.6181 | 3.7999 | 2.0027 | 18.5049 | 17.8421 | 18.5049 | 1
1313 | 3.4219 | 4.3745 | 5.2654 | 6.9749 | 4.9148 | 2.0516 | 16.8229 | 15.6538 | 16.8229 | 1
1314 | 4.5709 | 5.9227 | 7.2962 | 6.2011 | 5.1553 | 1.8342 | 18.5289 | 18.8566 | 18.8566 | 0
1315 | 5.4209 | 6.8639 | 5.4622 | 4.9353 | 4.5178 | 2.7109 | 19.931 | 18.1119 | 19.931 | 1
1316 | 4.4848 | 4.29 | 6.392 | 7.4413 | 4.5098 | 2.08 | 18.2962 | 17.4666 | 18.2962 | 1
1317 | 4.4252 | 4.3751 | 6.1299 | 5.6329 | 4.4149 | 2.2772 | 16.7104 | 17.2473 | 17.2473 | 0
1318 | 4.7319 | 3.6487 | 4.1364 | 6.3011 | 4.187 | 1.4863 | 16.168 | 14.5416 | 16.168 | 1
1319 | 3.2432 | 4.4222 | 7.1423 | 6.0962 | 4 | 2.619 | 16.3806 | 17.0045 | 17.0045 | 0
1320 | 4.8951 | 5.7495 | 4.9285 | 4.8532 | 3.4059 | 1.8426 | 17.3403 | 15.072 | 17.3403 | 1
1321 | 4.0879 | 5.5265 | 5.9469 | 5.9488 | 3.8819 | 2.0493 | 17.6126 | 15.9661 | 17.6126 | 1
1322 | 5.0907 | 5.265 | 4.7552 | 6.1893 | 3.7745 | 1.9293 | 18.4742 | 15.5496 | 18.4742 | 1
1323 | 3.5926 | 4.5766 | 6.7444 | 4.9543 | 3.2861 | 1.4112 | 14.5347 | 15.0344 | 15.0344 | 0
1324 | 4.3732 | 4.8288 | 7.3203 | 5.7871 | 3.3524 | 2.1068 | 17.0959 | 17.1527 | 17.1527 | 0
1325 | 5.1176 | 3.7075 | 6.5536 | 5.9196 | 4.2704 | 1.5411 | 16.2858 | 17.4828 | 17.4828 | 0
1326 | 2.6433 | 4.9181 | 6.3161 | 6.0914 | 4.205 | 2.3648 | 16.0176 | 15.5291 | 16.0176 | 1
1327 | 3.2334 | 4.2605 | 5.5065 | 7.262 | 3.1698 | 1.5958 | 16.3516 | 13.5054 | 16.3516 | 1
1328 | 3.3572 | 5.9945 | 6.1053 | 6.5626 | 4.3889 | 1.5087 | 17.4231 | 15.3602 | 17.4231 | 1
1329 | 3.4405 | 5.7345 | 5.2112 | 4.6057 | 4.4025 | 1.7893 | 15.57 | 14.8436 | 15.57 | 1
1330 | 3.9443 | 4.1232 | 4.581 | 5.3429 | 3.7529 | 1.7592 | 15.1696 | 14.0374 | 15.1696 | 1
1331 | 3.3256 | 4.8199 | 7.3676 | 4.4082 | 3.767 | 2.1909 | 14.7445 | 16.651 | 16.651 | 0
1332 | 3.6415 | 6.2395 | 3.1853 | 5.1496 | 4.0843 | 2.5857 | 17.6163 | 13.4969 | 17.6163 | 1
1333 | 3.0336 | 4.4628 | 5.5589 | 4.7118 | 3.7367 | 2.2497 | 14.4579 | 14.5789 | 14.5789 | 0
1334 | 2.5756 | 6.6548 | 6.3938 | 6.5962 | 4.2529 | 1.229 | 17.0555 | 14.4512 | 17.0555 | 1
1335 | 2.2531 | 4.509 | 5.8544 | 4.5468 | 3.7939 | 1.9962 | 13.3051 | 13.8976 | 13.8976 | 0
1336 | 2.9885 | 3.8359 | 6.7356 | 5.6373 | 5.2872 | 2.4268 | 14.8884 | 17.438 | 17.438 | 0
1337 | 4.6331 | 6.5011 | 7.3624 | 4.4836 | 5.6304 | 1.7154 | 17.3332 | 19.3413 | 19.3413 | 0
1338 | 3.7397 | 3.0748 | 5.9207 | 4.304 | 5.1863 | 1.8081 | 12.9265 | 16.6547 | 16.6547 | 0
1339 | 4.9842 | 3.5015 | 4.8428 | 4.0834 | 4.2952 | 1.9745 | 14.5435 | 16.0966 | 16.0966 | 0
1340 | 2.4349 | 4.3958 | 4.0329 | 5.049 | 5.4395 | 1.5535 | 13.4332 | 13.4608 | 13.4608 | 0
1341 | 4.267 | 6.13 | 6.5631 | 4.7778 | 3.8477 | 1.6485 | 16.8231 | 16.3262 | 16.8231 | 1
1342 | 3.7686 | 5.7749 | 6.8888 | 6.1958 | 4.614 | 1.5726 | 17.3119 | 16.8439 | 17.3119 | 1
1343 | 3.7675 | 4.4045 | 3.2478 | 4.5704 | 4.2265 | 1.8812 | 14.6235 | 13.123 | 14.6235 | 1
1344 | 2.5626 | 5.3303 | 5.9639 | 5.7947 | 4.5689 | 2.4996 | 16.1872 | 15.595 | 16.1872 | 1
1345 | 4.3709 | 4.1415 | 6.1281 | 6.2792 | 3.8983 | 1.4694 | 16.261 | 15.8667 | 16.261 | 1
1346 | 3.7633 | 5.0014 | 5.3112 | 4.6955 | 4.6966 | 2.5602 | 16.0204 | 16.3313 | 16.3313 | 0
1347 | 2.6502 | 8.2374 | 4.347 | 5.8257 | 3.3655 | 1.5666 | 18.2799 | 11.9292 | 18.2799 | 1
1348 | 3.5656 | 5.0515 | 4.3702 | 5.4586 | 4.1409 | 1.415 | 15.4907 | 13.4918 | 15.4907 | 1
1349 | 4.6995 | 4.2882 | 5.6042 | 5.6134 | 3.9438 | 1.4948 | 16.0959 | 15.7424 | 16.0959 | 1
1350 | 3.3375 | 4.504 | 6.5028 | 5.953 | 3.6195 | 2.4918 | 16.2863 | 15.9517 | 16.2863 | 1
1351 | 3.2441 | 5.6444 | 6.5635 | 4.4819 | 4.9126 | 1.9378 | 15.3082 | 16.6579 | 16.6579 | 0
1352 | 4.2692 | 3.623 | 6.0805 | 4.7349 | 4.2193 | 2.1583 | 14.7854 | 16.7273 | 16.7273 | 0
1353 | 4.5128 | 4.2764 | 6.1815 | 4.2254 | 3.8045 | 2.0957 | 15.1103 | 16.5945 | 16.5945 | 0
1354 | 4.1131 | 4.1418 | 5.7213 | 4.3902 | 4.5877 | 2.4606 | 15.1057 | 16.8826 | 16.8826 | 0
1355 | 3.848 | 7.0603 | 5.6655 | 5.0145 | 4.2155 | 2.3929 | 18.3158 | 16.122 | 18.3158 | 1
1356 | 4.5691 | 4.3942 | 5.1846 | 5.6637 | 5.6309 | 1.544 | 16.171 | 16.9286 | 16.9286 | 0
1357 | 4.835 | 5.887 | 6.5415 | 4.6843 | 5.823 | 1.1866 | 16.5929 | 18.3861 | 18.3861 | 0
1358 | 3.9861 | 7.1115 | 7.086 | 5.1683 | 4.3931 | 1.2142 | 17.4801 | 16.6792 | 17.4801 | 1
1359 | 4.335 | 6.0359 | 6.1698 | 4.4963 | 4.2271 | 1.4599 | 16.3271 | 16.1918 | 16.3271 | 1
1360 | 3.688 | 6.1535 | 6.9158 | 4.684 | 5.1997 | 2.1525 | 16.6779 | 17.956 | 17.956 | 0
1361 | 4.9437 | 4.9715 | 5.3595 | 6.3955 | 5.908 | 1.4299 | 17.7406 | 17.641 | 17.7406 | 1
1362 | 4.9922 | 3.7014 | 7.0155 | 6.7556 | 3.4752 | 1.7031 | 17.1523 | 17.186 | 17.186 | 0
1363 | 3.3366 | 3.7979 | 3.9863 | 6.2848 | 6.2259 | 2.2167 | 15.636 | 15.7655 | 15.7655 | 0
1364 | 4.0813 | 3.7534 | 5.117 | 6.2033 | 4.9029 | 1.8486 | 15.8866 | 15.9498 | 15.9498 | 0
1365 | 2.6305 | 4.272 | 5.1856 | 5.7071 | 3.783 | 2.3454 | 14.955 | 13.9445 | 14.955 | 1
1366 | 2.814 | 5.8532 | 4.9809 | 4.8242 | 5.7921 | 1.7059 | 15.1973 | 15.2928 | 15.2928 | 0
1367 | 3.1797 | 5.2931 | 6.4364 | 4.3097 | 4.4686 | 2.4396 | 15.222 | 16.5242 | 16.5242 | 0
1368 | 5.2594 | 4.0749 | 6.7662 | 4.8093 | 3.4368 | 1.2724 | 15.416 | 16.7348 | 16.7348 | 0
1369 | 4.0594 | 4.1849 | 6.429 | 5.3053 | 4.738 | 2.1658 | 15.7155 | 17.3923 | 17.3923 | 0
1370 | 4.2851 | 7.1243 | 3.7893 | 6.1542 | 3.5096 | 1.758 | 19.3216 | 13.3419 | 19.3216 | 1
1371 | 3.8155 | 3.6905 | 5.682 | 5.8016 | 3.2842 | 2.07 | 15.3776 | 14.8518 | 15.3776 | 1
1372 | 3.7879 | 4.8821 | 5.3566 | 5.0941 | 3.3699 | 1.8505 | 15.6146 | 14.3649 | 15.6146 | 1
1373 | 3.8501 | 5.0951 | 5.9535 | 5.8386 | 3.752 | 1.287 | 16.0708 | 14.8426 | 16.0708 | 1
1374 | 4.7184 | 4.9855 | 7.1145 | 4.7681 | 4.7372 | 1.6184 | 16.0903 | 18.1884 | 18.1884 | 0
1375 | 3.4655 | 3.8982 | 5.3057 | 5.2734 | 5.9675 | 1.8483 | 14.4853 | 16.587 | 16.587 | 0
1376 | 3.6078 | 4.7123 | 6.681 | 6.3217 | 5.0898 | 1.9074 | 16.5492 | 17.286 | 17.286 | 0
1377 | 4.3478 | 4.8977 | 5.2647 | 6.6298 | 4.597 | 2.4712 | 18.3465 | 16.6806 | 18.3465 | 1
1378 | 3.3279 | 5.4335 | 4.6006 | 4.8331 | 5.4707 | 2.1497 | 15.7442 | 15.5489 | 15.7442 | 1
1379 | 3.6728 | 6.7159 | 4.0907 | 5.2402 | 3.1966 | 2.023 | 17.6518 | 12.983 | 17.6518 | 1
1380 | 3.4881 | 6.8092 | 7.0404 | 5.8261 | 3.678 | 1.7213 | 17.8448 | 15.9279 | 17.8448 | 1
1381 | 5.6688 | 5.2344 | 6.4136 | 5.7464 | 5.8694 | 1.9459 | 18.5955 | 19.8976 | 19.8976 | 0
1382 | 4.1784 | 6.2305 | 5.2336 | 5.0446 | 4.8992 | 1.8766 | 17.3301 | 16.1878 | 17.3301 | 1
1383 | 3.3551 | 6.2811 | 3.9141 | 5.1125 | 3.8282 | 1.7242 | 16.4729 | 12.8217 | 16.4729 | 1
1384 | 4.9183 | 5.7976 | 6.4752 | 5.6385 | 3.3455 | 2.7671 | 19.1214 | 17.5061 | 19.1214 | 1
1385 | 5.2069 | 4.9789 | 7.9663 | 4.8737 | 4.9883 | 2.2094 | 17.2689 | 20.3709 | 20.3709 | 0
1386 | 2.6323 | 5.5357 | 7.167 | 4.6127 | 3.4646 | 1.7435 | 14.5243 | 15.0074 | 15.0074 | 0
1387 | 3.6344 | 5.3449 | 5.5324 | 4.9576 | 5.0503 | 1.4502 | 15.3871 | 15.6673 | 15.6673 | 0
1388 | 4.7978 | 5.1502 | 5.2849 | 4.4503 | 4.0872 | 2.0154 | 16.4137 | 16.1854 | 16.4137 | 1
1389 | 4.1027 | 4.0502 | 5.4645 | 4.9348 | 4.1561 | 2.0501 | 15.1377 | 15.7734 | 15.7734 | 0
1390 | 4.0155 | 4.9072 | 7.3852 | 6.2744 | 3.2074 | 1.9196 | 17.1167 | 16.5277 | 17.1167 | 1
1391 | 3.2104 | 5.5595 | 6.2151 | 5.1214 | 4.146 | 2.1677 | 16.0591 | 15.7391 | 16.0591 | 1
1392 | 2.9442 | 4.7299 | 6.1403 | 4.2913 | 3.7646 | 1.9259 | 13.8913 | 14.7751 | 14.7751 | 0
1393 | 3.5088 | 6.6322 | 5.3118 | 4.4611 | 4.1408 | 2.1219 | 16.724 | 15.0833 | 16.724 | 1
1394 | 5.0877 | 5.0529 | 5.1164 | 6.0644 | 4.2311 | 2.8364 | 19.0413 | 17.2716 | 19.0413 | 1
1395 | 3.8701 | 4.144 | 3.9601 | 4.7467 | 4.0509 | 1.8714 | 14.6323 | 13.7525 | 14.6323 | 1
1396 | 4.4771 | 7.0978 | 4.2034 | 4.9179 | 5.6004 | 2.6921 | 19.1848 | 16.973 | 19.1848 | 1
1397 | 3.1563 | 5.1589 | 4.2992 | 5.7504 | 5.2788 | 2.6093 | 16.6749 | 15.3437 | 16.6749 | 1
1398 | 3.9614 | 6.0658 | 6.1516 | 5.6497 | 3.0938 | 2.4952 | 18.1722 | 15.7021 | 18.1722 | 1
1399 | 3.4118 | 4.0858 | 6.981 | 5.0221 | 5.1795 | 2.4644 | 14.9842 | 18.0368 | 18.0368 | 0
1400 | 4.358 | 4.3081 | 6.9944 | 4.3297 | 3.8484 | 1.5635 | 14.5593 | 16.7644 | 16.7644 | 0
1401 | 4.3534 | 3.8463 | 7.5321 | 4.5831 | 4.8634 | 2.2817 | 15.0645 | 19.0306 | 19.0306 | 0
1402 | 3.6053 | 6.4858 | 6.1563 | 5.2877 | 4.3921 | 1.6466 | 17.0253 | 15.8002 | 17.0253 | 1
1403 | 4.3765 | 4.4186 | 7.5515 | 4.7268 | 4.625 | 2.2467 | 15.7686 | 18.7997 | 18.7997 | 0
1404 | 4.0729 | 5.3477 | 5.5541 | 6.3053 | 3.1345 | 1.1969 | 16.9227 | 13.9582 | 16.9227 | 1
1405 | 5.3899 | 7.1994 | 6.04 | 5.8046 | 5.5098 | 1.8357 | 20.2296 | 18.7755 | 20.2296 | 1
1406 | 3.5476 | 3.6451 | 4.4922 | 5.0015 | 4.8105 | 1.9099 | 14.104 | 14.7602 | 14.7602 | 0
1407 | 3.0265 | 4.0883 | 6.1664 | 5.3839 | 4.3592 | 2.5979 | 15.0966 | 16.15 | 16.15 | 0
1408 | 4.9095 | 5.7615 | 6.8454 | 5.1953 | 3.6075 | 2.2191 | 18.0855 | 17.5816 | 18.0855 | 1
1409 | 5.182 | 6.7111 | 3.2658 | 6.538 | 5.6217 | 1.8343 | 20.2654 | 15.9038 | 20.2654 | 1
1410 | 4.702 | 5.9558 | 4.7344 | 5.186 | 4.8569 | 2.0279 | 17.8717 | 16.3212 | 17.8717 | 1
1411 | 4.1649 | 3.7182 | 5.3661 | 6.7102 | 4.1636 | 2.7617 | 17.355 | 16.4562 | 17.355 | 1
1412 | 3.8604 | 6.3141 | 3.9095 | 5.7338 | 5.2071 | 2.2619 | 18.1703 | 15.2389 | 18.1703 | 1
1413 | 5.0782 | 6.5223 | 5.8214 | 5.4068 | 4.3562 | 2.5676 | 19.5748 | 17.8233 | 19.5748 | 1
1414 | 4.3162 | 4.3332 | 4.8078 | 6.6549 | 4.1026 | 1.2547 | 16.559 | 14.4814 | 16.559 | 1
1415 | 4.1728 | 7.0026 | 5.581 | 5.1726 | 5.5352 | 2.0904 | 18.4383 | 17.3793 | 18.4383 | 1
1416 | 4.7098 | 4.4279 | 6.6069 | 6.4187 | 6.1512 | 2.0534 | 17.6099 | 19.5213 | 19.5213 | 0
1417 | 3.8335 | 4.5756 | 5.9472 | 4.7364 | 5.1824 | 2.0122 | 15.1577 | 16.9753 | 16.9753 | 0
1418 | 4.6328 | 6.5759 | 6.5796 | 4.1544 | 3.7161 | 2.5562 | 17.9193 | 17.4846 | 17.9193 | 1
1419 | 2.8893 | 7.427 | 6.1802 | 5.2366 | 4.4265 | 2.7092 | 18.2621 | 16.2052 | 18.2621 | 1
1420 | 4.1263 | 5.4963 | 5.636 | 5.7666 | 3.3087 | 2.2254 | 17.6146 | 15.2965 | 17.6146 | 1
1421 | 4.2708 | 4.7946 | 5.5154 | 5.5572 | 4.0337 | 1.9516 | 16.5742 | 15.7715 | 16.5742 | 1
1422 | 3.3934 | 4.6583 | 5.5709 | 5.1366 | 3.5185 | 2.5688 | 15.7572 | 15.0516 | 15.7572 | 1
1423 | 4.7456 | 5.0261 | 6.164 | 6.507 | 4.445 | 1.8757 | 18.1545 | 17.2303 | 18.1545 | 1
1424 | 4.9253 | 5.6717 | 5.416 | 5.0787 | 4.2708 | 2.2486 | 17.9243 | 16.8607 | 17.9243 | 1
1425 | 3.4326 | 5.5267 | 5.1018 | 5.8988 | 4.5179 | 2.4562 | 17.3143 | 15.5085 | 17.3143 | 1
1426 | 4.4885 | 3.4851 | 2.9814 | 5.1731 | 5.0714 | 2.0487 | 15.1953 | 14.5899 | 15.1953 | 1
1427 | 5.7379 | 4.8143 | 6.7311 | 6.0445 | 3.9204 | 1.5894 | 18.1861 | 17.9787 | 18.1861 | 1
1428 | 4.3537 | 6.2375 | 5.0555 | 6.1714 | 4.9268 | 1.9601 | 18.7227 | 16.2961 | 18.7227 | 1
1429 | 4.4559 | 4.5885 | 5.6236 | 5.2415 | 3.4812 | 2.1718 | 16.4577 | 15.7325 | 16.4577 | 1
1430 | 3.1659 | 7.4638 | 7.9486 | 4.6616 | 4.1912 | 1.9936 | 17.2849 | 17.2993 | 17.2993 | 0
1431 | 3.6734 | 6.4027 | 4.6825 | 5.1514 | 4.1383 | 2.2299 | 17.4574 | 14.724 | 17.4574 | 1
1432 | 3.163 | 4.5641 | 7.5502 | 5.9671 | 3.1622 | 2.1706 | 15.8647 | 16.046 | 16.046 | 0
1433 | 4.1693 | 6.4992 | 5.4035 | 6.5111 | 3.5998 | 1.4167 | 18.5963 | 14.5892 | 18.5963 | 1
1434 | 4.6841 | 7.7322 | 5.6509 | 5.0007 | 3.8391 | 1.9613 | 19.3782 | 16.1354 | 19.3782 | 1
1435 | 4.7172 | 3.8298 | 5.4136 | 4.7273 | 3.6201 | 2.5181 | 15.7924 | 16.269 | 16.269 | 0
1436 | 3.6611 | 6.0832 | 6.3346 | 5.4526 | 3.5483 | 2.1559 | 17.3528 | 15.7 | 17.3528 | 1
1437 | 3.9868 | 6.5751 | 4.1792 | 4.8688 | 3.3811 | 1.8618 | 17.2924 | 13.4089 | 17.2924 | 1
1438 | 3.6772 | 5.858 | 7.3324 | 4.7658 | 3.1646 | 2.0111 | 16.3121 | 16.1852 | 16.3121 | 1
1439 | 4.0335 | 7.978 | 3.964 | 4.6772 | 3.9237 | 2.8361 | 19.5248 | 14.7573 | 19.5248 | 1
1440 | 3.3883 | 5.293 | 6.3808 | 6.8341 | 3.9065 | 1.9498 | 17.4652 | 15.6254 | 17.4652 | 1
1441 | 4.0852 | 6.9699 | 7.3986 | 5.4434 | 3.6222 | 1.7191 | 18.2176 | 16.8251 | 18.2176 | 1
1442 | 4.1194 | 4.9299 | 7.1492 | 7.0213 | 3.1182 | 2.2322 | 18.3028 | 16.6189 | 18.3028 | 1
1443 | 4.0356 | 6.6111 | 5.7551 | 4.5536 | 4.3483 | 1.5863 | 16.7865 | 15.7253 | 16.7865 | 1
1444 | 3.3931 | 7.4368 | 5.4762 | 4.4745 | 4.1658 | 2.0126 | 17.317 | 15.0478 | 17.317 | 1
1445 | 4.7854 | 7.3639 | 5.7396 | 5.7525 | 3.759 | 1.8865 | 19.7883 | 16.1704 | 19.7883 | 1
1446 | 4.2254 | 7.0945 | 7.3958 | 5.9754 | 3.4931 | 1.5151 | 18.8104 | 16.6294 | 18.8104 | 1
1447 | 4.1509 | 6.1087 | 5.2942 | 4.2455 | 3.9473 | 2.3058 | 16.8109 | 15.6982 | 16.8109 | 1
1448 | 4.1694 | 6.3233 | 5.9453 | 4.8676 | 3.9975 | 1.942 | 17.3023 | 16.0543 | 17.3023 | 1
1449 | 4.5374 | 4.1056 | 5.2125 | 4.8358 | 4.2629 | 1.6535 | 15.1323 | 15.6662 | 15.6662 | 0
1450 | 4.6778 | 3.9953 | 5.6986 | 4.7818 | 5.2524 | 2.0654 | 15.5203 | 17.6943 | 17.6943 | 0
1451 | 4.2005 | 6.0359 | 6.7586 | 6.1814 | 4.4433 | 2.001 | 18.4189 | 17.4034 | 18.4189 | 1
1452 | 3.0617 | 6.0461 | 3.4818 | 4.8156 | 3.4787 | 1.8074 | 15.7309 | 11.8297 | 15.7309 | 1
1453 | 3.9871 | 3.4644 | 4.1124 | 4.1557 | 4.5447 | 2.1931 | 13.8002 | 14.8373 | 14.8373 | 0
1454 | 4.4959 | 3.3339 | 4.4599 | 4.2957 | 3.3019 | 2.2127 | 14.3382 | 14.4704 | 14.4704 | 0
1455 | 3.6997 | 4.7695 | 4.9133 | 5.6246 | 4.3171 | 2.5022 | 16.596 | 15.4324 | 16.596 | 1
1456 | 3.2318 | 6.0884 | 4.7578 | 5.1557 | 3.8571 | 1.8592 | 16.3352 | 13.7059 | 16.3352 | 1
1457 | 4.9114 | 5.0439 | 6.0903 | 5.9475 | 4.64 | 2.13 | 18.0328 | 17.7717 | 18.0328 | 1
1458 | 5.0912 | 7.0862 | 5.1232 | 5.3523 | 3.3901 | 1.4469 | 18.9765 | 15.0514 | 18.9765 | 1
1459 | 4.2159 | 6.8176 | 4.8896 | 5.0905 | 3.6026 | 1.645 | 17.769 | 14.3531 | 17.769 | 1
1460 | 4.3781 | 4.7915 | 7.0161 | 5.7861 | 4.3164 | 2.0526 | 17.0083 | 17.7632 | 17.7632 | 0
1461 | 2.5093 | 4.1574 | 7.2405 | 4.9109 | 3.6466 | 2.6878 | 14.2655 | 16.0842 | 16.0842 | 0
1462 | 4.103 | 5.0151 | 6.816 | 5.7567 | 5.3594 | 2.7208 | 17.5956 | 18.9992 | 18.9992 | 0
1463 | 5.7431 | 4.9729 | 6.7825 | 5.9546 | 4.9951 | 1.6551 | 18.3257 | 19.1759 | 19.1759 | 0
1464 | 4.3649 | 5.1762 | 4.2325 | 4.4062 | 3.6468 | 2.5546 | 16.5019 | 14.7989 | 16.5019 | 1
1465 | 4.9792 | 4.3514 | 5.9073 | 5.0447 | 3.562 | 1.8998 | 16.2752 | 16.3483 | 16.3483 | 0
1466 | 4.0775 | 5.1525 | 6.9722 | 4.48 | 4.6005 | 1.5007 | 15.2106 | 17.1509 | 17.1509 | 0
1467 | 5.1823 | 4.5471 | 2.9608 | 4.5927 | 4.7266 | 2.5842 | 16.9062 | 15.4539 | 16.9062 | 1
1468 | 4.5004 | 4.9235 | 6.8655 | 4.8686 | 3.0866 | 1.7094 | 16.0018 | 16.1619 | 16.1619 | 0
1469 | 2.7039 | 4.6654 | 5.9023 | 5.8029 | 3.5216 | 1.3499 | 14.5221 | 13.4777 | 14.5221 | 1
1470 | 2.3131 | 6.927 | 6.9895 | 4.7801 | 4.2302 | 2.0597 | 16.0798 | 15.5924 | 16.0798 | 1
1471 | 3.5627 | 7.4418 | 4.9095 | 5.4161 | 4.0383 | 2.3038 | 18.7244 | 14.8143 | 18.7244 | 1
1472 | 5.419 | 6.6657 | 3.7162 | 4.8503 | 3.9238 | 1.7256 | 18.6606 | 14.7846 | 18.6606 | 1
1473 | 3.705 | 5.0274 | 6.861 | 4.673 | 3.8174 | 2.2523 | 15.6576 | 16.6357 | 16.6357 | 0
1474 | 3.2169 | 4.8308 | 4.3909 | 5.1453 | 3.4906 | 2.2055 | 15.3985 | 13.3038 | 15.3985 | 1
1475 | 4.4235 | 5.9703 | 3.8101 | 5.8578 | 3.7167 | 2.1927 | 18.4442 | 14.143 | 18.4442 | 1
1476 | 5.2789 | 7.0478 | 7.3492 | 5.5533 | 4.1431 | 1.3087 | 19.1887 | 18.0799 | 19.1887 | 1
1477 | 4.506 | 7.771 | 6.3745 | 5.9063 | 3.3241 | 2.7018 | 20.8851 | 16.9064 | 20.8851 | 1
1478 | 4.0306 | 4.1986 | 2.9185 | 4.764 | 5.0774 | 1.3109 | 14.3041 | 13.3374 | 14.3041 | 1
1479 | 4.4765 | 5.0034 | 5.023 | 4.863 | 3.72 | 2.208 | 16.5509 | 15.4275 | 16.5509 | 1
1480 | 3.6857 | 4.5966 | 5.7439 | 4.9423 | 5.9141 | 1.3813 | 14.6059 | 16.7249 | 16.7249 | 0
1481 | 4.3763 | 5.7902 | 6.069 | 4.5941 | 4.1631 | 1.8585 | 16.6191 | 16.4668 | 16.6191 | 1
1482 | 5.4451 | 3.7438 | 5.437 | 5.2988 | 4.3339 | 2.1832 | 16.671 | 17.3993 | 17.3993 | 0
1483 | 4.4594 | 4.7593 | 5.7213 | 6.2744 | 4.1125 | 1.9191 | 17.4122 | 16.2123 | 17.4122 | 1
1484 | 5.2293 | 7.7378 | 7.172 | 5.403 | 5.0845 | 2.6414 | 21.0115 | 20.1272 | 21.0115 | 1
1485 | 2.7468 | 5.769 | 6.3878 | 5.4795 | 4.7891 | 2.3909 | 16.3863 | 16.3145 | 16.3863 | 1
1486 | 5.1196 | 3.9026 | 3.9379 | 4.6902 | 3.6023 | 2.4903 | 16.2027 | 15.1501 | 16.2027 | 1
1487 | 4.8316 | 4.3021 | 4.1763 | 5.0523 | 3.62 | 1.7118 | 15.8978 | 14.3397 | 15.8978 | 1
1488 | 3.8545 | 6.9583 | 4.5223 | 5.6008 | 4.759 | 1.9993 | 18.4128 | 15.135 | 18.4128 | 1
1489 | 3.8235 | 4.4991 | 6.6309 | 5.9302 | 3.6706 | 1.9771 | 16.2299 | 16.102 | 16.2299 | 1
1490 | 3.4799 | 5.0094 | 4.9536 | 6.889 | 4.1352 | 1.7125 | 17.0907 | 14.2811 | 17.0907 | 1
1491 | 2.8841 | 4.4671 | 4.1871 | 4.4584 | 4.1649 | 1.4551 | 13.2647 | 12.6912 | 13.2647 | 1
1492 | 2.8369 | 4.464 | 6.0223 | 4.3687 | 4.7665 | 2.2081 | 13.8778 | 15.8338 | 15.8338 | 0
1493 | 4.3665 | 7.6462 | 6.8313 | 4.4265 | 3.2137 | 1.645 | 18.0842 | 16.0566 | 18.0842 | 1
1494 | 4.4822 | 5.3052 | 7.0171 | 6.9259 | 3.5957 | 1.5262 | 18.2395 | 16.6212 | 18.2395 | 1
1495 | 3.1761 | 6.3285 | 4.6938 | 4.2819 | 3.8862 | 2.3619 | 16.1484 | 14.1181 | 16.1484 | 1
1496 | 4.8811 | 3.9075 | 4.5747 | 4.9492 | 4.5537 | 2.3032 | 16.0409 | 16.3126 | 16.3126 | 0
1497 | 3.4917 | 4.3506 | 6.6687 | 5.5759 | 4.3941 | 2.021 | 15.4392 | 16.5756 | 16.5756 | 0
1498 | 3.592 | 7.8391 | 6.0973 | 6.7614 | 3.2373 | 1.3887 | 19.5813 | 14.3154 | 19.5813 | 1
1499 | 4.6192 | 3.5091 | 5.5109 | 5.397 | 4.1172 | 1.8971 | 15.4224 | 16.1443 | 16.1443 | 0
1500 | 4.9921 | 4.3559 | 4.6828 | 6.4285 | 3.3625 | 2.5706 | 18.3471 | 15.608 | 18.3471 | 1
1501 | 4.0947 | 5.2653 | 3.8934 | 4.7765 | 4.8485 | 1.9009 | 16.0375 | 14.7376 | 16.0375 | 1
1502 | 5.3695 | 4.8239 | 7.308 | 5.309 | 4.0265 | 2.3416 | 17.844 | 19.0456 | 19.0456 | 0
1503 | 4.3888 | 6.3687 | 3.9102 | 5.0821 | 5.2144 | 1.9217 | 17.7613 | 15.4352 | 17.7613 | 1
1504 | 3.5329 | 6.04 | 5.8713 | 4.735 | 5.2077 | 1.4824 | 15.7903 | 16.0942 | 16.0942 | 0
1505 | 3.5611 | 4.8219 | 6.4835 | 4.5973 | 3.8913 | 1.9005 | 14.8808 | 15.8364 | 15.8364 | 0
1506 | 4.0572 | 6.115 | 5.3129 | 6.6142 | 4.0775 | 1.4102 | 18.1965 | 14.8577 | 18.1965 | 1
1507 | 4.8523 | 6.9944 | 4.76 | 4.2253 | 4.4391 | 2.4235 | 18.4955 | 16.4749 | 18.4955 | 1
1508 | 2.8739 | 5.6963 | 5.036 | 5.8963 | 3.8059 | 2.7947 | 17.2612 | 14.5105 | 17.2612 | 1
1509 | 3.9241 | 3.6066 | 5.7559 | 4.4187 | 4.7636 | 1.7787 | 13.7281 | 16.2223 | 16.2223 | 0
1510 | 3.7537 | 5.0137 | 4.7994 | 5.7828 | 4.8477 | 1.8527 | 16.4029 | 15.2535 | 16.4029 | 1
1511 | 2.6533 | 4.568 | 7.5289 | 5.7743 | 5.4926 | 1.9938 | 14.9894 | 17.6686 | 17.6686 | 0
1512 | 4.1336 | 3.7658 | 6.7187 | 5.0932 | 3.7963 | 2.0856 | 15.0781 | 16.7341 | 16.7341 | 0
1513 | 4.4139 | 6.0081 | 7.1928 | 5.3738 | 4.6082 | 1.9259 | 17.7216 | 18.1408 | 18.1408 | 0
1514 | 4.1164 | 5.7945 | 5.3164 | 4.7497 | 3.803 | 1.2231 | 15.8836 | 14.4589 | 15.8836 | 1
1515 | 5.4626 | 5.1236 | 7.0139 | 5.1774 | 4.8793 | 2.1463 | 17.91 | 19.5021 | 19.5021 | 0
1516 | 4.253 | 4.8244 | 6.8311 | 5.5551 | 3.8834 | 1.6766 | 16.3092 | 16.6441 | 16.6441 | 0
1517 | 5.4383 | 6.8737 | 4.6991 | 4.2794 | 4.4031 | 2.2409 | 18.8323 | 16.7814 | 18.8323 | 1
1518 | 4.5327 | 5.413 | 3.6033 | 5.3848 | 4.7293 | 1.8403 | 17.1708 | 14.7056 | 17.1708 | 1
1519 | 3.1716 | 6.0762 | 7.0247 | 4.887 | 3.758 | 1.3779 | 15.5127 | 15.3323 | 15.5127 | 1
1520 | 2.8955 | 4.821 | 6.6849 | 6.4039 | 5.2557 | 1.8816 | 16.002 | 16.7177 | 16.7177 | 0
1521 | 4.403 | 5.679 | 5.5414 | 5.7801 | 3.4444 | 2.6182 | 18.4803 | 16.007 | 18.4803 | 1
1522 | 4.3073 | 4.6054 | 2.6332 | 7.053 | 4.1199 | 2.1861 | 18.1518 | 13.2465 | 18.1518 | 1
1523 | 4.3863 | 6.4965 | 3.6274 | 5.568 | 3.6114 | 1.7957 | 18.2465 | 13.4208 | 18.2465 | 1
1524 | 4.6006 | 5.0245 | 4.6245 | 6.0731 | 3.4704 | 1.4509 | 17.149 | 14.1463 | 17.149 | 1
1525 | 4.0967 | 6.221 | 4.7877 | 5.8498 | 3.9339 | 2.1353 | 18.3028 | 14.9537 | 18.3028 | 1
1526 | 3.8594 | 4.8542 | 3.636 | 4.8157 | 3.985 | 2.2066 | 15.7359 | 13.687 | 15.7359 | 1
1527 | 3.509 | 5.6414 | 5.5909 | 5.1067 | 3.3083 | 1.4882 | 15.7453 | 13.8964 | 15.7453 | 1
1528 | 4.3174 | 6.7926 | 6.8847 | 5.0637 | 5.0587 | 2.0294 | 18.203 | 18.2902 | 18.2902 | 0
1529 | 5.3173 | 5.8694 | 5.4679 | 5.3692 | 4.9406 | 2.3688 | 18.9248 | 18.0947 | 18.9248 | 1
1530 | 3.7711 | 4.26 | 4.1969 | 7.1163 | 4.681 | 2.6267 | 17.7741 | 15.2757 | 17.7741 | 1
1531 | 4.4343 | 5.8409 | 7.5811 | 5.8504 | 4.2448 | 2.2201 | 18.3458 | 18.4803 | 18.4803 | 0
1532 | 4.7135 | 4.3846 | 5.6498 | 5.3099 | 3.5372 | 1.8574 | 16.2654 | 15.7579 | 16.2654 | 1
1533 | 3.7314 | 7.4823 | 5.0706 | 4.7346 | 4.7921 | 1.7588 | 17.7071 | 15.3529 | 17.7071 | 1
1534 | 4.4878 | 7.1471 | 5.8219 | 5.2729 | 4.5257 | 2.2893 | 19.197 | 17.1247 | 19.197 | 1
1535 | 4.02 | 6.1979 | 3.4611 | 4.0538 | 4.5155 | 1.9287 | 16.2004 | 13.9254 | 16.2004 | 1
1536 | 3.6422 | 4.5589 | 3.1249 | 4.9635 | 4.5048 | 2.1825 | 15.3471 | 13.4544 | 15.3471 | 1
1537 | 3.0653 | 5.5122 | 4.8592 | 4.3564 | 4.0925 | 2.0438 | 14.9777 | 14.0608 | 14.9777 | 1
1538 | 5.07 | 5.4882 | 5.588 | 6.4727 | 4.583 | 1.3297 | 18.3606 | 16.5707 | 18.3606 | 1
1539 | 3.2668 | 4.2687 | 6.7515 | 4.5053 | 5.5849 | 1.8884 | 13.9292 | 17.4916 | 17.4916 | 0
1540 | 3.5148 | 5.0998 | 5.1828 | 5.6583 | 5.0577 | 2.0741 | 16.3469 | 15.8293 | 16.3469 | 1
1541 | 4.288 | 4.7006 | 5.0497 | 5.4825 | 3.2416 | 1.4979 | 15.969 | 14.0771 | 15.969 | 1
1542 | 3.1078 | 5.0926 | 4.9006 | 6.5427 | 3.8511 | 1.7682 | 16.5113 | 13.6277 | 16.5113 | 1
1543 | 4.5088 | 4.8479 | 6.6846 | 4.827 | 4.5212 | 2.3513 | 16.5351 | 18.066 | 18.066 | 0
1544 | 4.597 | 6.0037 | 5.7454 | 4.6698 | 3.7478 | 1.9103 | 17.1809 | 16.0006 | 17.1809 | 1
1545 | 4.2489 | 4.9788 | 6.5689 | 5.0371 | 3.5604 | 1.8321 | 16.0968 | 16.2103 | 16.2103 | 0
1546 | 2.746 | 6.2092 | 4.4165 | 5.0104 | 3.0978 | 1.969 | 15.9346 | 12.2293 | 15.9346 | 1
1547 | 4.4558 | 5.3459 | 4.5187 | 6.855 | 4.3353 | 2.0256 | 18.6823 | 15.3355 | 18.6823 | 1
1548 | 4.2832 | 4.2637 | 7.4321 | 4.9451 | 3.545 | 2.1672 | 15.6593 | 17.4275 | 17.4275 | 0
1549 | 4.0068 | 4.7917 | 6.2101 | 4.6086 | 4.5589 | 2.0312 | 15.4383 | 16.807 | 16.807 | 0
1550 | 2.5673 | 4.4861 | 6.8169 | 5.0099 | 5.5017 | 1.7722 | 13.8354 | 16.658 | 16.658 | 0
1551 | 3.44 | 3.4979 | 6.9254 | 5.796 | 4.3832 | 2.738 | 15.4719 | 17.4867 | 17.4867 | 0
1552 | 4.9668 | 4.4243 | 6.8321 | 5.0969 | 4.2941 | 1.8595 | 16.3475 | 17.9525 | 17.9525 | 0
1553 | 5.4119 | 4.2336 | 5.6764 | 4.5994 | 4.4767 | 2.5612 | 16.8061 | 18.1262 | 18.1262 | 0
1554 | 3.4537 | 5.6214 | 5.9447 | 4.4165 | 4.7969 | 2.0934 | 15.585 | 16.2886 | 16.2886 | 0
1555 | 3.6185 | 6.477 | 4.0888 | 4.9621 | 4.0932 | 1.9748 | 17.0324 | 13.7753 | 17.0324 | 1
1556 | 3.6962 | 6.4844 | 5.9573 | 5.5097 | 4.6814 | 1.8679 | 17.5582 | 16.2027 | 17.5582 | 1
1557 | 4.4066 | 6.769 | 6.7932 | 5.8209 | 5.0572 | 1.9368 | 18.9333 | 18.1937 | 18.9333 | 1
1558 | 3.8094 | 4.2115 | 5.1224 | 5.8177 | 5.5436 | 2.5312 | 16.3698 | 17.0067 | 17.0067 | 0
1559 | 2.6874 | 4.2442 | 5.1088 | 5.5411 | 3.445 | 2.1408 | 14.6135 | 13.382 | 14.6135 | 1
1560 | 3.0121 | 7.2084 | 6.4846 | 5.8838 | 3.7171 | 2.5958 | 18.7001 | 15.8095 | 18.7001 | 1
1561 | 5.5004 | 6.0733 | 6.6588 | 4.4622 | 5.1079 | 2.1861 | 18.2221 | 19.4533 | 19.4533 | 0
1562 | 3.1534 | 4.6298 | 6.5444 | 5.5042 | 4.2211 | 2.4805 | 15.7679 | 16.3994 | 16.3994 | 0
1563 | 3.4642 | 5.405 | 6.8766 | 6.3355 | 4.33 | 1.6521 | 16.8569 | 16.323 | 16.8569 | 1
1564 | 4.3811 | 7.8497 | 4.216 | 4.4051 | 3.8922 | 1.9154 | 18.5513 | 14.4047 | 18.5513 | 1
1565 | 4.4915 | 4.5993 | 5.9898 | 6.5534 | 4.9334 | 1.9139 | 17.5581 | 17.3286 | 17.5581 | 1
1566 | 3.1756 | 5.2848 | 5.1745 | 5.8876 | 3.2043 | 1.6288 | 15.9769 | 13.1832 | 15.9769 | 1
1567 | 3.4086 | 5.3478 | 5.5623 | 6.3094 | 3.7686 | 1.4754 | 16.5411 | 14.2149 | 16.5411 | 1
1568 | 4.7162 | 5.3159 | 6.7336 | 4.7226 | 4.0022 | 2.1986 | 16.9533 | 17.6506 | 17.6506 | 0
1569 | 3.4835 | 3.3565 | 6.1976 | 4.7315 | 3.5922 | 1.8931 | 13.4646 | 15.1664 | 15.1664 | 0
1570 | 3.7711 | 6.2845 | 6.8168 | 6.2286 | 5.9982 | 2.4782 | 18.7624 | 19.0643 | 19.0643 | 0
1571 | 3.0376 | 5.2635 | 2.8746 | 5.5367 | 4.2201 | 2.4644 | 16.3023 | 12.5967 | 16.3023 | 1
1572 | 4.0906 | 4.1422 | 4.8466 | 4.4177 | 3.8064 | 1.9113 | 14.5618 | 14.6549 | 14.6549 | 0
1573 | 3.9916 | 5.3772 | 6.6357 | 4.9706 | 4.736 | 2.7621 | 17.1015 | 18.1254 | 18.1254 | 0
1574 | 4.4296 | 5.4227 | 5.2239 | 4.7454 | 3.3455 | 2.009 | 16.6067 | 15.0081 | 16.6067 | 1
1575 | 3.9087 | 4.8753 | 3.649 | 4.3517 | 3.695 | 2.5546 | 15.6903 | 13.8073 | 15.6903 | 1
1576 | 3.8005 | 6.7772 | 4.6201 | 6.628 | 4.8511 | 1.9819 | 19.1876 | 15.2536 | 19.1876 | 1
1577 | 4.3412 | 6.297 | 5.216 | 5.2312 | 5.1445 | 1.2882 | 17.1575 | 15.9899 | 17.1575 | 1
1578 | 4.716 | 7.2438 | 4.4905 | 4.274 | 4.2043 | 1.9425 | 18.1763 | 15.3533 | 18.1763 | 1
1579 | 3.0803 | 6.2253 | 5.5315 | 5.675 | 4.2104 | 1.2154 | 16.196 | 14.0376 | 16.196 | 1
1580 | 4.4301 | 5.5407 | 6.0428 | 6.137 | 3.6778 | 1.5392 | 17.647 | 15.6898 | 17.647 | 1
1581 | 4.1515 | 5.9115 | 5.8597 | 4.8255 | 5.1801 | 1.3623 | 16.2508 | 16.5537 | 16.5537 | 0
1582 | 4.3713 | 6.956 | 5.0435 | 5.5152 | 3.7723 | 1.5997 | 18.4423 | 14.7869 | 18.4423 | 1
1583 | 3.5209 | 3.0419 | 5.8488 | 4.8616 | 3.2637 | 2.7168 | 14.1413 | 15.3502 | 15.3502 | 0
1584 | 3.6766 | 8.3566 | 6.1081 | 5.6723 | 3.5544 | 2.2433 | 19.9487 | 15.5823 | 19.9487 | 1
1585 | 4.1519 | 5.8061 | 4.323 | 4.3211 | 3.5977 | 2.1194 | 16.3985 | 14.192 | 16.3985 | 1
1586 | 3.8828 | 5.7444 | 5.4877 | 6.4725 | 5.2534 | 1.6466 | 17.7464 | 16.2704 | 17.7464 | 1
1587 | 4.4807 | 4.8335 | 5.5167 | 4.1616 | 4.2566 | 1.7686 | 15.2445 | 16.0227 | 16.0227 | 0
1588 | 4.7667 | 4.1587 | 6.1367 | 4.6144 | 4.1434 | 1.6338 | 15.1736 | 16.6806 | 16.6806 | 0
1589 | 4.9077 | 3.7546 | 5.7437 | 4.3692 | 5.4428 | 2.3015 | 15.3332 | 18.3957 | 18.3957 | 0
1590 | 5.1118 | 7.235 | 7.7648 | 4.0498 | 5.2393 | 1.9722 | 18.3689 | 20.0882 | 20.0882 | 0
1591 | 3.2691 | 5.0651 | 7.1514 | 5.1768 | 5.2455 | 1.5323 | 15.0433 | 17.1983 | 17.1983 | 0
1592 | 4.6048 | 4.2281 | 6.3198 | 5.1638 | 3.5834 | 2.2843 | 16.2809 | 16.7922 | 16.7922 | 0
1593 | 4.4171 | 5.1056 | 7.3378 | 5.3278 | 3.9128 | 1.7045 | 16.555 | 17.3722 | 17.3722 | 0
1594 | 4.4087 | 5.4802 | 6.5639 | 6.44 | 3.2788 | 1.8857 | 18.2146 | 16.1371 | 18.2146 | 1
1595 | 5.1539 | 4.8822 | 6.3432 | 6.3713 | 5.5124 | 2.2766 | 18.6841 | 19.2861 | 19.2861 | 0
1596 | 3.7672 | 4.821 | 5.8739 | 5.003 | 3.612 | 1.5503 | 15.1415 | 14.8034 | 15.1415 | 1
1597 | 2.8834 | 4.8264 | 3.7611 | 4.8156 | 5.4442 | 2.0616 | 14.5872 | 14.1503 | 14.5872 | 1
1598 | 4.4973 | 7.7451 | 6.8815 | 4.3835 | 5.3014 | 2.4011 | 19.027 | 19.0814 | 19.0814 | 0
1599 | 4.7376 | 5.4571 | 5.5655 | 4.1546 | 4.1263 | 2.2614 | 16.6107 | 16.6907 | 16.6907 | 0
1600 | 3.7436 | 4.1587 | 5.2383 | 5.7082 | 5.1516 | 1.6597 | 15.2702 | 15.7932 | 15.7932 | 0
1601 | 4.0786 | 4.6586 | 7.5798 | 5.5441 | 4.6387 | 2.2413 | 16.5226 | 18.5384 | 18.5384 | 0
1602 | 4.0979 | 5.7662 | 5.6362 | 4.6126 | 4.3758 | 1.8881 | 16.3649 | 15.9981 | 16.3649 | 1
1603 | 3.2606 | 5.6636 | 5.9572 | 5.0319 | 4.2668 | 1.4957 | 15.4518 | 14.9803 | 15.4518 | 1
1604 | 3.2849 | 6.2165 | 5.4469 | 4.7955 | 3.684 | 1.4275 | 15.7243 | 13.8432 | 15.7243 | 1
1605 | 3.0093 | 3.7353 | 7.3391 | 5.8256 | 5.3576 | 1.6833 | 14.2535 | 17.3893 | 17.3893 | 0
1606 | 2.6375 | 5.2483 | 5.4262 | 4.7194 | 5.1879 | 1.8108 | 14.4159 | 15.0624 | 15.0624 | 0
1607 | 2.8474 | 6.0833 | 2.4152 | 5.6844 | 4.1866 | 1.408 | 16.0232 | 10.8573 | 16.0232 | 1
1608 | 4.6594 | 5.5276 | 5.886 | 4.2542 | 4.8095 | 2.253 | 16.6943 | 17.6078 | 17.6078 | 0
1609 | 4.072 | 3.7109 | 4.0322 | 4.5393 | 4.0718 | 2.4709 | 14.7931 | 14.6468 | 14.7931 | 1
1610 | 4.7783 | 4.9491 | 3.8661 | 4.8578 | 4.4401 | 1.7435 | 16.3287 | 14.828 | 16.3287 | 1
1611 | 3.5161 | 4.1447 | 6.8859 | 4.297 | 4.0893 | 2.2697 | 14.2275 | 16.761 | 16.761 | 0
1612 | 4.6089 | 6.2771 | 5.9595 | 6.3433 | 5.5863 | 2.1692 | 19.3985 | 18.3239 | 19.3985 | 1
1613 | 3.4121 | 5.0445 | 5.6236 | 5.3062 | 6.2907 | 1.8754 | 15.6382 | 17.2018 | 17.2018 | 0
1614 | 3.8059 | 6.0579 | 5.0321 | 5.6642 | 3.4684 | 2.1143 | 17.6423 | 14.4207 | 17.6423 | 1
1615 | 4.5178 | 6.8933 | 5.3795 | 5.5723 | 3.8145 | 1.6515 | 18.6349 | 15.3633 | 18.6349 | 1
1616 | 3.9661 | 6.4723 | 6.1794 | 5.6576 | 4.1803 | 1.9985 | 18.0945 | 16.3244 | 18.0945 | 1
1617 | 5.7509 | 5.1662 | 5.7955 | 5.9229 | 3.7132 | 1.5977 | 18.4378 | 16.8573 | 18.4378 | 1
1618 | 3.9179 | 3.8372 | 6.1327 | 4.6788 | 3.6066 | 2.2857 | 14.7196 | 15.9428 | 15.9428 | 0
1619 | 4.1999 | 3.9099 | 6.9539 | 5.9179 | 4.5797 | 2.4061 | 16.4338 | 18.1396 | 18.1396 | 0
1620 | 3.6409 | 6.4653 | 7.1085 | 4.9837 | 4.9921 | 1.6589 | 16.7489 | 17.4005 | 17.4005 | 0
1621 | 4.6563 | 4.4615 | 6.2505 | 5.1236 | 4.3258 | 2.565 | 16.8064 | 17.7976 | 17.7976 | 0
1622 | 3.6848 | 7.9308 | 4.3786 | 6.2912 | 5.3369 | 1.4692 | 19.3759 | 14.8694 | 19.3759 | 1
1623 | 3.7345 | 5.0727 | 5.0859 | 4.5236 | 4.1627 | 2.4608 | 15.7916 | 15.444 | 15.7916 | 1
1624 | 5.2967 | 6.5004 | 3.8336 | 4.6309 | 4.9035 | 1.924 | 18.352 | 15.9578 | 18.352 | 1
1625 | 3.9267 | 5.3344 | 4.2363 | 6.4328 | 4.2414 | 2.4313 | 18.1252 | 14.8358 | 18.1252 | 1
1626 | 4.5269 | 6.0708 | 5.2654 | 5.8941 | 3.9665 | 1.9227 | 18.4146 | 15.6816 | 18.4146 | 1
1627 | 4.805 | 5.9195 | 6.4618 | 5.3646 | 5.032 | 2.1194 | 18.2085 | 18.4183 | 18.4183 | 0
1628 | 4.7976 | 5.038 | 7.4396 | 6.2613 | 5.6198 | 1.7143 | 17.8112 | 19.5713 | 19.5713 | 0
1629 | 3.9654 | 5.7905 | 6.4153 | 6.6023 | 4.4287 | 1.7447 | 18.1029 | 16.5541 | 18.1029 | 1
1630 | 3.7508 | 6.9002 | 4.3062 | 5.1431 | 5.3568 | 2.1641 | 17.9582 | 15.5779 | 17.9582 | 1
1631 | 4.464 | 4.5451 | 6.5014 | 5.9085 | 5.3311 | 1.6598 | 16.5773 | 17.9562 | 17.9562 | 0
1632 | 4.2263 | 4.9029 | 6.0871 | 6.4735 | 3.343 | 1.4021 | 17.0048 | 15.0585 | 17.0048 | 1
1633 | 2.9516 | 3.8899 | 5.8762 | 4.9301 | 5.0554 | 2.2518 | 14.0235 | 16.1351 | 16.1351 | 0
1634 | 3.57 | 5.1042 | 7.7692 | 4.7707 | 3.7596 | 2.1671 | 15.6119 | 17.2658 | 17.2658 | 0
1635 | 2.4149 | 4.3234 | 4.9625 | 4.6803 | 4.6104 | 1.9887 | 13.4073 | 13.9765 | 13.9765 | 0
1636 | 3.3752 | 4.557 | 5.9508 | 4.6011 | 4.0689 | 2.0399 | 14.5731 | 15.4348 | 15.4348 | 0
1637 | 4.4618 | 5.8615 | 5.3473 | 6.2543 | 4.2017 | 2.1043 | 18.682 | 16.1152 | 18.682 | 1
1638 | 3.4853 | 4.6415 | 6.2835 | 5.7775 | 3.8758 | 1.9975 | 15.9018 | 15.6422 | 15.9018 | 1
1639 | 5.0979 | 5.8773 | 6.7838 | 6.4008 | 4.9478 | 2.7198 | 20.0959 | 19.5493 | 20.0959 | 1
1640 | 4.1589 | 4.6198 | 6.3578 | 5.4085 | 3.7965 | 2.2779 | 16.4651 | 16.5911 | 16.5911 | 0
1641 | 3.4869 | 4.7015 | 5.7882 | 5.229 | 4.6877 | 1.9439 | 15.3613 | 15.9068 | 15.9068 | 0
1642 | 3.7343 | 4.5919 | 6.1287 | 4.5196 | 4.2971 | 1.5642 | 14.41 | 15.7243 | 15.7243 | 0
1643 | 2.8161 | 4.8472 | 6.4572 | 6.0808 | 4.1103 | 1.7497 | 15.4939 | 15.1334 | 15.4939 | 1
1644 | 5.7005 | 4.3609 | 6.3313 | 4.9738 | 6.2041 | 1.5112 | 16.5463 | 19.747 | 19.747 | 0
1645 | 3.6804 | 5.9593 | 4.7847 | 6.6355 | 4.2169 | 1.3679 | 17.6431 | 14.0499 | 17.6431 | 1
1646 | 3.9794 | 4.5 | 6.5956 | 4.1839 | 3.879 | 1.9552 | 14.6186 | 16.4093 | 16.4093 | 0
1647 | 4.6749 | 4.6921 | 4.4304 | 5.8432 | 5.2263 | 1.8237 | 17.034 | 16.1554 | 17.034 | 1
1648 | 4.718 | 4.4697 | 6.271 | 6.2807 | 4.0771 | 2.1124 | 17.5808 | 17.1784 | 17.5808 | 1
1649 | 4.176 | 5.776 | 7.0359 | 4.2157 | 3.7771 | 1.9944 | 16.162 | 16.9834 | 16.9834 | 0
1650 | 4.6311 | 5.3449 | 6.5885 | 5.3633 | 5.0649 | 1.6387 | 16.9781 | 17.9232 | 17.9232 | 0
1651 | 4.2681 | 5.0387 | 6.215 | 5.9 | 3.9634 | 2.204 | 17.4108 | 16.6506 | 17.4108 | 1
1652 | 5.351 | 4.4793 | 4.6103 | 4.4967 | 4.6585 | 2.6324 | 16.9594 | 17.2522 | 17.2522 | 0
1653 | 5.1331 | 4.4274 | 4.7834 | 6.3106 | 5.6303 | 2.3634 | 18.2344 | 17.9102 | 18.2344 | 1
1654 | 3.0763 | 4.1043 | 6.0803 | 4.8994 | 4.664 | 1.1813 | 13.2614 | 15.0019 | 15.0019 | 0
1655 | 4.406 | 3.5077 | 7.3844 | 5.8334 | 3.4777 | 2.5826 | 16.3297 | 17.8508 | 17.8508 | 0
1656 | 3.7561 | 3.9814 | 6.455 | 7.0184 | 5.1642 | 1.7894 | 16.5453 | 17.1647 | 17.1647 | 0
1657 | 5.1529 | 7.9777 | 4.9769 | 5.119 | 4.1221 | 1.9225 | 20.172 | 16.1744 | 20.172 | 1
1658 | 4.9236 | 5.6497 | 3.969 | 5.1615 | 4.2476 | 2.0846 | 17.8195 | 15.2249 | 17.8195 | 1
1659 | 4.9687 | 7.675 | 4.9465 | 5.4179 | 4.2238 | 2.1395 | 20.2011 | 16.2786 | 20.2011 | 1
1660 | 3.963 | 4.2676 | 6.8585 | 6.2963 | 4.3323 | 2.4314 | 16.9583 | 17.5852 | 17.5852 | 0
1661 | 4.2558 | 4.4715 | 5.2338 | 5.5312 | 4.1442 | 1.5769 | 15.8354 | 15.2107 | 15.8354 | 1
1662 | 3.1858 | 5.7217 | 5.6538 | 7.0021 | 4.8682 | 2.5658 | 18.4755 | 16.2736 | 18.4755 | 1
1663 | 4.3374 | 6.8399 | 7.1547 | 7.1264 | 4.9366 | 2.1231 | 20.4269 | 18.5518 | 20.4269 | 1
1664 | 4.7589 | 6.2098 | 7.4307 | 5.6244 | 4.372 | 1.9215 | 18.5146 | 18.483 | 18.5146 | 1
1665 | 4.1346 | 7.4479 | 4.5701 | 6.4876 | 4.6224 | 2.5014 | 20.5714 | 15.8284 | 20.5714 | 1
1666 | 5.2851 | 6.1005 | 7.4323 | 5.253 | 3.6107 | 2.4532 | 19.0918 | 18.7813 | 19.0918 | 1
1667 | 4.4308 | 4.988 | 4.6189 | 5.4939 | 3.7482 | 2.2625 | 17.1752 | 15.0603 | 17.1752 | 1
1668 | 2.7811 | 5.2956 | 5.922 | 6.2057 | 4.9777 | 1.8043 | 16.0867 | 15.4852 | 16.0867 | 1
1669 | 4.8334 | 3.8095 | 6.254 | 5.2705 | 4.1689 | 1.4802 | 15.3935 | 16.7365 | 16.7365 | 0
1670 | 3.7635 | 5.5697 | 5.0236 | 5.4923 | 3.8778 | 2.0421 | 16.8675 | 14.7069 | 16.8675 | 1
1671 | 5.0914 | 5.1975 | 4.533 | 7.2012 | 3.4299 | 2.0743 | 19.5643 | 15.1285 | 19.5643 | 1
1672 | 5.4781 | 4.5922 | 5.9643 | 5.1843 | 5.1718 | 2.3036 | 17.5581 | 18.9177 | 18.9177 | 0
1673 | 4.0188 | 5.8521 | 7.2841 | 5.4357 | 3.7124 | 2.0011 | 17.3078 | 17.0165 | 17.3078 | 1
1674 | 3.7177 | 5.9063 | 5.4546 | 5.1571 | 4.4493 | 1.8021 | 16.5832 | 15.4237 | 16.5832 | 1
1675 | 3.6012 | 7.6022 | 7.3129 | 5.9525 | 3.758 | 2.5152 | 19.671 | 17.1872 | 19.671 | 1
1676 | 5.2348 | 6.9634 | 6.8314 | 4.6224 | 3.8211 | 1.5701 | 18.3908 | 17.4575 | 18.3908 | 1
1677 | 2.7064 | 7.7789 | 5.1068 | 6.2706 | 3.6438 | 1.8165 | 18.5725 | 13.2736 | 18.5725 | 1
1678 | 4.5858 | 6.6572 | 6.0045 | 6.0565 | 4.8038 | 2.014 | 19.3135 | 17.4081 | 19.3135 | 1
1679 | 4.3338 | 5.4959 | 4.1254 | 5.0921 | 3.4858 | 2.4507 | 17.3725 | 14.3957 | 17.3725 | 1
1680 | 4.0287 | 4.4434 | 5.8595 | 4.828 | 3.2411 | 2.0962 | 15.3962 | 15.2255 | 15.3962 | 1
1681 | 4.3835 | 4.9452 | 5.9324 | 4.5355 | 3.1838 | 1.4968 | 15.3611 | 14.9964 | 15.3611 | 1
1682 | 4.9042 | 5.0493 | 7.1094 | 5.3178 | 4.8269 | 2.2515 | 17.5227 | 19.0919 | 19.0919 | 0
1683 | 5.3728 | 4.6872 | 7.6664 | 5.4487 | 4.572 | 2.1763 | 17.6851 | 19.7875 | 19.7875 | 0
1684 | 5.2649 | 6.2627 | 6.4913 | 6.2067 | 3.1961 | 2.3773 | 20.1115 | 17.3295 | 20.1115 | 1
1685 | 3.8189 | 5.4997 | 4.4625 | 4.9173 | 5.465 | 2.3997 | 16.6357 | 16.1461 | 16.6357 | 1
1686 | 3.3561 | 7.4579 | 6.8094 | 5.5785 | 4.0179 | 1.9668 | 18.3593 | 16.1502 | 18.3593 | 1
1687 | 4.9068 | 3.5654 | 6.7526 | 5.2799 | 3.9103 | 2.0133 | 15.7653 | 17.583 | 17.583 | 0
1688 | 4.676 | 3.5884 | 4.2002 | 5.0673 | 5.1196 | 1.1626 | 14.4943 | 15.1584 | 15.1584 | 0
1689 | 4.6263 | 4.1014 | 5.7579 | 4.6899 | 3.3425 | 1.7989 | 15.2163 | 15.5255 | 15.5255 | 0
1690 | 4.3244 | 4.9411 | 6.3276 | 5.6703 | 4.6169 | 1.4238 | 16.3595 | 16.6927 | 16.6927 | 0
1691 | 4.39 | 4.6606 | 7.327 | 4.1468 | 4.2496 | 2.7169 | 15.9143 | 18.6835 | 18.6835 | 0
1692 | 3.3477 | 6.1182 | 3.18 | 6.9062 | 4.6347 | 1.2258 | 17.5979 | 12.3882 | 17.5979 | 1
1693 | 2.7516 | 5.8623 | 6.5861 | 6.7086 | 3.7337 | 1.906 | 17.2285 | 14.9774 | 17.2285 | 1
1694 | 5.3149 | 6.0944 | 4.4778 | 4.3076 | 3.557 | 2.3384 | 18.0554 | 15.6881 | 18.0554 | 1
1695 | 4.2537 | 6.8628 | 3.3058 | 5.911 | 3.8044 | 1.903 | 18.9305 | 13.2669 | 18.9305 | 1
1696 | 3.6093 | 5.1549 | 7.6784 | 6.5883 | 4.9186 | 2.207 | 17.5595 | 18.4133 | 18.4133 | 0
1697 | 4.7413 | 6.2208 | 4.2363 | 4.5449 | 3.4331 | 2.6668 | 18.1738 | 15.0774 | 18.1738 | 1
1698 | 3.6756 | 5.3573 | 4.6829 | 5.6663 | 3.3487 | 2.2886 | 16.9878 | 13.9958 | 16.9878 | 1
1699 | 4.0418 | 5.5613 | 5.0055 | 4.7964 | 4.1299 | 2.3893 | 16.7889 | 15.5665 | 16.7889 | 1
1700 | 3.8672 | 5.5831 | 5.6983 | 4.885 | 4.3413 | 2.022 | 16.3573 | 15.9287 | 16.3573 | 1
1701 | 4.2852 | 6.366 | 4.991 | 4.461 | 5.8003 | 1.792 | 16.9043 | 16.8686 | 16.9043 | 1
1702 | 4.5522 | 5.4226 | 6.1562 | 5.4861 | 5.1096 | 2.1066 | 17.5676 | 17.9247 | 17.9247 | 0
1703 | 4.5343 | 5.7711 | 5.5666 | 6.0381 | 5.6139 | 1.5861 | 17.9297 | 17.301 | 17.9297 | 1
1704 | 3.5941 | 5.7977 | 6.9175 | 6.1154 | 4.7998 | 2.5351 | 18.0422 | 17.8465 | 18.0422 | 1
1705 | 3.3783 | 5.7333 | 6.4053 | 5.8048 | 4.4061 | 1.5158 | 16.4321 | 15.7055 | 16.4321 | 1
1706 | 3.1269 | 5.2528 | 6.7829 | 5.2818 | 3.1254 | 1.9762 | 15.6376 | 15.0113 | 15.6376 | 1
1707 | 5.3867 | 4.1175 | 4.8639 | 5.3382 | 4.3044 | 2.1263 | 16.9688 | 16.6815 | 16.9688 | 1
1708 | 3.4894 | 3.2709 | 6.8794 | 4.993 | 5.5958 | 1.4721 | 13.2255 | 17.4367 | 17.4367 | 0
1709 | 5.2539 | 5.7173 | 2.5823 | 6.3734 | 4.6724 | 1.3403 | 18.6848 | 13.8489 | 18.6848 | 1
1710 | 4.7403 | 4.5857 | 3.6324 | 6.2835 | 4.717 | 1.3909 | 17.0004 | 14.4805 | 17.0004 | 1
1711 | 5.0002 | 5.7385 | 5.0713 | 5.1031 | 4.6341 | 1.3075 | 17.1493 | 16.0131 | 17.1493 | 1
1712 | 4.8579 | 5.4766 | 5.2539 | 4.5837 | 4.7752 | 1.9621 | 16.8803 | 16.8491 | 16.8803 | 1
1713 | 3.8249 | 6.2024 | 4.6079 | 4.6736 | 4.2167 | 1.6742 | 16.3752 | 14.3238 | 16.3752 | 1
1714 | 3.9873 | 5.3648 | 7.2329 | 5.2004 | 6.0649 | 1.4588 | 16.0113 | 18.744 | 18.744 | 0
1715 | 3.5511 | 5.7716 | 6.2411 | 6.1106 | 5.2538 | 2.7561 | 18.1895 | 17.8022 | 18.1895 | 1
1716 | 3.5373 | 6.3367 | 6.367 | 4.8514 | 4.3756 | 2.2718 | 16.9972 | 16.5518 | 16.9972 | 1
1717 | 3.5516 | 5.3215 | 5.6099 | 5.6898 | 4.0822 | 1.9375 | 16.5004 | 15.1812 | 16.5004 | 1
1718 | 4.9418 | 3.4481 | 7.2687 | 5.1324 | 4.8215 | 1.9717 | 15.4941 | 19.0037 | 19.0037 | 0
1719 | 3.2452 | 4.0353 | 6.0694 | 5.8451 | 4.2281 | 2.3513 | 15.4769 | 15.894 | 15.894 | 0
1720 | 2.708 | 3.4402 | 7.3583 | 5.4641 | 4.7128 | 1.9241 | 13.5364 | 16.7033 | 16.7033 | 0
1721 | 3.9711 | 6.9457 | 4.9586 | 5.151 | 3.7586 | 1.8562 | 17.9239 | 14.5444 | 17.9239 | 1
1722 | 3.434 | 5.8169 | 6.2793 | 4.3737 | 3.0864 | 1.4559 | 15.0805 | 14.2557 | 15.0805 | 1
1723 | 3.4755 | 4.4987 | 4.3006 | 4.6353 | 4.2014 | 1.9028 | 14.5123 | 13.8804 | 14.5123 | 1
1724 | 3.7142 | 3.1872 | 5.1359 | 6.0252 | 3.9679 | 1.8376 | 14.7642 | 14.6557 | 14.7642 | 1
1725 | 4.1744 | 5.2003 | 5.1057 | 5.0868 | 5.3477 | 2.213 | 16.6744 | 16.8407 | 16.8407 | 0
1726 | 5.1078 | 5.7153 | 6.0559 | 5.0017 | 3.3315 | 2.6388 | 18.4636 | 17.1339 | 18.4636 | 1
1727 | 2.8512 | 5.9591 | 6.8034 | 4.6251 | 5.1006 | 1.3175 | 14.7528 | 16.0728 | 16.0728 | 0
1728 | 3.8133 | 4.4786 | 6.2402 | 5.9821 | 4.7369 | 1.9813 | 16.2552 | 16.7716 | 16.7716 | 0
1729 | 3.3995 | 3.9678 | 6.2324 | 5.5734 | 4.5073 | 2.3696 | 15.3103 | 16.5088 | 16.5088 | 0
1730 | 4.2003 | 5.6852 | 4.9045 | 4.5844 | 4.238 | 1.977 | 16.447 | 15.3198 | 16.447 | 1
1731 | 4.3955 | 4.2586 | 6.1292 | 4.3006 | 3.5556 | 2.0997 | 15.0544 | 16.18 | 16.18 | 0
1732 | 2.485 | 3.9545 | 5.8728 | 6.2645 | 5.5168 | 1.9617 | 14.6657 | 15.8363 | 15.8363 | 0
1733 | 4.9073 | 5.5474 | 5.4732 | 5.398 | 5.1219 | 1.898 | 17.7507 | 17.4005 | 17.7507 | 1
1734 | 3.627 | 5.0127 | 5.1449 | 5.5106 | 5.1669 | 2.2218 | 16.3721 | 16.1605 | 16.3721 | 1
1735 | 3.8756 | 3.3062 | 4.4772 | 5.1463 | 4.8352 | 2.217 | 14.5452 | 15.405 | 15.405 | 0
1736 | 3.9444 | 4.1238 | 7.2469 | 4.7654 | 4.3839 | 2.543 | 15.3766 | 18.1183 | 18.1183 | 0
1737 | 3.5939 | 4.23 | 7.3665 | 4.1962 | 3.5112 | 1.8606 | 13.8806 | 16.3322 | 16.3322 | 0
1738 | 4.0669 | 3.7245 | 6.135 | 5.3023 | 3.9305 | 1.7961 | 14.8899 | 15.9285 | 15.9285 | 0
1739 | 4.423 | 4.4995 | 6.7434 | 4.2899 | 5.2996 | 1.4002 | 14.6126 | 17.8662 | 17.8662 | 0
1740 | 3.1673 | 4.8717 | 6.3539 | 5.1868 | 3.7005 | 1.4321 | 14.6579 | 14.6538 | 14.6579 | 1
1741 | 3.3695 | 5.2638 | 7.2506 | 4.4869 | 4.2314 | 2.0348 | 15.1549 | 16.8863 | 16.8863 | 0
1742 | 3.4652 | 5.3364 | 7.2955 | 6.5097 | 4.5069 | 2.165 | 17.4763 | 17.4327 | 17.4763 | 1
1743 | 3.2178 | 4.8777 | 6.9872 | 5.0385 | 4.0843 | 2.0791 | 15.2131 | 16.3684 | 16.3684 | 0
1744 | 3.7441 | 4.4169 | 6.2661 | 4.8223 | 3.9885 | 1.7905 | 14.7739 | 15.7892 | 15.7892 | 0
1745 | 5.2232 | 5.0099 | 4.3811 | 5.2739 | 3.3745 | 1.5051 | 17.0121 | 14.4839 | 17.0121 | 1
1746 | 4.0944 | 4.4699 | 4.779 | 5.483 | 4.1766 | 1.3909 | 15.4382 | 14.4409 | 15.4382 | 1
1747 | 4.3122 | 4.0273 | 4.7337 | 4.8174 | 3.9045 | 1.821 | 14.9779 | 14.7714 | 14.9779 | 1
1748 | 3.0136 | 4.5756 | 7.305 | 4.2661 | 3.8044 | 1.2986 | 13.1538 | 15.4215 | 15.4215 | 0
1749 | 3.9816 | 5.5688 | 5.3438 | 5.5689 | 4.1214 | 1.7914 | 16.9106 | 15.2382 | 16.9106 | 1
1750 | 5.2029 | 5.2531 | 4.4943 | 4.8347 | 3.3577 | 2.4644 | 17.755 | 15.5192 | 17.755 | 1
1751 | 3.3032 | 6.141 | 3.4205 | 4.2066 | 4.2947 | 1.7559 | 15.4067 | 12.7743 | 15.4067 | 1
1752 | 4.2459 | 4.0715 | 7.7535 | 5.0952 | 3.9992 | 1.3598 | 14.7723 | 17.3584 | 17.3584 | 0
1753 | 3.6073 | 6.7496 | 3.7968 | 4.8211 | 4.8628 | 2.7692 | 17.9473 | 15.0362 | 17.9473 | 1
1754 | 4.4175 | 5.8622 | 4.6048 | 5.2379 | 3.6704 | 1.7512 | 17.2689 | 14.4439 | 17.2689 | 1
1755 | 4.5202 | 4.603 | 5.3517 | 5.1545 | 3.585 | 2.1365 | 16.4142 | 15.5934 | 16.4142 | 1
1756 | 4.6226 | 5.298 | 6.9342 | 4.441 | 3.1394 | 2.3668 | 16.7283 | 17.0629 | 17.0629 | 0
1757 | 4.2617 | 3.6283 | 5.9705 | 4.6389 | 3.811 | 2.1911 | 14.72 | 16.2342 | 16.2342 | 0
1758 | 4.4355 | 3.8925 | 5.0648 | 4.7592 | 4.5076 | 1.8264 | 14.9137 | 15.8343 | 15.8343 | 0
1759 | 2.9065 | 7.0843 | 7.6977 | 6.6324 | 4.4991 | 1.6154 | 18.2386 | 16.7186 | 18.2386 | 1
1760 | 3.6556 | 5.3036 | 5.9734 | 5.3275 | 3.884 | 1.6832 | 15.97 | 15.1962 | 15.97 | 1
1761 | 5.4935 | 6.4121 | 6.3707 | 5.3995 | 5.0549 | 1.5751 | 18.8802 | 18.4941 | 18.8802 | 1
1762 | 5.3072 | 7.3322 | 7.3056 | 5.5799 | 3.9103 | 2.1042 | 20.3236 | 18.6274 | 20.3236 | 1
1763 | 4.4668 | 4.6749 | 7.0553 | 4.9659 | 4.4178 | 2.1511 | 16.2587 | 18.0911 | 18.0911 | 0
1764 | 3.3448 | 6.8568 | 5.3537 | 5.3218 | 3.1927 | 1.3164 | 16.8399 | 13.2076 | 16.8399 | 1
1765 | 2.8061 | 6.6295 | 5.5512 | 5.2034 | 4.384 | 1.6564 | 16.2954 | 14.3976 | 16.2954 | 1
1766 | 3.7476 | 5.6643 | 6.4382 | 4.7315 | 4.1546 | 2.3416 | 16.485 | 16.682 | 16.682 | 0
1767 | 3.6139 | 6.6028 | 6.0302 | 6.401 | 4.5722 | 2.1532 | 18.7709 | 16.3695 | 18.7709 | 1
1768 | 4.0246 | 5.258 | 4.3612 | 4.7743 | 3.7857 | 2.3756 | 16.4326 | 14.5472 | 16.4326 | 1
1769 | 2.9062 | 4.3098 | 5.0245 | 4.3685 | 4.3874 | 2.2186 | 13.8031 | 14.5367 | 14.5367 | 0
1770 | 4.0035 | 4.8695 | 7.6335 | 5.5563 | 3.2465 | 2.0992 | 16.5285 | 16.9827 | 16.9827 | 0
1771 | 3.0063 | 6.5453 | 5.0564 | 6.444 | 3.8958 | 2.4407 | 18.4363 | 14.3993 | 18.4363 | 1
1772 | 3.9657 | 4.9538 | 5.159 | 4.7714 | 4.6247 | 1.9244 | 15.6153 | 15.6738 | 15.6738 | 0
1773 | 4.6685 | 6.3248 | 6.8228 | 4.2817 | 3.8984 | 1.8694 | 17.1443 | 17.259 | 17.259 | 0
1774 | 4.1515 | 5.6205 | 5.2207 | 7.1087 | 5.5135 | 1.3476 | 18.2283 | 16.2333 | 18.2283 | 1
1775 | 4.1852 | 3.8957 | 7.425 | 5.3604 | 3.447 | 1.6275 | 15.0688 | 16.6847 | 16.6847 | 0
1776 | 4.5111 | 3.736 | 6.3766 | 6.0062 | 3.9761 | 2.1664 | 16.4197 | 17.0302 | 17.0302 | 0
1777 | 3.012 | 6.0392 | 7.1699 | 4.6364 | 5.4795 | 2.3475 | 16.0352 | 18.0089 | 18.0089 | 0
1778 | 4.5851 | 5.27 | 6.8547 | 5.0619 | 4.1833 | 1.7528 | 16.6699 | 17.376 | 17.376 | 0
1779 | 4.7112 | 4.1691 | 6.2694 | 6.0618 | 3.8745 | 2.1113 | 17.0534 | 16.9663 | 17.0534 | 1
1780 | 2.1989 | 6.3638 | 6.2134 | 6.3639 | 3.9636 | 2.441 | 17.3676 | 14.8168 | 17.3676 | 1
1781 | 3.2743 | 4.5418 | 4.8028 | 6.17 | 4.0145 | 1.8512 | 15.8372 | 13.9428 | 15.8372 | 1
1782 | 4.9023 | 5.2549 | 6.1808 | 5.3814 | 4.3255 | 2.0357 | 17.5743 | 17.4443 | 17.5743 | 1
1783 | 2.659 | 4.2153 | 3.9456 | 5.8621 | 5.2416 | 2.0966 | 14.833 | 13.9429 | 14.833 | 1
1784 | 3.2789 | 5.633 | 6.8729 | 5.0449 | 4.293 | 2.1927 | 16.1495 | 16.6375 | 16.6375 | 0
1785 | 3.671 | 7.0613 | 6.9187 | 5.4745 | 4.2759 | 1.5139 | 17.7207 | 16.3795 | 17.7207 | 1
1786 | 5.1986 | 4.9226 | 4.6638 | 5.5299 | 5.103 | 1.9312 | 17.5823 | 16.8966 | 17.5823 | 1
1787 | 4.8145 | 4.4126 | 6.5133 | 4.6506 | 5.0275 | 1.743 | 15.6207 | 18.0983 | 18.0983 | 0
1788 | 3.8506 | 7.1797 | 6.0584 | 4.3684 | 4.3217 | 2.0293 | 17.428 | 16.2599 | 17.428 | 1
1789 | 4.2619 | 5.1714 | 6.3692 | 5.8445 | 3.5865 | 1.8525 | 17.1302 | 16.0701 | 17.1302 | 1
1790 | 3.7737 | 6.7396 | 7.2017 | 5.2286 | 3.307 | 1.9307 | 17.6726 | 16.2132 | 17.6726 | 1
1791 | 3.3437 | 6.3438 | 7.0807 | 5.0309 | 4.8572 | 2.2046 | 16.9231 | 17.4863 | 17.4863 | 0
1792 | 4.7445 | 6.1267 | 6.9849 | 6.3489 | 3.5169 | 1.5522 | 18.7723 | 16.7984 | 18.7723 | 1
1793 | 4.0134 | 6.7413 | 5.8757 | 5.7707 | 5.9168 | 2.3 | 18.8254 | 18.106 | 18.8254 | 1
1794 | 4.1216 | 4.9628 | 4.9371 | 5.4821 | 4.2643 | 2.0479 | 16.6145 | 15.3709 | 16.6145 | 1
1795 | 3.6436 | 3.7761 | 6.5698 | 6.9817 | 4.4445 | 1.5829 | 15.9842 | 16.2407 | 16.2407 | 0
1796 | 2.381 | 4.2122 | 5.158 | 6.6413 | 3.8688 | 1.9914 | 15.2258 | 13.399 | 15.2258 | 1
1797 | 3.732 | 5.8749 | 6.8313 | 5.9023 | 3.6734 | 2.3353 | 17.8444 | 16.5719 | 17.8444 | 1
1798 | 2.9311 | 6.1209 | 4.9585 | 5.6964 | 5.1296 | 1.5986 | 16.347 | 14.6178 | 16.347 | 1
1799 | 4.1702 | 6.9311 | 4.6655 | 4.8199 | 5.2827 | 2.4554 | 18.3766 | 16.5738 | 18.3766 | 1
1800 | 5.3534 | 4.9616 | 5.375 | 5.1743 | 4.33 | 2.7304 | 18.2196 | 17.7887 | 18.2196 | 1
1801 | 2.6017 | 4.6449 | 4.2381 | 5.4162 | 4.9419 | 2.1776 | 14.8404 | 13.9593 | 14.8404 | 1
1802 | 3.7936 | 4.366 | 6.2246 | 5.2527 | 4.3547 | 2.3412 | 15.7536 | 16.7142 | 16.7142 | 0
1803 | 3.7562 | 5.2333 | 5.8893 | 4.4275 | 4.3836 | 1.7737 | 15.1906 | 15.8028 | 15.8028 | 0
1804 | 3.9117 | 4.2951 | 5.9351 | 7.032 | 5.8346 | 2.4854 | 17.7242 | 18.1668 | 18.1668 | 0
1805 | 3.7597 | 6.5035 | 4.6897 | 6.301 | 4.3464 | 2.5154 | 19.0796 | 15.3113 | 19.0796 | 1
1806 | 3.4299 | 4.6294 | 7.0334 | 6.1481 | 3.2011 | 2.3188 | 16.5262 | 15.9832 | 16.5262 | 1
1807 | 3.8307 | 5.5693 | 4.6605 | 5.4776 | 4.3453 | 2.1736 | 17.0512 | 15.0101 | 17.0512 | 1
1808 | 4.3886 | 3.6499 | 6.3943 | 4.5225 | 3.6068 | 1.857 | 14.4181 | 16.2467 | 16.2467 | 0
1809 | 4.7795 | 4.5852 | 5.3793 | 5.3475 | 5.2774 | 2.1178 | 16.83 | 17.5539 | 17.5539 | 0
1810 | 3.6067 | 5.2931 | 5.12 | 5.5806 | 3.3267 | 1.7058 | 16.1862 | 13.7592 | 16.1862 | 1
1811 | 3.8664 | 5.3756 | 5.8693 | 5.177 | 3.4503 | 1.972 | 16.391 | 15.158 | 16.391 | 1
1812 | 4.625 | 5.4379 | 5.8376 | 4.9108 | 5.2523 | 2.2405 | 17.2141 | 17.9554 | 17.9554 | 0
1813 | 3.8778 | 4.369 | 5.5213 | 5.3791 | 3.1302 | 2.1668 | 15.7929 | 14.6962 | 15.7929 | 1
1814 | 3.5954 | 4.9151 | 7.1429 | 5.0691 | 3.9888 | 2.6142 | 16.1939 | 17.3413 | 17.3413 | 0
1815 | 3.6911 | 5.6708 | 6.7909 | 5.8703 | 4.2095 | 2.1341 | 17.3662 | 16.8256 | 17.3662 | 1
1816 | 4.0163 | 3.5855 | 6.2574 | 4.7232 | 5.4146 | 1.7472 | 14.0722 | 17.4355 | 17.4355 | 0
1817 | 4.2025 | 3.0747 | 6.475 | 5.4137 | 4.1711 | 2.5798 | 15.2708 | 17.4285 | 17.4285 | 0
1818 | 3.2074 | 3.8009 | 7.0958 | 4.9979 | 4.251 | 2.5317 | 14.538 | 17.0859 | 17.0859 | 0
1819 | 4.8757 | 5.217 | 3.7853 | 5.5992 | 3.2801 | 1.7447 | 17.4366 | 13.6859 | 17.4366 | 1
1820 | 4.4605 | 5.9292 | 6.2909 | 5.6563 | 5.415 | 1.933 | 17.9789 | 18.0994 | 18.0994 | 0
1821 | 3.4416 | 4.905 | 6.3306 | 5.4619 | 4.0662 | 1.9019 | 15.7105 | 15.7403 | 15.7403 | 0
1822 | 3.8255 | 4.2516 | 7.0265 | 5.0305 | 4.8452 | 2.2737 | 15.3812 | 17.9709 | 17.9709 | 0
1823 | 4.4333 | 6.4656 | 5.4519 | 6.2167 | 4.6555 | 1.7946 | 18.9102 | 16.3353 | 18.9102 | 1
1824 | 3.9027 | 7.5608 | 5.0195 | 5.8154 | 4.5253 | 1.3197 | 18.5985 | 14.7672 | 18.5985 | 1
1825 | 3.0154 | 5.0063 | 3.3256 | 6.105 | 3.4309 | 2.156 | 16.2827 | 11.928 | 16.2827 | 1
1826 | 4.065 | 5.1188 | 4.7079 | 5.3266 | 4.3226 | 2.0439 | 16.5544 | 15.1393 | 16.5544 | 1
1827 | 4.2911 | 5.1662 | 6.4815 | 4.7155 | 4.5737 | 1.8744 | 16.0472 | 17.2208 | 17.2208 | 0
1828 | 4.7889 | 6.8168 | 3.3854 | 6.7751 | 4.9014 | 2.1981 | 20.579 | 15.2739 | 20.579 | 1
1829 | 3.1353 | 4.2419 | 7.5108 | 5.2237 | 4.2481 | 1.9332 | 14.5341 | 16.8274 | 16.8274 | 0
1830 | 5.0341 | 3.4611 | 4.6345 | 4.5932 | 3.7636 | 1.2056 | 14.294 | 14.6377 | 14.6377 | 0
1831 | 4.1386 | 3.9831 | 6.6605 | 5.9765 | 4.2653 | 2.27 | 16.3682 | 17.3344 | 17.3344 | 0
1832 | 4.9596 | 4.5527 | 6.3566 | 6.2674 | 3.8284 | 1.3619 | 17.1416 | 16.5064 | 17.1416 | 1
1833 | 5.1561 | 4.7602 | 5.6049 | 4.6272 | 4.066 | 2.0725 | 16.6161 | 16.8995 | 16.8995 | 0
1834 | 3.8879 | 4.6049 | 6.294 | 5.0678 | 5.6218 | 1.2187 | 14.7793 | 17.0224 | 17.0224 | 0
1835 | 4.4872 | 4.0007 | 5.4691 | 5.0683 | 3.4689 | 2.0207 | 15.5768 | 15.4458 | 15.5768 | 1
1836 | 4.6749 | 3.8814 | 5.8349 | 6.4009 | 3.4436 | 1.83 | 16.7872 | 15.7834 | 16.7872 | 1
1837 | 4.5954 | 7.882 | 4.9028 | 4.8648 | 4.9814 | 2.9138 | 20.2559 | 17.3935 | 20.2559 | 1
1838 | 4.7023 | 5.0247 | 4.525 | 6.068 | 3.5456 | 2.6774 | 18.4724 | 15.4503 | 18.4724 | 1
1839 | 4.5274 | 4.8337 | 3.0351 | 5.495 | 4.3323 | 1.3236 | 16.1796 | 13.2183 | 16.1796 | 1
1840 | 4.7412 | 5.8623 | 5.0367 | 4.6877 | 4.5119 | 1.2261 | 16.5173 | 15.5159 | 16.5173 | 1
1841 | 3.0741 | 5.6333 | 7.0466 | 5.087 | 4.0403 | 1.9398 | 15.7342 | 16.1008 | 16.1008 | 0
1842 | 5.1651 | 6.242 | 5.7526 | 4.8689 | 4.2586 | 2.0329 | 18.309 | 17.2092 | 18.309 | 1
1843 | 4.548 | 4.6079 | 6.8622 | 6.4761 | 3.8477 | 2.6478 | 18.2798 | 17.9058 | 18.2798 | 1
1844 | 4.1852 | 5.5678 | 4.0183 | 6.0405 | 3.2482 | 1.467 | 17.2605 | 12.9187 | 17.2605 | 1
1845 | 2.8112 | 5.4566 | 3.3018 | 4.5613 | 3.4104 | 2.5424 | 15.3716 | 12.0658 | 15.3716 | 1
1846 | 5.0263 | 6.1324 | 7.2545 | 7.3327 | 4.2981 | 1.6735 | 20.1649 | 18.2524 | 20.1649 | 1
1847 | 3.8399 | 5.8702 | 6.6084 | 6.327 | 3.5981 | 2.3906 | 18.4278 | 16.4371 | 18.4278 | 1
1848 | 3.8618 | 4.6949 | 3.8064 | 4.3304 | 3.6194 | 1.7797 | 14.6669 | 13.0673 | 14.6669 | 1
1849 | 4.4548 | 6.9315 | 6.4363 | 5.48 | 5.6272 | 2.7611 | 19.6274 | 19.2795 | 19.6274 | 1
1850 | 4.7739 | 3.911 | 4.6201 | 4.7152 | 4.4969 | 1.3838 | 14.7838 | 15.2747 | 15.2747 | 0
1851 | 3.7858 | 5.6234 | 5.1645 | 4.9684 | 3.9459 | 1.9153 | 16.2929 | 14.8115 | 16.2929 | 1
1852 | 4.5672 | 3.5101 | 7.2345 | 6.3006 | 3.6897 | 1.7442 | 16.1221 | 17.2356 | 17.2356 | 0
1853 | 4.6553 | 5.0053 | 4.1118 | 5.454 | 3.5363 | 1.4527 | 16.5673 | 13.7561 | 16.5673 | 1
1854 | 3.8223 | 7.5937 | 4.3216 | 5.9107 | 4.6552 | 2.0344 | 19.3611 | 14.8334 | 19.3611 | 1
1855 | 5.089 | 6.2361 | 7.6933 | 5.7021 | 3.8119 | 2.0111 | 19.0382 | 18.6053 | 19.0382 | 1
1856 | 2.5604 | 6.4273 | 4.4315 | 6.1112 | 3.6547 | 2.1235 | 17.2225 | 12.7702 | 17.2225 | 1
1857 | 3.0218 | 4.9585 | 6.9046 | 5.2726 | 3.5618 | 2.7124 | 15.9653 | 16.2006 | 16.2006 | 0
1858 | 4.5502 | 5.5891 | 5.5133 | 5.4263 | 4.0912 | 2.5612 | 18.1268 | 16.7159 | 18.1268 | 1
1859 | 2.3156 | 4.6827 | 4.6516 | 5.3922 | 4.65 | 2.091 | 14.4814 | 13.7081 | 14.4814 | 1
1860 | 4.0542 | 4.7856 | 6.8005 | 4.8229 | 5.0109 | 1.595 | 15.2576 | 17.4606 | 17.4606 | 0
1861 | 4.2372 | 5.0126 | 6.9803 | 4.3374 | 4.0684 | 2.3237 | 15.9109 | 17.6096 | 17.6096 | 0
1862 | 3.5904 | 6.3317 | 6.3306 | 6.0901 | 4.5984 | 2.2658 | 18.2781 | 16.7852 | 18.2781 | 1
1863 | 3.9501 | 4.6042 | 7.0456 | 4.3509 | 4.5968 | 2.5411 | 15.4463 | 18.1337 | 18.1337 | 0
1864 | 4.4265 | 5.0959 | 5.7188 | 5.3629 | 4.4195 | 1.6943 | 16.5796 | 16.2591 | 16.5796 | 1
1865 | 2.9687 | 5.1131 | 6.7275 | 5.7215 | 4.4315 | 2.0911 | 15.8945 | 16.2188 | 16.2188 | 0
1866 | 4.9188 | 4.2933 | 6.7991 | 4.7378 | 3.1208 | 2.3086 | 16.2585 | 17.1473 | 17.1473 | 0
1867 | 4.1427 | 6.8869 | 7.4814 | 5.3077 | 4.7025 | 2.0026 | 18.34 | 18.3292 | 18.34 | 1
1868 | 2.6685 | 3.593 | 7.356 | 5.6806 | 4.7056 | 2.4077 | 14.3497 | 17.1378 | 17.1378 | 0
1869 | 3.6584 | 5.6105 | 6.7557 | 5.0359 | 4.2815 | 1.866 | 16.1707 | 16.5615 | 16.5615 | 0
1870 | 4.1895 | 5.9316 | 5.8397 | 6.3592 | 4.2826 | 1.6613 | 18.1416 | 15.973 | 18.1416 | 1
1871 | 3.2409 | 3.7428 | 3.4151 | 6.5925 | 4.9082 | 2.3701 | 15.9464 | 13.9343 | 15.9464 | 1
1872 | 4.1991 | 4.5042 | 6.1387 | 5.8176 | 6.3231 | 1.8152 | 16.3361 | 18.4761 | 18.4761 | 0
1873 | 3.5715 | 4.2262 | 6.8496 | 4.9095 | 4.486 | 1.6837 | 14.391 | 16.5909 | 16.5909 | 0
1874 | 2.938 | 5.9466 | 4.4107 | 6.894 | 4.985 | 1.6698 | 17.4484 | 14.0034 | 17.4484 | 1
1875 | 4.3597 | 4.0772 | 5.4414 | 4.9932 | 4.9746 | 1.4952 | 14.9253 | 16.2709 | 16.2709 | 0
1876 | 4.8725 | 6.868 | 4.0764 | 5.2583 | 3.9387 | 2.2734 | 19.2722 | 15.161 | 19.2722 | 1
1877 | 4.4887 | 6.9372 | 6.0134 | 4.6627 | 4.7246 | 2.3338 | 18.4224 | 17.5605 | 18.4224 | 1
1878 | 3.442 | 7.1874 | 3.4085 | 6.0321 | 5.279 | 1.7788 | 18.4403 | 13.9083 | 18.4403 | 1
1879 | 5.0283 | 6.7142 | 4.5952 | 5.8366 | 4.9913 | 2.8135 | 20.3926 | 17.4283 | 20.3926 | 1
1880 | 3.1964 | 5.8806 | 7.0628 | 6.8287 | 3.7527 | 1.5047 | 17.4104 | 15.5166 | 17.4104 | 1
1881 | 4.1688 | 5.4066 | 5.895 | 6.0202 | 3.8306 | 1.6926 | 17.2881 | 15.5869 | 17.2881 | 1
1882 | 3.6652 | 7.6096 | 5.9207 | 4.9208 | 3.5766 | 1.9714 | 18.167 | 15.1339 | 18.167 | 1
1883 | 5.0373 | 3.9481 | 6.9784 | 5.1914 | 3.6723 | 1.766 | 15.9428 | 17.4541 | 17.4541 | 0
1884 | 3.7994 | 8.0155 | 5.5503 | 5.9909 | 4.3806 | 1.7301 | 19.5359 | 15.4604 | 19.5359 | 1
1885 | 4.0177 | 6.2616 | 6.7051 | 5.9983 | 4.2839 | 1.9348 | 18.2125 | 16.9415 | 18.2125 | 1
1886 | 5.1194 | 4.0835 | 6.0182 | 4.6807 | 4.0887 | 2.4775 | 16.361 | 17.7038 | 17.7038 | 0
1887 | 4.1612 | 4.1545 | 5.744 | 4.8221 | 4.2338 | 2.4461 | 15.5838 | 16.5851 | 16.5851 | 0
1888 | 4.3633 | 5.5181 | 5.873 | 6.2968 | 3.9419 | 1.7146 | 17.8928 | 15.8928 | 17.8928 | 1
1889 | 3.1532 | 5.1388 | 6.331 | 6.1956 | 4.6816 | 2.0351 | 16.5226 | 16.2008 | 16.5226 | 1
1890 | 3.6539 | 3.5564 | 7.1398 | 4.7438 | 4.8338 | 1.8885 | 13.8425 | 17.516 | 17.516 | 0
1891 | 4.4331 | 4.5711 | 6.5707 | 5.4344 | 3.9586 | 1.6664 | 16.105 | 16.6288 | 16.6288 | 0
1892 | 4.4115 | 5.5074 | 7.0528 | 4.6658 | 4.7332 | 2.4307 | 17.0155 | 18.6282 | 18.6282 | 0
1893 | 3.1528 | 5.4815 | 5.7755 | 4.3954 | 3.7267 | 2.507 | 15.5366 | 15.1619 | 15.5366 | 1
1894 | 3.0436 | 5.995 | 4.3339 | 4.6975 | 5.3956 | 2.3144 | 16.0505 | 15.0875 | 16.0505 | 1
1895 | 4.382 | 3.7634 | 6.9963 | 5.2742 | 3.81 | 1.5592 | 14.9787 | 16.7475 | 16.7475 | 0
1896 | 2.8725 | 5.1066 | 5.6726 | 6.2205 | 4.0534 | 2.5769 | 16.7765 | 15.1754 | 16.7765 | 1
1897 | 3.7523 | 4.881 | 6.6524 | 6.1889 | 3.4842 | 2.0732 | 16.8954 | 15.9622 | 16.8954 | 1
1898 | 5.1209 | 4.4501 | 7.1064 | 5.4995 | 3.3999 | 1.8613 | 16.932 | 17.4886 | 17.4886 | 0
1899 | 5.1239 | 4.0345 | 4.8006 | 5.2041 | 5.2136 | 1.963 | 16.3254 | 17.1011 | 17.1011 | 0
1900 | 2.9207 | 5.3789 | 5.3807 | 5.197 | 3.1722 | 2.2156 | 15.7122 | 13.6892 | 15.7122 | 1
1901 | 3.7036 | 6.2899 | 6.1759 | 4.8124 | 5.1077 | 1.6174 | 16.4233 | 16.6046 | 16.6046 | 0
1902 | 3.4154 | 6.2709 | 4.632 | 5.793 | 3.2645 | 1.6779 | 17.1572 | 12.9898 | 17.1572 | 1
1903 | 5.328 | 7.7146 | 6.2519 | 6.1348 | 3.8459 | 1.4428 | 20.6201 | 16.8686 | 20.6201 | 1
1904 | 3.0993 | 4.8375 | 5.5054 | 6.5922 | 3.6975 | 1.1552 | 15.6841 | 13.4574 | 15.6841 | 1
1905 | 3.9405 | 5.8499 | 6.7354 | 6.1185 | 4.9205 | 2.0346 | 17.9435 | 17.631 | 17.9435 | 1
1906 | 5.5973 | 5.154 | 6.7496 | 5.8898 | 5.2925 | 2.6004 | 19.2416 | 20.2399 | 20.2399 | 0
1907 | 5.1331 | 4.1702 | 4.9904 | 4.6512 | 4.4343 | 1.9446 | 15.8991 | 16.5024 | 16.5024 | 0
1908 | 3.724 | 4.1507 | 6.0748 | 4.3193 | 3.7561 | 1.8652 | 14.0593 | 15.4201 | 15.4201 | 0
1909 | 2.7598 | 3.872 | 7.118 | 5.5282 | 3.8341 | 2.5454 | 14.7054 | 16.2574 | 16.2574 | 0
1910 | 2.7345 | 4.9318 | 4.6471 | 5.3873 | 3.3818 | 2.6973 | 15.7509 | 13.4606 | 15.7509 | 1
1911 | 4.2727 | 6.5187 | 6.3573 | 4.601 | 3.5631 | 1.4572 | 16.8495 | 15.6503 | 16.8495 | 1
1912 | 4.3289 | 5.2855 | 6.5372 | 4.0405 | 5.2381 | 2.015 | 15.6698 | 18.1191 | 18.1191 | 0
1913 | 4.9406 | 4.359 | 4.4534 | 4.3809 | 4.6515 | 1.8681 | 15.5486 | 15.9136 | 15.9136 | 0
1914 | 3.6845 | 4.9097 | 3.1858 | 5.7673 | 3.9962 | 2.3442 | 16.7056 | 13.2107 | 16.7056 | 1
1915 | 4.1786 | 6.8828 | 4.3748 | 7.0569 | 5.6693 | 1.7691 | 19.8874 | 15.9918 | 19.8874 | 1
1916 | 4.0558 | 4.0304 | 2.9723 | 5.4957 | 5.782 | 2.1372 | 15.7191 | 14.9473 | 15.7191 | 1
1917 | 4.9313 | 4.3447 | 6.9235 | 6.4637 | 3.5759 | 2.2301 | 17.9698 | 17.6608 | 17.9698 | 1
1918 | 4.1976 | 6.7017 | 5.066 | 4.9298 | 5.5617 | 2.4968 | 18.326 | 17.3222 | 18.326 | 1
1919 | 4.6847 | 6.1139 | 7.0677 | 4.4787 | 6.0064 | 1.4645 | 16.7417 | 19.2233 | 19.2233 | 0
1920 | 3.1055 | 4.7516 | 5.8069 | 5.2344 | 3.3103 | 2.44 | 15.5315 | 14.6627 | 15.5315 | 1
1921 | 3.0484 | 5.0293 | 6.615 | 5.1019 | 4.0562 | 2.2381 | 15.4177 | 15.9578 | 15.9578 | 0
1922 | 4.6009 | 4.402 | 6.5148 | 6.2344 | 4.0862 | 2.029 | 17.2663 | 17.231 | 17.2663 | 1
1923 | 4.3148 | 3.3681 | 5.1554 | 5.9763 | 3.7928 | 2.5454 | 16.2046 | 15.8084 | 16.2046 | 1
1924 | 3.4696 | 4.4335 | 3.4004 | 5.5576 | 3.4814 | 2.2489 | 15.7096 | 12.6003 | 15.7096 | 1
1925 | 3.8472 | 5.647 | 4.3723 | 5.1979 | 3.6435 | 1.7028 | 16.3948 | 13.5657 | 16.3948 | 1
1926 | 3.7428 | 5.5355 | 4.1412 | 4.5891 | 4.3552 | 2.6566 | 16.5239 | 14.8958 | 16.5239 | 1
1927 | 4.9373 | 7.3102 | 5.3328 | 4.8544 | 4.841 | 2.3927 | 19.4945 | 17.5038 | 19.4945 | 1
1928 | 3.0563 | 5.8051 | 6.5647 | 4.6104 | 3.4305 | 2.2432 | 15.7149 | 15.2946 | 15.7149 | 1
1929 | 4.6793 | 5.7855 | 4.8788 | 4.7139 | 4.5316 | 2.2938 | 17.4725 | 16.3834 | 17.4725 | 1
1930 | 3.2037 | 5.572 | 5.8678 | 4.7455 | 3.4254 | 1.7121 | 15.2333 | 14.2089 | 15.2333 | 1
1931 | 3.8763 | 6.134 | 4.1802 | 6.0611 | 4.0151 | 1.3793 | 17.4508 | 13.451 | 17.4508 | 1
1932 | 4.9027 | 7.3239 | 5.0132 | 4.479 | 3.3011 | 2.6101 | 19.3157 | 15.827 | 19.3157 | 1
1933 | 3.8 | 4.5955 | 5.2114 | 4.3453 | 3.0993 | 2.8374 | 15.5782 | 14.9481 | 15.5782 | 1
1934 | 2.9538 | 5.8995 | 5.8368 | 4.3791 | 4.3311 | 2.5841 | 15.8165 | 15.7058 | 15.8165 | 1
1935 | 3.3277 | 5.9443 | 4.409 | 4.3895 | 3.8713 | 2.0983 | 15.7598 | 13.7063 | 15.7598 | 1
1936 | 3.5738 | 5.4541 | 6.6637 | 5.0777 | 3.5305 | 2.4037 | 16.5093 | 16.1718 | 16.5093 | 1
1937 | 3.6817 | 5.8468 | 7.1787 | 5.7562 | 3.3565 | 2.4097 | 17.6943 | 16.6266 | 17.6943 | 1
1938 | 2.6785 | 7.1953 | 6.519 | 5.2658 | 4.3899 | 1.9127 | 17.0522 | 15.5001 | 17.0522 | 1
1939 | 4.2566 | 4.8322 | 7.046 | 4.9493 | 5.0914 | 2.7547 | 16.7928 | 19.1487 | 19.1487 | 0
1940 | 3.1073 | 6.7302 | 4.8746 | 4.7203 | 5.8415 | 2.5444 | 17.1022 | 16.3678 | 17.1022 | 1
1941 | 4.6339 | 4.6426 | 5.1642 | 5.7161 | 5.4673 | 2.081 | 17.0737 | 17.3464 | 17.3464 | 0
1942 | 4.2888 | 4.4974 | 6.7439 | 4.3534 | 3.6444 | 2.3283 | 15.4679 | 17.0055 | 17.0055 | 0
1943 | 4.0889 | 4.6272 | 6.9042 | 5.1053 | 3.7748 | 2.0918 | 15.9132 | 16.8597 | 16.8597 | 0
1944 | 3.6608 | 3.6438 | 3.7852 | 4.5699 | 4.5304 | 2.1866 | 14.0611 | 14.163 | 14.163 | 0
1945 | 4.3822 | 6.1215 | 6.472 | 4.241 | 3.4403 | 1.5686 | 16.3133 | 15.8632 | 16.3133 | 1
1946 | 3.8421 | 6.3774 | 5.9396 | 5.6495 | 3.914 | 2.6993 | 18.5682 | 16.3949 | 18.5682 | 1
1947 | 3.2494 | 5.975 | 5.7939 | 5.9609 | 4.8806 | 2.3101 | 17.4953 | 16.234 | 17.4953 | 1
1948 | 3.1615 | 8.4823 | 5.3975 | 5.5622 | 5.5797 | 1.4349 | 18.6409 | 15.5737 | 18.6409 | 1
1949 | 4.0346 | 4.8313 | 5.5006 | 5.5619 | 3.5547 | 2.2894 | 16.7172 | 15.3794 | 16.7172 | 1
1950 | 4.2709 | 5.0548 | 6.1543 | 6.4032 | 3.3027 | 2.8249 | 18.5539 | 16.5528 | 18.5539 | 1
1951 | 3.3288 | 6.7925 | 5.2054 | 5.4049 | 4.404 | 1.4319 | 16.958 | 14.3701 | 16.958 | 1
1952 | 3.8754 | 4.2207 | 4.2204 | 4.3054 | 4.2797 | 1.6599 | 14.0614 | 14.0354 | 14.0614 | 1
1953 | 3.9318 | 4.765 | 5.963 | 5.1546 | 5.3325 | 1.758 | 15.6094 | 16.9853 | 16.9853 | 0
1954 | 4.1668 | 3.614 | 6.5534 | 6.7925 | 3.7357 | 1.36 | 15.9334 | 15.8159 | 15.9334 | 1
1955 | 3.4888 | 5.6553 | 6.8363 | 5.5177 | 5.4325 | 2.3544 | 17.0162 | 18.1119 | 18.1119 | 0
1956 | 5.2379 | 5.7823 | 6.1962 | 5.3581 | 3.162 | 2.465 | 18.8433 | 17.061 | 18.8433 | 1
1957 | 2.4687 | 5.9145 | 6.5096 | 6.3733 | 4.7407 | 1.9109 | 16.6675 | 15.6299 | 16.6675 | 1
1958 | 4.935 | 5.8396 | 6.8127 | 5.7559 | 3.9666 | 1.7726 | 18.3031 | 17.4869 | 18.3031 | 1
1959 | 2.6143 | 3.51 | 3.7788 | 4.8646 | 5.351 | 2.0253 | 13.0142 | 13.7693 | 13.7693 | 0
1960 | 4.5511 | 5.4523 | 5.3298 | 5.1431 | 3.6274 | 2.4262 | 17.5727 | 15.9345 | 17.5727 | 1
1961 | 3.0871 | 3.4905 | 6.7515 | 5.0436 | 3.8333 | 1.5545 | 13.1758 | 15.2265 | 15.2265 | 0
1962 | 4.474 | 6.4947 | 6.8315 | 5.7572 | 4.3938 | 2.3089 | 19.0348 | 18.0082 | 19.0348 | 1
1963 | 2.4745 | 3.9995 | 5.2776 | 5.4422 | 4.7748 | 2.2113 | 14.1275 | 14.7381 | 14.7381 | 0
1964 | 4.5856 | 4.5183 | 4.2217 | 5.9846 | 4.9621 | 2.6019 | 17.6905 | 16.3714 | 17.6905 | 1
1965 | 4.6659 | 3.9129 | 6.5838 | 5.5462 | 4.0948 | 1.5926 | 15.7176 | 16.9371 | 16.9371 | 0
1966 | 4.1267 | 5.2613 | 4.3621 | 5.7173 | 4.1739 | 1.9907 | 17.096 | 14.6534 | 17.096 | 1
1967 | 3.8135 | 7.9456 | 5.873 | 5.0589 | 3.6036 | 2.2871 | 19.1051 | 15.5772 | 19.1051 | 1
1968 | 5.0598 | 6.9255 | 5.5864 | 5.0466 | 5.3412 | 1.506 | 18.5379 | 17.4934 | 18.5379 | 1
1969 | 4.4598 | 3.5161 | 7.7085 | 4.744 | 5.5069 | 1.9388 | 14.6587 | 19.6139 | 19.6139 | 0
1970 | 3.6232 | 3.8077 | 6.5906 | 5.3536 | 4.6223 | 1.6296 | 14.414 | 16.4657 | 16.4657 | 0
1971 | 5.0515 | 6.0011 | 2.9208 | 5.8884 | 4.7937 | 1.4608 | 18.4018 | 14.2268 | 18.4018 | 1
1972 | 3.1864 | 6.5045 | 5.4279 | 5.9729 | 5.4393 | 2.8393 | 18.5031 | 16.8929 | 18.5031 | 1
1973 | 4.1131 | 5.612 | 5.6448 | 6.4314 | 4.6484 | 1.5922 | 17.7487 | 15.9985 | 17.7487 | 1
1974 | 3.8708 | 5.4612 | 4.8471 | 5.6794 | 4.4832 | 2.3636 | 17.3749 | 15.5647 | 17.3749 | 1
1975 | 3.8106 | 6.1313 | 6.7358 | 4.3379 | 4.1539 | 2.428 | 16.7077 | 17.1282 | 17.1282 | 0
1976 | 4.1199 | 5.3434 | 5.9331 | 6.532 | 4.9302 | 2.0049 | 18.0002 | 16.9881 | 18.0002 | 1
1977 | 4.8377 | 4.7952 | 5.1477 | 4.9534 | 3.5562 | 1.4446 | 16.031 | 14.9863 | 16.031 | 1
1978 | 3.8573 | 5.5563 | 3.8019 | 5.1244 | 4.9285 | 1.469 | 16.007 | 14.0568 | 16.007 | 1
1979 | 2.8597 | 4.8334 | 6.6136 | 6.6342 | 3.4997 | 1.7943 | 16.1215 | 14.7672 | 16.1215 | 1
1980 | 4.8226 | 3.431 | 7.0458 | 5.8012 | 3.7017 | 2.0436 | 16.0984 | 17.6137 | 17.6137 | 0
1981 | 4.236 | 4.4926 | 5.759 | 5.1403 | 4.4911 | 1.9766 | 15.8456 | 16.4628 | 16.4628 | 0
1982 | 3.7574 | 4.3686 | 4.0491 | 4.3549 | 3.699 | 1.72 | 14.2009 | 13.2256 | 14.2009 | 1
1983 | 3.4525 | 3.7213 | 4.7464 | 5.2892 | 4.8057 | 1.9739 | 14.4369 | 14.9785 | 14.9785 | 0
1984 | 4.5846 | 6.446 | 4.8871 | 5.6071 | 4.8109 | 1.885 | 18.5228 | 16.1676 | 18.5228 | 1
1985 | 4.8485 | 6.2024 | 6.0535 | 5.8055 | 3.7043 | 1.7829 | 18.6393 | 16.3892 | 18.6393 | 1
1986 | 5.3231 | 4.4673 | 5.8804 | 4.556 | 3.2608 | 1.5273 | 15.8736 | 15.9916 | 15.9916 | 0
1987 | 4.4818 | 3.4457 | 5.8746 | 5.3971 | 4.2078 | 1.9714 | 15.296 | 16.5356 | 16.5356 | 0
1988 | 4.825 | 4.5461 | 4.7773 | 4.9105 | 5.1661 | 2.1696 | 16.4512 | 16.938 | 16.938 | 0
1989 | 3.7756 | 6.3297 | 6.3465 | 5.4493 | 4.1218 | 1.7229 | 17.2776 | 15.9669 | 17.2776 | 1
1990 | 3.906 | 5.2651 | 5.018 | 5.3335 | 3.5205 | 1.9065 | 16.4111 | 14.351 | 16.4111 | 1
1991 | 2.8967 | 4.3293 | 5.5949 | 5.4718 | 3.7378 | 2.2253 | 14.9231 | 14.4548 | 14.9231 | 1
1992 | 3.4034 | 6.1329 | 7.5139 | 5.3204 | 3.9731 | 2.1587 | 17.0153 | 17.049 | 17.049 | 0
1993 | 3.612 | 4.9031 | 5.4488 | 5.9623 | 3.994 | 1.5072 | 15.9847 | 14.5621 | 15.9847 | 1
1994 | 4.2707 | 6.2283 | 5.577 | 5.4251 | 3.3771 | 2.6657 | 18.5898 | 15.8905 | 18.5898 | 1
1995 | 4.0565 | 4.7129 | 6.242 | 5.9446 | 3.3282 | 2.7313 | 17.4453 | 16.358 | 17.4453 | 1
1996 | 3.9958 | 6.0128 | 6.8587 | 5.7074 | 3.6818 | 1.5623 | 17.2783 | 16.0986 | 17.2783 | 1
1997 | 2.6961 | 4.4539 | 4.1239 | 4.7868 | 3.8361 | 2.0334 | 13.9701 | 12.6894 | 13.9701 | 1
1998 | 2.3016 | 4.8541 | 6.1264 | 5.1109 | 3.9799 | 1.759 | 14.0256 | 14.1669 | 14.1669 | 0
1999 | 3.5096 | 4.4684 | 6.1406 | 5.3669 | 5.1555 | 1.7474 | 15.0923 | 16.5531 | 16.5531 | 0
2000 | 2.9312 | 6.6597 | 5.6953 | 4.0986 | 5.6993 | 2.1103 | 15.7999 | 16.4362 | 16.4362 | 0
2001 | 5.0491 | 4.0482 | 4.6491 | 5.5214 | 3.8103 | 2.382 | 17.0006 | 15.8904 | 17.0006 | 1
2002 | 3.8828 | 3.2613 | 5.8539 | 4.6611 | 3.8057 | 2.3435 | 14.1488 | 15.8859 | 15.8859 | 0
2003 | 4.6289 | 5.0228 | 5.4671 | 6.371 | 3.8835 | 2.0418 | 18.0645 | 16.0213 | 18.0645 | 1
2004 | 4.1664 | 4.7223 | 5.5075 | 5.6816 | 4.297 | 2.0774 | 16.6476 | 16.0483 | 16.6476 | 1
2005 | 4.728 | 5.1194 | 5.6177 | 5.5449 | 4.9693 | 1.7953 | 17.1875 | 17.1103 | 17.1875 | 1
2006 | 4.8108 | 7.1205 | 5.9411 | 5.0781 | 3.7419 | 2.4334 | 19.4428 | 16.9272 | 19.4428 | 1
2007 | 4.8218 | 4.519 | 6.8229 | 4.8729 | 5.3927 | 1.4772 | 15.6908 | 18.5145 | 18.5145 | 0
2008 | 3.5716 | 5.7902 | 5.3361 | 5.9997 | 4.8781 | 2.1023 | 17.4638 | 15.888 | 17.4638 | 1
2009 | 3.8832 | 4.4641 | 6.2226 | 5.7351 | 4.8688 | 1.9277 | 16.01 | 16.9022 | 16.9022 | 0
2010 | 4.1926 | 5.8389 | 6.8922 | 4.6738 | 4.9654 | 2.428 | 17.1333 | 18.4783 | 18.4783 | 0
2011 | 2.5791 | 3.6297 | 5.7245 | 5.8617 | 4.5285 | 1.5152 | 13.5857 | 14.3473 | 14.3473 | 0
2012 | 4.1995 | 6.9301 | 5.7651 | 5.6178 | 3.9909 | 2.577 | 19.3244 | 16.5325 | 19.3244 | 1
2013 | 4.0457 | 6.4703 | 4.084 | 6.0405 | 4.0676 | 2.427 | 18.9836 | 14.6242 | 18.9836 | 1
2014 | 3.4252 | 5.0553 | 5.9983 | 6.3883 | 5.0297 | 2.4009 | 17.2697 | 16.8541 | 17.2697 | 1
2015 | 4.0952 | 6.1557 | 5.1431 | 6.2194 | 3.2929 | 2.0493 | 18.5196 | 14.5805 | 18.5196 | 1
2016 | 3.0705 | 5.2192 | 6.8283 | 5.12 | 3.906 | 2.0647 | 15.4745 | 15.8695 | 15.8695 | 0
2017 | 3.2417 | 6.3177 | 4.3658 | 5.031 | 6.0343 | 2.1695 | 16.76 | 15.8114 | 16.76 | 1
2018 | 4.3192 | 5.4316 | 3.9301 | 5.1863 | 6.1081 | 1.3989 | 16.336 | 15.7562 | 16.336 | 1
2019 | 5.0606 | 8.2581 | 5.0947 | 4.7376 | 4.084 | 1.5688 | 19.6251 | 15.8081 | 19.6251 | 1
2020 | 2.6529 | 4.4348 | 7.481 | 5.2113 | 3.4643 | 1.4198 | 13.7187 | 15.018 | 15.018 | 0
2021 | 4.9823 | 7.2522 | 5.516 | 5.5638 | 6.553 | 2.3157 | 20.114 | 19.367 | 20.114 | 1
2022 | 5.6269 | 6.6846 | 5.5463 | 4.3975 | 5.7935 | 1.8833 | 18.5922 | 18.8499 | 18.8499 | 0
2023 | 4.7338 | 5.4838 | 5.8245 | 5.3384 | 5.9029 | 1.9432 | 17.4992 | 18.4044 | 18.4044 | 0
2024 | 4.6089 | 7.8191 | 6.3399 | 4.8515 | 3.6423 | 1.8527 | 19.1322 | 16.4438 | 19.1322 | 1
2025 | 4.5554 | 6.4475 | 4.8408 | 4.6017 | 5.6539 | 1.5413 | 17.1459 | 16.5914 | 17.1459 | 1
2026 | 2.6956 | 4.7848 | 6.5366 | 5.2322 | 5.9667 | 2.2761 | 14.9886 | 17.4749 | 17.4749 | 0
2027 | 4.873 | 4.6808 | 7.0361 | 4.2699 | 3.151 | 1.8961 | 15.7198 | 16.9561 | 16.9561 | 0
2028 | 5.5085 | 4.9949 | 4.3445 | 6.1054 | 5.1361 | 2.3793 | 18.9881 | 17.3683 | 18.9881 | 1
2029 | 4.6213 | 4.7095 | 6.1247 | 5.177 | 4.9251 | 2.7358 | 17.2436 | 18.4069 | 18.4069 | 0
2030 | 4.1827 | 4.2152 | 7.0297 | 5.3336 | 5.027 | 2.5345 | 16.266 | 18.7738 | 18.7738 | 0
2031 | 3.3417 | 7.6125 | 3.7804 | 4.4037 | 3.9467 | 2.1727 | 17.5306 | 13.2415 | 17.5306 | 1
2032 | 4.7773 | 3.6696 | 7.5145 | 6.0239 | 3.7993 | 1.8275 | 16.2984 | 17.9187 | 17.9187 | 0
2033 | 4.4109 | 6.0009 | 6.8134 | 4.8553 | 3.5395 | 2.3717 | 17.6388 | 17.1355 | 17.6388 | 1
2034 | 2.9065 | 5.364 | 4.414 | 6.6236 | 4.7083 | 2.5969 | 17.491 | 14.6257 | 17.491 | 1
2035 | 3.8295 | 6.7063 | 6.1974 | 6.2026 | 5.0275 | 2.638 | 19.3764 | 17.6923 | 19.3764 | 1
2036 | 3.339 | 6.3257 | 4.4909 | 6.7886 | 3.9195 | 1.9982 | 18.4514 | 13.7476 | 18.4514 | 1
2037 | 3.5867 | 3.8544 | 5.8817 | 4.9365 | 5.2985 | 1.8017 | 14.1794 | 16.5686 | 16.5686 | 0
2038 | 4.8926 | 4.6746 | 5.703 | 5.8184 | 4.2105 | 2.7475 | 18.1331 | 17.5536 | 18.1331 | 1
2039 | 4.5016 | 7.325 | 5.2467 | 5.3051 | 3.9964 | 2.2387 | 19.3704 | 15.9833 | 19.3704 | 1
2040 | 4.824 | 6.7138 | 3.4486 | 4.5447 | 4.3471 | 2.4099 | 18.4924 | 15.0296 | 18.4924 | 1
2041 | 2.6894 | 5.1133 | 5.1299 | 4.908 | 4.2002 | 2.3207 | 15.0314 | 14.3403 | 15.0314 | 1
2042 | 3.55 | 6.8826 | 5.1692 | 7.013 | 3.4738 | 2.4542 | 19.8998 | 14.6471 | 19.8998 | 1
2043 | 3.5926 | 4.8417 | 5.1657 | 6.2612 | 4.3503 | 2.0792 | 16.7747 | 15.1879 | 16.7747 | 1
2044 | 3.2908 | 6.1175 | 4.4418 | 4.4172 | 5.2581 | 1.8288 | 15.6543 | 14.8195 | 15.6543 | 1
2045 | 3.2715 | 5.7181 | 5.4122 | 4.9965 | 5.0558 | 1.7869 | 15.773 | 15.5263 | 15.773 | 1
2046 | 4.4828 | 3.9018 | 6.6731 | 4.3018 | 4.6107 | 1.3036 | 13.99 | 17.0702 | 17.0702 | 0
2047 | 4.0688 | 3.8261 | 3.4029 | 5.3862 | 3.7122 | 1.6262 | 14.9073 | 12.8101 | 14.9073 | 1
2048 | 4.5493 | 5.6022 | 5.9635 | 4.7645 | 3.6874 | 2.0033 | 16.9193 | 16.2035 | 16.9193 | 1
2049 | 3.2025 | 5.8883 | 4.7077 | 6.2751 | 4.1132 | 2.1148 | 17.4807 | 14.1383 | 17.4807 | 1
2050 | 4.053 | 5.2583 | 2.7182 | 5.7745 | 5.2043 | 1.7527 | 16.8385 | 13.7283 | 16.8385 | 1
2051 | 3.7115 | 6.2533 | 3.0148 | 5.0381 | 4.6204 | 1.9746 | 16.9774 | 13.3213 | 16.9774 | 1
2052 | 3.3057 | 6.014 | 6.7696 | 6.0085 | 3.8011 | 1.6285 | 16.9567 | 15.505 | 16.9567 | 1
2053 | 5.4554 | 6.1872 | 3.0815 | 5.4376 | 3.8482 | 2.6945 | 19.7748 | 15.0796 | 19.7748 | 1
2054 | 4.0186 | 3.9104 | 5.8844 | 5.8025 | 4.9618 | 1.8243 | 15.5559 | 16.6891 | 16.6891 | 0
2055 | 4.1387 | 6.725 | 3.7673 | 5.1121 | 3.8996 | 1.7092 | 17.685 | 13.5149 | 17.685 | 1
2056 | 3.5658 | 6.4264 | 6.4156 | 4.5186 | 3.2991 | 2.1016 | 16.6123 | 15.3821 | 16.6123 | 1
2057 | 4.5905 | 5.8555 | 6.8499 | 4.9935 | 3.5904 | 1.8186 | 17.2582 | 16.8494 | 17.2582 | 1
2058 | 4.6141 | 6.7471 | 5.6419 | 6.0364 | 4.3304 | 2.4644 | 19.8621 | 17.0509 | 19.8621 | 1
2059 | 2.64 | 6.3537 | 4.7107 | 6.4001 | 3.6859 | 1.9439 | 17.3377 | 12.9806 | 17.3377 | 1
2060 | 3.9571 | 6.495 | 5.8885 | 4.1823 | 4.7994 | 2.0056 | 16.6401 | 16.6506 | 16.6506 | 0
2061 | 4.9439 | 3.5693 | 6.3297 | 4.3918 | 3.7993 | 1.8571 | 14.7621 | 16.93 | 16.93 | 0
2062 | 4.6226 | 5.6473 | 5.9754 | 5.6888 | 3.6342 | 1.5628 | 17.5215 | 15.795 | 17.5215 | 1
2063 | 2.8475 | 6.2244 | 6.4661 | 6.2046 | 3.5233 | 1.8236 | 17.1002 | 14.6605 | 17.1002 | 1
2064 | 3.6805 | 4.3332 | 4.8924 | 4.3952 | 4.5167 | 1.7791 | 14.1879 | 14.8686 | 14.8686 | 0
2065 | 4.9219 | 4.2017 | 4.8803 | 4.7357 | 3.8855 | 1.789 | 15.6483 | 15.4766 | 15.6483 | 1
2066 | 4.3351 | 4.2773 | 5.3087 | 5.4566 | 4.587 | 2.075 | 16.1441 | 16.3058 | 16.3058 | 0
2067 | 3.7395 | 5.2467 | 4.2756 | 4.9615 | 4.2154 | 1.9562 | 15.9038 | 14.1867 | 15.9038 | 1
2068 | 3.9527 | 4.123 | 7.0095 | 4.8572 | 4.4261 | 1.5548 | 14.4876 | 16.9431 | 16.9431 | 0
2069 | 4.0343 | 4.578 | 6.1925 | 5.7672 | 3.997 | 2.2264 | 16.6058 | 16.4502 | 16.6058 | 1
2070 | 3.5304 | 5.0705 | 6.5184 | 4.8797 | 4.6683 | 2.4275 | 15.9081 | 17.1445 | 17.1445 | 0
2071 | 3.5474 | 5.7047 | 3.93 | 6.6072 | 4.3451 | 1.7182 | 17.5775 | 13.5407 | 17.5775 | 1
2072 | 3.2243 | 5.8009 | 6.7146 | 4.6675 | 3.2434 | 2.5645 | 16.2572 | 15.7468 | 16.2572 | 1
2073 | 4.6736 | 5.5397 | 5.5926 | 6.1655 | 3.4039 | 1.9245 | 18.3033 | 15.5945 | 18.3033 | 1
2074 | 3.3815 | 6.2054 | 5.2465 | 5.8165 | 5.4229 | 2.2611 | 17.6645 | 16.3121 | 17.6645 | 1
2075 | 2.9583 | 3.638 | 4.8978 | 5.5389 | 3.9601 | 1.9324 | 14.0677 | 13.7486 | 14.0677 | 1
2076 | 4.3731 | 4.4249 | 6.013 | 5.6282 | 3.3705 | 2.4877 | 16.9139 | 16.2443 | 16.9139 | 1
2077 | 4.7865 | 5.1304 | 7.1162 | 5.0448 | 4.6863 | 2.1171 | 17.0787 | 18.7061 | 18.7061 | 0
2078 | 5.4949 | 6.909 | 4.6312 | 4.4701 | 5.1964 | 2.6652 | 19.5391 | 17.9876 | 19.5391 | 1
2079 | 4.1274 | 6.5715 | 6.3086 | 5.7055 | 4.7961 | 1.6738 | 18.0782 | 16.9059 | 18.0782 | 1
2080 | 4.7599 | 6.2882 | 5.1093 | 4.8382 | 3.9877 | 2.0933 | 17.9796 | 15.9502 | 17.9796 | 1
2081 | 3.7275 | 5.4947 | 5.1525 | 6.2981 | 3.8288 | 1.9241 | 17.4445 | 14.6329 | 17.4445 | 1
2082 | 4.4159 | 3.3874 | 3.4796 | 5.4453 | 3.1084 | 2.4474 | 15.6959 | 13.4513 | 15.6959 | 1
2083 | 3.593 | 5.3965 | 4.9089 | 5.1483 | 4.2417 | 1.6399 | 15.7776 | 14.3835 | 15.7776 | 1
2084 | 4.1127 | 4.765 | 4.1168 | 6.1107 | 5.3324 | 2.0581 | 17.0465 | 15.6201 | 17.0465 | 1
2085 | 4.0476 | 5.0218 | 6.0413 | 5.2105 | 3.7699 | 1.7547 | 16.0346 | 15.6135 | 16.0346 | 1
2086 | 2.7958 | 7.3779 | 5.7386 | 4.6395 | 4.4741 | 2.0961 | 16.9093 | 15.1046 | 16.9093 | 1
2087 | 2.824 | 5.8382 | 4.7745 | 5.7201 | 4.1261 | 1.8547 | 16.2369 | 13.5792 | 16.2369 | 1
2088 | 4.5071 | 3.6428 | 5.3479 | 5.5226 | 3.4174 | 1.4754 | 15.1479 | 14.7479 | 15.1479 | 1
2089 | 4.0807 | 5.5693 | 5.1651 | 5.0371 | 4.0421 | 2.3039 | 16.991 | 15.5918 | 16.991 | 1
2090 | 4.6728 | 3.7172 | 3.3073 | 4.4792 | 3.5254 | 1.9572 | 14.8264 | 13.4627 | 14.8264 | 1
2091 | 4.0477 | 3.8476 | 7.0686 | 4.5586 | 4.4604 | 2.1056 | 14.5595 | 17.6822 | 17.6822 | 0
2092 | 3.1542 | 6.4783 | 4.5236 | 5.4593 | 3.7843 | 1.5719 | 16.6637 | 13.034 | 16.6637 | 1
2093 | 5.7086 | 4.5779 | 3.3714 | 6.4578 | 4.0296 | 2.0165 | 18.7608 | 15.1262 | 18.7608 | 1
2094 | 4.4651 | 4.9392 | 5.1699 | 4.1462 | 4.0851 | 1.9227 | 15.4732 | 15.6428 | 15.6428 | 0
2095 | 4.7227 | 4.6401 | 5.6512 | 4.7053 | 3.9582 | 1.6649 | 15.733 | 15.9971 | 15.9971 | 0
2096 | 3.9446 | 5.0031 | 4.4048 | 4.6358 | 4.487 | 2.0267 | 15.6101 | 14.8631 | 15.6101 | 1
2097 | 3.6927 | 3.5669 | 6.8905 | 6.0796 | 4.8892 | 2.3756 | 15.7148 | 17.848 | 17.848 | 0
2098 | 4.6449 | 3.9465 | 3.7534 | 5.6412 | 5.6919 | 2.1329 | 16.3655 | 16.223 | 16.3655 | 1
2099 | 4.0969 | 4.2822 | 4.9486 | 5.4065 | 3.5757 | 2.2299 | 16.0155 | 14.8511 | 16.0155 | 1
2100 | 5.1481 | 5.7541 | 5.2103 | 5.125 | 5.4956 | 2.6409 | 18.6681 | 18.4949 | 18.6681 | 1
2101 | 3.723 | 7.5551 | 5.3108 | 5.2397 | 4.8706 | 1.7621 | 18.2799 | 15.6664 | 18.2799 | 1
2102 | 4.448 | 6.0174 | 6.582 | 5.2062 | 5.0382 | 1.6878 | 17.3595 | 17.7561 | 17.7561 | 0
2103 | 4.2188 | 7.3509 | 6.7207 | 6.1627 | 4.6293 | 1.6404 | 19.3729 | 17.2092 | 19.3729 | 1
2104 | 5.0916 | 5.6157 | 6.4027 | 5.4385 | 4.6987 | 2.0117 | 18.1575 | 18.2046 | 18.2046 | 0
2105 | 4.4134 | 6.0695 | 7.3154 | 4.5159 | 4.4044 | 1.9061 | 16.9049 | 18.0393 | 18.0393 | 0
2106 | 2.8283 | 5.9328 | 6.1185 | 5.4882 | 4.4474 | 1.5245 | 15.7738 | 14.9188 | 15.7738 | 1
2107 | 4.2478 | 5.863 | 6.4662 | 4.5169 | 4.3097 | 1.7265 | 16.3542 | 16.7502 | 16.7502 | 0
2108 | 4.2866 | 6.0535 | 4.2561 | 5.4226 | 4.5709 | 2.1808 | 17.9435 | 15.2944 | 17.9435 | 1
2109 | 4.3067 | 4.2798 | 5.1451 | 5.4089 | 3.9187 | 2.7523 | 16.7477 | 16.1228 | 16.7477 | 1
2110 | 3.5314 | 4.695 | 7.5684 | 6.8675 | 3.5194 | 1.7638 | 16.8577 | 16.383 | 16.8577 | 1
2111 | 3.485 | 3.8972 | 6.6819 | 6.1439 | 4.7978 | 2.0517 | 15.5778 | 17.0164 | 17.0164 | 0
2112 | 3.4426 | 5.0764 | 5.6785 | 4.5938 | 5.4991 | 1.9403 | 15.0531 | 16.5605 | 16.5605 | 0
2113 | 3.4838 | 5.3237 | 5.2849 | 6.8466 | 4.3175 | 1.86 | 17.514 | 14.9461 | 17.514 | 1
2114 | 3.449 | 7.0571 | 6.1963 | 5.0814 | 4.0645 | 1.8769 | 17.4643 | 15.5868 | 17.4643 | 1
2115 | 5.1061 | 6.9654 | 5.4445 | 5.2749 | 3.6491 | 1.7965 | 19.1429 | 15.9962 | 19.1429 | 1
2116 | 3.0193 | 6.1091 | 3.9497 | 5.8423 | 4.5559 | 1.1454 | 16.116 | 12.6703 | 16.116 | 1
2117 | 5.2319 | 5.2854 | 6.7797 | 5.8378 | 3.7233 | 1.7871 | 18.1422 | 17.522 | 18.1422 | 1
2118 | 4.2743 | 4.4782 | 4.0529 | 5.3312 | 5.6847 | 2.6196 | 16.7033 | 16.6314 | 16.7033 | 1
2119 | 3.2584 | 6.117 | 5.3326 | 5.987 | 3.4552 | 2.2407 | 17.603 | 14.2868 | 17.603 | 1
2120 | 4.861 | 5.2178 | 5.9985 | 5.0655 | 3.3524 | 1.9512 | 17.0954 | 16.1631 | 17.0954 | 1
2121 | 5.0216 | 7.9714 | 6.6583 | 6.6904 | 4.919 | 2.1273 | 21.8107 | 18.7263 | 21.8107 | 1
2122 | 3.7246 | 6.7846 | 6.3924 | 5.1729 | 4.4159 | 2.0069 | 17.689 | 16.5398 | 17.689 | 1
2123 | 3.2381 | 6.2827 | 5.9053 | 4.9477 | 3.2991 | 1.7408 | 16.2093 | 14.1834 | 16.2093 | 1
2124 | 4.0197 | 5.0515 | 4.0906 | 5.9419 | 4.0528 | 1.4126 | 16.4257 | 13.5758 | 16.4257 | 1
2125 | 4.7377 | 5.4672 | 6.8173 | 5.0211 | 4.0924 | 2.1188 | 17.3448 | 17.7662 | 17.7662 | 0
2126 | 4.7582 | 5.3601 | 4.9734 | 4.5476 | 3.438 | 1.9942 | 16.66 | 15.1636 | 16.66 | 1
2127 | 4.283 | 4.6037 | 6.2718 | 4.4915 | 3.6084 | 2.3464 | 15.7246 | 16.5096 | 16.5096 | 0
2128 | 3.9642 | 6.416 | 6.2994 | 5.2441 | 5.2594 | 2.4458 | 18.0701 | 17.9687 | 18.0701 | 1
2129 | 3.984 | 7.2993 | 5.5805 | 5.3745 | 4.7109 | 2.4346 | 19.0924 | 16.7099 | 19.0924 | 1
2130 | 3.613 | 6.261 | 6.2437 | 6.7777 | 3.3589 | 2.4166 | 19.0683 | 15.6322 | 19.0683 | 1
2131 | 3.6402 | 6.0278 | 4.8168 | 5.0709 | 5.2807 | 1.9613 | 16.7002 | 15.699 | 16.7002 | 1
2132 | 4.3121 | 4.2326 | 5.7866 | 6.7503 | 3.2335 | 2.3583 | 17.6533 | 15.6906 | 17.6533 | 1
2133 | 4.3805 | 4.633 | 5.8842 | 4.3096 | 4.3447 | 2.2419 | 15.565 | 16.8513 | 16.8513 | 0
2134 | 3.7984 | 5.3067 | 5.9165 | 5.2081 | 4.1306 | 2.4526 | 16.7658 | 16.298 | 16.7658 | 1
2135 | 4.1543 | 5.6386 | 3.4659 | 5.8469 | 5.3113 | 2.5739 | 18.2137 | 15.5054 | 18.2137 | 1
2136 | 4.2975 | 5.1786 | 4.5825 | 6.2356 | 4.9897 | 1.5815 | 17.2932 | 15.4513 | 17.2932 | 1
2137 | 2.9665 | 4.8061 | 5.8545 | 5.872 | 4.2072 | 1.996 | 15.6406 | 15.0241 | 15.6406 | 1
2138 | 4.7544 | 6.232 | 5.0013 | 6.0193 | 3.9232 | 2.3716 | 19.3773 | 16.0505 | 19.3773 | 1
2139 | 2.6804 | 4.4627 | 6.6209 | 5.2449 | 5.8298 | 1.5473 | 13.9353 | 16.6785 | 16.6785 | 0
2140 | 3.3579 | 6.4298 | 5.7984 | 5.8997 | 3.8799 | 2.0577 | 17.7451 | 15.0939 | 17.7451 | 1
2141 | 4.0171 | 4.3242 | 4.9291 | 6.2103 | 3.5415 | 2.6722 | 17.2238 | 15.1599 | 17.2238 | 1
2142 | 3.0175 | 5.8237 | 4.8731 | 5.3317 | 5.0939 | 2.3654 | 16.5383 | 15.35 | 16.5383 | 1
2143 | 3.8691 | 4.3446 | 3.9889 | 7.1844 | 3.6322 | 1.9073 | 17.3054 | 13.3975 | 17.3054 | 1
2144 | 3.7643 | 4.7626 | 7.0479 | 5.0387 | 4.6809 | 1.6446 | 15.2102 | 17.1377 | 17.1377 | 0
2145 | 4.449 | 5.864 | 5.0387 | 5.3593 | 3.3698 | 1.8534 | 17.5256 | 14.7108 | 17.5256 | 1
2146 | 4.5151 | 6.6582 | 7.335 | 4.7241 | 4.6738 | 1.376 | 17.2734 | 17.8998 | 17.8998 | 0
2147 | 5.1956 | 3.8845 | 5.6393 | 4.6643 | 3.789 | 1.6681 | 15.4124 | 16.292 | 16.292 | 0
2148 | 3.8047 | 6.2287 | 4.9809 | 5.3706 | 3.6403 | 2.2177 | 17.6217 | 14.6435 | 17.6217 | 1
2149 | 4.223 | 4.3982 | 6.6249 | 5.5408 | 3.9092 | 2.282 | 16.4441 | 17.0392 | 17.0392 | 0
2150 | 5.6107 | 4.1974 | 4.7388 | 6.44 | 3.9065 | 1.9742 | 18.2223 | 16.2303 | 18.2223 | 1
2151 | 4.9636 | 5.38 | 2.8119 | 4.9795 | 3.9364 | 1.9932 | 17.3163 | 13.705 | 17.3163 | 1
2152 | 5.662 | 5.8721 | 4.025 | 5.334 | 5.8682 | 2.6825 | 19.5506 | 18.2376 | 19.5506 | 1
2153 | 4.8791 | 4.5338 | 6.068 | 6.5849 | 4.2818 | 2.0889 | 18.0867 | 17.3178 | 18.0867 | 1
2154 | 3.4378 | 6.6554 | 7.688 | 4.6933 | 4.887 | 1.5485 | 16.335 | 17.5614 | 17.5614 | 0
2155 | 3.8249 | 4.3441 | 5.0982 | 5.0782 | 3.9873 | 1.1755 | 14.4226 | 14.0858 | 14.4226 | 1
2156 | 4.2829 | 5.9354 | 6.5815 | 6.9363 | 6.6316 | 1.6791 | 18.8337 | 19.1751 | 19.1751 | 0
2157 | 3.8251 | 4.6054 | 2.9028 | 4.964 | 4.9679 | 1.4644 | 14.8589 | 13.1603 | 14.8589 | 1
2158 | 5.0888 | 3.6013 | 4.9963 | 6.1623 | 3.4569 | 2.227 | 17.0793 | 15.769 | 17.0793 | 1
2159 | 3.8421 | 5.9362 | 5.4556 | 5.7738 | 5.1797 | 2.1116 | 17.6637 | 16.5891 | 17.6637 | 1
2160 | 3.665 | 6.2461 | 4.3366 | 5.4212 | 4.3598 | 1.9388 | 17.2711 | 14.3002 | 17.2711 | 1
2161 | 4.0522 | 5.5465 | 6.5842 | 4.6581 | 3.3696 | 1.8961 | 16.1529 | 15.9021 | 16.1529 | 1
2162 | 5.0207 | 5.6719 | 6.7073 | 5.3886 | 4.7932 | 2.483 | 18.5642 | 19.0042 | 19.0042 | 0
2163 | 3.7566 | 7.1049 | 6.2849 | 6.2785 | 4.2076 | 1.7636 | 18.9036 | 16.0126 | 18.9036 | 1
2164 | 4.9159 | 5.8228 | 4.6678 | 4.1692 | 4.9429 | 1.899 | 16.807 | 16.4257 | 16.807 | 1
2165 | 3.9841 | 6.0789 | 6.2325 | 5.0079 | 3.4467 | 2.0164 | 17.0874 | 15.6797 | 17.0874 | 1
2166 | 2.8561 | 5.0009 | 4.7622 | 6.4153 | 3.7081 | 2.021 | 16.2933 | 13.3474 | 16.2933 | 1
2167 | 3.9258 | 6.4335 | 4.7709 | 4.512 | 4.8792 | 2.2093 | 17.0806 | 15.7852 | 17.0806 | 1
2168 | 3.1594 | 4.2352 | 5.2786 | 6.0275 | 4.2078 | 2.4532 | 15.8752 | 15.099 | 15.8752 | 1
2169 | 4.7078 | 5.1204 | 4.8357 | 4.3514 | 5.5612 | 1.9719 | 16.1515 | 17.0766 | 17.0766 | 0
2170 | 4.7472 | 5.016 | 7.3873 | 5.0475 | 4.5139 | 2.4446 | 17.2552 | 19.0929 | 19.0929 | 0
2171 | 2.9578 | 4.4045 | 7.7366 | 4.5101 | 3.7539 | 1.4325 | 13.3049 | 15.8809 | 15.8809 | 0
2172 | 4.4269 | 7.1692 | 5.247 | 5.6654 | 3.6975 | 2.2281 | 19.4895 | 15.5995 | 19.4895 | 1
2173 | 3.5348 | 4.814 | 5.7095 | 4.9073 | 3.2292 | 2.5768 | 15.8329 | 15.0504 | 15.8329 | 1
2174 | 4.7602 | 6.5073 | 6.5586 | 6.1629 | 5.4343 | 2.5609 | 19.9913 | 19.3139 | 19.9913 | 1
2175 | 2.7914 | 4.4893 | 5.1507 | 6.292 | 4.545 | 2.5863 | 16.1591 | 15.0734 | 16.1591 | 1
2176 | 5.529 | 5.23 | 4.8233 | 4.8107 | 4.6787 | 1.7698 | 17.3395 | 16.8008 | 17.3395 | 1
2177 | 3.2618 | 5.2449 | 4.7839 | 5.8263 | 4.7589 | 2.0429 | 16.3759 | 14.8475 | 16.3759 | 1
2178 | 4.2609 | 5.8986 | 6.6263 | 4.646 | 4.0371 | 2.2541 | 17.0596 | 17.1785 | 17.1785 | 0
2179 | 2.5409 | 6.8258 | 7.1293 | 6.4092 | 4.9132 | 1.8454 | 17.6214 | 16.4289 | 17.6214 | 1
2180 | 3.5645 | 4.615 | 6.0652 | 4.998 | 3.7374 | 1.8019 | 14.9794 | 15.169 | 15.169 | 0
2181 | 3.9204 | 5.8059 | 3.9856 | 6.2848 | 3.696 | 2.2896 | 18.3006 | 13.8916 | 18.3006 | 1
2182 | 5.5385 | 3.2358 | 5.5276 | 6.216 | 4.7526 | 1.9237 | 16.914 | 17.7424 | 17.7424 | 0
2183 | 3.8796 | 5.1467 | 5.8811 | 5.3625 | 3.9299 | 2.1555 | 16.5442 | 15.846 | 16.5442 | 1
2184 | 3.4109 | 8.1721 | 3.8719 | 4.8138 | 4.2129 | 2.1146 | 18.5114 | 13.6103 | 18.5114 | 1
2185 | 4.388 | 4.5049 | 6.4679 | 5.4059 | 4.3545 | 2.2579 | 16.5567 | 17.4683 | 17.4683 | 0
2186 | 3.5188 | 4.8672 | 6.4924 | 5.2493 | 5.7323 | 2.3617 | 15.997 | 18.1053 | 18.1053 | 0
2187 | 3.5232 | 4.3231 | 6.9045 | 4.9553 | 3.8182 | 1.5921 | 14.3937 | 15.838 | 15.838 | 0
2188 | 2.933 | 3.5614 | 3.4898 | 6.8809 | 3.1539 | 2.0407 | 15.4161 | 11.6175 | 15.4161 | 1
2189 | 3.7919 | 3.7102 | 4.1939 | 4.6983 | 4.7667 | 1.567 | 13.7673 | 14.3195 | 14.3195 | 0
2190 | 3.7283 | 4.5246 | 5.4975 | 4.5542 | 3.9534 | 2.0863 | 14.8935 | 15.2656 | 15.2656 | 0
2191 | 3.5183 | 5.3034 | 3.8866 | 5.6018 | 4.6704 | 1.4506 | 15.8742 | 13.526 | 15.8742 | 1
2192 | 4.0978 | 5.5875 | 4.6804 | 4.7574 | 3.6921 | 2.0653 | 16.5081 | 14.5356 | 16.5081 | 1
2193 | 2.5825 | 3.427 | 6.4755 | 6.1833 | 3.612 | 2.6652 | 14.8581 | 15.3352 | 15.3352 | 0
2194 | 5.2728 | 6.5159 | 5.2236 | 6.6005 | 3.4234 | 2.2677 | 20.6569 | 16.1874 | 20.6569 | 1
2195 | 4.6169 | 6.7148 | 7.597 | 5.5942 | 3.5407 | 1.8283 | 18.7541 | 17.5828 | 18.7541 | 1
2196 | 3.3544 | 6.4774 | 4.5175 | 5.3875 | 4.0938 | 1.987 | 17.2063 | 13.9526 | 17.2063 | 1
2197 | 3.8439 | 4.8232 | 4.2878 | 5.0605 | 4.5833 | 2.1658 | 15.8934 | 14.8809 | 15.8934 | 1
2198 | 3.6475 | 5.8554 | 7.4338 | 4.584 | 3.6244 | 2.5882 | 16.6751 | 17.2939 | 17.2939 | 0
2199 | 3.9992 | 3.7874 | 6.1536 | 5.9008 | 4.0915 | 2.4369 | 16.1244 | 16.6812 | 16.6812 | 0
2200 | 2.5611 | 5.3646 | 4.4464 | 5.1497 | 4.4276 | 2.3992 | 15.4746 | 13.8343 | 15.4746 | 1
2201 | 4.4414 | 3.4566 | 5.9494 | 5.1755 | 5.1772 | 1.8692 | 14.9427 | 17.4372 | 17.4372 | 0
2202 | 5.4083 | 4.0297 | 6.2179 | 4.9301 | 3.5734 | 1.7707 | 16.1388 | 16.9702 | 16.9702 | 0
2203 | 3.4945 | 4.7794 | 4.6884 | 5.5976 | 5.3277 | 2.7742 | 16.6456 | 16.2848 | 16.6456 | 1
2204 | 3.8273 | 4.8138 | 4.0053 | 6.0213 | 3.5901 | 2.1857 | 16.8482 | 13.6085 | 16.8482 | 1
2205 | 4.2073 | 5.7922 | 4.9384 | 4.4547 | 4.0554 | 1.5866 | 16.0409 | 14.7877 | 16.0409 | 1
2206 | 4.6994 | 6.006 | 7.5654 | 5.4347 | 3.9511 | 2.5024 | 18.6426 | 18.7183 | 18.7183 | 0
2207 | 4.0722 | 6.1428 | 6.3339 | 6.0212 | 5.7579 | 1.7801 | 18.0163 | 17.9441 | 18.0163 | 1
2208 | 4.2627 | 3.5477 | 7.0124 | 5.6085 | 6.3525 | 2.3288 | 15.7477 | 19.9564 | 19.9564 | 0
2209 | 5.4559 | 6.771 | 6.0471 | 6.0124 | 4.7453 | 1.6596 | 19.8989 | 17.908 | 19.8989 | 1
2210 | 4.4828 | 3.6365 | 4.1002 | 5.2875 | 3.8632 | 1.5361 | 14.9429 | 13.9823 | 14.9429 | 1
2211 | 3.9538 | 4.074 | 4.3547 | 5.7534 | 5.0008 | 2.8309 | 16.6121 | 16.1403 | 16.6121 | 1
2212 | 3.8582 | 6.1941 | 4.9642 | 4.6562 | 4.4021 | 2.3615 | 17.07 | 15.586 | 17.07 | 1
2213 | 4.4605 | 4.7441 | 5.0544 | 5.8639 | 4.1008 | 2.1276 | 17.196 | 15.7432 | 17.196 | 1
2214 | 5.0879 | 6.4953 | 5.2032 | 5.4109 | 4.6539 | 2.3909 | 19.3849 | 17.3359 | 19.3849 | 1
2215 | 3.8956 | 5.5945 | 5.1154 | 5.1831 | 5.4602 | 1.9289 | 16.6021 | 16.4001 | 16.6021 | 1
2216 | 3.2354 | 6.8558 | 5.5817 | 5.368 | 3.2819 | 2.325 | 17.7843 | 14.4241 | 17.7843 | 1
2217 | 3.3874 | 6.8268 | 5.428 | 4.8285 | 3.3718 | 1.5947 | 16.6375 | 13.7819 | 16.6375 | 1
2218 | 3.2341 | 5.1563 | 7.4324 | 4.2723 | 4.769 | 1.8228 | 14.4855 | 17.2583 | 17.2583 | 0
2219 | 4.17 | 5.8673 | 6.7514 | 6.9226 | 4.9971 | 1.938 | 18.8979 | 17.8566 | 18.8979 | 1
2220 | 3.3025 | 5.7035 | 7.0235 | 4.6856 | 4.7295 | 1.774 | 15.4655 | 16.8295 | 16.8295 | 0
2221 | 3.823 | 5.0603 | 7.1233 | 5.7837 | 4.1089 | 1.5121 | 16.1791 | 16.5674 | 16.5674 | 0
2222 | 4.7142 | 4.6263 | 7.6092 | 4.414 | 4.7413 | 1.6291 | 15.3836 | 18.6938 | 18.6938 | 0
2223 | 3.6521 | 4.1471 | 5.8424 | 6.2647 | 3.7008 | 2.7062 | 16.77 | 15.9014 | 16.77 | 1
2224 | 3.9811 | 5.4723 | 5.2962 | 5.5543 | 3.5753 | 1.8743 | 16.8819 | 14.7268 | 16.8819 | 1
2225 | 4.603 | 4.9288 | 5.9262 | 4.3083 | 5.3419 | 1.7048 | 15.545 | 17.5759 | 17.5759 | 0
2226 | 4.7886 | 5.2182 | 4.5285 | 6.4119 | 4.9009 | 2.4839 | 18.9026 | 16.7018 | 18.9026 | 1
2227 | 3.7335 | 4.4991 | 4.2609 | 6.4823 | 5.4605 | 2.3953 | 17.1102 | 15.8501 | 17.1102 | 1
2228 | 4.6993 | 3.9688 | 5.6005 | 5.9516 | 3.2793 | 2.7228 | 17.3426 | 16.302 | 17.3426 | 1
2229 | 4.3469 | 7.088 | 6.6597 | 5.5476 | 4.4187 | 1.81 | 18.7925 | 17.2353 | 18.7925 | 1
2230 | 4.6606 | 5.405 | 3.1123 | 7.1953 | 4.629 | 2.5916 | 19.8525 | 14.9935 | 19.8525 | 1
2231 | 3.0838 | 5.8776 | 5.593 | 4.7983 | 5.083 | 2.2653 | 16.0249 | 16.0251 | 16.0251 | 0
2232 | 3.495 | 5.8785 | 7.2421 | 5.6785 | 3.6921 | 2.0505 | 17.1024 | 16.4796 | 17.1024 | 1
2233 | 3.7409 | 3.995 | 4.9134 | 4.8727 | 5.6898 | 2.4725 | 15.0812 | 16.8166 | 16.8166 | 0
2234 | 3.7821 | 4.3991 | 4.7919 | 4.5776 | 4.2753 | 2.1212 | 14.88 | 14.9705 | 14.9705 | 0
2235 | 4.222 | 5.6398 | 5.3762 | 6.3164 | 4.4205 | 1.5855 | 17.7637 | 15.6043 | 17.7637 | 1
2236 | 3.4927 | 5.1401 | 5.603 | 4.5072 | 4.0176 | 2.0905 | 15.2306 | 15.2038 | 15.2306 | 1
2237 | 3.6123 | 5.1068 | 7.6811 | 6.5592 | 4.5283 | 1.369 | 16.6473 | 17.1908 | 17.1908 | 0
2238 | 4.7439 | 4.7233 | 4.3256 | 4.9217 | 4.025 | 1.7679 | 16.1568 | 14.8624 | 16.1568 | 1
2239 | 4.9528 | 5.5113 | 4.479 | 5.4032 | 4.4715 | 1.7414 | 17.6087 | 15.6446 | 17.6087 | 1
2240 | 3.4037 | 4.449 | 5.0395 | 4.5929 | 5.327 | 1.844 | 14.2894 | 15.6142 | 15.6142 | 0
2241 | 3.9069 | 5.6312 | 5.0693 | 6.4239 | 3.373 | 2.0801 | 18.0421 | 14.4293 | 18.0421 | 1
2242 | 2.3464 | 5.5716 | 3.5212 | 6.1184 | 4.4453 | 1.1344 | 15.1709 | 11.4474 | 15.1709 | 1
2243 | 3.8989 | 5.1462 | 4.6673 | 5.384 | 5.7016 | 1.9667 | 16.3958 | 16.2346 | 16.3958 | 1
2244 | 3.8925 | 4.3555 | 4.8138 | 5.2775 | 4.3451 | 1.22 | 14.7455 | 14.2714 | 14.7455 | 1
2245 | 4.1552 | 4.6081 | 5.4144 | 4.9467 | 4.0401 | 1.9869 | 15.6969 | 15.5967 | 15.6969 | 1
2246 | 4.4886 | 5.421 | 6.2903 | 5.1517 | 4.1903 | 2.8491 | 17.9104 | 17.8182 | 17.9104 | 1
2247 | 3.0791 | 5.1588 | 6.7275 | 4.6387 | 3.5747 | 2.4895 | 15.3661 | 15.8708 | 15.8708 | 0
2248 | 3.1577 | 6.359 | 6.1946 | 4.3374 | 3.2166 | 2.0459 | 15.9 | 14.6148 | 15.9 | 1
2249 | 4.5867 | 4.0809 | 3.9093 | 4.3727 | 4.0638 | 1.2541 | 14.2944 | 13.814 | 14.2944 | 1
2250 | 5.0279 | 5.6541 | 5.2309 | 5.9848 | 5.007 | 2.2898 | 18.9565 | 17.5556 | 18.9565 | 1
2251 | 4.3988 | 3.4005 | 6.3188 | 5.7658 | 5.0832 | 1.8085 | 15.3736 | 17.6093 | 17.6093 | 0
2252 | 3.4404 | 3.7238 | 6.6037 | 5.7724 | 4.2605 | 2.4446 | 15.3812 | 16.7492 | 16.7492 | 0
2253 | 4.2956 | 7.0781 | 6.3763 | 4.3582 | 5.2155 | 1.8105 | 17.5423 | 17.6978 | 17.6978 | 0
2254 | 3.5941 | 5.5996 | 6.8304 | 5.0565 | 4.5048 | 1.7385 | 15.9885 | 16.6678 | 16.6678 | 0
2255 | 4.2722 | 6.2904 | 5.1944 | 4.9895 | 4.5431 | 2.575 | 18.1271 | 16.5846 | 18.1271 | 1
2256 | 5.0862 | 3.9539 | 7.0612 | 5.1692 | 5.0136 | 2.1917 | 16.4009 | 19.3526 | 19.3526 | 0
2257 | 3.1554 | 4.3421 | 6.5805 | 5.1334 | 3.4939 | 1.3681 | 13.9991 | 14.5979 | 14.5979 | 0
2258 | 3.146 | 5.0023 | 5.4044 | 5.6505 | 4.4985 | 2.266 | 16.0647 | 15.315 | 16.0647 | 1
2259 | 2.5636 | 5.1174 | 4.1327 | 4.9022 | 5.795 | 2.1069 | 14.6902 | 14.5982 | 14.6902 | 1
2260 | 2.5343 | 3.7097 | 3.7137 | 5.8239 | 5.498 | 2.6856 | 14.7535 | 14.4317 | 14.7535 | 1
2261 | 4.2771 | 7.2056 | 4.0598 | 5.0171 | 5.2824 | 1.5737 | 18.0735 | 15.1931 | 18.0735 | 1
2262 | 4.8372 | 5.3936 | 4.1638 | 4.7591 | 3.5834 | 2.4322 | 17.4221 | 15.0167 | 17.4221 | 1
2263 | 4.9558 | 7.9365 | 4.3469 | 5.8469 | 4.5569 | 1.9802 | 20.7194 | 15.8399 | 20.7194 | 1
2264 | 4.7736 | 4.0063 | 6.2324 | 5.0739 | 5.073 | 1.5952 | 15.449 | 17.6742 | 17.6742 | 0
2265 | 4.2024 | 4.8107 | 6.6176 | 5.3395 | 4.8819 | 2.1458 | 16.4984 | 17.8477 | 17.8477 | 0
2266 | 3.844 | 4.0055 | 5.8614 | 6.8649 | 3.163 | 1.6562 | 16.3705 | 14.5245 | 16.3705 | 1
2267 | 5.1074 | 6.8053 | 6.4335 | 5.2627 | 3.6582 | 2.541 | 19.7164 | 17.7402 | 19.7164 | 1
2268 | 2.8523 | 6.5585 | 5.6576 | 5.1511 | 3.7343 | 2.1467 | 16.7086 | 14.391 | 16.7086 | 1
2269 | 2.8428 | 4.9421 | 6.7231 | 5.671 | 4.2619 | 1.1744 | 14.6303 | 15.0023 | 15.0023 | 0
2270 | 4.9159 | 5.7535 | 4.9529 | 4.9559 | 4.5106 | 2.3512 | 17.9765 | 16.7306 | 17.9765 | 1
2271 | 3.8493 | 5.7463 | 5.2628 | 4.7031 | 6.3358 | 1.7923 | 16.091 | 17.2401 | 17.2401 | 0
2272 | 5.4678 | 6.0882 | 3.6685 | 5.5738 | 4.4749 | 1.0561 | 18.1859 | 14.6673 | 18.1859 | 1
2273 | 5.2378 | 4.2811 | 5.04 | 4.4733 | 3.4535 | 2.0103 | 16.0026 | 15.7416 | 16.0026 | 1
2274 | 3.9325 | 3.2543 | 4.714 | 4.6653 | 3.3562 | 1.9071 | 13.7592 | 13.9097 | 13.9097 | 0
2275 | 4.1146 | 4.0752 | 7.56 | 7.243 | 4.0905 | 2.1092 | 17.542 | 17.8743 | 17.8743 | 0
2276 | 3.1665 | 5.6006 | 6.9274 | 6.7409 | 6.1874 | 2.7175 | 18.2255 | 18.9988 | 18.9988 | 0
2277 | 3.7074 | 6.4545 | 4.1942 | 5.0036 | 5.0466 | 2.0221 | 17.1875 | 14.9702 | 17.1875 | 1
2278 | 5.3598 | 6.3905 | 4.2081 | 6.2229 | 5.007 | 1.5051 | 19.4783 | 16.0801 | 19.4783 | 1
2279 | 3.8592 | 4.9191 | 4.311 | 4.7608 | 3.5576 | 2.5359 | 16.0749 | 14.2636 | 16.0749 | 1
2280 | 4.7856 | 6.5504 | 5.9174 | 6.216 | 3.1849 | 2.0535 | 19.6055 | 15.9414 | 19.6055 | 1
2281 | 4.2643 | 5.6918 | 6.2426 | 6.1349 | 4.0052 | 2.2391 | 18.3301 | 16.7512 | 18.3301 | 1
2282 | 4.3376 | 6.5567 | 6.9802 | 4.4537 | 3.6718 | 2.2288 | 17.5768 | 17.2184 | 17.5768 | 1
2283 | 3.9413 | 3.7315 | 4.4005 | 5.5184 | 4.3794 | 1.9646 | 15.1558 | 14.6858 | 15.1558 | 1
2284 | 4.9617 | 4.164 | 4.9361 | 5.2613 | 3.3967 | 1.7465 | 16.1335 | 15.041 | 16.1335 | 1
2285 | 2.6328 | 3.9884 | 6.3462 | 5.8071 | 4.4052 | 2.0838 | 14.5121 | 15.468 | 15.468 | 0
2286 | 3.5898 | 5.8992 | 5.9835 | 4.843 | 4.5277 | 2.6675 | 16.9995 | 16.7685 | 16.9995 | 1
2287 | 2.7406 | 5.1335 | 6.1147 | 6.005 | 5.0017 | 2.4946 | 16.3737 | 16.3517 | 16.3737 | 1
2288 | 3.4367 | 6.5241 | 5.6883 | 6.1247 | 3.9403 | 1.7491 | 17.8345 | 14.8143 | 17.8345 | 1
2289 | 3.8924 | 5.7959 | 5.0956 | 4.5922 | 4.0926 | 2.67 | 16.9505 | 15.7507 | 16.9505 | 1
2290 | 3.3461 | 4.6665 | 5.1713 | 5.1408 | 4.6621 | 1.8631 | 15.0165 | 15.0425 | 15.0425 | 0
2291 | 3.2103 | 4.0053 | 6.8546 | 6.4282 | 3.3438 | 2.2571 | 15.901 | 15.6659 | 15.901 | 1
2292 | 4.6291 | 3.8998 | 6.5908 | 4.606 | 4.8001 | 1.8089 | 14.9438 | 17.8289 | 17.8289 | 0
2293 | 4.1603 | 3.4049 | 6.3366 | 5.802 | 3.4431 | 2.0914 | 15.4587 | 16.0315 | 16.0315 | 0
2294 | 5.1431 | 4.786 | 4.6594 | 5.1624 | 4.0019 | 2.5848 | 17.6762 | 16.3892 | 17.6762 | 1
2295 | 3.5257 | 7.1526 | 5.6922 | 5.4495 | 4.4818 | 1.6313 | 17.759 | 15.331 | 17.759 | 1
2296 | 4.9076 | 5.5529 | 3.4394 | 5.0023 | 5.4571 | 1.515 | 16.9779 | 15.3192 | 16.9779 | 1
2297 | 3.4629 | 4.7257 | 5.8092 | 4.5541 | 3.3862 | 1.6581 | 14.4008 | 14.3164 | 14.4008 | 1
2298 | 4.1046 | 6.7172 | 7.7819 | 4.7954 | 3.3054 | 2.1806 | 17.7977 | 17.3725 | 17.7977 | 1
2299 | 5.3683 | 6.2646 | 6.8296 | 5.948 | 4.2588 | 2.5108 | 20.0917 | 18.9674 | 20.0917 | 1
2300 | 3.5105 | 5.4406 | 6.3641 | 4.635 | 4.0065 | 1.7425 | 15.3286 | 15.6236 | 15.6236 | 0
2301 | 2.9644 | 5.4762 | 6.2417 | 4.7174 | 4.0348 | 2.0792 | 15.2373 | 15.3201 | 15.3201 | 0
2302 | 3.6457 | 4.0377 | 6.574 | 5.1339 | 5.1625 | 2.2994 | 15.1167 | 17.6816 | 17.6816 | 0
2303 | 4.2344 | 3.724 | 7.0131 | 6.2459 | 4.2054 | 2.0515 | 16.2559 | 17.5044 | 17.5044 | 0
2304 | 3.8896 | 3.9623 | 4.2928 | 4.6787 | 3.6055 | 2.0992 | 14.6298 | 13.8871 | 14.6298 | 1
2305 | 4.4376 | 6.1033 | 4.9027 | 6.0657 | 5.3491 | 1.6169 | 18.2235 | 16.3062 | 18.2235 | 1
2306 | 3.6568 | 5.8571 | 6.6332 | 5.1205 | 4.8082 | 2.6456 | 17.2799 | 17.7437 | 17.7437 | 0
2307 | 4.6106 | 4.54 | 5.0244 | 4.6241 | 4.7358 | 1.6649 | 15.4396 | 16.0357 | 16.0357 | 0
2308 | 3.2917 | 6.4646 | 6.8513 | 4.9898 | 4.2343 | 2.1214 | 16.8675 | 16.4986 | 16.8675 | 1
2309 | 3.7894 | 5.398 | 5.628 | 5.0877 | 3.6271 | 1.6919 | 15.967 | 14.7364 | 15.967 | 1
2310 | 4.9724 | 6.633 | 5.5052 | 4.4637 | 3.9895 | 2.0172 | 18.0863 | 16.4844 | 18.0863 | 1
2311 | 4.4542 | 5.2467 | 3.7861 | 5.7791 | 3.3538 | 2.224 | 17.704 | 13.8181 | 17.704 | 1
2312 | 4.8486 | 4.757 | 7.0717 | 5.8359 | 4.5713 | 2.1598 | 17.6014 | 18.6515 | 18.6515 | 0
2313 | 4.2466 | 5.5579 | 5.6847 | 4.3296 | 4.0706 | 1.835 | 15.9691 | 15.8368 | 15.9691 | 1
2314 | 5.2321 | 6.3123 | 4.8061 | 5.1897 | 4.8538 | 1.541 | 18.2751 | 16.4331 | 18.2751 | 1
2315 | 2.2636 | 5.7459 | 3.7174 | 5.936 | 5.0295 | 2.2201 | 16.1655 | 13.2306 | 16.1655 | 1
2316 | 4.2883 | 7.0909 | 5.2117 | 6.2966 | 4.9119 | 1.4831 | 19.159 | 15.895 | 19.159 | 1
2317 | 4.1716 | 5.2661 | 5.1259 | 5.0551 | 3.6944 | 1.9404 | 16.4332 | 14.9324 | 16.4332 | 1
2318 | 4.7259 | 4.5501 | 3.5828 | 5.3616 | 5.227 | 1.5758 | 16.2135 | 15.1116 | 16.2135 | 1
2319 | 5.5612 | 4.7585 | 6.6581 | 4.3832 | 4.7098 | 1.7562 | 16.4591 | 18.6853 | 18.6853 | 0
2320 | 4.8434 | 7.6443 | 5.3531 | 5.1739 | 3.7506 | 1.962 | 19.6235 | 15.909 | 19.6235 | 1
2321 | 4.7477 | 3.9564 | 7.4439 | 4.5131 | 4.2356 | 2.2134 | 15.4306 | 18.6407 | 18.6407 | 0
2322 | 2.8954 | 5.9726 | 5.7913 | 4.7965 | 4.1355 | 1.9012 | 15.5657 | 14.7233 | 15.5657 | 1
2323 | 3.747 | 4.0488 | 5.8907 | 4.9046 | 3.6639 | 2.0425 | 14.7429 | 15.344 | 15.344 | 0
2324 | 3.5221 | 5.7445 | 4.3063 | 4.5811 | 3.8402 | 1.6893 | 15.537 | 13.358 | 15.537 | 1
2325 | 3.9007 | 5.1036 | 6.3326 | 5.0923 | 5.066 | 2.3174 | 16.414 | 17.6167 | 17.6167 | 0
2326 | 3.5173 | 4.7112 | 5.3925 | 4.2636 | 3.6844 | 2.0371 | 14.5291 | 14.6312 | 14.6312 | 0
2327 | 5.2285 | 6.0576 | 5.9259 | 5.3214 | 4.433 | 1.5948 | 18.2023 | 17.1822 | 18.2023 | 1
2328 | 4.7542 | 5.0088 | 7.2273 | 5.4581 | 4.3692 | 2.3154 | 17.5366 | 18.6661 | 18.6661 | 0
2329 | 4.3257 | 4.8844 | 5.3432 | 4.9428 | 5.0629 | 2.0411 | 16.194 | 16.7728 | 16.7728 | 0
2330 | 3.367 | 6.1768 | 5.44 | 6.7 | 4.2653 | 1.511 | 17.7548 | 14.5833 | 17.7548 | 1
2331 | 3.6085 | 5.6184 | 5.087 | 6.2794 | 4.2537 | 2.3872 | 17.8935 | 15.3363 | 17.8935 | 1
2332 | 4.87 | 6.1903 | 4.4758 | 4.1666 | 4.162 | 2.4429 | 17.6697 | 15.9507 | 17.6697 | 1
2333 | 2.7261 | 4.4521 | 5.982 | 4.1919 | 6.2336 | 2.0202 | 13.3904 | 16.9619 | 16.9619 | 0
2334 | 4.6071 | 3.8173 | 6.1148 | 5.1611 | 4.1808 | 1.36 | 14.9456 | 16.2627 | 16.2627 | 0
2335 | 4.3807 | 6.1545 | 5.7242 | 6.2093 | 4.7643 | 1.8351 | 18.5795 | 16.7042 | 18.5795 | 1
2336 | 3.9477 | 4.8674 | 4.5439 | 4.3212 | 3.5779 | 1.4701 | 14.6064 | 13.5397 | 14.6064 | 1
2337 | 3.3325 | 5.5301 | 6.3976 | 5.7619 | 4.0544 | 2.3425 | 16.967 | 16.127 | 16.967 | 1
2338 | 3.3897 | 5.3887 | 6.9106 | 5.4037 | 3.3122 | 2.4973 | 16.6793 | 16.1097 | 16.6793 | 1
2339 | 4.487 | 4.992 | 6.8938 | 5.478 | 4.1094 | 1.1223 | 16.0792 | 16.6125 | 16.6125 | 0
2340 | 4.4915 | 6.7503 | 6.0056 | 4.2805 | 3.2877 | 2.0191 | 17.5415 | 15.804 | 17.5415 | 1
2341 | 4.8982 | 3.9973 | 6.4553 | 4.4905 | 4.0422 | 1.5958 | 14.9817 | 16.9915 | 16.9915 | 0
2342 | 5.0877 | 6.4854 | 4.0719 | 4.5796 | 3.1982 | 2.3778 | 18.5305 | 14.7356 | 18.5305 | 1
2343 | 3.2334 | 6.1667 | 4.926 | 6.0599 | 4.5697 | 1.9897 | 17.4498 | 14.7189 | 17.4498 | 1
2344 | 3.8251 | 6.3765 | 5.1767 | 4.5532 | 4.1227 | 1.8064 | 16.5613 | 14.931 | 16.5613 | 1
2345 | 3.0572 | 4.0907 | 6.9283 | 4.677 | 4.06 | 1.5133 | 13.3382 | 15.5587 | 15.5587 | 0
2346 | 2.9863 | 4.7233 | 7.2401 | 4.2905 | 5.6374 | 1.8657 | 13.8657 | 17.7294 | 17.7294 | 0
2347 | 5.0297 | 6.4809 | 5.7448 | 4.2442 | 6.065 | 2.0241 | 17.7789 | 18.8636 | 18.8636 | 0
2348 | 4.7322 | 7.1225 | 6.6722 | 5.2545 | 5.7332 | 1.9813 | 19.0904 | 19.1189 | 19.1189 | 0
2349 | 3.6078 | 3.7181 | 4.732 | 5.8081 | 5.0702 | 2.5791 | 15.713 | 15.989 | 15.989 | 0
2350 | 2.7616 | 5.15 | 4.407 | 5.8382 | 4.0599 | 1.4653 | 15.215 | 12.6937 | 15.215 | 1
2351 | 2.9844 | 5.5965 | 7.0092 | 4.706 | 3.8328 | 1.458 | 14.7449 | 15.2843 | 15.2843 | 0
2352 | 4.4493 | 4.715 | 5.1567 | 6.5489 | 4.362 | 2.3501 | 18.0634 | 16.3181 | 18.0634 | 1
2353 | 5.3671 | 4.9283 | 5.2121 | 4.4379 | 4.459 | 2.143 | 16.8764 | 17.1813 | 17.1813 | 0
2354 | 4.2719 | 3.7692 | 6.3449 | 4.663 | 5.2253 | 1.9948 | 14.6989 | 17.8369 | 17.8369 | 0
2355 | 3.3429 | 3.6857 | 7.4969 | 4.1576 | 3.562 | 2.1903 | 13.3764 | 16.592 | 16.592 | 0
2356 | 3.6415 | 4.6892 | 5.9692 | 5.9014 | 5.6554 | 1.8802 | 16.1125 | 17.1463 | 17.1463 | 0
2357 | 2.4881 | 3.5196 | 6.9876 | 4.4027 | 4.3067 | 1.5859 | 11.9962 | 15.3683 | 15.3683 | 0
2358 | 4.6397 | 5.7436 | 5.117 | 5.4085 | 4.3237 | 2.3544 | 18.1461 | 16.4348 | 18.1461 | 1
2359 | 4.3313 | 7.0485 | 6.7307 | 5.1568 | 3.692 | 1.4075 | 17.9441 | 16.1615 | 17.9441 | 1
2360 | 3.8333 | 4.5856 | 7.2463 | 5.2338 | 5.0109 | 1.8751 | 15.5277 | 17.9656 | 17.9656 | 0
2361 | 4.4871 | 3.7421 | 6.6092 | 5.8016 | 4.7343 | 2.1235 | 16.1543 | 17.954 | 17.954 | 0
2362 | 3.5273 | 6.2741 | 7.3455 | 6.4603 | 6.2818 | 1.7233 | 17.9851 | 18.878 | 18.878 | 0
2363 | 3.8126 | 3.7359 | 5.4022 | 5.0951 | 4.0093 | 2.1871 | 14.8306 | 15.4112 | 15.4112 | 0
2364 | 3.4312 | 7.4302 | 6.2093 | 5.0771 | 4.0782 | 2.2204 | 18.1589 | 15.9391 | 18.1589 | 1
2365 | 3.0893 | 6.8764 | 5.5515 | 5.5037 | 4.6805 | 1.759 | 17.2285 | 15.0803 | 17.2285 | 1
2366 | 4.289 | 3.7883 | 4.44 | 4.4855 | 5.127 | 1.2637 | 13.8266 | 15.1197 | 15.1197 | 0
2367 | 3.5473 | 4.0066 | 6.7694 | 5.4289 | 3.5651 | 2.3762 | 15.359 | 16.2581 | 16.2581 | 0
2368 | 4.0175 | 3.9658 | 3.7287 | 6.2925 | 4.2869 | 1.7685 | 16.0442 | 13.8016 | 16.0442 | 1
2369 | 4.1042 | 6.6378 | 2.9818 | 4.3594 | 3.1291 | 2.1829 | 17.2844 | 12.398 | 17.2844 | 1
2370 | 3.1223 | 4.2891 | 4.4831 | 5.0685 | 4.5214 | 1.6498 | 14.1296 | 13.7766 | 14.1296 | 1
2371 | 3.6534 | 4.9683 | 6.6972 | 4.9715 | 5.214 | 1.9953 | 15.5885 | 17.5598 | 17.5598 | 0
2372 | 4.8573 | 5.8459 | 5.607 | 5.519 | 4.1337 | 1.958 | 18.1803 | 16.5561 | 18.1803 | 1
2373 | 3.9446 | 5.169 | 6.5135 | 5.8408 | 3.1871 | 1.8021 | 16.7565 | 15.4473 | 16.7565 | 1
2374 | 3.0284 | 7.1412 | 5.6639 | 6.399 | 3.7246 | 2.136 | 18.7046 | 14.5528 | 18.7046 | 1
2375 | 5.1797 | 7.9504 | 4.7687 | 5.3821 | 4.1437 | 2.1282 | 20.6403 | 16.2203 | 20.6403 | 1
2376 | 4.2146 | 4.6419 | 5.6769 | 6.4457 | 3.4659 | 2.1223 | 17.4245 | 15.4797 | 17.4245 | 1
2377 | 4.7518 | 4.669 | 5.9887 | 5.227 | 5.4301 | 2.4872 | 17.135 | 18.6577 | 18.6577 | 0
2378 | 3.3837 | 6.755 | 6.0629 | 5.2145 | 5.3227 | 2.3961 | 17.7492 | 17.1654 | 17.7492 | 1
2379 | 3.3531 | 6.2293 | 6.6196 | 5.7634 | 5.1399 | 2.3275 | 17.6734 | 17.4401 | 17.6734 | 1
2380 | 4.9899 | 6.4323 | 4.7259 | 5.0066 | 3.6402 | 1.4498 | 17.8785 | 14.8057 | 17.8785 | 1
2381 | 3.6704 | 3.5115 | 6.7385 | 6.3435 | 3.304 | 2.2728 | 15.7982 | 15.9857 | 15.9857 | 0
2382 | 4.2363 | 4.5989 | 3.2726 | 4.8133 | 4.7778 | 1.9572 | 15.6057 | 14.244 | 15.6057 | 1
2383 | 4.0009 | 4.255 | 7.0497 | 5.5055 | 4.0718 | 2.0418 | 15.8032 | 17.1642 | 17.1642 | 0
2384 | 4.1553 | 6.8611 | 6.0505 | 5.4245 | 3.8401 | 2.1191 | 18.56 | 16.1651 | 18.56 | 1
2385 | 3.4528 | 6.6665 | 6.4013 | 5.1566 | 3.8109 | 1.5998 | 16.8757 | 15.2648 | 16.8757 | 1
2386 | 4.7553 | 5.7421 | 5.8125 | 5.9082 | 3.5063 | 2.7785 | 19.1841 | 16.8526 | 19.1841 | 1
2387 | 3.8367 | 5.625 | 6.0153 | 5.0513 | 3.4769 | 2.48 | 16.9931 | 15.8089 | 16.9931 | 1
2388 | 3.4767 | 5.6714 | 3.6663 | 5.4523 | 5.2158 | 1.9224 | 16.5227 | 14.2812 | 16.5227 | 1
2389 | 3.9555 | 5.7445 | 5.5096 | 5.7528 | 3.702 | 2.0604 | 17.5132 | 15.2276 | 17.5132 | 1
2390 | 5.2244 | 3.4672 | 4.629 | 4.6811 | 3.5962 | 1.8741 | 15.2467 | 15.3237 | 15.3237 | 0
2391 | 3.5487 | 3.8717 | 4.7388 | 4.6085 | 3.5849 | 2.438 | 14.4669 | 14.3104 | 14.4669 | 1
2392 | 4.1762 | 5.3144 | 5.8457 | 5.7031 | 3.1644 | 2.1639 | 17.3577 | 15.3503 | 17.3577 | 1
2393 | 5.0564 | 3.1675 | 5.8488 | 5.1946 | 4.6309 | 1.6817 | 15.1002 | 17.2178 | 17.2178 | 0
2394 | 3.9112 | 5.0988 | 6.5847 | 4.955 | 4.6547 | 1.278 | 15.243 | 16.4287 | 16.4287 | 0
2395 | 3.6478 | 7.7021 | 7.1698 | 5.0779 | 3.7194 | 1.7741 | 18.202 | 16.3111 | 18.202 | 1
2396 | 5.1359 | 6.4133 | 5.9981 | 5.4715 | 6.0357 | 1.419 | 18.4398 | 18.5887 | 18.5887 | 0
2397 | 4.2522 | 4.6895 | 6.3527 | 5.6164 | 4.1192 | 1.8137 | 16.3717 | 16.5377 | 16.5377 | 0
2398 | 3.6176 | 5.9277 | 6.5293 | 5.4515 | 4.0323 | 1.7678 | 16.7646 | 15.947 | 16.7646 | 1
2399 | 4.8606 | 6.9894 | 6.8796 | 6.1924 | 4.437 | 1.5746 | 19.617 | 17.7518 | 19.617 | 1
2400 | 4.3096 | 5.9706 | 7.3788 | 5.2431 | 4.7303 | 2.4113 | 17.9346 | 18.8301 | 18.8301 | 0
2401 | 2.3588 | 4.1737 | 6.3751 | 5.2144 | 4.5432 | 2.1533 | 13.9003 | 15.4305 | 15.4305 | 0
2402 | 2.6943 | 6.4594 | 4.5868 | 4.4302 | 4.2167 | 2.2517 | 15.8355 | 13.7494 | 15.8355 | 1
2403 | 3.0661 | 7.5179 | 6.1359 | 4.9007 | 5.0841 | 1.7587 | 17.2433 | 16.0448 | 17.2433 | 1
2404 | 4.9733 | 6.0333 | 5.1172 | 4.6245 | 3.8493 | 1.6453 | 17.2763 | 15.5851 | 17.2763 | 1
2405 | 2.561 | 5.553 | 6.2141 | 5.4528 | 4.0576 | 2.0371 | 15.6039 | 14.8698 | 15.6039 | 1
2406 | 5.3557 | 5.4149 | 7.3076 | 6.0173 | 3.7554 | 1.8721 | 18.66 | 18.2907 | 18.66 | 1
2407 | 4.4526 | 5.8237 | 5.9812 | 5.277 | 5.4357 | 2.0767 | 17.6301 | 17.9462 | 17.9462 | 0
2408 | 5.2603 | 6.6994 | 5.4745 | 4.9537 | 6.094 | 2.3247 | 19.2381 | 19.1534 | 19.2381 | 1
2409 | 4.8783 | 4.9546 | 4.1975 | 5.1195 | 5.2531 | 1.9173 | 16.8697 | 16.2461 | 16.8697 | 1
2410 | 5.7614 | 7.6501 | 7.3173 | 5.2856 | 3.9036 | 2.2631 | 20.9601 | 19.2454 | 20.9601 | 1
2411 | 4.7614 | 4.5504 | 4.18 | 4.6666 | 5.0191 | 1.2901 | 15.2684 | 15.2506 | 15.2684 | 1
2412 | 3.9877 | 7.082 | 5.6647 | 4.902 | 4.1252 | 2.7199 | 18.6915 | 16.4974 | 18.6915 | 1
2413 | 4.6082 | 5.8121 | 4.5203 | 4.7026 | 4.5071 | 2.3253 | 17.4482 | 15.961 | 17.4482 | 1
2414 | 5.2184 | 6.1803 | 6.8677 | 5.6236 | 4.5833 | 2.255 | 19.2772 | 18.9243 | 19.2772 | 1
2415 | 5.0326 | 4.3167 | 6.1985 | 4.4154 | 4.8364 | 2.3699 | 16.1346 | 18.4375 | 18.4375 | 0
2416 | 4.8961 | 5.1331 | 6.2043 | 5.014 | 3.6607 | 2.3207 | 17.364 | 17.0818 | 17.364 | 1
2417 | 3.6999 | 5.9419 | 5.9328 | 5.1557 | 5.3409 | 2.136 | 16.9335 | 17.1097 | 17.1097 | 0
2418 | 3.3489 | 5.9462 | 4.3066 | 4.7248 | 6.1296 | 2.3759 | 16.3958 | 16.1609 | 16.3958 | 1
2419 | 3.1241 | 4.8908 | 6.4347 | 4.8823 | 3.2817 | 2.2889 | 15.1861 | 15.1294 | 15.1861 | 1
2420 | 4.1998 | 4.6025 | 4.4133 | 5.5481 | 4.2132 | 1.3927 | 15.7431 | 14.219 | 15.7431 | 1
2421 | 3.1849 | 5.72 | 5.738 | 5.2047 | 3.8758 | 2.1761 | 16.2858 | 14.9749 | 16.2858 | 1
2422 | 4.785 | 4.4062 | 3.9226 | 6.1626 | 4.467 | 2.2343 | 17.5881 | 15.4089 | 17.5881 | 1
2423 | 3.8652 | 5.2696 | 4.0887 | 5.6738 | 3.1818 | 1.8088 | 16.6175 | 12.9445 | 16.6175 | 1
2424 | 5.1694 | 3.733 | 6.5224 | 4.5099 | 4.4653 | 1.4037 | 14.8161 | 17.5608 | 17.5608 | 0
2425 | 2.9881 | 3.7878 | 5.8183 | 4.8365 | 4.275 | 1.4365 | 13.0489 | 14.5178 | 14.5178 | 0
2426 | 5.2071 | 6.7389 | 4.9642 | 5.4779 | 5.4589 | 1.5102 | 18.934 | 17.1403 | 18.934 | 1
2427 | 3.7814 | 5.0767 | 4.6895 | 4.7707 | 4.9173 | 1.4915 | 15.1204 | 14.8797 | 15.1204 | 1
2428 | 4.797 | 4.6958 | 6.7242 | 4.8273 | 4.5981 | 2.305 | 16.6252 | 18.4244 | 18.4244 | 0
2429 | 4.3937 | 4.1311 | 6.0302 | 4.8075 | 5.2853 | 2.5079 | 15.8402 | 18.2171 | 18.2171 | 0
2430 | 4.4667 | 5.8399 | 5.7405 | 5.4999 | 4.4102 | 2.0433 | 17.8498 | 16.6606 | 17.8498 | 1
2431 | 3.2907 | 4.1632 | 5.9 | 5.4324 | 5.4957 | 1.3799 | 14.2661 | 16.0663 | 16.0663 | 0
2432 | 3.8967 | 5.4068 | 6.9097 | 5.4082 | 3.8022 | 1.506 | 16.2177 | 16.1147 | 16.2177 | 1
2433 | 5.1479 | 6.2547 | 5.8847 | 5.031 | 3.8638 | 2.2657 | 18.6993 | 17.1621 | 18.6993 | 1
2434 | 5.1974 | 5.5356 | 4.5855 | 5.2752 | 4.015 | 1.9479 | 17.956 | 15.7458 | 17.956 | 1
2435 | 4.8363 | 6.167 | 5.6694 | 7.1198 | 3.6602 | 2.1044 | 20.2275 | 16.2703 | 20.2275 | 1
2436 | 3.9529 | 6.0688 | 7.0574 | 4.3585 | 4.6014 | 2.0767 | 16.4569 | 17.6883 | 17.6883 | 0
2437 | 4.622 | 7.2218 | 6.8595 | 5.0395 | 4.5547 | 2.564 | 19.4472 | 18.6001 | 19.4472 | 1
2438 | 3.5332 | 5.1472 | 6.1424 | 5.1455 | 5.4202 | 1.6106 | 15.4365 | 16.7064 | 16.7064 | 0
2439 | 4.8013 | 7.4586 | 6.6795 | 5.5297 | 3.9354 | 1.7512 | 19.5408 | 17.1675 | 19.5408 | 1
2440 | 3.426 | 6.2064 | 7.2142 | 7.5974 | 4.5029 | 1.267 | 18.4967 | 16.4102 | 18.4967 | 1
2441 | 3.3171 | 4.2949 | 6.5623 | 4.807 | 3.8104 | 2.423 | 14.842 | 16.1127 | 16.1127 | 0
2442 | 3.5283 | 6.5039 | 6.4428 | 5.4638 | 3.855 | 2.0179 | 17.5139 | 15.8441 | 17.5139 | 1
2443 | 3.7937 | 6.4631 | 4.5502 | 5.7413 | 4.1093 | 2.0274 | 18.0255 | 14.4806 | 18.0255 | 1
2444 | 3.4406 | 4.4419 | 5.5959 | 6.0302 | 3.7979 | 2.231 | 16.1437 | 15.0654 | 16.1437 | 1
2445 | 3.4381 | 5.4126 | 6.6727 | 6.4705 | 4.1239 | 2.2306 | 17.5517 | 16.4653 | 17.5517 | 1
2446 | 4.7382 | 5.7267 | 3.7482 | 4.821 | 5.576 | 1.8264 | 17.1122 | 15.8888 | 17.1122 | 1
2447 | 4.042 | 5.7934 | 6.2223 | 5.3378 | 5.1605 | 2.0859 | 17.2591 | 17.5108 | 17.5108 | 0
2448 | 3.6539 | 4.3978 | 6.2607 | 5.9919 | 5.8934 | 1.6181 | 15.6617 | 17.426 | 17.426 | 0
2449 | 3.1458 | 4.6528 | 3.5078 | 5.7107 | 5.2834 | 2.7079 | 16.2171 | 14.6448 | 16.2171 | 1
2450 | 3.657 | 5.2025 | 5.3329 | 4.7501 | 3.8604 | 1.91 | 15.5196 | 14.7603 | 15.5196 | 1
2451 | 2.7268 | 5.0964 | 4.1381 | 5.128 | 4.0327 | 2.2408 | 15.192 | 13.1385 | 15.192 | 1
2452 | 3.1092 | 5.2125 | 5.7331 | 5.1321 | 4.5689 | 1.7949 | 15.2488 | 15.2062 | 15.2488 | 1
2453 | 3.0904 | 4.3367 | 7.5418 | 5.1 | 3.4494 | 2.1608 | 14.6879 | 16.2424 | 16.2424 | 0
2454 | 3.8102 | 5.2553 | 6.7081 | 5.4054 | 3.8437 | 1.9812 | 16.4521 | 16.3433 | 16.4521 | 1
2455 | 3.7206 | 7.1542 | 3.9812 | 5.7906 | 4.0334 | 1.6865 | 18.3519 | 13.4217 | 18.3519 | 1
2456 | 5.5701 | 3.2907 | 6.3757 | 5.1906 | 5.1779 | 2.5964 | 16.6478 | 19.7201 | 19.7201 | 0
2457 | 4.4893 | 5.3864 | 5.7132 | 4.9117 | 3.8726 | 2.6347 | 17.4221 | 16.7097 | 17.4221 | 1
2458 | 3.4708 | 4.3381 | 6.9702 | 4.7668 | 3.1214 | 2.4802 | 15.0558 | 16.0426 | 16.0426 | 0
2459 | 2.397 | 4.9555 | 6.4614 | 4.7329 | 4.0429 | 2.0122 | 14.0977 | 14.9136 | 14.9136 | 0
2460 | 3.7604 | 7.4766 | 5.6526 | 4.7286 | 5.1684 | 2.7768 | 18.7422 | 17.3581 | 18.7422 | 1
2461 | 2.9207 | 5.1996 | 6.7247 | 6.4328 | 4.8923 | 1.8989 | 16.4519 | 16.4366 | 16.4519 | 1
2462 | 5.0992 | 6.9051 | 7.5437 | 6.5472 | 5.2097 | 1.2886 | 19.8401 | 19.1412 | 19.8401 | 1
2463 | 4.0027 | 4.9719 | 3.5495 | 5.0436 | 4.9154 | 1.8614 | 15.8796 | 14.3291 | 15.8796 | 1
2464 | 5.0713 | 4.6982 | 4.432 | 5.9204 | 4.5697 | 2.4464 | 18.1363 | 16.5194 | 18.1363 | 1
2465 | 4.6619 | 4.0297 | 6.3069 | 5.7027 | 5.0904 | 2.7167 | 17.1111 | 18.7759 | 18.7759 | 0
2466 | 3.1892 | 4.0841 | 5.9133 | 4.662 | 3.645 | 1.7622 | 13.6974 | 14.5096 | 14.5096 | 0
2467 | 2.9528 | 4.7308 | 5.9115 | 4.8199 | 4.9823 | 1.6525 | 14.1561 | 15.4992 | 15.4992 | 0
2468 | 4.5202 | 5.2751 | 4.4015 | 4.7795 | 5.1118 | 2.5321 | 17.107 | 16.5657 | 17.107 | 1
2469 | 3.0462 | 5.5607 | 4.6983 | 4.8809 | 5.0706 | 1.9682 | 15.4559 | 14.7833 | 15.4559 | 1
2470 | 5.0584 | 5.0754 | 4.6761 | 4.8797 | 4.5703 | 2.4922 | 17.5057 | 16.797 | 17.5057 | 1
2471 | 3.6512 | 4.3482 | 4.8577 | 4.3636 | 3.9174 | 2.0598 | 14.4227 | 14.486 | 14.486 | 0
2472 | 4.789 | 5.7649 | 5.4394 | 5.4651 | 3.2287 | 1.5758 | 17.5949 | 15.0329 | 17.5949 | 1
2473 | 4.3062 | 4.0507 | 2.4858 | 4.6103 | 4.2675 | 1.8433 | 14.8105 | 12.9028 | 14.8105 | 1
2474 | 3.7923 | 4.5801 | 6.0533 | 4.6358 | 4.1127 | 1.6792 | 14.6873 | 15.6375 | 15.6375 | 0
2475 | 2.2892 | 3.9893 | 4.4257 | 5.0038 | 3.2809 | 2.4668 | 13.7491 | 12.4626 | 13.7491 | 1
2476 | 2.6591 | 3.9734 | 4.349 | 5.5754 | 4.93 | 2.2813 | 14.4891 | 14.2195 | 14.4891 | 1
2477 | 4.6064 | 6.2944 | 7.1818 | 4.7617 | 3.6635 | 2.2861 | 17.9486 | 17.7378 | 17.9486 | 1
2478 | 4.7181 | 4.0938 | 4.5525 | 5.8953 | 3.5052 | 2.4098 | 17.117 | 15.1856 | 17.117 | 1
2479 | 4.7656 | 3.5175 | 5.8173 | 5.3341 | 3.4194 | 1.7312 | 15.3484 | 15.7335 | 15.7335 | 0
2480 | 4.4398 | 4.189 | 5.5522 | 6.419 | 3.6701 | 2.0111 | 17.0589 | 15.6732 | 17.0589 | 1
2481 | 2.5428 | 3.825 | 5.7939 | 4.8371 | 4.1851 | 1.3552 | 12.5601 | 13.877 | 13.877 | 0
2482 | 5.0906 | 7.2102 | 5.0995 | 6.0054 | 4.0234 | 2.722 | 21.0282 | 16.9355 | 21.0282 | 1
2483 | 2.5413 | 7.3715 | 6.4765 | 5.7036 | 4.2696 | 2.1646 | 17.781 | 15.4519 | 17.781 | 1
2484 | 2.6153 | 7.4158 | 7.3737 | 4.6308 | 4.461 | 2.825 | 17.487 | 17.2751 | 17.487 | 1
2485 | 2.4128 | 5.554 | 5.3848 | 4.6861 | 5.9144 | 1.4951 | 14.148 | 15.2071 | 15.2071 | 0
2486 | 3.7333 | 6.2281 | 3.0863 | 6.6768 | 4.465 | 2.1452 | 18.7834 | 13.4299 | 18.7834 | 1
2487 | 5.285 | 3.8361 | 7.0173 | 4.2931 | 4.8738 | 1.9171 | 15.3313 | 19.0932 | 19.0932 | 0
2488 | 4.9145 | 4.5207 | 5.3919 | 4.7919 | 4.5317 | 2.4912 | 16.7183 | 17.3293 | 17.3293 | 0
2489 | 4.6956 | 3.4661 | 6.5704 | 4.5645 | 3.0957 | 1.7055 | 14.4316 | 16.0672 | 16.0672 | 0
2490 | 3.4898 | 7.1838 | 6.2087 | 5.8764 | 4.8244 | 2.4464 | 18.9964 | 16.9694 | 18.9964 | 1
2491 | 3.649 | 6.0243 | 6.071 | 4.1162 | 4.5731 | 1.4545 | 15.244 | 15.7476 | 15.7476 | 0
2492 | 4.8175 | 5.3385 | 5.8454 | 5.6145 | 4.1742 | 1.9881 | 17.7586 | 16.8252 | 17.7586 | 1
2493 | 2.9346 | 6.7323 | 5.2633 | 4.3213 | 5.3923 | 2.0858 | 16.0739 | 15.676 | 16.0739 | 1
2494 | 3.2824 | 4.4548 | 6.7713 | 4.9103 | 5.3766 | 1.9141 | 14.5617 | 17.3445 | 17.3445 | 0
2495 | 2.9032 | 5.2932 | 4.7011 | 4.232 | 3.3599 | 2.1108 | 14.5393 | 13.0751 | 14.5393 | 1
2496 | 4.5796 | 5.4971 | 3.4889 | 4.8689 | 3.6069 | 2.4261 | 17.3717 | 14.1016 | 17.3717 | 1
2497 | 3.8828 | 4.1364 | 5.1962 | 4.181 | 4.8006 | 1.4945 | 13.6947 | 15.374 | 15.374 | 0
2498 | 5.0973 | 4.8101 | 7.9005 | 4.9637 | 3.297 | 1.7016 | 16.5728 | 17.9965 | 17.9965 | 0
2499 | 4.172 | 7.0353 | 6.9274 | 6.7733 | 3.8737 | 2.7529 | 20.7334 | 17.726 | 20.7334 | 1
2500 | 2.6676 | 6.2772 | 4.7857 | 5.7188 | 3.7399 | 1.7986 | 16.4623 | 12.9918 | 16.4623 | 1
2501 | 3.7221 | 5.1184 | 5.8919 | 5.9251 | 5.1711 | 2.2383 | 17.0039 | 17.0233 | 17.0233 | 0
2502 | 3.5659 | 4.4735 | 4.0404 | 6.3517 | 4.0699 | 1.264 | 15.6551 | 12.9403 | 15.6551 | 1
2503 | 4.3906 | 4.0748 | 4.9357 | 5.319 | 4.2843 | 2.6853 | 16.4698 | 16.296 | 16.4698 | 1
2504 | 4.0291 | 6.5602 | 6.2685 | 4.7349 | 5.5232 | 2.1894 | 17.5137 | 18.0103 | 18.0103 | 0
2505 | 3.1902 | 3.8908 | 6.1917 | 5.8238 | 3.5302 | 1.5886 | 14.4933 | 14.5007 | 14.5007 | 0
2506 | 3.0581 | 4.6484 | 5.942 | 5.35 | 3.4384 | 2.077 | 15.1334 | 14.5154 | 15.1334 | 1
2507 | 3.6053 | 6.9355 | 4.903 | 5.7832 | 3.6477 | 1.4834 | 17.8074 | 13.6394 | 17.8074 | 1
2508 | 4.0616 | 6.9209 | 4.7111 | 5.2365 | 5.6787 | 2.1225 | 18.3416 | 16.5739 | 18.3416 | 1
2509 | 4.6625 | 6.1855 | 6.6667 | 4.6072 | 3.5026 | 1.8761 | 17.3314 | 16.708 | 17.3314 | 1
2510 | 3.6103 | 4.6058 | 4.4018 | 5.0471 | 4.8493 | 1.9012 | 15.1644 | 14.7626 | 15.1644 | 1
2511 | 3.5309 | 4.0503 | 5.4941 | 6.0622 | 3.6749 | 1.2931 | 14.9365 | 13.993 | 14.9365 | 1
2512 | 4.8071 | 3.5132 | 4.7204 | 6.0228 | 5.4004 | 1.924 | 16.2671 | 16.8519 | 16.8519 | 0
2513 | 3.5594 | 6.5585 | 4.145 | 4.7537 | 4.1568 | 2.2724 | 17.1441 | 14.1337 | 17.1441 | 1
2514 | 3.7631 | 3.8763 | 6.6337 | 4.4317 | 3.1832 | 2.4464 | 14.5175 | 16.0264 | 16.0264 | 0
2515 | 4.492 | 7.2188 | 4.6465 | 5.6278 | 4.4555 | 1.8952 | 19.2337 | 15.4892 | 19.2337 | 1
2516 | 4.4231 | 3.4045 | 7.5792 | 5.3682 | 4.1117 | 1.4293 | 14.6251 | 17.5434 | 17.5434 | 0
2517 | 3.7001 | 3.9233 | 3.5197 | 4.7845 | 3.5695 | 1.8698 | 14.2777 | 12.6591 | 14.2777 | 1
2518 | 5.0782 | 5.5068 | 6.8706 | 5.6578 | 4.8989 | 2.1708 | 18.4136 | 19.0184 | 19.0184 | 0
2519 | 4.3862 | 4.7643 | 3.5903 | 6.27 | 4.8852 | 1.5986 | 17.0191 | 14.4604 | 17.0191 | 1
2520 | 3.7291 | 4.4972 | 3.3473 | 4.2675 | 5.2515 | 1.9109 | 14.4047 | 14.2389 | 14.4047 | 1
2521 | 4.3514 | 7.0137 | 4.3571 | 5.3719 | 3.334 | 2.1018 | 18.8388 | 14.1442 | 18.8388 | 1
2522 | 4.3428 | 3.4138 | 5.3438 | 5.4921 | 4.3767 | 2.1528 | 15.4015 | 16.2161 | 16.2161 | 0
2523 | 4.4675 | 5.7901 | 5.8696 | 5.7097 | 3.9554 | 2.0403 | 18.0076 | 16.3328 | 18.0076 | 1
2524 | 5.2547 | 4.4974 | 6.568 | 6.1778 | 3.4397 | 2.4955 | 18.4254 | 17.7579 | 18.4254 | 1
2525 | 2.5655 | 5.3784 | 5.0637 | 4.2871 | 4.5841 | 2.2156 | 14.4467 | 14.429 | 14.4467 | 1
2526 | 3.3285 | 4.9272 | 5.7443 | 4.6045 | 3.509 | 2.5652 | 15.4254 | 15.147 | 15.4254 | 1
2527 | 3.3903 | 5.6585 | 4.6799 | 5.9606 | 4.2561 | 1.6584 | 16.6678 | 13.9847 | 16.6678 | 1
2528 | 4.3626 | 4.1029 | 6.4414 | 7.2794 | 3.7267 | 2.0625 | 17.8075 | 16.5932 | 17.8075 | 1
2529 | 4.6634 | 5.8314 | 5.0331 | 4.8741 | 3.5484 | 2.0835 | 17.4524 | 15.3284 | 17.4524 | 1
2530 | 4.8029 | 6.7163 | 6.1015 | 6.1927 | 3.6539 | 2.3199 | 20.0318 | 16.8781 | 20.0318 | 1
2531 | 4.0674 | 7.8181 | 4.0109 | 5.2518 | 5.1561 | 1.2517 | 18.3891 | 14.4862 | 18.3891 | 1
2532 | 4.631 | 6.0476 | 5.2914 | 4.7829 | 3.4443 | 1.7149 | 17.1765 | 15.0816 | 17.1765 | 1
2533 | 2.6842 | 3.7011 | 4.492 | 4.8827 | 3.428 | 2.2637 | 13.5317 | 12.8678 | 13.5317 | 1
2534 | 3.7649 | 3.6707 | 6.9375 | 5.8225 | 4.6542 | 2.6281 | 15.8862 | 17.9847 | 17.9847 | 0
2535 | 3.6795 | 4.4967 | 5.1168 | 6.2074 | 4.7611 | 1.7944 | 16.178 | 15.3517 | 16.178 | 1
2536 | 4.0763 | 4.9696 | 6.0709 | 5.3944 | 3.4269 | 1.9073 | 16.3476 | 15.4814 | 16.3476 | 1
2537 | 4.5046 | 5.2609 | 5.5828 | 4.5507 | 4.7635 | 2.6196 | 16.9359 | 17.4705 | 17.4705 | 0
2538 | 3.0105 | 3.6089 | 6.2831 | 4.5706 | 4.2521 | 1.9111 | 13.1012 | 15.4568 | 15.4568 | 0
2539 | 4.7817 | 5.3167 | 4.5378 | 5.6987 | 5.5398 | 2.331 | 18.1281 | 17.1902 | 18.1281 | 1
2540 | 4.2494 | 5.5487 | 6.4594 | 4.6888 | 4.2819 | 2.0831 | 16.5699 | 17.0738 | 17.0738 | 0
2541 | 4.0572 | 3.7785 | 4.3154 | 5.4416 | 3.8687 | 1.8651 | 15.1423 | 14.1065 | 15.1423 | 1
2542 | 5.3405 | 6.3373 | 6.7463 | 4.9075 | 3.9113 | 1.9358 | 18.521 | 17.9339 | 18.521 | 1
2543 | 3.9456 | 6.0446 | 7.0602 | 6.6548 | 4.5794 | 2.4175 | 19.0625 | 18.0027 | 19.0625 | 1
2544 | 3.1556 | 5.3072 | 5.3124 | 5.2257 | 4.2826 | 1.9884 | 15.6769 | 14.7389 | 15.6769 | 1
2545 | 3.6855 | 6.9188 | 5.243 | 4.9936 | 3.4523 | 2.2969 | 17.8949 | 14.6778 | 17.8949 | 1
2546 | 3.1937 | 7.5032 | 6.9904 | 5.4066 | 3.2805 | 2.6821 | 18.7857 | 16.1467 | 18.7857 | 1
2547 | 4.2767 | 4.002 | 6.0163 | 4.9352 | 3.7283 | 2.4259 | 15.6399 | 16.4472 | 16.4472 | 0
2548 | 3.298 | 6.1172 | 5.6743 | 4.9997 | 3.3643 | 1.923 | 16.3379 | 14.2595 | 16.3379 | 1
2549 | 3.5896 | 5.3912 | 4.1351 | 4.7217 | 4.6727 | 2.2613 | 15.9638 | 14.6587 | 15.9638 | 1
2550 | 3.1703 | 6.997 | 5.2366 | 5.0586 | 4.3059 | 2.41 | 17.6358 | 15.1228 | 17.6358 | 1
2551 | 2.8956 | 5.1255 | 7.2263 | 5.7238 | 4.5632 | 2.6705 | 16.4154 | 17.3555 | 17.3555 | 0
2552 | 4.0143 | 5.067 | 5.4916 | 5.9138 | 4.1063 | 2.1515 | 17.1466 | 15.7638 | 17.1466 | 1
2553 | 3.1851 | 6.0052 | 4.9191 | 5.1078 | 3.7418 | 2.2603 | 16.5585 | 14.1064 | 16.5585 | 1
2554 | 3.7021 | 6.864 | 5.2856 | 4.7669 | 4.8222 | 2.5263 | 17.8593 | 16.3362 | 17.8593 | 1
2555 | 4.4599 | 5.2303 | 6.5344 | 4.7776 | 3.2012 | 2.1925 | 16.6604 | 16.3881 | 16.6604 | 1
2556 | 4.4617 | 4.5708 | 7.365 | 5.696 | 4.9181 | 2.4745 | 17.2031 | 19.2194 | 19.2194 | 0
2557 | 3.7409 | 5.1767 | 6.6717 | 6.9578 | 4.111 | 1.9402 | 17.8156 | 16.4639 | 17.8156 | 1
2558 | 4.6727 | 4.0925 | 7.1628 | 5.0805 | 4.2049 | 2.3862 | 16.2318 | 18.4266 | 18.4266 | 0
2559 | 3.4352 | 3.7522 | 5.1115 | 6.1663 | 4.2572 | 1.6617 | 15.0153 | 14.4655 | 15.0153 | 1
2560 | 3.9391 | 5.6993 | 7.018 | 5.1511 | 4.1928 | 2.0995 | 16.8891 | 17.2495 | 17.2495 | 0
2561 | 4.8858 | 4.7604 | 5.9058 | 5.7788 | 4.0509 | 1.6196 | 17.0446 | 16.4621 | 17.0446 | 1
2562 | 5.0135 | 6.6968 | 7.3673 | 4.4515 | 3.3489 | 2.4109 | 18.5727 | 18.1406 | 18.5727 | 1
2563 | 5.1833 | 4.4802 | 7.5253 | 5.7227 | 4.5155 | 2.0647 | 17.451 | 19.2888 | 19.2888 | 0
2564 | 3.2717 | 4.3386 | 5.7959 | 6.6444 | 3.7586 | 2.0357 | 16.2904 | 14.8619 | 16.2904 | 1
2565 | 2.8007 | 5.1114 | 7.1037 | 4.5043 | 4.3601 | 1.9595 | 14.376 | 16.224 | 16.224 | 0
2566 | 3.5418 | 4.8143 | 7.4152 | 4.8128 | 4.9699 | 1.5178 | 14.6867 | 17.4447 | 17.4447 | 0
2567 | 3.9491 | 4.3961 | 5.6175 | 4.912 | 3.7942 | 1.2801 | 14.5373 | 14.6409 | 14.6409 | 0
2568 | 3.7511 | 5.3219 | 4.9093 | 5.4792 | 4.6152 | 1.5955 | 16.1476 | 14.8711 | 16.1476 | 1
2569 | 4.8547 | 4.5533 | 5.5179 | 5.1012 | 3.682 | 1.5252 | 16.0344 | 15.5797 | 16.0344 | 1
2570 | 4.4224 | 4.6009 | 7.9099 | 5.2652 | 4.7613 | 1.8927 | 16.1812 | 18.9864 | 18.9864 | 0
2571 | 2.2567 | 4.9902 | 7.7809 | 4.6583 | 4.2767 | 2.5385 | 14.4436 | 16.8527 | 16.8527 | 0
2572 | 2.4983 | 4.7315 | 5.6981 | 4.6877 | 3.6256 | 1.4054 | 13.3229 | 13.2274 | 13.3229 | 1
2573 | 4.1969 | 3.9723 | 6.3534 | 5.41 | 4.2967 | 2.1696 | 15.7489 | 17.0166 | 17.0166 | 0
2574 | 4.8909 | 4.2971 | 5.2157 | 4.8914 | 4.5462 | 1.5053 | 15.5847 | 16.1582 | 16.1582 | 0
2575 | 4.4982 | 5.8353 | 6.4724 | 5.3444 | 5.1193 | 2.6909 | 18.3688 | 18.7808 | 18.7808 | 0
2576 | 4.4845 | 4.7811 | 6.6132 | 5.6259 | 4.6916 | 1.6514 | 16.5428 | 17.4407 | 17.4407 | 0
2577 | 3.4123 | 4.7073 | 5.0956 | 4.7922 | 4.422 | 1.7461 | 14.6579 | 14.676 | 14.676 | 0
2578 | 3.6452 | 6.4041 | 5.6343 | 5.4032 | 4.0653 | 1.4601 | 16.9126 | 14.8049 | 16.9126 | 1
2579 | 4.0071 | 4.9172 | 6.1081 | 5.5679 | 5.6742 | 2.3017 | 16.7939 | 18.0911 | 18.0911 | 0
2580 | 5.0761 | 6.946 | 6.76 | 6.2994 | 4.7998 | 1.5291 | 19.8506 | 18.1649 | 19.8506 | 1
2581 | 3.9477 | 4.5699 | 6.9929 | 6.6568 | 4.8009 | 1.3074 | 16.4819 | 17.049 | 17.049 | 0
2582 | 4.8477 | 5.0986 | 6.7621 | 5.1463 | 5.1093 | 2.01 | 17.1027 | 18.7292 | 18.7292 | 0
2583 | 3.9712 | 5.4782 | 6.3771 | 6.8354 | 4.5675 | 2.4068 | 18.6915 | 17.3225 | 18.6915 | 1
2584 | 4.0067 | 6.7952 | 3.7494 | 4.8106 | 3.9758 | 2.2212 | 17.8335 | 13.953 | 17.8335 | 1
2585 | 5.1251 | 5.5908 | 4.3235 | 5.7169 | 4.5869 | 1.53 | 17.9628 | 15.5655 | 17.9628 | 1
2586 | 4.466 | 4.029 | 4.7615 | 4.12 | 4.1513 | 2.4826 | 15.0975 | 15.8615 | 15.8615 | 0
2587 | 4.3685 | 4.8099 | 5.4894 | 5.3926 | 4.3365 | 2.0126 | 16.5836 | 16.207 | 16.5836 | 1
2588 | 3.2321 | 5.015 | 3.6868 | 5.6028 | 4.3897 | 1.8278 | 15.6777 | 13.1364 | 15.6777 | 1
2589 | 3.8554 | 4.4471 | 6.0892 | 4.1428 | 4.24 | 2.374 | 14.8193 | 16.5586 | 16.5586 | 0
2590 | 3.4597 | 5.6159 | 4.2807 | 4.5411 | 3.4079 | 1.7974 | 15.4141 | 12.9457 | 15.4141 | 1
2591 | 3.6552 | 6.4406 | 6.1488 | 4.7792 | 5.1558 | 2.1992 | 17.0743 | 17.1589 | 17.1589 | 0
2592 | 4.8678 | 5.6387 | 6.5569 | 7.1771 | 3.9514 | 2.5745 | 20.2581 | 17.9506 | 20.2581 | 1
2593 | 3.3293 | 5.3411 | 7.4803 | 4.8143 | 3.7879 | 2.1572 | 15.6418 | 16.7547 | 16.7547 | 0
2594 | 3.485 | 5.7675 | 3.7034 | 4.0381 | 4.887 | 2.1374 | 15.428 | 14.2128 | 15.428 | 1
2595 | 4.2351 | 5.3689 | 5.9965 | 5.2406 | 4.2015 | 1.4548 | 16.2995 | 15.888 | 16.2995 | 1
2596 | 5.1976 | 4.695 | 4.2562 | 6.6618 | 4.164 | 2.1611 | 18.7155 | 15.7789 | 18.7155 | 1
2597 | 3.1728 | 7.6381 | 6.3165 | 4.2 | 3.8362 | 1.8156 | 16.8265 | 15.1411 | 16.8265 | 1
2598 | 2.5984 | 6.6616 | 5.3045 | 4.6134 | 4.8387 | 1.4382 | 15.3116 | 14.1797 | 15.3116 | 1
2599 | 2.8644 | 4.5935 | 6.9145 | 5.3007 | 4.5944 | 1.9968 | 14.7554 | 16.3702 | 16.3702 | 0
2600 | 4.345 | 4.4561 | 5.5554 | 5.5033 | 3.6472 | 1.4045 | 15.709 | 14.9521 | 15.709 | 1
2601 | 3.6309 | 5.7993 | 5.5724 | 4.8856 | 4.0414 | 2.2204 | 16.5361 | 15.4651 | 16.5361 | 1
2602 | 3.8183 | 3.9445 | 5.1938 | 4.9721 | 6.1439 | 2.0201 | 14.7549 | 17.1761 | 17.1761 | 0
2603 | 5.0428 | 6.5264 | 5.813 | 5.2291 | 4.6918 | 2.7056 | 19.504 | 18.2532 | 19.504 | 1
2604 | 3.9484 | 5.8944 | 6.9025 | 5.2056 | 3.9639 | 2.5104 | 17.5587 | 17.3251 | 17.5587 | 1
2605 | 3.4035 | 6.3826 | 6.1729 | 5.4499 | 4.8181 | 2.2685 | 17.5045 | 16.663 | 17.5045 | 1
2606 | 4.6359 | 3.7983 | 3.6126 | 5.7167 | 4.9765 | 1.6691 | 15.8199 | 14.8941 | 15.8199 | 1
2607 | 2.8702 | 5.4644 | 5.3337 | 4.74 | 3.7713 | 1.9703 | 15.0449 | 13.9455 | 15.0449 | 1
2608 | 4.3757 | 5.091 | 7.1904 | 6.1684 | 4.5265 | 1.6239 | 17.259 | 17.7164 | 17.7164 | 0
2609 | 4.1693 | 4.07 | 5.7911 | 6.1965 | 4.8501 | 1.9068 | 16.3426 | 16.7173 | 16.7173 | 0
2610 | 2.278 | 5.3279 | 6.0907 | 5.3977 | 5.6364 | 1.4118 | 14.4153 | 15.4168 | 15.4168 | 0
2611 | 3.8327 | 6.7873 | 3.8569 | 4.4569 | 4.0079 | 1.4551 | 16.532 | 13.1526 | 16.532 | 1
2612 | 4.1861 | 6.5252 | 4.9319 | 4.5919 | 5.9828 | 1.9272 | 17.2303 | 17.0281 | 17.2303 | 1
2613 | 5.1198 | 6.2024 | 6.9809 | 4.7877 | 4.0931 | 1.5825 | 17.6924 | 17.7764 | 17.7764 | 0
2614 | 5.5216 | 4.9471 | 5.6311 | 5.6755 | 3.8889 | 2.4928 | 18.637 | 17.5345 | 18.637 | 1
2615 | 4.7965 | 5.2582 | 4.8394 | 6.0061 | 3.7512 | 2.3385 | 18.3993 | 15.7255 | 18.3993 | 1
2616 | 3.2535 | 6.7279 | 7.0084 | 5.6183 | 4.6365 | 2.4785 | 18.0782 | 17.3768 | 18.0782 | 1
2617 | 4.12 | 6.6605 | 5.5671 | 4.4281 | 5.2904 | 2.3821 | 17.5907 | 17.3596 | 17.5907 | 1
2618 | 5.0564 | 6.3037 | 5.6342 | 4.3177 | 3.4236 | 2.0202 | 17.6979 | 16.1344 | 17.6979 | 1
2619 | 3.9359 | 5.7332 | 4.0673 | 5.1468 | 3.4914 | 1.8874 | 16.7032 | 13.3819 | 16.7032 | 1
2620 | 3.5547 | 4.4203 | 5.6162 | 4.9274 | 3.6307 | 2.1372 | 15.0396 | 14.9388 | 15.0396 | 1
2621 | 3.2162 | 5.5897 | 5.8217 | 5.09 | 3.6542 | 1.7954 | 15.6913 | 14.4876 | 15.6913 | 1
2622 | 4.4003 | 5.7616 | 5.8653 | 5.4277 | 3.1972 | 2.1742 | 17.7638 | 15.637 | 17.7638 | 1
2623 | 3.8989 | 7.2383 | 5.9857 | 4.8461 | 3.2949 | 1.9843 | 17.9676 | 15.1638 | 17.9676 | 1
2624 | 3.8252 | 5.9682 | 7.3126 | 4.8801 | 4.555 | 1.6174 | 16.2909 | 17.3101 | 17.3101 | 0
2625 | 2.4298 | 6.9698 | 7.4291 | 6.4384 | 4.2714 | 1.9282 | 17.7661 | 16.0584 | 17.7661 | 1
2626 | 5.2146 | 4.8136 | 4.8198 | 4.4193 | 4.1211 | 2.465 | 16.9125 | 16.6205 | 16.9125 | 1
2627 | 4.0881 | 7.0591 | 4.5285 | 5.8332 | 4.3717 | 1.4746 | 18.455 | 14.4628 | 18.455 | 1
2628 | 5.3314 | 4.6324 | 4.4448 | 5.9921 | 4.2918 | 2.1929 | 18.1488 | 16.2609 | 18.1488 | 1
2629 | 4.1358 | 6.1887 | 4.8475 | 5.7836 | 4.3228 | 1.8511 | 17.9592 | 15.1573 | 17.9592 | 1
2630 | 4.0623 | 7.2386 | 6.2372 | 5.2258 | 3.3941 | 2.2637 | 18.7904 | 15.9573 | 18.7904 | 1
2631 | 5.1118 | 5.4166 | 5.1619 | 5.6603 | 4.1827 | 1.5452 | 17.7339 | 16.0016 | 17.7339 | 1
2632 | 3.9259 | 6.4361 | 6.1139 | 5.9013 | 3.8705 | 2.8131 | 19.0764 | 16.7235 | 19.0764 | 1
2633 | 3.6456 | 5.1842 | 6.2951 | 5.7442 | 4.9446 | 1.7925 | 16.3665 | 16.6778 | 16.6778 | 0
2634 | 3.5327 | 5.6634 | 6.708 | 7.2135 | 4.8427 | 1.7796 | 18.1892 | 16.863 | 18.1892 | 1
2635 | 4.4386 | 5.8669 | 5.1562 | 5.0455 | 4.2787 | 2.5076 | 17.8585 | 16.381 | 17.8585 | 1
2636 | 3.5927 | 4.1631 | 6.5613 | 4.391 | 3.7313 | 2.2121 | 14.3588 | 16.0974 | 16.0974 | 0
2637 | 2.8172 | 5.1414 | 4.66 | 4.9771 | 4.1185 | 1.5253 | 14.461 | 13.1211 | 14.461 | 1
2638 | 3.1766 | 5.6232 | 7.4426 | 6.1652 | 3.2764 | 1.8477 | 16.8126 | 15.7433 | 16.8126 | 1
2639 | 4.9706 | 3.7448 | 5.0366 | 5.2401 | 4.0466 | 1.9194 | 15.8749 | 15.9732 | 15.9732 | 0
2640 | 3.9393 | 4.6376 | 3.9605 | 6.9992 | 5.0498 | 2.432 | 18.0081 | 15.3816 | 18.0081 | 1
2641 | 4.2306 | 3.4254 | 6.4443 | 5.7437 | 3.9441 | 1.9826 | 15.3822 | 16.6016 | 16.6016 | 0
2642 | 3.2205 | 5.6454 | 6.2625 | 5.2421 | 6.4179 | 2.2043 | 16.3123 | 18.1053 | 18.1053 | 0
2643 | 4.1587 | 5.1294 | 4.9533 | 5.6866 | 5.9582 | 1.7824 | 16.7571 | 16.8526 | 16.8526 | 0
2644 | 5.2914 | 5.7796 | 4.2183 | 5.1365 | 3.5052 | 1.9371 | 18.1446 | 14.952 | 18.1446 | 1
2645 | 2.5823 | 5.8038 | 6.6555 | 5.3503 | 4.6733 | 1.5009 | 15.2374 | 15.412 | 15.412 | 0
2646 | 4.0843 | 5.6327 | 6.4964 | 4.7296 | 4.7352 | 1.9816 | 16.4283 | 17.2975 | 17.2975 | 0
2647 | 4.7635 | 6.3768 | 5.3636 | 4.3871 | 4.0343 | 2.0198 | 17.5472 | 16.1811 | 17.5472 | 1
2648 | 3.5894 | 6.7768 | 3.3464 | 4.2761 | 3.9363 | 1.7064 | 16.3488 | 12.5786 | 16.3488 | 1
2649 | 4.9528 | 3.5943 | 6.8811 | 5.5379 | 4.0542 | 1.7983 | 15.8833 | 17.6865 | 17.6865 | 0
2650 | 3.6573 | 5.3077 | 4.5269 | 5.555 | 4.0041 | 2.3279 | 16.8478 | 14.5162 | 16.8478 | 1
2651 | 3.9931 | 3.5768 | 3.4316 | 4.8901 | 5.5346 | 1.9676 | 14.4276 | 14.9269 | 14.9269 | 0
2652 | 4.386 | 3.7953 | 2.6518 | 4.437 | 4.848 | 2.2782 | 14.8966 | 14.1641 | 14.8966 | 1
2653 | 3.9874 | 5.1467 | 5.6213 | 6.2272 | 3.377 | 1.7014 | 17.0626 | 14.6871 | 17.0626 | 1
2654 | 4.1382 | 7.5307 | 7.5316 | 5.2548 | 3.8394 | 1.6411 | 18.5649 | 17.1503 | 18.5649 | 1
2655 | 4.8868 | 3.5925 | 7.5028 | 6.1433 | 3.6416 | 2.1401 | 16.7626 | 18.1713 | 18.1713 | 0
2656 | 5.1429 | 6.0025 | 7.1096 | 4.1646 | 5.1442 | 1.9374 | 17.2473 | 19.334 | 19.334 | 0
2657 | 4.4347 | 4.8892 | 5.1311 | 5.8363 | 4.4927 | 1.985 | 17.1453 | 16.0436 | 17.1453 | 1
2658 | 3.6288 | 5.4877 | 5.2589 | 4.4122 | 3.4008 | 2.5117 | 16.0403 | 14.8002 | 16.0403 | 1
2659 | 4.1925 | 4.6806 | 5.0986 | 5.4704 | 4.0733 | 1.333 | 15.6765 | 14.6975 | 15.6765 | 1
2660 | 4.8559 | 6.7276 | 5.5018 | 4.9693 | 4.6497 | 1.7397 | 18.2925 | 16.7472 | 18.2925 | 1
2661 | 3.4783 | 6.6451 | 5.392 | 6.6613 | 4.173 | 2.0408 | 18.8255 | 15.0841 | 18.8255 | 1
2662 | 4.7359 | 5.9676 | 4.8523 | 6.3298 | 3.4368 | 1.371 | 18.4043 | 14.396 | 18.4043 | 1
2663 | 4.0553 | 6.5962 | 7.0931 | 6.4587 | 4.0978 | 2.2789 | 19.3892 | 17.525 | 19.3892 | 1
2664 | 3.4498 | 4.6682 | 5.6138 | 4.7757 | 3.7501 | 1.8932 | 14.7869 | 14.7069 | 14.7869 | 1
2665 | 3.9968 | 6.1289 | 6.6538 | 5.3313 | 4.3322 | 1.318 | 16.775 | 16.3008 | 16.775 | 1
2666 | 3.5895 | 4.8325 | 7.2074 | 5.7004 | 3.9319 | 1.9587 | 16.0811 | 16.6874 | 16.6874 | 0
2667 | 4.2117 | 5.7184 | 5.3965 | 5.2489 | 4.2099 | 1.6455 | 16.8245 | 15.4636 | 16.8245 | 1
2668 | 4.7613 | 5.3173 | 7.2865 | 5.2624 | 3.9337 | 1.9506 | 17.2915 | 17.9321 | 17.9321 | 0
2669 | 4.7086 | 3.5746 | 4.6384 | 5.4238 | 4.275 | 2.0459 | 15.7529 | 15.6679 | 15.7529 | 1
2670 | 3.9136 | 5.9909 | 6.7036 | 5.2105 | 4.2499 | 1.6336 | 16.7486 | 16.5007 | 16.7486 | 1
2671 | 4.2112 | 4.956 | 5.0223 | 4.6522 | 3.6699 | 2.4043 | 16.2237 | 15.3078 | 16.2237 | 1
2672 | 5.2581 | 6.9808 | 5.8468 | 5.8657 | 5.5082 | 1.3512 | 19.4558 | 17.9643 | 19.4558 | 1
2673 | 5.2831 | 6.9379 | 5.169 | 5.3672 | 3.1114 | 2.2283 | 19.8164 | 15.7917 | 19.8164 | 1
2674 | 4.9247 | 4.9192 | 5.6362 | 5.9281 | 4.7436 | 1.9352 | 17.7072 | 17.2397 | 17.7072 | 1
2675 | 4.0236 | 4.1389 | 7.6322 | 5.5838 | 4.5797 | 2.2114 | 15.9576 | 18.4469 | 18.4469 | 0
2676 | 4.9016 | 7.0255 | 7.4576 | 4.5423 | 5.0895 | 1.3618 | 17.8312 | 18.8104 | 18.8104 | 0
2677 | 4.7174 | 6.6484 | 4.2206 | 6.2611 | 5.1838 | 1.6277 | 19.2546 | 15.7495 | 19.2546 | 1
2678 | 3.2804 | 3.712 | 3.287 | 5.6943 | 3.8287 | 1.2953 | 13.9819 | 11.6914 | 13.9819 | 1
2679 | 3.5126 | 4.9224 | 6.0912 | 6.199 | 4.3598 | 1.6365 | 16.2706 | 15.6001 | 16.2706 | 1
2680 | 5.0598 | 5.7522 | 4.7889 | 6.087 | 4.2405 | 1.5116 | 18.4106 | 15.6008 | 18.4106 | 1
2681 | 3.8387 | 4.4819 | 7.4001 | 4.5507 | 4.2191 | 1.1074 | 13.9787 | 16.5654 | 16.5654 | 0
2682 | 2.9837 | 6.5325 | 7.2084 | 4.956 | 5.071 | 1.9479 | 16.4201 | 17.211 | 17.211 | 0
2683 | 3.9336 | 3.1572 | 5.4008 | 5.4352 | 5.7184 | 2.4426 | 14.9687 | 17.4954 | 17.4954 | 0
2684 | 4.0504 | 5.1029 | 5.6591 | 4.3846 | 4.664 | 1.74 | 15.2779 | 16.1135 | 16.1135 | 0
2685 | 4.3795 | 5.9626 | 7.3051 | 5.3126 | 4.084 | 1.5037 | 17.1584 | 17.2723 | 17.2723 | 0
2686 | 3.1799 | 3.7355 | 6.2706 | 4.4401 | 3.9488 | 2.1004 | 13.4559 | 15.4997 | 15.4997 | 0
2687 | 2.8635 | 3.9957 | 4.4352 | 5.4309 | 5.5275 | 1.6608 | 13.9509 | 14.4869 | 14.4869 | 0
2688 | 2.6639 | 6.1949 | 3.4474 | 5.0151 | 4.0679 | 1.4572 | 15.3312 | 11.6364 | 15.3312 | 1
2689 | 3.7271 | 5.23 | 7.3255 | 4.5818 | 4.0889 | 1.5312 | 15.0701 | 16.6727 | 16.6727 | 0
2690 | 3.2732 | 6.2446 | 6.5442 | 5.656 | 3.9827 | 2.6491 | 17.8229 | 16.4493 | 17.8229 | 1
2691 | 4.1452 | 6.0789 | 6.4364 | 5.9909 | 3.9357 | 1.8529 | 18.0679 | 16.3702 | 18.0679 | 1
2692 | 4.3158 | 6.1752 | 4.6666 | 5.3789 | 4.2452 | 2.3964 | 18.2663 | 15.6239 | 18.2663 | 1
2693 | 2.9961 | 3.877 | 6.7769 | 6.538 | 3.5646 | 2.4312 | 15.8424 | 15.7687 | 15.8424 | 1
2694 | 3.4588 | 5.1141 | 7.0995 | 5.0041 | 3.8797 | 2.5288 | 16.1057 | 16.9668 | 16.9668 | 0
2695 | 5.0264 | 7.3447 | 4.7399 | 4.9709 | 4.6032 | 2.6026 | 19.9446 | 16.9721 | 19.9446 | 1
2696 | 2.7236 | 4.3871 | 6.7072 | 4.4478 | 5.0842 | 2.0067 | 13.5652 | 16.5217 | 16.5217 | 0
2697 | 2.8754 | 5.1627 | 6.0422 | 4.5583 | 4.0875 | 1.5884 | 14.1848 | 14.5935 | 14.5935 | 0
2698 | 3.9668 | 5.0511 | 7.2216 | 6.3935 | 4.6884 | 1.7973 | 17.2087 | 17.6741 | 17.6741 | 0
2699 | 3.1718 | 6.3701 | 4.9455 | 5.3992 | 4.5409 | 1.7929 | 16.734 | 14.4511 | 16.734 | 1
2700 | 4.8607 | 3.1005 | 5.933 | 6.2164 | 5.4816 | 2.1277 | 16.3052 | 18.403 | 18.403 | 0
2701 | 5.1515 | 5.0033 | 7.3575 | 5.4365 | 4.3208 | 1.7439 | 17.3352 | 18.5737 | 18.5737 | 0
2702 | 4.8037 | 6.021 | 5.5838 | 6.1781 | 4.1506 | 2.4351 | 19.4379 | 16.9733 | 19.4379 | 1
2703 | 4.4373 | 5.1194 | 3.3921 | 5.16 | 5.3566 | 1.7611 | 16.4778 | 14.9472 | 16.4778 | 1
2704 | 3.7574 | 4.5094 | 6.7563 | 4.1982 | 4.0123 | 2.6843 | 15.1493 | 17.2103 | 17.2103 | 0
2705 | 4.1668 | 4.6116 | 5.8505 | 5.429 | 4.2785 | 1.7781 | 15.9855 | 16.0739 | 16.0739 | 0
2706 | 4.2527 | 5.6712 | 5.2561 | 6.46 | 4.8088 | 2.7423 | 19.1262 | 17.0599 | 19.1262 | 1
2707 | 3.8193 | 3.8214 | 3.7212 | 5.8581 | 4.733 | 1.4581 | 14.9569 | 13.7316 | 14.9569 | 1
2708 | 3.5216 | 7.0973 | 6.3286 | 4.8666 | 5.5393 | 1.7836 | 17.2691 | 17.1731 | 17.2691 | 1
2709 | 2.3407 | 5.0881 | 4.2142 | 5.7086 | 4.7408 | 2.508 | 15.6454 | 13.8037 | 15.6454 | 1
2710 | 5.7047 | 4.4027 | 6.3825 | 5.8849 | 5.4814 | 1.835 | 17.8273 | 19.4037 | 19.4037 | 0
2711 | 4.9045 | 6.0851 | 4.4749 | 4.7415 | 4.3731 | 1.3626 | 17.0937 | 15.1151 | 17.0937 | 1
2712 | 4.0637 | 4.7427 | 7.5251 | 5.7102 | 4.2351 | 2.4414 | 16.9579 | 18.2652 | 18.2652 | 0
2713 | 4.8576 | 7.6548 | 6.647 | 4.6093 | 4.5729 | 2.4526 | 19.5743 | 18.53 | 19.5743 | 1
2714 | 2.683 | 4.6763 | 5.362 | 4.8166 | 4.7108 | 1.8584 | 14.0343 | 14.6141 | 14.6141 | 0
2715 | 4.0937 | 7.0229 | 5.9711 | 5.1384 | 3.6064 | 1.6567 | 17.9117 | 15.328 | 17.9117 | 1
2716 | 3.6244 | 4.315 | 5.9311 | 4.5407 | 4.44 | 2.3637 | 14.8437 | 16.3591 | 16.3591 | 0
2717 | 3.1988 | 5.4106 | 3.8184 | 5.7516 | 5.2772 | 2.1393 | 16.5002 | 14.4337 | 16.5002 | 1
2718 | 4.3936 | 5.4356 | 7.2268 | 5.6393 | 4.7963 | 2.1165 | 17.585 | 18.5333 | 18.5333 | 0
2719 | 3.0389 | 6.6446 | 3.9051 | 6.1418 | 4.4581 | 1.9703 | 17.7956 | 13.3724 | 17.7956 | 1
2720 | 4.3103 | 5.4982 | 4.8897 | 5.8133 | 4.3883 | 2.4987 | 18.1206 | 16.0871 | 18.1206 | 1
2721 | 4.0701 | 4.2144 | 6.6993 | 5.0836 | 5.7385 | 2.2283 | 15.5964 | 18.7362 | 18.7362 | 0
2722 | 3.6942 | 4.9802 | 6.9176 | 5.5826 | 3.5684 | 1.7139 | 15.9709 | 15.8941 | 15.9709 | 1
2723 | 5.2986 | 6.9315 | 4.1585 | 4.9651 | 3.8819 | 1.4311 | 18.6264 | 14.7702 | 18.6264 | 1
2724 | 4.407 | 5.7233 | 4.279 | 5.4749 | 3.3663 | 1.7054 | 17.3105 | 13.7577 | 17.3105 | 1
2725 | 4.2094 | 5.2422 | 5.2261 | 5.5401 | 3.9236 | 2.2473 | 17.239 | 15.6064 | 17.239 | 1
2726 | 4.9656 | 4.8911 | 6.3547 | 4.9542 | 3.8939 | 2.6038 | 17.4146 | 17.818 | 17.818 | 0
2727 | 2.5212 | 5.9981 | 7.6796 | 5.3092 | 4.4176 | 1.7398 | 15.5683 | 16.3582 | 16.3582 | 0
2728 | 2.9399 | 6.7791 | 4.4846 | 6.2206 | 3.2145 | 2.6577 | 18.5973 | 13.2966 | 18.5973 | 1
2729 | 3.8693 | 5.2582 | 6.4435 | 5.5527 | 5.2049 | 1.7678 | 16.448 | 17.2855 | 17.2855 | 0
2730 | 3.0618 | 6.597 | 7.0618 | 4.9872 | 3.808 | 2.3357 | 16.9817 | 16.2674 | 16.9817 | 1
2731 | 3.9755 | 5.2913 | 6.8509 | 5.4415 | 3.9769 | 2.7694 | 17.4777 | 17.5727 | 17.5727 | 0
2732 | 4.4483 | 5.2312 | 5.8819 | 5.2136 | 4.024 | 1.7816 | 16.6747 | 16.1359 | 16.6747 | 1
2733 | 3.4796 | 7.3369 | 7.5262 | 5.5962 | 3.8743 | 1.5666 | 17.9792 | 16.4467 | 17.9792 | 1
2734 | 4.458 | 3.6124 | 6.6998 | 5.0968 | 3.4061 | 1.8095 | 14.9766 | 16.3734 | 16.3734 | 0
2735 | 3.4867 | 5.2451 | 6.3631 | 5.7703 | 4.9726 | 2.1998 | 16.7019 | 17.0222 | 17.0222 | 0
2736 | 2.8213 | 3.7651 | 6.6332 | 5.1123 | 4.8729 | 2.45 | 14.1486 | 16.7775 | 16.7775 | 0
2737 | 4.6103 | 5.1987 | 6.1927 | 5.6514 | 4.175 | 2.2771 | 17.7375 | 17.2551 | 17.7375 | 1
2738 | 3.6128 | 4.7938 | 5.191 | 4.9313 | 6.4396 | 2.6152 | 15.9532 | 17.8586 | 17.8586 | 0
2739 | 3.3282 | 4.9816 | 6.9131 | 4.2279 | 4.9533 | 2.4234 | 14.961 | 17.618 | 17.618 | 0
2740 | 4.38 | 7.6617 | 3.684 | 5.1455 | 4.193 | 1.3515 | 18.5387 | 13.6085 | 18.5387 | 1
2741 | 2.5061 | 4.2951 | 5.9618 | 5.076 | 3.9143 | 2.1417 | 14.0189 | 14.5239 | 14.5239 | 0
2742 | 3.1306 | 3.7767 | 6.4559 | 6.0136 | 3.3813 | 1.7721 | 14.693 | 14.7398 | 14.7398 | 0
2743 | 3.3445 | 6.9651 | 7.3702 | 4.9318 | 4.0432 | 2.4154 | 17.6568 | 17.1733 | 17.6568 | 1
2744 | 3.3941 | 3.802 | 6.4535 | 6.5491 | 3.999 | 2.0201 | 15.7654 | 15.8667 | 15.8667 | 0
2745 | 4.1775 | 5.932 | 6.9645 | 5.6063 | 4.1262 | 2.4885 | 18.2042 | 17.7566 | 18.2042 | 1
2746 | 3.0745 | 6.5077 | 6.61 | 5.1372 | 3.3485 | 2.1152 | 16.8345 | 15.1482 | 16.8345 | 1
2747 | 4.1111 | 6.0408 | 6.414 | 4.6453 | 3.9876 | 1.6821 | 16.4794 | 16.1949 | 16.4794 | 1
2748 | 3.6265 | 4.3974 | 7.7006 | 5.3237 | 4.6873 | 1.8059 | 15.1535 | 17.8204 | 17.8204 | 0
2749 | 3.4985 | 5.026 | 4.9715 | 4.6621 | 3.2894 | 1.1643 | 14.3509 | 12.9238 | 14.3509 | 1
2750 | 4.0707 | 4.4606 | 5.0106 | 5.0968 | 3.3673 | 2.334 | 15.9622 | 14.7826 | 15.9622 | 1
2751 | 2.7361 | 5.0136 | 6.2154 | 6.3226 | 4.7033 | 1.948 | 16.0202 | 15.6027 | 16.0202 | 1
2752 | 3.3727 | 5.793 | 6.9055 | 4.8094 | 3.2599 | 1.3213 | 15.2964 | 14.8594 | 15.2964 | 1
2753 | 2.992 | 5.4865 | 6.4288 | 6.4376 | 3.292 | 2.0931 | 17.0092 | 14.8059 | 17.0092 | 1
2754 | 3.125 | 5.9555 | 4.071 | 4.9646 | 4.3698 | 2.3039 | 16.3491 | 13.8698 | 16.3491 | 1
2755 | 3.61 | 5.6133 | 6.9046 | 6.8349 | 5.0278 | 2.1065 | 18.1647 | 17.6489 | 18.1647 | 1
2756 | 5.2604 | 3.6556 | 5.0146 | 4.9739 | 5.1542 | 2.7417 | 16.6315 | 18.1708 | 18.1708 | 0
2757 | 3.5077 | 5.3118 | 6.6836 | 5.7239 | 4.1853 | 2.3681 | 16.9116 | 16.7447 | 16.9116 | 1
2758 | 3.3367 | 6.0536 | 3.8757 | 6.1811 | 3.9346 | 2.1464 | 17.7179 | 13.2934 | 17.7179 | 1
2759 | 3.8853 | 5.3789 | 5.2987 | 5.6824 | 3.6948 | 1.7153 | 16.6618 | 14.594 | 16.6618 | 1
2760 | 2.1332 | 5.3617 | 5.4104 | 4.7135 | 4.8484 | 2.3075 | 14.5159 | 14.6995 | 14.6995 | 0
2761 | 4.0313 | 5.9971 | 5.7153 | 5.803 | 3.7577 | 1.6413 | 17.4727 | 15.1457 | 17.4727 | 1
2762 | 4.5484 | 4.3147 | 6.583 | 5.1178 | 4.6489 | 1.8385 | 15.8193 | 17.6187 | 17.6187 | 0
2763 | 4.0149 | 4.8532 | 5.2566 | 5.8559 | 3.7428 | 2.5744 | 17.2983 | 15.5887 | 17.2983 | 1
2764 | 5.0465 | 4.7449 | 5.7828 | 6.0349 | 5.2966 | 2.2629 | 18.0893 | 18.3888 | 18.3888 | 0
2765 | 3.7701 | 6.5958 | 6.4137 | 5.4254 | 3.823 | 1.8522 | 17.6435 | 15.859 | 17.6435 | 1
2766 | 3.1503 | 3.9977 | 6.1496 | 5.9133 | 4.7586 | 2.3393 | 15.4006 | 16.3978 | 16.3978 | 0
2767 | 3.5473 | 3.7876 | 5.7968 | 4.4206 | 5.0838 | 1.4169 | 13.1724 | 15.8449 | 15.8449 | 0
2768 | 4.6783 | 5.4585 | 4.9723 | 4.914 | 5.1334 | 2.2981 | 17.3489 | 17.0822 | 17.3489 | 1
2769 | 4.4734 | 6.4084 | 5.3088 | 5.4361 | 4.5059 | 2.0495 | 18.3673 | 16.3376 | 18.3673 | 1
2770 | 4.9792 | 5.6006 | 6.4653 | 4.6876 | 4.5148 | 2.0583 | 17.3257 | 18.0176 | 18.0176 | 0
2771 | 5.4777 | 5.2022 | 5.7695 | 5.9739 | 4.3054 | 1.8863 | 18.54 | 17.4388 | 18.54 | 1
2772 | 4.2049 | 7.2804 | 5.6293 | 4.8213 | 4.4005 | 2.1186 | 18.4253 | 16.3533 | 18.4253 | 1
2773 | 5.0621 | 6.2042 | 6.3726 | 4.4329 | 3.6643 | 2.818 | 18.5172 | 17.917 | 18.5172 | 1
2774 | 3.5661 | 6.2618 | 4.8379 | 5.2014 | 4.4808 | 2.0987 | 17.128 | 14.9835 | 17.128 | 1
2775 | 3.0486 | 7.9501 | 5.2462 | 6.248 | 3.8525 | 1.7066 | 18.9533 | 13.8539 | 18.9533 | 1
2776 | 3.0346 | 3.8886 | 5.7091 | 4.6962 | 3.9696 | 1.8318 | 13.4512 | 14.545 | 14.545 | 0
2777 | 3.7379 | 4.1272 | 6.6926 | 4.9973 | 4.7813 | 2.5412 | 15.4036 | 17.753 | 17.753 | 0
2778 | 4.8051 | 4.13 | 5.6344 | 4.4405 | 3.6685 | 1.1568 | 14.5324 | 15.2648 | 15.2648 | 0
2779 | 4.2461 | 4.0118 | 5.6127 | 6.4503 | 4.6439 | 1.5034 | 16.2116 | 16.0062 | 16.2116 | 1
2780 | 3.728 | 3.7003 | 5.078 | 6.401 | 5.3705 | 2.2191 | 16.0484 | 16.3956 | 16.3956 | 0
2781 | 4.3698 | 4.1232 | 6.3536 | 4.5962 | 4.6755 | 1.7942 | 14.8835 | 17.1931 | 17.1931 | 0
2782 | 3.8062 | 5.9906 | 7.9029 | 5.0362 | 3.6937 | 1.9407 | 16.7737 | 17.3435 | 17.3435 | 0
2783 | 3.2705 | 5.139 | 5.3819 | 5.8384 | 4.3928 | 1.1397 | 15.3876 | 14.1849 | 15.3876 | 1
2784 | 3.4663 | 4.8987 | 6.1561 | 5.0592 | 4.2299 | 1.5 | 14.9243 | 15.3523 | 15.3523 | 0
2785 | 4.9353 | 7.8487 | 6.0227 | 5.9539 | 3.2021 | 2.0925 | 20.8304 | 16.2526 | 20.8304 | 1
2786 | 4.5117 | 6.9085 | 5.4512 | 4.6271 | 3.7033 | 1.4275 | 17.4748 | 15.0937 | 17.4748 | 1
2787 | 5.1527 | 4.8808 | 7.4436 | 4.2196 | 4.7268 | 1.4694 | 15.7225 | 18.7925 | 18.7925 | 0
2788 | 4.9954 | 6.4121 | 6.5157 | 5.7775 | 3.1825 | 2.4827 | 19.6677 | 17.1764 | 19.6677 | 1
2789 | 3.9771 | 5.3377 | 4.8712 | 5.1571 | 4.4074 | 2.4585 | 16.9304 | 15.7141 | 16.9304 | 1
2790 | 5.0096 | 5.6851 | 6.4934 | 7.4271 | 5.5169 | 2.884 | 21.0058 | 19.904 | 21.0058 | 1
2791 | 4.6078 | 5.675 | 7.4723 | 4.8303 | 3.6074 | 1.485 | 16.5981 | 17.1725 | 17.1725 | 0
2792 | 3.0283 | 5.5185 | 6.3885 | 5.2549 | 5.3504 | 2.2238 | 16.0256 | 16.991 | 16.991 | 0
2793 | 2.7431 | 3.4162 | 5.5886 | 4.1688 | 3.9901 | 2.3951 | 12.7231 | 14.717 | 14.717 | 0
2794 | 3.8488 | 7.3547 | 6.0426 | 4.2278 | 6.1768 | 2.3966 | 17.8279 | 18.4648 | 18.4648 | 0
2795 | 4.8934 | 4.2202 | 4.9075 | 4.7934 | 3.6783 | 1.7111 | 15.6181 | 15.1903 | 15.6181 | 1
2796 | 5.0032 | 6.4543 | 4.7746 | 5.2229 | 3.4124 | 1.9061 | 18.5866 | 15.0964 | 18.5866 | 1
2797 | 3.4632 | 3.389 | 4.0201 | 5.3978 | 3.2175 | 1.8817 | 14.1317 | 12.5825 | 14.1317 | 1
2798 | 2.8118 | 3.8287 | 5.3302 | 5.2388 | 3.5811 | 2.1207 | 14 | 13.8439 | 14 | 1
2799 | 3.9189 | 4.0377 | 5.0943 | 5.4563 | 3.392 | 1.9156 | 15.3284 | 14.3208 | 15.3284 | 1
2800 | 3.8927 | 6.483 | 5.6276 | 5.2882 | 5.0619 | 2.2227 | 17.8865 | 16.8048 | 17.8865 | 1
2801 | 4.3728 | 4.3338 | 7.2452 | 4.2844 | 5.2251 | 2.3307 | 15.3218 | 19.1738 | 19.1738 | 0
2802 | 3.9851 | 5.7107 | 7.3815 | 4.9579 | 4.4457 | 1.9652 | 16.6189 | 17.7774 | 17.7774 | 0
2803 | 4.4208 | 4.143 | 6.1189 | 5.5965 | 6.0157 | 2.4539 | 16.6142 | 19.0093 | 19.0093 | 0
2804 | 3.4225 | 7.1706 | 6.2626 | 5.1461 | 5.1642 | 1.7271 | 17.4663 | 16.5763 | 17.4663 | 1
2805 | 3.4243 | 5.8187 | 5.7168 | 5.8295 | 4.1401 | 1.7964 | 16.869 | 15.0776 | 16.869 | 1
2806 | 4.2598 | 4.3146 | 4.247 | 4.1228 | 3.6441 | 2.26 | 14.9573 | 14.4109 | 14.9573 | 1
2807 | 3.7031 | 3.9247 | 5.28 | 5.3242 | 4.0347 | 2.518 | 15.4701 | 15.5357 | 15.5357 | 0
2808 | 4.1934 | 3.7658 | 5.1813 | 6.2934 | 4.0671 | 2.5262 | 16.7788 | 15.968 | 16.7788 | 1
2809 | 3.4364 | 5.3214 | 3.5513 | 4.9695 | 4.8686 | 2.6263 | 16.3537 | 14.4827 | 16.3537 | 1
2810 | 4.0288 | 6.2295 | 7.5383 | 5.6627 | 3.4357 | 2.437 | 18.3581 | 17.4399 | 18.3581 | 1
2811 | 3.3336 | 3.5692 | 6.172 | 5.1221 | 4.6804 | 2.1633 | 14.1882 | 16.3492 | 16.3492 | 0
2812 | 5.342 | 6.3883 | 5.7327 | 5.9774 | 4.7636 | 1.5927 | 19.3005 | 17.4311 | 19.3005 | 1
2813 | 3.8897 | 7.8291 | 5.5049 | 5.5684 | 5.0966 | 1.8902 | 19.1774 | 16.3814 | 19.1774 | 1
2814 | 4.339 | 5.9376 | 4.7668 | 4.3767 | 3.1982 | 2.06 | 16.7133 | 14.3639 | 16.7133 | 1
2815 | 3.277 | 8.3203 | 4.9721 | 5.1203 | 3.9143 | 1.9089 | 18.6266 | 14.0723 | 18.6266 | 1
2816 | 4.712 | 5.8111 | 4.5564 | 5.112 | 3.592 | 1.8022 | 17.4373 | 14.6626 | 17.4373 | 1
2817 | 5.0994 | 4.8846 | 5.6723 | 5.1854 | 4.4899 | 2.026 | 17.1954 | 17.2877 | 17.2877 | 0
2818 | 4.2249 | 5.9678 | 5.3199 | 5.9574 | 4.1701 | 1.6845 | 17.8346 | 15.3994 | 17.8346 | 1
2819 | 3.1806 | 4.1964 | 7.0222 | 4.7001 | 4.2225 | 1.8734 | 13.9504 | 16.2987 | 16.2987 | 0
2820 | 4.4459 | 6.3974 | 5.3685 | 5.7245 | 4.0865 | 2.084 | 18.6518 | 15.9849 | 18.6518 | 1
2821 | 4.1426 | 4.7001 | 4.2215 | 5.0918 | 3.7771 | 2.1007 | 16.0351 | 14.2419 | 16.0351 | 1
2822 | 2.9644 | 6.4582 | 5.6231 | 5.2397 | 4.0788 | 1.4784 | 16.1407 | 14.1447 | 16.1407 | 1
2823 | 4.1623 | 4.6238 | 4.5796 | 4.3918 | 3.8249 | 2.1803 | 15.3581 | 14.7469 | 15.3581 | 1
2824 | 3.7711 | 5.1732 | 6.0865 | 7.1564 | 5.867 | 2.3801 | 18.4808 | 18.1046 | 18.4808 | 1
2825 | 3.4706 | 4.406 | 4.0981 | 5.9774 | 5.6648 | 1.5695 | 15.4235 | 14.803 | 15.4235 | 1
2826 | 4.7086 | 4.632 | 5.0085 | 4.9223 | 3.3668 | 2.0989 | 16.3619 | 15.1829 | 16.3619 | 1
2827 | 4.7998 | 4.2423 | 7.1373 | 5.0998 | 3.2943 | 2.641 | 16.7829 | 17.8724 | 17.8724 | 0
2828 | 2.9797 | 4.9976 | 6.3204 | 5.7507 | 4.2605 | 1.6194 | 15.3475 | 15.18 | 15.3475 | 1
2829 | 3.5309 | 4.492 | 6.5895 | 6.2125 | 3.3867 | 1.5291 | 15.7645 | 15.0361 | 15.7645 | 1
2830 | 3.265 | 7.3872 | 5.4007 | 5.609 | 4.0298 | 2.0805 | 18.3417 | 14.776 | 18.3417 | 1
2831 | 4.8866 | 7.0304 | 6.6345 | 5.0493 | 4.7995 | 2.2968 | 19.2631 | 18.6174 | 19.2631 | 1
2832 | 4.0811 | 4.7907 | 6.2012 | 4.556 | 3.4094 | 2.5004 | 15.9282 | 16.192 | 16.192 | 0
2833 | 4.5808 | 7.2918 | 6.3034 | 5.878 | 4.1612 | 2.298 | 20.0486 | 17.3435 | 20.0486 | 1
2834 | 3.9501 | 6.5631 | 3.3765 | 5.3879 | 4.5901 | 1.7722 | 17.6733 | 13.6889 | 17.6733 | 1
2835 | 3.125 | 7.705 | 6.7117 | 4.1417 | 4.3997 | 1.9502 | 16.9219 | 16.1866 | 16.9219 | 1
2836 | 3.6608 | 5.55 | 5.7038 | 5.4899 | 4.8058 | 1.6608 | 16.3614 | 15.8312 | 16.3614 | 1
2837 | 2.8465 | 5.9572 | 5.0824 | 5.4304 | 5.2075 | 1.865 | 16.099 | 15.0014 | 16.099 | 1
2838 | 3.9529 | 4.7038 | 6.8509 | 4.7292 | 4.0371 | 1.9033 | 15.2892 | 16.7442 | 16.7442 | 0
2839 | 3.717 | 4.5881 | 4.8461 | 4.6529 | 4.2532 | 1.6684 | 14.6264 | 14.4848 | 14.6264 | 1
2840 | 3.7112 | 6.5406 | 6.1893 | 6.428 | 5.1599 | 1.8448 | 18.5246 | 16.9052 | 18.5246 | 1
2841 | 4.236 | 4.6472 | 4.7472 | 4.7033 | 4.067 | 2.4249 | 16.0114 | 15.475 | 16.0114 | 1
2842 | 3.004 | 6.4502 | 4.9752 | 4.0968 | 3.2516 | 1.7728 | 15.3238 | 13.0036 | 15.3238 | 1
2843 | 4.3481 | 3.5913 | 6.0116 | 4.768 | 3.4715 | 2.0174 | 14.7249 | 15.8486 | 15.8486 | 0
2844 | 4.2948 | 4.606 | 7.5378 | 4.4001 | 4.2497 | 1.8118 | 15.1127 | 17.8941 | 17.8941 | 0
2845 | 4.4375 | 3.5775 | 5.8367 | 5.129 | 6.769 | 1.9219 | 15.066 | 18.9652 | 18.9652 | 0
2846 | 2.7541 | 5.1601 | 6.3715 | 5.2572 | 3.2331 | 1.6292 | 14.8006 | 13.988 | 14.8006 | 1
2847 | 3.2758 | 5.3813 | 7.1854 | 5.8504 | 4.5983 | 1.607 | 16.1144 | 16.6664 | 16.6664 | 0
2848 | 2.7883 | 5.9914 | 4.593 | 5.5641 | 5.3801 | 1.927 | 16.2708 | 14.6885 | 16.2708 | 1
2849 | 3.9605 | 5.6783 | 4.7452 | 6.603 | 4.5336 | 1.504 | 17.7458 | 14.7433 | 17.7458 | 1
2850 | 4.38 | 6.3501 | 6.9999 | 4.0488 | 4.5902 | 2.1357 | 16.9146 | 18.1059 | 18.1059 | 0
2851 | 3.3997 | 5.532 | 5.7136 | 7.2585 | 4.3305 | 2.1167 | 18.3069 | 15.5605 | 18.3069 | 1
2852 | 4.2071 | 6.0682 | 5.1984 | 4.9426 | 3.8046 | 2.2682 | 17.4861 | 15.4783 | 17.4861 | 1
2853 | 4.6024 | 4.7479 | 3.2532 | 4.5984 | 3.8853 | 2.3283 | 16.2771 | 14.0693 | 16.2771 | 1
2854 | 3.1751 | 4.9551 | 5.3028 | 5.2567 | 3.709 | 1.6689 | 15.0558 | 13.8559 | 15.0558 | 1
2855 | 4.8562 | 4.2139 | 5.1341 | 5.9043 | 4.5581 | 1.5157 | 16.4901 | 16.0641 | 16.4901 | 1
2856 | 3.4711 | 6.0383 | 7.3479 | 5.7079 | 4.1224 | 2.1757 | 17.393 | 17.1171 | 17.393 | 1
2857 | 3.2388 | 5.6433 | 5.7621 | 5.5648 | 5.1596 | 1.9875 | 16.4344 | 16.148 | 16.4344 | 1
2858 | 4.1805 | 5.566 | 4.8329 | 6.0313 | 3.3026 | 1.313 | 17.0907 | 13.6289 | 17.0907 | 1
2859 | 3.1359 | 4.5375 | 6.7316 | 4.7324 | 3.5953 | 2.2126 | 14.6184 | 15.6754 | 15.6754 | 0
2860 | 3.0727 | 5.8141 | 6.9407 | 4.3946 | 4.6607 | 2.0552 | 15.3366 | 16.7293 | 16.7293 | 0
2861 | 3.6615 | 5.5076 | 5.0101 | 4.6787 | 4.1541 | 1.6673 | 15.5151 | 14.4931 | 15.5151 | 1
2862 | 2.5558 | 5.0925 | 5.673 | 5.8531 | 3.8838 | 1.8878 | 15.3891 | 14.0003 | 15.3891 | 1
2863 | 3.6852 | 6.7174 | 3.4373 | 5.4307 | 4.1314 | 2.4777 | 18.311 | 13.7316 | 18.311 | 1
2864 | 4.0269 | 6.2453 | 6.8449 | 4.9944 | 4.8907 | 2.4638 | 17.7304 | 18.2263 | 18.2263 | 0
2865 | 3.2925 | 5.0471 | 5.0709 | 4.5827 | 4.7317 | 2.4851 | 15.4074 | 15.5803 | 15.5803 | 0
2866 | 4.2608 | 7.362 | 5.4526 | 5.6175 | 5.2405 | 2.3039 | 19.5441 | 17.2577 | 19.5441 | 1
2867 | 3.4987 | 6.9386 | 6.4102 | 5.3223 | 5.1025 | 1.7664 | 17.5259 | 16.7777 | 17.5259 | 1
2868 | 3.4596 | 4.1419 | 6.6014 | 6.0478 | 5.2142 | 1.8772 | 15.5266 | 17.1525 | 17.1525 | 0
2869 | 5.2794 | 4.6113 | 5.1051 | 4.8404 | 3.9862 | 2.0257 | 16.7568 | 16.3964 | 16.7568 | 1
2870 | 2.8883 | 6.737 | 7.505 | 6.292 | 5.75 | 1.9394 | 17.8567 | 18.0828 | 18.0828 | 0
2871 | 5.2037 | 4.6378 | 7.0039 | 6.3141 | 4.4493 | 1.7681 | 17.9237 | 18.4249 | 18.4249 | 0
2872 | 3.4926 | 6.303 | 3.969 | 5.3383 | 3.8589 | 1.8062 | 16.9401 | 13.1267 | 16.9401 | 1
2873 | 3.5427 | 5.8623 | 5.3841 | 5.0866 | 5.8809 | 2.0949 | 16.5865 | 16.9026 | 16.9026 | 0
2874 | 5.0819 | 5.9208 | 6.4408 | 5.7466 | 4.1112 | 1.5746 | 18.3239 | 17.2085 | 18.3239 | 1
2875 | 4.3599 | 5.2208 | 4.2811 | 4.1766 | 4.1008 | 1.5931 | 15.3504 | 14.3348 | 15.3504 | 1
2876 | 4.1727 | 5.0958 | 7.6778 | 4.6977 | 4.7525 | 1.6271 | 15.5932 | 18.2301 | 18.2301 | 0
2877 | 4.8497 | 4.973 | 5.8192 | 4.6428 | 4.5162 | 1.9573 | 16.4229 | 17.1425 | 17.1425 | 0
2878 | 3.3617 | 5.0904 | 5.7884 | 4.7691 | 3.4681 | 1.3538 | 14.5749 | 13.9719 | 14.5749 | 1
2879 | 4.3757 | 6.898 | 7.2413 | 4.5141 | 3.8798 | 2.3106 | 18.0984 | 17.8074 | 18.0984 | 1
2880 | 3.8921 | 5.2825 | 6.7617 | 7.3167 | 4.736 | 1.4794 | 17.9708 | 16.8692 | 17.9708 | 1
2881 | 3.6976 | 6.0864 | 2.9561 | 6.3491 | 4.4161 | 2.226 | 18.359 | 13.2957 | 18.359 | 1
2882 | 5.1104 | 3.5239 | 3.8562 | 5.3096 | 4.6874 | 2.293 | 16.2369 | 15.947 | 16.2369 | 1
2883 | 3.0739 | 6.2794 | 7.1386 | 5.2075 | 3.462 | 1.6648 | 16.2256 | 15.3394 | 16.2256 | 1
2884 | 2.7917 | 4.8579 | 5.3794 | 4.6055 | 4.7051 | 2.3403 | 14.5954 | 15.2165 | 15.2165 | 0
2885 | 3.0135 | 4.9429 | 6.1031 | 5.4 | 4.0488 | 1.9669 | 15.3233 | 15.1324 | 15.3233 | 1
2886 | 2.9305 | 4.2036 | 6.5203 | 4.5185 | 3.4703 | 1.8388 | 13.4913 | 14.7599 | 14.7599 | 0
2887 | 2.9384 | 5.97 | 4.9696 | 4.8158 | 4.8747 | 1.7303 | 15.4545 | 14.513 | 15.4545 | 1
2888 | 3.9402 | 7.0794 | 5.2359 | 6.1116 | 4.096 | 1.7419 | 18.8731 | 15.0141 | 18.8731 | 1
2889 | 3.2196 | 4.121 | 3.9346 | 5.2417 | 3.545 | 1.5358 | 14.1181 | 12.235 | 14.1181 | 1
2890 | 4.6005 | 5.6182 | 6.3385 | 6.7766 | 5.991 | 1.8622 | 18.8574 | 18.7922 | 18.8574 | 1
2891 | 3.8712 | 3.6339 | 4.612 | 5.2252 | 4.6772 | 1.8615 | 14.5919 | 15.0218 | 15.0218 | 0
2892 | 3.4373 | 4.1081 | 6.8159 | 6.4422 | 3.661 | 1.5772 | 15.5648 | 15.4915 | 15.5648 | 1
2893 | 4.3196 | 4.5908 | 6.3615 | 6.7097 | 3.7274 | 1.5477 | 17.1679 | 15.9563 | 17.1679 | 1
2894 | 4.6759 | 5.6961 | 7.4475 | 5.03 | 3.6859 | 2.4177 | 17.8197 | 18.2269 | 18.2269 | 0
2895 | 4.9192 | 6.3399 | 6.9254 | 6.1784 | 4.176 | 1.9643 | 19.4017 | 17.9849 | 19.4017 | 1
2896 | 4.5997 | 6.5465 | 7.1502 | 4.201 | 3.4536 | 2.0488 | 17.396 | 17.2523 | 17.396 | 1
2897 | 2.7399 | 3.5238 | 6.8332 | 4.1202 | 4.9909 | 2.2194 | 12.6032 | 16.7834 | 16.7834 | 0
2898 | 3.7878 | 4.694 | 6.1647 | 5.7011 | 4.1287 | 2.5006 | 16.6835 | 16.5817 | 16.6835 | 1
2899 | 3.8696 | 4.447 | 5.7039 | 5.813 | 3.5914 | 2.0951 | 16.2247 | 15.26 | 16.2247 | 1
2900 | 4.2412 | 5.5314 | 4.8657 | 4.5538 | 4.6398 | 1.4352 | 15.7615 | 15.1819 | 15.7615 | 1
2901 | 4.1844 | 3.4805 | 4.6916 | 6.8795 | 3.5437 | 2.4042 | 16.9485 | 14.8239 | 16.9485 | 1
2902 | 2.8104 | 4.4631 | 5.7273 | 5.0191 | 4.8737 | 1.4662 | 13.7588 | 14.8776 | 14.8776 | 0
2903 | 2.3153 | 3.8064 | 5.3713 | 5.2795 | 4.3643 | 2.3728 | 13.774 | 14.4237 | 14.4237 | 0
2904 | 4.4391 | 6.2602 | 6.6789 | 5.4612 | 5.2445 | 2.4725 | 18.6329 | 18.835 | 18.835 | 0
2905 | 3.8953 | 5.9613 | 7.2918 | 5.6834 | 5.557 | 1.5863 | 17.1263 | 18.3305 | 18.3305 | 0
2906 | 4.4746 | 7.8627 | 5.295 | 4.6187 | 5.5009 | 1.972 | 18.9281 | 17.2426 | 18.9281 | 1
2907 | 3.8588 | 3.3693 | 6.17 | 6.8207 | 3.7699 | 2.6756 | 16.7244 | 16.4743 | 16.7244 | 1
2908 | 3.6874 | 5.354 | 6.3703 | 5.3042 | 3.9304 | 2.209 | 16.5546 | 16.1971 | 16.5546 | 1
2909 | 2.7477 | 4.5669 | 7.5893 | 4.4309 | 4.0485 | 2.5641 | 14.3096 | 16.9496 | 16.9496 | 0
2910 | 2.9421 | 4.3626 | 5.1379 | 5.8893 | 4.9342 | 2.1433 | 15.3373 | 15.1575 | 15.3373 | 1
2911 | 2.8983 | 4.0337 | 6.0975 | 4.2627 | 4.611 | 1.1036 | 12.2983 | 14.7105 | 14.7105 | 0
2912 | 4.5777 | 3.3996 | 4.9299 | 6.0758 | 5.0426 | 2.5947 | 16.6479 | 17.145 | 17.145 | 0
2913 | 3.0205 | 5.4332 | 6.1234 | 4.5647 | 4.4981 | 1.5062 | 14.5246 | 15.1481 | 15.1481 | 0
2914 | 4.1099 | 7.7263 | 6.6559 | 4.6698 | 3.8043 | 1.4262 | 17.9323 | 15.9964 | 17.9323 | 1
2915 | 4.2035 | 5.4383 | 5.6757 | 7.0777 | 5.406 | 2.205 | 18.9245 | 17.4901 | 18.9245 | 1
2916 | 2.9517 | 4.9326 | 6.8403 | 4.6315 | 4.7531 | 1.7842 | 14.3 | 16.3293 | 16.3293 | 0
2917 | 3.7876 | 4.9661 | 6.6154 | 5.1544 | 4.1312 | 2.016 | 15.9241 | 16.5502 | 16.5502 | 0
2918 | 4.0517 | 5.5647 | 6.1616 | 5.081 | 4.4771 | 1.6763 | 16.3737 | 16.3667 | 16.3737 | 1
2919 | 2.7083 | 6.5988 | 6.8557 | 5.1632 | 3.447 | 2.2006 | 16.6708 | 15.2116 | 16.6708 | 1
2920 | 4.5524 | 4.9211 | 7.0085 | 5.7111 | 4.3014 | 2.3158 | 17.5004 | 18.1782 | 18.1782 | 0
2921 | 3.3494 | 4.7365 | 5.8397 | 4.5469 | 4.9068 | 2.029 | 14.6618 | 16.1249 | 16.1249 | 0
2922 | 3.7653 | 6.9378 | 3.3159 | 4.2725 | 5.0567 | 2.1729 | 17.1484 | 14.3108 | 17.1484 | 1
2923 | 3.3735 | 5.5747 | 7.0604 | 4.4392 | 3.5426 | 1.3993 | 14.7867 | 15.3758 | 15.3758 | 0
2924 | 3.955 | 5.1954 | 6.9659 | 5.4631 | 5.1319 | 2.4324 | 17.046 | 18.4853 | 18.4853 | 0
2925 | 3.0624 | 6.3353 | 5.5819 | 6.5621 | 3.8215 | 1.5838 | 17.5437 | 14.0497 | 17.5437 | 1
2926 | 3.1803 | 4.9011 | 4.9255 | 7.0346 | 4.9033 | 2.2575 | 17.3735 | 15.2666 | 17.3735 | 1
2927 | 2.4765 | 5.2592 | 6.8886 | 5.5102 | 4.397 | 1.3685 | 14.6145 | 15.1306 | 15.1306 | 0
2928 | 3.3233 | 4.6835 | 7.0623 | 5.3757 | 3.8517 | 2.2816 | 15.6641 | 16.5189 | 16.5189 | 0
2929 | 2.4086 | 5.735 | 5.345 | 5.0084 | 3.6761 | 1.9425 | 15.0945 | 13.3722 | 15.0945 | 1
2930 | 3.0316 | 4.9657 | 6.3297 | 5.9902 | 3.8895 | 2.6902 | 16.6777 | 15.9411 | 16.6777 | 1
2931 | 3.9794 | 4.1486 | 6.3862 | 4.1194 | 5.3895 | 2.247 | 14.4944 | 18.0021 | 18.0021 | 0
2932 | 3.3395 | 7.1301 | 5.8884 | 4.2524 | 3.6674 | 1.954 | 16.676 | 14.8493 | 16.676 | 1
2933 | 3.7354 | 5.7848 | 5.0903 | 4.9623 | 5.826 | 2.5344 | 17.0168 | 17.1861 | 17.1861 | 0
2934 | 3.1519 | 6.03 | 4.9411 | 5.9963 | 3.7703 | 2.3744 | 17.5526 | 14.2378 | 17.5526 | 1
2935 | 4.7701 | 7.0023 | 6.0757 | 5.335 | 3.8335 | 1.5438 | 18.6512 | 16.2231 | 18.6512 | 1
2936 | 4.5195 | 8.1631 | 6.4106 | 5.8584 | 4.6473 | 1.7924 | 20.3334 | 17.3697 | 20.3334 | 1
2937 | 3.8347 | 5.7614 | 6.4308 | 4.1095 | 3.5949 | 1.7224 | 15.4279 | 15.5827 | 15.5827 | 0
2938 | 3.3319 | 6.0531 | 3.0095 | 5.3113 | 4.5052 | 2.2169 | 16.9131 | 13.0635 | 16.9131 | 1
2939 | 3.9511 | 6.8064 | 5.6042 | 5.6673 | 4.6519 | 2.1563 | 18.5812 | 16.3635 | 18.5812 | 1
2940 | 3.8751 | 6.2689 | 4.1958 | 7.4023 | 3.7729 | 2.6893 | 20.2356 | 14.5332 | 20.2356 | 1
2941 | 4.786 | 5.3853 | 7.8092 | 4.9782 | 4.9313 | 2.5518 | 17.7014 | 20.0783 | 20.0783 | 0
2942 | 3.3292 | 7.6414 | 6.2508 | 5.2066 | 5.0695 | 2.3595 | 18.5367 | 17.009 | 18.5367 | 1
2943 | 3.1463 | 5.8 | 7.0978 | 5.6308 | 3.2564 | 1.6251 | 16.2022 | 15.1257 | 16.2022 | 1
2944 | 4.0996 | 4.5272 | 6.3939 | 4.5564 | 4.1999 | 1.994 | 15.1772 | 16.6874 | 16.6874 | 0
2945 | 3.8893 | 5.2794 | 5.8696 | 5.6323 | 3.9528 | 2.3676 | 17.1686 | 16.0793 | 17.1686 | 1
2946 | 2.5303 | 7.0444 | 5.7506 | 6.1694 | 3.3334 | 2.0176 | 17.7617 | 13.6318 | 17.7617 | 1
2947 | 5.5086 | 5.102 | 7.14 | 5.2446 | 3.5018 | 2.4358 | 18.291 | 18.5863 | 18.5863 | 0
2948 | 2.7209 | 4.1407 | 6.6162 | 4.3869 | 4.52 | 1.58 | 12.8285 | 15.4371 | 15.4371 | 0
2949 | 4.2383 | 5.1783 | 5.8987 | 5.5031 | 3.4766 | 1.9452 | 16.865 | 15.5588 | 16.865 | 1
2950 | 4.0502 | 4.6892 | 6.1519 | 4.5911 | 4.0213 | 1.3747 | 14.7053 | 15.5982 | 15.5982 | 0
2951 | 5.4784 | 4.6577 | 5.7247 | 6.6228 | 6.1144 | 2.0969 | 18.8559 | 19.4145 | 19.4145 | 0
2952 | 3.4594 | 5.0217 | 4.4976 | 5.1449 | 3.6259 | 1.7845 | 15.4105 | 13.3674 | 15.4105 | 1
2953 | 5.5483 | 5.8437 | 6.1687 | 5.6843 | 4.3402 | 2.1732 | 19.2495 | 18.2303 | 19.2495 | 1
2954 | 4.8331 | 8.1265 | 7.0927 | 4.8222 | 5.2539 | 1.9654 | 19.747 | 19.145 | 19.747 | 1
2955 | 4.4665 | 4.4166 | 5.1113 | 5.0308 | 4.8812 | 2.2821 | 16.1959 | 16.7411 | 16.7411 | 0
2956 | 3.0327 | 6.3204 | 4.1674 | 4.9092 | 5.0089 | 1.7849 | 16.0473 | 13.994 | 16.0473 | 1
2957 | 4.77 | 4.6395 | 5.6609 | 4.9573 | 5.4384 | 2.2377 | 16.6046 | 18.107 | 18.107 | 0
2958 | 3.593 | 5.6596 | 5.5162 | 6.1038 | 4.3341 | 2.0058 | 17.3622 | 15.4491 | 17.3622 | 1
2959 | 3.2062 | 5.6367 | 6.2208 | 4.7582 | 5.072 | 1.5006 | 15.1017 | 15.9995 | 15.9995 | 0
2960 | 4.3866 | 7.3983 | 6.7506 | 5.0724 | 4.5004 | 1.8084 | 18.6657 | 17.446 | 18.6657 | 1
2961 | 3.6788 | 7.1744 | 6.6828 | 6.4822 | 4.8806 | 1.9099 | 19.2452 | 17.1521 | 19.2452 | 1
2962 | 4.3568 | 3.7002 | 5.1717 | 6.2597 | 4.77 | 1.9148 | 16.2315 | 16.2133 | 16.2315 | 1
2963 | 4.8345 | 6.883 | 6.6411 | 5.0226 | 3.9536 | 2.1884 | 18.9285 | 17.6176 | 18.9285 | 1
2964 | 3.8878 | 5.4639 | 4.7784 | 5.8134 | 5.0004 | 2.1904 | 17.3554 | 15.8569 | 17.3554 | 1
2965 | 2.9734 | 4.5369 | 5.1462 | 5.9996 | 3.8132 | 2.0834 | 15.5933 | 14.0162 | 15.5933 | 1
2966 | 4.3594 | 5.1769 | 7.3263 | 5.4027 | 3.1272 | 1.4243 | 16.3633 | 16.2372 | 16.3633 | 1
2967 | 5.1596 | 5.2933 | 6.5118 | 4.7775 | 4.1736 | 1.6066 | 16.8369 | 17.4516 | 17.4516 | 0
2968 | 3.9303 | 4.1818 | 3.8973 | 7.0015 | 3.9001 | 1.9805 | 17.0941 | 13.7082 | 17.0941 | 1
2969 | 3.2783 | 4.273 | 4.4284 | 4.8157 | 4.0142 | 2.4485 | 14.8154 | 14.1694 | 14.8154 | 1
2970 | 4.3688 | 4.551 | 5.8972 | 6.8246 | 4.1775 | 1.9473 | 17.6917 | 16.3908 | 17.6917 | 1
2971 | 3.1145 | 6.9315 | 6.2211 | 4.0793 | 5.6774 | 2.5603 | 16.6856 | 17.5733 | 17.5733 | 0
2972 | 4.7439 | 7.5311 | 3.8457 | 5.1975 | 4.234 | 2.2164 | 19.6889 | 15.0401 | 19.6889 | 1
2973 | 2.2375 | 6.7474 | 6.5203 | 4.5396 | 3.5881 | 1.6897 | 15.2142 | 14.0356 | 15.2142 | 1
2974 | 3.8045 | 5.122 | 5.9224 | 5.7211 | 5.4874 | 1.4507 | 16.0983 | 16.6651 | 16.6651 | 0
2975 | 5.0497 | 4.8982 | 7.2842 | 5.7082 | 4.9612 | 2.3289 | 17.985 | 19.6238 | 19.6238 | 0
2976 | 5.2429 | 7.1488 | 6.0588 | 5.4017 | 4.8895 | 2.235 | 20.0284 | 18.4262 | 20.0284 | 1
2977 | 5.6756 | 7.8852 | 6.8754 | 5.5743 | 3.5715 | 1.6715 | 20.8066 | 17.794 | 20.8066 | 1
2978 | 5.2031 | 5.0496 | 6.4901 | 6.0397 | 3.9264 | 1.4841 | 17.7764 | 17.1037 | 17.7764 | 1
2979 | 3.9552 | 5.3763 | 5.4405 | 6.0317 | 4.1237 | 1.4768 | 16.84 | 14.9961 | 16.84 | 1
2980 | 3.532 | 6.2912 | 7.5959 | 5.2705 | 4.0321 | 2.3566 | 17.4504 | 17.5167 | 17.5167 | 0
2981 | 3.448 | 3.532 | 5.5776 | 4.3645 | 3.6832 | 2.5017 | 13.8462 | 15.2105 | 15.2105 | 0
2982 | 2.8004 | 5.6054 | 4.6266 | 4.3994 | 4.0214 | 2.0791 | 14.8842 | 13.5275 | 14.8842 | 1
2983 | 3.6763 | 3.768 | 4.1847 | 4.4251 | 3.5552 | 1.97 | 13.8394 | 13.3861 | 13.8394 | 1
2984 | 3.7333 | 4.1006 | 6.0405 | 4.6796 | 3.2861 | 1.8642 | 14.3777 | 14.924 | 14.924 | 0
2985 | 4.1022 | 5.4999 | 4.1428 | 5.0889 | 4.3851 | 2.1843 | 16.8752 | 14.8144 | 16.8752 | 1
2986 | 4.2901 | 5.3775 | 7.2881 | 6.3332 | 3.4385 | 1.2807 | 17.2816 | 16.2975 | 17.2816 | 1
2987 | 4.9749 | 5.8261 | 6.5908 | 5.7692 | 4.1557 | 2.4572 | 19.0274 | 18.1786 | 19.0274 | 1
2988 | 4.5554 | 6.3045 | 6.1934 | 6.2506 | 4.9416 | 2.2346 | 19.3452 | 17.9251 | 19.3452 | 1
2989 | 4.5384 | 5.3172 | 5.0617 | 4.9429 | 5.0103 | 2.1669 | 16.9654 | 16.7773 | 16.9654 | 1
2990 | 4.0002 | 5.9364 | 5.7752 | 4.3433 | 3.5682 | 2.2882 | 16.5682 | 15.6319 | 16.5682 | 1
2991 | 3.2281 | 6.2648 | 4.8549 | 4.8164 | 3.5223 | 1.8805 | 16.1899 | 13.4859 | 16.1899 | 1
2992 | 5.1842 | 5.4086 | 5.7144 | 4.7121 | 3.55 | 1.9182 | 17.223 | 16.3667 | 17.223 | 1
2993 | 4.0217 | 5.3078 | 4.7218 | 6.4153 | 3.3074 | 2.1694 | 17.9142 | 14.2203 | 17.9142 | 1
2994 | 3.7472 | 4.7303 | 5.6282 | 5.803 | 4.5459 | 2.4416 | 16.7221 | 16.3628 | 16.7221 | 1
2995 | 4.7279 | 4.8226 | 5.5269 | 5.3376 | 3.7979 | 1.7536 | 16.6417 | 15.8063 | 16.6417 | 1
2996 | 4.9263 | 6.4333 | 5.7747 | 4.7823 | 5.7133 | 1.4041 | 17.546 | 17.8184 | 17.8184 | 0
2997 | 4.4224 | 4.851 | 6.9928 | 6.4554 | 5.4728 | 2.0014 | 17.7302 | 18.8894 | 18.8894 | 0
2998 | 4.9212 | 3.929 | 6.8156 | 4.5802 | 3.5364 | 1.6705 | 15.101 | 16.9437 | 16.9437 | 0
2999 | 4.1642 | 3.4743 | 5.0136 | 5.0516 | 4.4291 | 1.7293 | 14.4194 | 15.3362 | 15.3362 | 0
3000 | 4.223 | 4.9181 | 5.6894 | 5.0735 | 5.099 | 2.1302 | 16.3448 | 17.1416 | 17.1416 | 0
3001 | 3.5461 | 5.3066 | 5.0971 | 4.6706 | 4.0285 | 1.778 | 15.3012 | 14.4497 | 15.3012 | 1
3002 | 3.8342 | 4.2391 | 5.5098 | 5.8246 | 4.4861 | 2.1244 | 16.0223 | 15.9545 | 16.0223 | 1
3003 | 4.1971 | 5.2355 | 6.6957 | 5.2405 | 4.6688 | 2.1244 | 16.7975 | 17.686 | 17.686 | 0
3004 | 3.828 | 3.759 | 4.975 | 5.4578 | 5.2358 | 1.2669 | 14.3117 | 15.3057 | 15.3057 | 0
3005 | 4.2705 | 6.7047 | 5.2937 | 4.6755 | 4.2882 | 2.2904 | 17.9412 | 16.1428 | 17.9412 | 1
3006 | 5.0138 | 6.8288 | 4.2297 | 5.6937 | 4.7178 | 1.932 | 19.4683 | 15.8933 | 19.4683 | 1
3007 | 4.8677 | 3.4882 | 6.7117 | 4.4714 | 4.5043 | 1.2247 | 14.052 | 17.3084 | 17.3084 | 0
3008 | 4.523 | 4.5465 | 4.7315 | 5.7576 | 5.1815 | 2.203 | 17.03 | 16.6389 | 17.03 | 1
3009 | 4.4387 | 4.9704 | 6.0239 | 5.6874 | 3.9403 | 2.5188 | 17.6152 | 16.9217 | 17.6152 | 1
3010 | 5.515 | 4.8653 | 6.0104 | 5.6073 | 5.0639 | 1.3243 | 17.312 | 17.9137 | 17.9137 | 0
3011 | 4.4519 | 4.2787 | 6.1075 | 4.4405 | 4.0522 | 2.321 | 15.4921 | 16.9326 | 16.9326 | 0
3012 | 2.9632 | 6.595 | 5.7863 | 6.1254 | 4.3328 | 1.9357 | 17.6192 | 15.0179 | 17.6192 | 1
3013 | 4.3571 | 4.5788 | 5.2136 | 5.1837 | 4.2285 | 2.4176 | 16.5373 | 16.2169 | 16.5373 | 1
3014 | 3.3247 | 6.0433 | 5.9501 | 4.6524 | 4.87 | 2.0215 | 16.0419 | 16.1663 | 16.1663 | 0
3015 | 3.6739 | 6.1065 | 7.0688 | 5.9356 | 5.3858 | 2.0546 | 17.7705 | 18.183 | 18.183 | 0
3016 | 3.0699 | 5.1235 | 7.1892 | 4.5003 | 4.9372 | 1.8123 | 14.506 | 17.0085 | 17.0085 | 0
3017 | 4.3837 | 6.3321 | 5.7877 | 5.6347 | 5.8819 | 2.1178 | 18.4683 | 18.1712 | 18.4683 | 1
3018 | 3.4547 | 6.3574 | 4.7351 | 4.3207 | 6.0929 | 2.3154 | 16.4482 | 16.5981 | 16.5981 | 0
3019 | 4.5599 | 6.4887 | 5.0739 | 7.3057 | 3.8772 | 2.292 | 20.6463 | 15.8031 | 20.6463 | 1
3020 | 4.8188 | 4.5165 | 6.4425 | 6.9926 | 4.1055 | 1.9801 | 18.308 | 17.3469 | 18.308 | 1
3021 | 3.9008 | 4.6788 | 5.8928 | 4.5916 | 5.1926 | 1.5673 | 14.7385 | 16.5536 | 16.5536 | 0
3022 | 4.9633 | 6.1747 | 4.0677 | 4.0095 | 3.5117 | 2.3211 | 17.4687 | 14.8639 | 17.4687 | 1
3023 | 3.6182 | 3.6368 | 6.0533 | 4.1488 | 4.2714 | 2.5806 | 13.9844 | 16.5235 | 16.5235 | 0
3024 | 3.9246 | 3.731 | 4.2452 | 6.6799 | 4.6705 | 1.5669 | 15.9024 | 14.4072 | 15.9024 | 1
3025 | 4.832 | 3.6759 | 4.475 | 5.8397 | 4.7497 | 1.7565 | 16.1042 | 15.8133 | 16.1042 | 1
3026 | 4.8184 | 4.6219 | 4.9411 | 4.8907 | 5.8933 | 1.8218 | 16.1528 | 17.4746 | 17.4746 | 0
3027 | 5.0626 | 5.1528 | 4.553 | 6.022 | 4.1461 | 2.1428 | 18.3802 | 15.9045 | 18.3802 | 1
3028 | 4.2568 | 4.7501 | 6.5985 | 6.9149 | 3.4845 | 1.8929 | 17.8147 | 16.2327 | 17.8147 | 1
3029 | 4.5854 | 6.2673 | 7.7255 | 5.7405 | 3.1984 | 2.489 | 19.0822 | 17.9983 | 19.0822 | 1
3030 | 5.1656 | 6.332 | 5.0602 | 4.6589 | 3.9873 | 2.0565 | 18.2129 | 16.2696 | 18.2129 | 1
3031 | 4.866 | 5.9943 | 4.1415 | 5.3751 | 5.2583 | 1.5377 | 17.7731 | 15.8035 | 17.7731 | 1
3032 | 3.412 | 5.5684 | 3.4999 | 6.658 | 4.701 | 1.5642 | 17.2026 | 13.1771 | 17.2026 | 1
3033 | 4.0382 | 5.5108 | 4.9824 | 6.3588 | 4.8673 | 1.396 | 17.3038 | 15.284 | 17.3038 | 1
3034 | 3.9533 | 7.8131 | 6.431 | 4.5134 | 4.3299 | 1.3833 | 17.6632 | 16.0975 | 17.6632 | 1
3035 | 4.4682 | 5.7909 | 5.4782 | 4.9323 | 4.1972 | 1.8651 | 17.0564 | 16.0086 | 17.0564 | 1
3036 | 2.4129 | 3.2736 | 6.1702 | 4.6801 | 3.8792 | 2.1629 | 12.5295 | 14.6252 | 14.6252 | 0
3037 | 5.2855 | 4.0917 | 5.0419 | 6.1344 | 3.6819 | 2.518 | 18.0297 | 16.5274 | 18.0297 | 1
3038 | 2.9475 | 6.838 | 7.1635 | 5.2908 | 3.8098 | 1.9341 | 17.0103 | 15.8549 | 17.0103 | 1
3039 | 2.8492 | 3.5849 | 7.5656 | 4.4492 | 4.4647 | 1.5279 | 12.4112 | 16.4074 | 16.4074 | 0
3040 | 5.1523 | 4.4966 | 7.1013 | 5.1728 | 3.7584 | 1.4755 | 16.2972 | 17.4875 | 17.4875 | 0
3041 | 4.2814 | 5.3983 | 6.3997 | 4.2002 | 4.1993 | 2.1715 | 16.0515 | 17.052 | 17.052 | 0
3042 | 3.1747 | 4.7052 | 5.902 | 6.0159 | 3.7638 | 1.385 | 15.2808 | 14.2255 | 15.2808 | 1
3043 | 3.8291 | 4.2328 | 6.4778 | 5.8928 | 4.8956 | 1.9758 | 15.9305 | 17.1784 | 17.1784 | 0
3044 | 3.878 | 4.4671 | 3.6136 | 5.8304 | 5.3488 | 2.3245 | 16.5 | 15.1649 | 16.5 | 1
3045 | 3.9524 | 5.1979 | 3.2883 | 5.1193 | 4.3308 | 1.6244 | 15.8939 | 13.1959 | 15.8939 | 1
3046 | 4.2259 | 4.9822 | 4.6796 | 5.3969 | 3.6651 | 1.8963 | 16.5014 | 14.4669 | 16.5014 | 1
3047 | 4.4272 | 6.9276 | 5.9532 | 4.4422 | 4.3584 | 1.5845 | 17.3815 | 16.3233 | 17.3815 | 1
3048 | 3.4153 | 6.283 | 6.1565 | 5.3231 | 4.3987 | 1.5742 | 16.5956 | 15.5447 | 16.5956 | 1
3049 | 3.2069 | 3.8706 | 4.2231 | 5.1272 | 5.2504 | 2.2172 | 14.422 | 14.8976 | 14.8976 | 0
3050 | 4.3101 | 6.8417 | 6.3645 | 5.9752 | 3.8688 | 2.1042 | 19.2312 | 16.6475 | 19.2312 | 1
3051 | 4.1601 | 7.4302 | 6.6002 | 6.7461 | 4.9781 | 2.0094 | 20.3458 | 17.7478 | 20.3458 | 1
3052 | 5.0697 | 4.5993 | 6.3491 | 4.6029 | 4.3787 | 1.343 | 15.615 | 17.1405 | 17.1405 | 0
3053 | 4.4027 | 6.7099 | 7.4939 | 4.2154 | 3.9575 | 2.5015 | 17.8296 | 18.3557 | 18.3557 | 0
3054 | 4.6546 | 5.8376 | 5.3608 | 4.9167 | 4.0748 | 2.2173 | 17.6263 | 16.3075 | 17.6263 | 1
3055 | 4.2994 | 4.7195 | 7.0052 | 4.2895 | 3.7905 | 1.1546 | 14.463 | 16.2498 | 16.2498 | 0
3056 | 4.4236 | 4.6973 | 4.1172 | 5.0057 | 5.2388 | 1.1726 | 15.2993 | 14.9523 | 15.2993 | 1
3057 | 4.5216 | 3.7533 | 6.9394 | 5.1879 | 3.581 | 2.0151 | 15.478 | 17.0572 | 17.0572 | 0
3058 | 2.8186 | 5.7271 | 6.5051 | 4.3071 | 4.614 | 2.1988 | 15.0515 | 16.1365 | 16.1365 | 0
3059 | 4.341 | 4.0369 | 6.0007 | 5.382 | 4.6914 | 2.1003 | 15.8602 | 17.1334 | 17.1334 | 0
3060 | 2.8569 | 6.2096 | 4.9754 | 5.4657 | 3.8757 | 1.9725 | 16.5047 | 13.6805 | 16.5047 | 1
3061 | 3.1482 | 5.7517 | 4.6499 | 4.9563 | 4.25 | 2.1381 | 15.9943 | 14.1862 | 15.9943 | 1
3062 | 5.3231 | 6.8128 | 6.9782 | 4.1708 | 4.3547 | 1.9102 | 18.2169 | 18.5663 | 18.5663 | 0
3063 | 4.003 | 5.9383 | 5.2131 | 4.3451 | 4.3699 | 1.4469 | 15.7332 | 15.0328 | 15.7332 | 1
3064 | 3.3116 | 7.1828 | 5.7475 | 6.1955 | 4.1552 | 2.4665 | 19.1565 | 15.6808 | 19.1565 | 1
3065 | 3.7145 | 5.9008 | 2.9085 | 5.1917 | 3.6483 | 1.5129 | 16.3199 | 11.7842 | 16.3199 | 1
3066 | 3.6458 | 4.3813 | 6.301 | 5.4136 | 3.7639 | 1.4934 | 14.934 | 15.204 | 15.204 | 0
3067 | 5.1712 | 5.5073 | 4.9265 | 4.7081 | 3.9051 | 1.484 | 16.8706 | 15.4867 | 16.8706 | 1
3068 | 4.6359 | 3.7353 | 3.6097 | 4.5777 | 3.3809 | 2.3228 | 15.2717 | 13.9493 | 15.2717 | 1
3069 | 4.5904 | 7.781 | 2.9849 | 4.6087 | 5.0634 | 2.1758 | 19.1559 | 14.8144 | 19.1559 | 1
3070 | 3.6113 | 7.0394 | 3.7203 | 5.1593 | 4.3296 | 1.4275 | 17.2375 | 13.0887 | 17.2375 | 1
3071 | 4.4582 | 6.069 | 6.3151 | 6.3881 | 3.2283 | 1.8887 | 18.8039 | 15.8902 | 18.8039 | 1
3072 | 5.3068 | 5.26 | 7.1894 | 6.0779 | 4.9908 | 2.3479 | 18.9927 | 19.8349 | 19.8349 | 0
3073 | 3.6748 | 6.7864 | 6.4535 | 4.1559 | 4.3841 | 1.3568 | 15.9739 | 15.8692 | 15.9739 | 1
3074 | 4.6823 | 6.7708 | 5.1639 | 5.4544 | 6.2092 | 2.5376 | 19.4451 | 18.593 | 19.4451 | 1
3075 | 3.5551 | 4.2224 | 7.5316 | 4.6831 | 5.1082 | 2.0118 | 14.4724 | 18.2066 | 18.2066 | 0
3076 | 3.7278 | 7.2321 | 4.4284 | 5.3969 | 4.7941 | 2.4216 | 18.7783 | 15.3718 | 18.7783 | 1
3077 | 4.1282 | 4.7088 | 7.4844 | 4.8727 | 4.4466 | 1.9181 | 15.6278 | 17.9773 | 17.9773 | 0
3078 | 2.7453 | 5.7299 | 5.4876 | 4.6878 | 4.6864 | 2.0075 | 15.1704 | 14.9267 | 15.1704 | 1
3079 | 3.5414 | 5.5201 | 3.297 | 4.5481 | 5.3073 | 1.9196 | 15.5292 | 14.0653 | 15.5292 | 1
3080 | 2.9296 | 3.853 | 6.3197 | 4.7503 | 4.8991 | 1.7131 | 13.246 | 15.8615 | 15.8615 | 0
3081 | 4.0904 | 4.6802 | 7.4875 | 4.7826 | 4.0437 | 2.2267 | 15.7799 | 17.8483 | 17.8483 | 0
3082 | 4.9813 | 4.939 | 7.2454 | 6.1725 | 5.2451 | 1.3797 | 17.4725 | 18.8516 | 18.8516 | 0
3083 | 4.0954 | 6.1752 | 6.4588 | 5.1458 | 4.0503 | 1.7842 | 17.2006 | 16.3886 | 17.2006 | 1
3084 | 3.1864 | 6.1992 | 6.5584 | 4.8609 | 4.6271 | 1.8866 | 16.1332 | 16.2585 | 16.2585 | 0
3085 | 4.821 | 6.2516 | 5.611 | 4.2952 | 4.0647 | 1.6463 | 17.0141 | 16.1431 | 17.0141 | 1
3086 | 3.6553 | 5.2321 | 5.1109 | 5.3387 | 3.9432 | 1.9225 | 16.1487 | 14.6319 | 16.1487 | 1
3087 | 2.9765 | 3.9675 | 5.8777 | 4.3495 | 3.1857 | 1.3246 | 12.618 | 13.3645 | 13.3645 | 0
3088 | 4.5744 | 4.9595 | 6.6297 | 5.2384 | 3.272 | 2.3958 | 17.1681 | 16.8718 | 17.1681 | 1
3089 | 3.4992 | 3.7897 | 6.4603 | 5.8259 | 4.9474 | 1.7613 | 14.8761 | 16.6682 | 16.6682 | 0
3090 | 2.8505 | 4.9514 | 4.5935 | 5.5858 | 4.284 | 2.5178 | 15.9055 | 14.2457 | 15.9055 | 1
3091 | 4.3311 | 6.3795 | 6.2244 | 4.1047 | 3.8669 | 2.3692 | 17.1844 | 16.7915 | 17.1844 | 1
3092 | 4.7023 | 5.6514 | 5.9518 | 5.0295 | 4.1369 | 2.2948 | 17.678 | 17.0859 | 17.678 | 1
3093 | 4.2082 | 6.1279 | 4.8865 | 6.7646 | 4.4663 | 1.8158 | 18.9164 | 15.3768 | 18.9164 | 1
3094 | 3.9288 | 5.9294 | 7.4283 | 4.4317 | 4.752 | 1.6304 | 15.9203 | 17.7396 | 17.7396 | 0
3095 | 3.9879 | 4.4164 | 3.7767 | 4.7656 | 5.4282 | 1.3234 | 14.4934 | 14.5163 | 14.5163 | 0
3096 | 2.4381 | 4.6738 | 5.2431 | 5.3472 | 4.4296 | 1.733 | 14.1922 | 13.8438 | 14.1922 | 1
3097 | 4.8054 | 5.9002 | 4.8465 | 4.881 | 5.5682 | 1.5616 | 17.1481 | 16.7816 | 17.1481 | 1
3098 | 5.765 | 5.5364 | 5.7984 | 4.3179 | 4.1781 | 2.2304 | 17.8497 | 17.9719 | 17.9719 | 0
3099 | 2.9182 | 4.9619 | 7.3831 | 4.8982 | 4.2771 | 1.8047 | 14.5829 | 16.3831 | 16.3831 | 0
3100 | 4.5166 | 5.9319 | 7.4677 | 4.6286 | 3.9932 | 2.307 | 17.3842 | 18.2845 | 18.2845 | 0
3101 | 3.4599 | 4.9922 | 6.5332 | 5.6763 | 6.3751 | 1.6808 | 15.8093 | 18.0491 | 18.0491 | 0
3102 | 3.4058 | 5.4837 | 6.6312 | 5.1468 | 4.3243 | 2.1132 | 16.1495 | 16.4745 | 16.4745 | 0
3103 | 4.4736 | 5.3535 | 5.4551 | 6.5649 | 4.9658 | 1.6243 | 18.0163 | 16.5188 | 18.0163 | 1
3104 | 3.6828 | 6.5806 | 5.6944 | 4.7399 | 5.3383 | 2.5623 | 17.5656 | 17.2778 | 17.5656 | 1
3105 | 4.0403 | 3.5365 | 4.3522 | 4.5653 | 3.6859 | 1.3779 | 13.5199 | 13.4562 | 13.5199 | 1
3106 | 4.7967 | 7.1395 | 3.8632 | 6.471 | 3.1131 | 2.3882 | 20.7955 | 14.1612 | 20.7955 | 1
3107 | 3.6826 | 5.2575 | 7.6189 | 5.4117 | 3.7993 | 2.7562 | 17.1081 | 17.857 | 17.857 | 0
3108 | 5.5611 | 4.2429 | 6.3637 | 5.2319 | 3.9115 | 1.4906 | 16.5265 | 17.3269 | 17.3269 | 0
3109 | 3.9808 | 5.1851 | 5.4746 | 4.8171 | 5.895 | 2.1401 | 16.1231 | 17.4905 | 17.4905 | 0
3110 | 4.1376 | 7.118 | 5.7574 | 4.5021 | 4.7074 | 2.2083 | 17.966 | 16.8106 | 17.966 | 1
3111 | 4.3231 | 5.9962 | 6.0115 | 4.847 | 4.1623 | 1.5825 | 16.7489 | 16.0795 | 16.7489 | 1
3112 | 3.2369 | 4.1268 | 6.7344 | 5.2845 | 4.0093 | 1.6592 | 14.3073 | 15.6398 | 15.6398 | 0
3113 | 2.5241 | 5.0988 | 6.461 | 4.2709 | 3.9116 | 1.6538 | 13.5476 | 14.5504 | 14.5504 | 0
3114 | 3.6789 | 7.7628 | 7.1658 | 5.1778 | 3.849 | 2.1906 | 18.8102 | 16.8843 | 18.8102 | 1
3115 | 5.0365 | 8.193 | 4.6654 | 5.166 | 4.797 | 1.8364 | 20.2319 | 16.3352 | 20.2319 | 1
3116 | 4.0765 | 4.0796 | 6.686 | 4.5983 | 3.8295 | 2.2826 | 15.0371 | 16.8747 | 16.8747 | 0
3117 | 3.3102 | 5.7019 | 7.0964 | 4.5772 | 4.5922 | 2.8569 | 16.4462 | 17.8557 | 17.8557 | 0
3118 | 4.2828 | 5.3735 | 6.8839 | 4.8144 | 3.7137 | 1.9937 | 16.4643 | 16.874 | 16.874 | 0
3119 | 2.959 | 6.6349 | 5.138 | 5.5566 | 3.9004 | 1.9078 | 17.0583 | 13.9051 | 17.0583 | 1
3120 | 3.9464 | 4.2588 | 6.0304 | 5.4136 | 3.5592 | 2.1163 | 15.7351 | 15.6524 | 15.7351 | 1
3121 | 5.5807 | 5.5303 | 5.0821 | 5.1743 | 4.4297 | 2.1593 | 18.4446 | 17.2518 | 18.4446 | 1
3122 | 2.5264 | 5.0152 | 5.1203 | 5.1389 | 5.7696 | 1.4357 | 14.1163 | 14.8521 | 14.8521 | 0
3123 | 3.6403 | 4.4201 | 6.876 | 6.3621 | 4.607 | 2.4233 | 16.8459 | 17.5465 | 17.5465 | 0
3124 | 4.2542 | 5.0604 | 4.3256 | 4.7857 | 4.5575 | 1.7624 | 15.8628 | 14.8998 | 15.8628 | 1
3125 | 3.5083 | 3.9653 | 6.1117 | 4.838 | 3.6496 | 2.3441 | 14.6558 | 15.6137 | 15.6137 | 0
3126 | 4.99 | 7.5662 | 5.6407 | 4.1144 | 4.0095 | 2.1439 | 18.8145 | 16.784 | 18.8145 | 1
3127 | 4.2584 | 7.1743 | 6.6253 | 5.0974 | 3.4316 | 1.4097 | 17.9398 | 15.725 | 17.9398 | 1
3128 | 3.9947 | 5.7381 | 5.3832 | 4.5734 | 3.7689 | 2.1826 | 16.4889 | 15.3295 | 16.4889 | 1
3129 | 4.314 | 6.7023 | 7.4922 | 4.8832 | 5.3498 | 1.9552 | 17.8547 | 19.1112 | 19.1112 | 0
3130 | 2.5804 | 5.291 | 7.076 | 4.9433 | 4.1966 | 2.3211 | 15.1358 | 16.1741 | 16.1741 | 0
3131 | 3.6789 | 4.4213 | 5.6788 | 4.5813 | 5.6567 | 1.678 | 14.3595 | 16.6924 | 16.6924 | 0
3132 | 3.1648 | 7.1922 | 6.0778 | 4.5263 | 4.0745 | 1.7032 | 16.5866 | 15.0203 | 16.5866 | 1
3133 | 5.4758 | 5.8596 | 6.4967 | 6.5109 | 4.2513 | 1.7101 | 19.5564 | 17.9339 | 19.5564 | 1
3134 | 3.8606 | 6.7642 | 4.044 | 5.4601 | 4.651 | 2.1144 | 18.1992 | 14.6701 | 18.1992 | 1
3135 | 5.4058 | 5.377 | 6.656 | 6.2632 | 3.648 | 2.0986 | 19.1446 | 17.8084 | 19.1446 | 1
3136 | 4.2359 | 5.8535 | 7.1197 | 5.1772 | 4.2419 | 2.0934 | 17.3601 | 17.6909 | 17.6909 | 0
3137 | 3.7485 | 4.9242 | 6.3115 | 5.4086 | 5.4118 | 2.1618 | 16.2431 | 17.6336 | 17.6336 | 0
3138 | 4.7252 | 7.3633 | 4.161 | 4.2812 | 4.126 | 1.817 | 18.1867 | 14.8292 | 18.1867 | 1
3139 | 4.2184 | 6.6453 | 5.2792 | 4.5693 | 3.5343 | 1.9131 | 17.3461 | 14.9451 | 17.3461 | 1
3140 | 3.4559 | 6.3672 | 5.3116 | 4.6008 | 3.4142 | 1.4618 | 15.8857 | 13.6436 | 15.8857 | 1
3141 | 4.6742 | 4.3387 | 5.775 | 6.4732 | 4.2878 | 2.761 | 18.2471 | 17.498 | 18.2471 | 1
3142 | 4.2814 | 4.2407 | 6.0566 | 5.1464 | 4.2597 | 1.4043 | 15.0729 | 16.0021 | 16.0021 | 0
3143 | 3.1681 | 6.6223 | 4.7024 | 4.8573 | 3.4195 | 2.5796 | 17.2272 | 13.8696 | 17.2272 | 1
3144 | 4.1561 | 5.102 | 3.0998 | 5.6071 | 5.3234 | 1.9096 | 16.7749 | 14.4889 | 16.7749 | 1
3145 | 4.5735 | 3.942 | 7.5521 | 6.1221 | 5.9927 | 2.1559 | 16.7935 | 20.2742 | 20.2742 | 0
3146 | 4.9962 | 4.1375 | 6.5479 | 5.8689 | 4.5762 | 1.9028 | 16.9054 | 18.0232 | 18.0232 | 0
3147 | 3.1828 | 7.0622 | 3.9285 | 7.0213 | 4.5616 | 2.6152 | 19.8815 | 14.2881 | 19.8815 | 1
3148 | 5.5264 | 4.9892 | 3.2462 | 4.1552 | 5.2328 | 2.2178 | 16.8887 | 16.2231 | 16.8887 | 1
3149 | 4.0377 | 7.1231 | 6.1135 | 4.9986 | 4.8421 | 2.0808 | 18.2402 | 17.0741 | 18.2402 | 1
3150 | 4.5008 | 5.4396 | 5.0326 | 5.3989 | 4.9806 | 2.6618 | 18.0011 | 17.1759 | 18.0011 | 1
3151 | 4.0656 | 6.4644 | 4.8094 | 5.0872 | 3.8484 | 1.8669 | 17.4842 | 14.5903 | 17.4842 | 1
3152 | 3.7459 | 6.818 | 5.7911 | 5.6247 | 4.7485 | 2.6701 | 18.8587 | 16.9556 | 18.8587 | 1
3153 | 3.9954 | 5.938 | 5.6963 | 4.9084 | 5.3534 | 2.6267 | 17.4685 | 17.6718 | 17.6718 | 0
3154 | 4.8144 | 3.7612 | 5.3873 | 5.5296 | 4.3772 | 2.3028 | 16.408 | 16.8816 | 16.8816 | 0
3155 | 4.4877 | 4.7835 | 5.8241 | 4.2471 | 3.8387 | 2.1769 | 15.6952 | 16.3273 | 16.3273 | 0
3156 | 4.269 | 5.9345 | 7.0643 | 4.8672 | 4.4556 | 1.3662 | 16.4368 | 17.1551 | 17.1551 | 0
3157 | 4.2576 | 4.9846 | 6.7961 | 4.3871 | 3.6316 | 1.9716 | 15.6009 | 16.657 | 16.657 | 0
3158 | 4.6652 | 5.5026 | 5.6667 | 5.368 | 3.8671 | 2.1996 | 17.7354 | 16.3987 | 17.7354 | 1
3159 | 2.9007 | 6.0777 | 7.4029 | 6.383 | 3.5813 | 2.49 | 17.8514 | 16.375 | 17.8514 | 1
3160 | 4.108 | 5.2617 | 4.0818 | 5.9303 | 5.3768 | 1.9347 | 17.2347 | 15.5014 | 17.2347 | 1
3161 | 4.1749 | 5.5409 | 4.7834 | 5.1863 | 3.7576 | 1.6734 | 16.5754 | 14.3892 | 16.5754 | 1
3162 | 2.9385 | 4.4482 | 4.1809 | 6.2748 | 3.8493 | 2.4717 | 16.1331 | 13.4404 | 16.1331 | 1
3163 | 5.1918 | 6.0144 | 5.8476 | 4.6642 | 6.389 | 2.0738 | 17.9443 | 19.5022 | 19.5022 | 0
3164 | 3.3214 | 5.8471 | 5.5248 | 5.7353 | 3.846 | 2.0237 | 16.9274 | 14.7158 | 16.9274 | 1
3165 | 2.341 | 5.3947 | 6.9323 | 5.0542 | 4.951 | 1.5601 | 14.3501 | 15.7843 | 15.7843 | 0
3166 | 4.7473 | 4.0894 | 5.9674 | 5.0283 | 4.324 | 2.0368 | 15.9017 | 17.0754 | 17.0754 | 0
3167 | 4.1364 | 3.655 | 4.9479 | 4.2308 | 4.3964 | 2.1764 | 14.1986 | 15.6571 | 15.6571 | 0
3168 | 3.3312 | 6.1275 | 7.0039 | 4.4596 | 4.2448 | 2.6206 | 16.5388 | 17.2004 | 17.2004 | 0
3169 | 5.195 | 5.7742 | 5.3935 | 4.0685 | 3.5828 | 2.3822 | 17.4198 | 16.5534 | 17.4198 | 1
3170 | 4.0864 | 8.2086 | 6.1383 | 4.863 | 4.9573 | 1.9874 | 19.1454 | 17.1694 | 19.1454 | 1
3171 | 3.6667 | 5.9982 | 6.1967 | 4.5465 | 3.7941 | 2.0589 | 16.2703 | 15.7164 | 16.2703 | 1
3172 | 3.9207 | 6.8642 | 6.6752 | 5.4936 | 4.7847 | 1.4154 | 17.6938 | 16.796 | 17.6938 | 1
3173 | 3.233 | 5.7501 | 6.2417 | 5.1309 | 3.9485 | 1.5647 | 15.6787 | 14.988 | 15.6787 | 1
3174 | 3.9115 | 6.2431 | 5.7506 | 4.223 | 4.404 | 2.1244 | 16.502 | 16.1905 | 16.502 | 1
3175 | 4.4242 | 6.708 | 6.6465 | 4.7479 | 5.3258 | 1.9033 | 17.7834 | 18.2998 | 18.2998 | 0
3176 | 3.1405 | 4.172 | 4.341 | 5.5289 | 3.2194 | 1.6119 | 14.4533 | 12.3129 | 14.4533 | 1
3177 | 3.4028 | 5.5685 | 3.4219 | 5.6067 | 4.1611 | 1.6081 | 16.186 | 12.5938 | 16.186 | 1
3178 | 3.3561 | 5.3942 | 5.3413 | 6.7938 | 3.6488 | 1.6388 | 17.1828 | 13.985 | 17.1828 | 1
3179 | 3.9082 | 4.9348 | 5.0583 | 5.2511 | 5.1253 | 2.2043 | 16.2984 | 16.2961 | 16.2984 | 1
3180 | 4.4702 | 6.7517 | 4.7277 | 4.7901 | 5.6155 | 1.4917 | 17.5037 | 16.305 | 17.5037 | 1
3181 | 3.1401 | 4.4461 | 5.6528 | 4.1718 | 3.5561 | 1.7092 | 13.4672 | 14.0582 | 14.0582 | 0
3182 | 3.4746 | 5.2055 | 4.7677 | 5.671 | 4.6318 | 2.2282 | 16.5794 | 15.1024 | 16.5794 | 1
3183 | 3.2043 | 6.6007 | 4.5703 | 4.3754 | 3.6232 | 1.5831 | 15.7635 | 12.9809 | 15.7635 | 1
3184 | 4.1887 | 5.4362 | 6.226 | 5.8974 | 6.0601 | 1.8072 | 17.3294 | 18.282 | 18.282 | 0
3185 | 4.436 | 3.4222 | 6.474 | 4.077 | 4.0766 | 1.2846 | 13.2198 | 16.2712 | 16.2712 | 0
3186 | 3.6419 | 4.9539 | 6.3694 | 5.3631 | 4.2626 | 1.4066 | 15.3654 | 15.6804 | 15.6804 | 0
3187 | 3.0669 | 5.0924 | 4.8693 | 4.4932 | 3.4767 | 1.9764 | 14.6289 | 13.3892 | 14.6289 | 1
3188 | 3.3751 | 4.3028 | 7.0859 | 5.4574 | 5.9232 | 2.6434 | 15.7786 | 19.0276 | 19.0276 | 0
3189 | 5.1001 | 3.6621 | 4.442 | 6.2744 | 3.7984 | 2.5005 | 17.5371 | 15.841 | 17.5371 | 1
3190 | 4.8366 | 6.1308 | 6.1376 | 5.3875 | 4.7258 | 2.1947 | 18.5496 | 17.8948 | 18.5496 | 1
3191 | 4.0447 | 7.9879 | 4.9352 | 5.1707 | 4.1098 | 1.8659 | 19.0693 | 14.9557 | 19.0693 | 1
3192 | 4.1867 | 4.1721 | 5.2594 | 5.3574 | 3.7885 | 1.1402 | 14.8564 | 14.3749 | 14.8564 | 1
3193 | 2.4832 | 4.884 | 4.4402 | 6.3241 | 3.0898 | 2.4847 | 16.176 | 12.4979 | 16.176 | 1
3194 | 4.3694 | 4.4248 | 5.8441 | 4.8203 | 4.5352 | 1.8784 | 15.4929 | 16.6271 | 16.6271 | 0
3195 | 4.2723 | 5.3823 | 6.2988 | 4.4243 | 3.7942 | 2.173 | 16.2519 | 16.5383 | 16.5383 | 0
3196 | 4.7688 | 6.1688 | 4.9665 | 5.5016 | 5.2762 | 1.2381 | 17.6773 | 16.2496 | 17.6773 | 1
3197 | 3.7438 | 4.5824 | 6.345 | 6.0784 | 3.6474 | 1.6322 | 16.0367 | 15.3683 | 16.0367 | 1
3198 | 4.531 | 4.7973 | 4.0715 | 5.4074 | 5.4039 | 1.8735 | 16.6093 | 15.88 | 16.6093 | 1
3199 | 4.3219 | 6.3781 | 5.7946 | 5.3115 | 5.1291 | 2.2347 | 18.2462 | 17.4803 | 18.2462 | 1
3200 | 5.6368 | 7.0938 | 7.2232 | 5.0573 | 3.3695 | 2.7077 | 20.4956 | 18.9372 | 20.4956 | 1
3201 | 4.8817 | 5.1887 | 4.3534 | 4.5754 | 3.5109 | 1.8207 | 16.4664 | 14.5667 | 16.4664 | 1
3202 | 5.2097 | 3.8753 | 7.1336 | 6.7282 | 3.9927 | 1.4699 | 17.2832 | 17.806 | 17.806 | 0
3203 | 4.2173 | 6.4045 | 6.025 | 6.6924 | 4.9484 | 2.1556 | 19.4698 | 17.3462 | 19.4698 | 1
3204 | 4.4 | 7.5901 | 5.561 | 5.1031 | 3.8108 | 2.0864 | 19.1796 | 15.8583 | 19.1796 | 1
3205 | 4.1796 | 5.5202 | 6.1336 | 5.2523 | 4.7345 | 1.7526 | 16.7047 | 16.8003 | 16.8003 | 0
3206 | 4.421 | 4.6033 | 4.2629 | 5.6068 | 4.841 | 2.1964 | 16.8274 | 15.7212 | 16.8274 | 1
3207 | 4.9218 | 4.7823 | 7.3379 | 6.0491 | 4.2058 | 1.7565 | 17.5097 | 18.2219 | 18.2219 | 0
3208 | 4.2549 | 5.007 | 6.277 | 5.7076 | 4.5772 | 2.0477 | 17.0173 | 17.1569 | 17.1569 | 0
3209 | 4.5756 | 5.6261 | 5.6671 | 5.1545 | 3.3807 | 2.1767 | 17.533 | 15.8001 | 17.533 | 1
3210 | 4.1722 | 5.9732 | 7.4214 | 5.7962 | 3.8312 | 2.1116 | 18.0532 | 17.5364 | 18.0532 | 1
3211 | 3.2804 | 5.4768 | 6.5215 | 5.3658 | 3.8958 | 2.467 | 16.59 | 16.1646 | 16.59 | 1
3212 | 3.136 | 5.2988 | 6.3443 | 4.6346 | 4.0935 | 2.0621 | 15.1314 | 15.6359 | 15.6359 | 0
3213 | 4.5312 | 6.0585 | 5.3878 | 5.3435 | 3.5133 | 2.1608 | 18.0939 | 15.593 | 18.0939 | 1
3214 | 3.1334 | 3.8641 | 7.5351 | 5.7857 | 3.3732 | 1.8458 | 14.629 | 15.8875 | 15.8875 | 0
3215 | 3.793 | 4.6489 | 6.7935 | 6.626 | 4.4705 | 2.2871 | 17.355 | 17.3442 | 17.355 | 1
3216 | 4.1793 | 5.6146 | 7.6931 | 4.4191 | 3.3824 | 1.4704 | 15.6834 | 16.7252 | 16.7252 | 0
3217 | 3.4553 | 4.1726 | 5.8492 | 4.823 | 4.2134 | 1.7326 | 14.1835 | 15.2505 | 15.2505 | 0
3218 | 3.3527 | 5.1055 | 6.2239 | 4.1991 | 3.6914 | 1.7593 | 14.4166 | 15.0272 | 15.0272 | 0
3219 | 2.944 | 5.7809 | 6.5453 | 5.7693 | 4.7998 | 1.9719 | 16.4662 | 16.261 | 16.4662 | 1
3220 | 3.6733 | 5.3493 | 6.4294 | 5.8148 | 3.0929 | 2.4372 | 17.2745 | 15.6328 | 17.2745 | 1
3221 | 2.716 | 7.6823 | 7.6863 | 5.7198 | 3.482 | 2.1757 | 18.2938 | 16.06 | 18.2938 | 1
3222 | 3.9516 | 4.2953 | 5.734 | 4.8804 | 4.9537 | 1.5555 | 14.6828 | 16.1948 | 16.1948 | 0
3223 | 2.776 | 5.9118 | 4.0633 | 4.5083 | 4.4167 | 2.5658 | 15.762 | 13.8219 | 15.762 | 1
3224 | 3.8615 | 6.2486 | 5.5364 | 5.0714 | 3.7344 | 1.9094 | 17.0909 | 15.0416 | 17.0909 | 1
3225 | 4.9551 | 5.9949 | 5.6277 | 5.473 | 4.2133 | 2.2217 | 18.6447 | 17.0177 | 18.6447 | 1
3226 | 3.6504 | 4.7702 | 3.2178 | 4.0526 | 5.2368 | 1.4405 | 13.9137 | 13.5455 | 13.9137 | 1
3227 | 5.6944 | 5.7543 | 6.1628 | 4.4121 | 4.0843 | 1.926 | 17.7869 | 17.8676 | 17.8676 | 0
3228 | 3.9217 | 3.8879 | 6.3955 | 6.4437 | 4.1393 | 2.2181 | 16.4715 | 16.6747 | 16.6747 | 0
3229 | 4.4298 | 4.9865 | 4.3656 | 4.9427 | 4.1008 | 1.6999 | 16.0589 | 14.5961 | 16.0589 | 1
3230 | 4.3159 | 4.7905 | 4.7005 | 5.1795 | 4.4002 | 2.3285 | 16.6144 | 15.745 | 16.6144 | 1
3231 | 3.9795 | 6.1989 | 6.3399 | 5.5681 | 4.1305 | 1.6733 | 17.4198 | 16.1232 | 17.4198 | 1
3232 | 4.9283 | 4.6487 | 6.4013 | 5.2094 | 5.5822 | 1.6808 | 16.4672 | 18.5925 | 18.5925 | 0
3233 | 3.7245 | 5.4374 | 6.4083 | 4.5524 | 4.2947 | 2.195 | 15.9092 | 16.6223 | 16.6223 | 0
3234 | 3.7004 | 5.8271 | 4.1614 | 5.4647 | 4.1508 | 1.6164 | 16.6086 | 13.629 | 16.6086 | 1
3235 | 3.5205 | 6.7448 | 5.8319 | 6.7487 | 3.4559 | 2.3006 | 19.3145 | 15.1089 | 19.3145 | 1
3236 | 3.1392 | 7.5396 | 5.4381 | 4.5764 | 4.0467 | 1.6422 | 16.8974 | 14.2663 | 16.8974 | 1
3237 | 3.8922 | 4.4646 | 7.2428 | 6.3546 | 4.456 | 1.6568 | 16.3682 | 17.2478 | 17.2478 | 0
3238 | 5.0266 | 5.1067 | 6.5736 | 5.7744 | 5.0314 | 2.4761 | 18.3837 | 19.1076 | 19.1076 | 0
3239 | 4.4339 | 4.5345 | 5.406 | 6.6783 | 3.2049 | 2.0027 | 17.6495 | 15.0475 | 17.6495 | 1
3240 | 2.594 | 4.0831 | 5.968 | 4.6498 | 3.6699 | 1.5528 | 12.8797 | 13.7847 | 13.7847 | 0
3241 | 3.7973 | 7.7055 | 4.8251 | 4.5649 | 4.6057 | 2.3112 | 18.3788 | 15.5392 | 18.3788 | 1
3242 | 4.7963 | 4.8822 | 7.7082 | 5.4851 | 4.6979 | 1.7513 | 16.9149 | 18.9537 | 18.9537 | 0
3243 | 5.6516 | 5.4779 | 6.5725 | 5.2474 | 4.0463 | 1.9584 | 18.3352 | 18.2287 | 18.3352 | 1
3244 | 3.5123 | 3.7961 | 6.5439 | 4.7905 | 4.4293 | 2.2852 | 14.3841 | 16.7707 | 16.7707 | 0
3245 | 4.7785 | 4.7506 | 6.5289 | 6.3615 | 4.3477 | 1.9564 | 17.847 | 17.6115 | 17.847 | 1
3246 | 3.011 | 5.7951 | 5.299 | 5.9291 | 3.5783 | 2.0204 | 16.7557 | 13.9088 | 16.7557 | 1
3247 | 5.0024 | 3.6689 | 6.3861 | 4.8916 | 4.123 | 2.2073 | 15.7702 | 17.7188 | 17.7188 | 0
3248 | 3.0967 | 3.5227 | 5.1527 | 5.1053 | 5.2037 | 1.741 | 13.4657 | 15.1941 | 15.1941 | 0
3249 | 3.7155 | 4.8181 | 4.6519 | 4.6057 | 4.0695 | 2.3346 | 15.4739 | 14.7715 | 15.4739 | 1
3250 | 4.7928 | 3.5541 | 4.6588 | 5.1604 | 5.5974 | 1.6875 | 15.1948 | 16.7365 | 16.7365 | 0
3251 | 5.0637 | 5.2499 | 6.1244 | 6.5311 | 3.9351 | 1.605 | 18.4498 | 16.7283 | 18.4498 | 1
3252 | 4.109 | 4.4814 | 6.7149 | 5.2996 | 4.8034 | 1.9625 | 15.8524 | 17.5897 | 17.5897 | 0
3253 | 3.4418 | 5.1196 | 4.1409 | 4.5874 | 3.3068 | 2.2828 | 15.4316 | 13.1723 | 15.4316 | 1
3254 | 3.104 | 5.8453 | 5.1576 | 5.0463 | 3.8431 | 1.4405 | 15.4361 | 13.5451 | 15.4361 | 1
3255 | 3.118 | 4.0153 | 3.1028 | 5.4503 | 4.5194 | 2.4194 | 15.0029 | 13.1596 | 15.0029 | 1
3256 | 3.8743 | 5.5518 | 6.1084 | 4.3863 | 4.2059 | 2.2783 | 16.0908 | 16.4669 | 16.4669 | 0
3257 | 5.2695 | 4.9846 | 5.3151 | 5.1825 | 5.2036 | 1.7869 | 17.2235 | 17.5752 | 17.5752 | 0
3258 | 4.5109 | 3.94 | 7.3142 | 5.4752 | 3.2468 | 2.1705 | 16.0966 | 17.2425 | 17.2425 | 0
3259 | 4.2413 | 6.666 | 4.1418 | 6.8647 | 3.2735 | 2.2741 | 20.0461 | 13.9307 | 20.0461 | 1
3260 | 4.9 | 4.4369 | 4.0726 | 4.3095 | 3.9991 | 1.256 | 14.9025 | 14.2277 | 14.9025 | 1
3261 | 5.0512 | 4.9444 | 6.3425 | 4.7931 | 5.5433 | 2.0489 | 16.8376 | 18.9859 | 18.9859 | 0
3262 | 2.7253 | 5.9614 | 5.5686 | 4.9216 | 3.9794 | 2.1906 | 15.7988 | 14.4639 | 15.7988 | 1
3263 | 3.8447 | 4.4625 | 6.1374 | 4.0615 | 4.8482 | 2.2756 | 14.6442 | 17.1059 | 17.1059 | 0
3264 | 4.6501 | 6.4691 | 6.1185 | 4.7828 | 3.787 | 1.8938 | 17.7958 | 16.4494 | 17.7958 | 1
3265 | 3.7549 | 5.1838 | 5.2615 | 5.7164 | 4.7985 | 2.2371 | 16.8921 | 16.052 | 16.8921 | 1
3266 | 3.2379 | 4.431 | 7.4607 | 5.8961 | 4.0768 | 1.8093 | 15.3743 | 16.5848 | 16.5848 | 0
3267 | 3.0039 | 5.1596 | 6.4689 | 5.0322 | 3.9316 | 2.8034 | 15.999 | 16.2077 | 16.2077 | 0
3268 | 3.4811 | 3.6062 | 4.3344 | 4.5253 | 4.2146 | 1.7463 | 13.3589 | 13.7765 | 13.7765 | 0
3269 | 4.1185 | 5.8043 | 5.9161 | 5.8352 | 3.2445 | 1.8632 | 17.6212 | 15.1422 | 17.6212 | 1
3270 | 4.8732 | 6.7758 | 4.32 | 6.1863 | 4.6146 | 2.4477 | 20.2829 | 16.2555 | 20.2829 | 1
3271 | 4.1052 | 3.7604 | 3.3016 | 5.2299 | 3.9376 | 2.378 | 15.4734 | 13.7225 | 15.4734 | 1
3272 | 2.5749 | 4.5711 | 3.5205 | 5.6564 | 3.1859 | 1.7949 | 14.5973 | 11.0762 | 14.5973 | 1
3273 | 4.4699 | 5.8082 | 5.5372 | 6.0752 | 3.8895 | 2.5449 | 18.8982 | 16.4415 | 18.8982 | 1
3274 | 3.4832 | 5.1042 | 3.3141 | 6.4905 | 4.0374 | 2.4276 | 17.5055 | 13.2622 | 17.5055 | 1
3275 | 3.3321 | 6.6762 | 6.2073 | 5.7802 | 5.2356 | 2.3389 | 18.1274 | 17.1138 | 18.1274 | 1
3276 | 3.7973 | 6.0724 | 4.7659 | 4.4209 | 3.9793 | 1.6416 | 15.9322 | 14.1841 | 15.9322 | 1
3277 | 4.6443 | 7.2984 | 5.115 | 6.7412 | 3.6759 | 1.7937 | 20.4776 | 15.2289 | 20.4776 | 1
3278 | 3.2416 | 4.1363 | 5.0284 | 5.2775 | 4.1881 | 1.9996 | 14.655 | 14.4577 | 14.655 | 1
3279 | 2.9952 | 4.2656 | 5.1183 | 4.6788 | 4.2213 | 1.5725 | 13.5121 | 13.9073 | 13.9073 | 0
3280 | 4.4947 | 5.0839 | 5.6727 | 4.3409 | 4.5981 | 1.3542 | 15.2738 | 16.1198 | 16.1198 | 0
3281 | 3.7722 | 3.7677 | 5.4679 | 6.2277 | 3.8638 | 2.7713 | 16.5389 | 15.8752 | 16.5389 | 1
3282 | 3.9147 | 4.2567 | 5.9186 | 4.4228 | 3.4714 | 2.1646 | 14.7587 | 15.4692 | 15.4692 | 0
3283 | 3.0901 | 3.7847 | 5.6788 | 5.2067 | 4.678 | 1.7975 | 13.879 | 15.2444 | 15.2444 | 0
3284 | 3.5703 | 3.9828 | 5.6455 | 5.3373 | 4.8135 | 2.2357 | 15.1261 | 16.265 | 16.265 | 0
3285 | 3.6587 | 6.6465 | 5.6824 | 4.2878 | 5.2038 | 2.7221 | 17.3151 | 17.2671 | 17.3151 | 1
3286 | 3.9004 | 4.4518 | 5.8285 | 6.1005 | 3.9431 | 1.6961 | 16.1488 | 15.3681 | 16.1488 | 1
3287 | 5.4988 | 4.3179 | 6.5446 | 4.7567 | 4.7644 | 2.4031 | 16.9766 | 19.2108 | 19.2108 | 0
3288 | 3.6887 | 6.2135 | 5.3834 | 4.8249 | 4.196 | 1.1968 | 15.9239 | 14.4649 | 15.9239 | 1
3289 | 4.6965 | 4.024 | 5.4092 | 6.0232 | 3.6065 | 2.3929 | 17.1367 | 16.1051 | 17.1367 | 1
3290 | 3.0891 | 3.1882 | 6.2733 | 5.5687 | 3.4848 | 2.5143 | 14.3602 | 15.3615 | 15.3615 | 0
3291 | 3.0217 | 6.0053 | 6.5368 | 5.1681 | 5.6445 | 2.5177 | 16.7128 | 17.7207 | 17.7207 | 0
3292 | 3.8707 | 6.9447 | 5.1806 | 6.6136 | 3.3391 | 1.8901 | 19.3192 | 14.2805 | 19.3192 | 1
3293 | 3.9736 | 6.7042 | 4.7959 | 5.4449 | 3.2451 | 2.1478 | 18.2705 | 14.1624 | 18.2705 | 1
3294 | 4.2233 | 6.9395 | 3.7797 | 4.5945 | 4.5976 | 2.5046 | 18.2619 | 15.1053 | 18.2619 | 1
3295 | 5.7336 | 5.7643 | 4.0465 | 6.1185 | 5.4045 | 2.3354 | 19.9518 | 17.5201 | 19.9518 | 1
3296 | 3.6787 | 5.0808 | 6.894 | 4.5992 | 3.5421 | 2.0904 | 15.4491 | 16.2052 | 16.2052 | 0
3297 | 3.7953 | 4.7867 | 6.0333 | 5.8435 | 3.5041 | 1.9709 | 16.3964 | 15.3036 | 16.3964 | 1
3298 | 4.6158 | 7.6651 | 4.5154 | 4.2845 | 3.8157 | 1.4644 | 18.0299 | 14.4114 | 18.0299 | 1
3299 | 3.6808 | 6.4979 | 4.0732 | 4.8959 | 4.202 | 1.9741 | 17.0486 | 13.9301 | 17.0486 | 1
3300 | 4.1704 | 3.6658 | 4.0744 | 4.9636 | 5.0891 | 2.0824 | 14.8822 | 15.4164 | 15.4164 | 0
3301 | 3.803 | 4.8699 | 4.3122 | 6.1669 | 4.7568 | 1.4999 | 16.3397 | 14.372 | 16.3397 | 1
3302 | 3.4971 | 4.52 | 7.2868 | 6.5325 | 3.4011 | 1.7258 | 16.2754 | 15.9108 | 16.2754 | 1
3303 | 3.4716 | 6.2681 | 6.6096 | 4.8674 | 4.1636 | 2.061 | 16.668 | 16.3058 | 16.668 | 1
3304 | 4.5213 | 5.8714 | 6.2793 | 5.0934 | 4.9601 | 2.4288 | 17.9149 | 18.1896 | 18.1896 | 0
3305 | 3.2689 | 4.6414 | 4.7181 | 4.7149 | 5.5528 | 2.2426 | 14.8678 | 15.7824 | 15.7824 | 0
3306 | 4.5104 | 5.5624 | 6.6562 | 4.7494 | 5.1103 | 1.9383 | 16.7605 | 18.2153 | 18.2153 | 0
3307 | 4.6573 | 3.6184 | 4.6542 | 4.7048 | 3.1386 | 2.1498 | 15.1303 | 14.5999 | 15.1303 | 1
3308 | 4.9141 | 7.4805 | 3.7799 | 4.4778 | 4.0673 | 1.8766 | 18.7491 | 14.6379 | 18.7491 | 1
3309 | 4.3921 | 6.0618 | 6.3899 | 5.1212 | 5.9686 | 2.1944 | 17.7696 | 18.945 | 18.945 | 0
3310 | 5.3998 | 6.2982 | 6.0463 | 4.7635 | 4.5259 | 1.924 | 18.3856 | 17.896 | 18.3856 | 1
3311 | 2.8334 | 5.1941 | 5.5505 | 6.2665 | 4.0695 | 2.3464 | 16.6404 | 14.7998 | 16.6404 | 1
3312 | 4.3513 | 7.8042 | 6.0789 | 4.6713 | 3.5377 | 2.3253 | 19.1522 | 16.2932 | 19.1522 | 1
3313 | 3.0723 | 5.0727 | 6.2841 | 4.7066 | 4.9133 | 1.9704 | 14.822 | 16.2402 | 16.2402 | 0
3314 | 3.7425 | 5.9303 | 7.1237 | 5.0175 | 3.3772 | 2.0961 | 16.7863 | 16.3395 | 16.7863 | 1
3315 | 5.2914 | 5.7425 | 6.2523 | 5.3432 | 5.9917 | 2.3503 | 18.7274 | 19.8857 | 19.8857 | 0
3316 | 3.9786 | 6.0006 | 4.6466 | 5.2911 | 3.8078 | 2.3204 | 17.5908 | 14.7535 | 17.5908 | 1
3317 | 5.4725 | 5.769 | 6.6689 | 6.0141 | 3.8954 | 2.2863 | 19.542 | 18.3232 | 19.542 | 1
3318 | 4.5379 | 5.0023 | 6.2737 | 5.4789 | 4.1553 | 2.0544 | 17.0735 | 17.0213 | 17.0735 | 1
3319 | 4.2258 | 4.1724 | 5.9365 | 5.5408 | 3.9888 | 2.2622 | 16.2012 | 16.4133 | 16.4133 | 0
3320 | 4.2056 | 4.206 | 7.1207 | 6.6539 | 4.5949 | 1.8282 | 16.8937 | 17.7494 | 17.7494 | 0
3321 | 2.6295 | 5.0191 | 4.8539 | 4.8888 | 5.138 | 1.7899 | 14.3274 | 14.4113 | 14.4113 | 0
3322 | 4.5495 | 6.426 | 4.5911 | 6.7893 | 3.9762 | 2.2514 | 20.0163 | 15.3683 | 20.0163 | 1
3323 | 4.3881 | 3.9429 | 6.789 | 5.9953 | 3.9571 | 2.0928 | 16.4191 | 17.227 | 17.227 | 0
3324 | 5.0671 | 6.9199 | 5.462 | 4.1122 | 4.9856 | 2.0253 | 18.1245 | 17.5401 | 18.1245 | 1
3325 | 3.4222 | 8.0507 | 5.2161 | 5.9678 | 4.1672 | 2.0531 | 19.4938 | 14.8586 | 19.4938 | 1
3326 | 4.3599 | 5.9659 | 4.8853 | 5.6311 | 4.7608 | 1.7044 | 17.6613 | 15.7104 | 17.6613 | 1
3327 | 4.7302 | 7.5942 | 4.8723 | 4.698 | 3.148 | 2.2771 | 19.2996 | 15.0278 | 19.2996 | 1
3328 | 4.4044 | 7.1921 | 6.1245 | 5.2809 | 4.422 | 2.319 | 19.1964 | 17.2699 | 19.1964 | 1
3329 | 4.197 | 4.7939 | 5.9609 | 5.15 | 3.9282 | 2.3182 | 16.4592 | 16.4043 | 16.4592 | 1
3330 | 3.6025 | 6.2033 | 5.9923 | 4.8553 | 4.071 | 2.2837 | 16.9449 | 15.9496 | 16.9449 | 1
3331 | 5.3406 | 5.0962 | 6.421 | 5.9813 | 3.8411 | 1.4673 | 17.8853 | 17.07 | 17.8853 | 1
3332 | 3.1634 | 5.6861 | 3.9848 | 5.4889 | 3.7422 | 1.7773 | 16.1158 | 12.6677 | 16.1158 | 1
3333 | 4.5883 | 6.2431 | 5.7742 | 5.7077 | 5.2173 | 2.2063 | 18.7455 | 17.786 | 18.7455 | 1
3334 | 3.7686 | 6.5246 | 6.7498 | 5.9153 | 4.719 | 2.2036 | 18.4121 | 17.441 | 18.4121 | 1
3335 | 5.3786 | 7.1642 | 5.7569 | 5.4932 | 4.1349 | 1.3651 | 19.4012 | 16.6356 | 19.4012 | 1
3336 | 4.3179 | 5.0824 | 6.2294 | 4.7723 | 4.9487 | 1.9042 | 16.0767 | 17.4002 | 17.4002 | 0
3337 | 3.4762 | 5.012 | 3.4105 | 6.3809 | 4.7141 | 1.6598 | 16.5288 | 13.2605 | 16.5288 | 1
3338 | 3.3264 | 4.7895 | 6.2486 | 4.9595 | 3.3739 | 2.5591 | 15.6345 | 15.508 | 15.6345 | 1
3339 | 4.1788 | 5.3073 | 5.4246 | 4.965 | 4.6978 | 1.3892 | 15.8403 | 15.6903 | 15.8403 | 1
3340 | 5.1128 | 4.8783 | 5.5969 | 4.8878 | 5.1629 | 2.412 | 17.2908 | 18.2846 | 18.2846 | 0
3341 | 5.3274 | 5.3757 | 5.8184 | 4.7379 | 4.9545 | 1.4046 | 16.8456 | 17.5049 | 17.5049 | 0
3342 | 4.7651 | 4.4194 | 5.294 | 5.6018 | 3.5531 | 1.5854 | 16.3718 | 15.1976 | 16.3718 | 1
3343 | 3.7409 | 5.3519 | 4.4379 | 5.8674 | 5.4718 | 1.2881 | 16.2483 | 14.9386 | 16.2483 | 1
3344 | 4.4065 | 6.8506 | 4.4224 | 5.7318 | 4.34 | 2.4648 | 19.4538 | 15.6337 | 19.4538 | 1
3345 | 3.428 | 6.0107 | 6.2302 | 5.9013 | 4.0358 | 2.2234 | 17.5634 | 15.9174 | 17.5634 | 1
3346 | 4.14 | 4.8837 | 5.7887 | 5.7081 | 5.5393 | 1.9027 | 16.6345 | 17.3707 | 17.3707 | 0
3347 | 3.4358 | 6.7622 | 7.5526 | 5.574 | 4.9412 | 2.2336 | 18.0056 | 18.1631 | 18.1631 | 0
3348 | 3.455 | 4.2688 | 5.0023 | 5.4773 | 3.5667 | 2.1836 | 15.3847 | 14.2076 | 15.3847 | 1
3349 | 3.489 | 5.1541 | 3.8891 | 4.3082 | 4.5705 | 2.435 | 15.3864 | 14.3837 | 15.3864 | 1
3350 | 4.0748 | 4.3519 | 5.8 | 6.1684 | 4.4687 | 1.4761 | 16.0711 | 15.8196 | 16.0711 | 1
3351 | 3.0901 | 4.0653 | 4.7832 | 5.4891 | 4.2751 | 1.601 | 14.2455 | 13.7494 | 14.2455 | 1
3352 | 2.7302 | 4.3436 | 5.5202 | 6.7386 | 4.0045 | 2.3023 | 16.1146 | 14.5572 | 16.1146 | 1
3353 | 3.4547 | 5.9 | 4.8206 | 4.2535 | 3.5397 | 2.2299 | 15.838 | 14.0448 | 15.838 | 1
3354 | 5.4567 | 6.0392 | 4.9241 | 6.4986 | 3.337 | 2.0536 | 20.0482 | 15.7715 | 20.0482 | 1
3355 | 5.1928 | 5.5608 | 7.0203 | 5.6592 | 3.6934 | 2.4067 | 18.8195 | 18.3132 | 18.8195 | 1
3356 | 5.1796 | 4.0623 | 4.8662 | 6.5352 | 4.336 | 1.5574 | 17.3345 | 15.9391 | 17.3345 | 1
3357 | 4.1764 | 3.9728 | 5.3604 | 5.1233 | 3.2049 | 2.051 | 15.3234 | 14.7927 | 15.3234 | 1
3358 | 2.4564 | 3.8641 | 4.1359 | 4.996 | 4.0516 | 2.0628 | 13.3794 | 12.7067 | 13.3794 | 1
3359 | 4.7005 | 6.0655 | 7.2415 | 4.8749 | 3.5452 | 2.6185 | 18.2593 | 18.1056 | 18.2593 | 1
3360 | 3.0714 | 4.8838 | 5.2593 | 4.5481 | 4.5163 | 2.1364 | 14.6398 | 14.9834 | 14.9834 | 0
3361 | 3.5411 | 6.8038 | 4.7399 | 5.6723 | 4.6592 | 1.6317 | 17.6489 | 14.572 | 17.6489 | 1
3362 | 3.5823 | 4.0849 | 4.7691 | 4.8965 | 4.1743 | 2.7517 | 15.3153 | 15.2774 | 15.3153 | 1
3363 | 3.5891 | 4.7296 | 5.85 | 5.0713 | 4.0815 | 1.8743 | 15.2642 | 15.3948 | 15.3948 | 0
3364 | 3.3059 | 4.7651 | 6.5399 | 6.0949 | 4.6452 | 1.677 | 15.8429 | 16.1681 | 16.1681 | 0
3365 | 2.4228 | 5.1759 | 3.7858 | 5.1904 | 4.7748 | 2.0912 | 14.8804 | 13.0746 | 14.8804 | 1
3366 | 3.4367 | 6.3301 | 4.6714 | 5.7884 | 3.1173 | 1.0982 | 16.6534 | 12.3236 | 16.6534 | 1
3367 | 3.9883 | 4.9539 | 5.2138 | 4.5717 | 3.7626 | 2.4207 | 15.9345 | 15.3853 | 15.9345 | 1
3368 | 3.8677 | 4.4264 | 5.8067 | 6.6203 | 4.8587 | 1.8689 | 16.7832 | 16.4019 | 16.7832 | 1
3369 | 5.0604 | 6.6737 | 4.7275 | 4.6715 | 5.3386 | 2.1104 | 18.5161 | 17.2369 | 18.5161 | 1
3370 | 3.2207 | 6.0828 | 6.6489 | 5.2657 | 4.1088 | 1.6309 | 16.2 | 15.6093 | 16.2 | 1
3371 | 3.7852 | 6.0505 | 7.3794 | 6.5939 | 3.8724 | 2.7205 | 19.1501 | 17.7576 | 19.1501 | 1
3372 | 3.5806 | 5.6168 | 6.0139 | 5.3836 | 3.9585 | 1.4999 | 16.0808 | 15.0528 | 16.0808 | 1
3373 | 4.0343 | 3.4331 | 2.9739 | 5.5405 | 3.3411 | 2.4142 | 15.4221 | 12.7635 | 15.4221 | 1
3374 | 3.4763 | 3.8217 | 6.5619 | 6.2524 | 5.4149 | 2.101 | 15.6513 | 17.554 | 17.554 | 0
3375 | 5.1148 | 4.5241 | 6.6796 | 5.3821 | 4.3346 | 2.1443 | 17.1652 | 18.2733 | 18.2733 | 0
3376 | 4.6305 | 7.0181 | 6.2097 | 6.3543 | 3.3603 | 2.6904 | 20.6934 | 16.891 | 20.6934 | 1
3377 | 2.7855 | 4.6852 | 6.5285 | 5.2411 | 3.9135 | 2.2567 | 14.9684 | 15.4841 | 15.4841 | 0
3378 | 4.4607 | 3.7517 | 6.0394 | 4.7645 | 3.2162 | 2.7089 | 15.6858 | 16.4252 | 16.4252 | 0
3379 | 4.9381 | 3.7871 | 6.5908 | 5.3243 | 4.6273 | 2.2141 | 16.2636 | 18.3703 | 18.3703 | 0
3380 | 4.3378 | 6.1979 | 7.3387 | 4.5549 | 4.1036 | 2.0656 | 17.1562 | 17.8457 | 17.8457 | 0
3381 | 3.2757 | 5.5056 | 7.2863 | 5.9034 | 3.6063 | 1.9531 | 16.6378 | 16.1214 | 16.6378 | 1
3382 | 3.7376 | 3.8268 | 6.1242 | 5.3525 | 3.7883 | 1.7117 | 14.6285 | 15.3617 | 15.3617 | 0
3383 | 3.2365 | 4.637 | 6.5221 | 4.6297 | 3.707 | 1.5889 | 14.0921 | 15.0545 | 15.0545 | 0
3384 | 5.1877 | 4.2711 | 5.5184 | 5.2107 | 3.7125 | 1.2013 | 15.8708 | 15.6199 | 15.8708 | 1
3385 | 5.1163 | 6.8674 | 6.502 | 4.6073 | 4.5963 | 2.0274 | 18.6184 | 18.242 | 18.6184 | 1
3386 | 4.1481 | 5.1713 | 7.3276 | 4.8156 | 4.3131 | 1.82 | 15.9551 | 17.6088 | 17.6088 | 0
3387 | 4.5979 | 4.234 | 5.2895 | 5.6445 | 5.849 | 2.265 | 16.7414 | 18.0015 | 18.0015 | 0
3388 | 4.1275 | 5.8464 | 4.8277 | 5.573 | 3.9766 | 1.3832 | 16.9301 | 14.315 | 16.9301 | 1
3389 | 3.9155 | 6.8416 | 4.9423 | 5.1937 | 3.7508 | 2.7604 | 18.7112 | 15.369 | 18.7112 | 1
3390 | 4.5687 | 5.0026 | 7.07 | 4.4659 | 4.9028 | 1.6676 | 15.7049 | 18.2092 | 18.2092 | 0
3391 | 4.7113 | 6.1405 | 3.5171 | 5.2116 | 3.7204 | 2.1887 | 18.2521 | 14.1376 | 18.2521 | 1
3392 | 3.535 | 5.6456 | 7.2198 | 4.8428 | 4.797 | 2.2958 | 16.3192 | 17.8477 | 17.8477 | 0
3393 | 3.9744 | 5.6483 | 5.36 | 4.4453 | 3.6059 | 1.3909 | 15.4589 | 14.3311 | 15.4589 | 1
3394 | 2.7953 | 6.1792 | 5.5224 | 5.3494 | 3.9344 | 1.6876 | 16.0115 | 13.9396 | 16.0115 | 1
3395 | 5.4253 | 4.8925 | 6.5207 | 5.6643 | 3.7587 | 2.5393 | 18.5214 | 18.244 | 18.5214 | 1
3396 | 5.0071 | 6.04 | 5.0076 | 5.4931 | 4.4495 | 1.8709 | 18.411 | 16.335 | 18.411 | 1
3397 | 2.9283 | 4.5881 | 5.1177 | 6.2509 | 4.6762 | 1.8359 | 15.6033 | 14.5582 | 15.6033 | 1
3398 | 4.153 | 5.5795 | 6.6536 | 5.1033 | 4.1845 | 2.3181 | 17.1539 | 17.3092 | 17.3092 | 0
3399 | 5.0951 | 6.4205 | 6.8017 | 5.1553 | 3.4347 | 1.8081 | 18.479 | 17.1396 | 18.479 | 1
3400 | 4.3737 | 5.2809 | 5.981 | 5.7759 | 5.0694 | 1.3531 | 16.7836 | 16.7771 | 16.7836 | 1
3401 | 4.3751 | 5.5064 | 3.781 | 4.4193 | 4.9097 | 2.0533 | 16.3542 | 15.1192 | 16.3542 | 1
3402 | 5.092 | 6.722 | 5.879 | 4.5026 | 4.6249 | 1.7118 | 18.0283 | 17.3077 | 18.0283 | 1
3403 | 4.9509 | 4.9521 | 6.5268 | 4.7573 | 4.8913 | 1.5267 | 16.1871 | 17.8957 | 17.8957 | 0
3404 | 3.9494 | 7.0811 | 3.4771 | 4.6634 | 4.6325 | 2.5616 | 18.2556 | 14.6207 | 18.2556 | 1
3405 | 4.5481 | 3.4639 | 3.1607 | 6.062 | 4.3217 | 1.9482 | 16.0222 | 13.9787 | 16.0222 | 1
3406 | 2.4262 | 4.5605 | 4.0499 | 4.9104 | 3.464 | 2.5639 | 14.4611 | 12.504 | 14.4611 | 1
3407 | 4.5147 | 7.2883 | 5.3027 | 5.1868 | 4.4947 | 2.5468 | 19.5366 | 16.859 | 19.5366 | 1
3408 | 2.4478 | 4.8286 | 5.3195 | 5.6347 | 4.934 | 1.7322 | 14.6432 | 14.4334 | 14.6432 | 1
3409 | 3.9218 | 5.6046 | 6.1217 | 5.2041 | 4.6956 | 1.7063 | 16.4367 | 16.4454 | 16.4454 | 0
3410 | 3.3335 | 5.3087 | 5.9949 | 6.6306 | 4.1832 | 1.9575 | 17.2303 | 15.4691 | 17.2303 | 1
3411 | 3.2427 | 5.2375 | 4.851 | 4.8213 | 4.2708 | 2.2027 | 15.5042 | 14.5673 | 15.5042 | 1
3412 | 3.8816 | 3.7167 | 6.0037 | 4.4774 | 3.1299 | 2.2468 | 14.3225 | 15.2619 | 15.2619 | 0
3413 | 4.0448 | 6.7051 | 7.4823 | 5.6088 | 5.5431 | 1.9217 | 18.2804 | 18.9918 | 18.9918 | 0
3414 | 5.2001 | 4.4011 | 7.7138 | 6.3611 | 3.158 | 2.3806 | 18.3428 | 18.4525 | 18.4525 | 0
3415 | 4.8387 | 5.5193 | 6.2172 | 4.8798 | 3.1893 | 1.9538 | 17.1915 | 16.1989 | 17.1915 | 1
3416 | 5.4758 | 6.3206 | 4.3385 | 5.3922 | 4.182 | 2.0423 | 19.231 | 16.0386 | 19.231 | 1
3417 | 3.1908 | 4.9206 | 6.5413 | 5.2312 | 4.3998 | 1.7161 | 15.0586 | 15.8479 | 15.8479 | 0
3418 | 4.3242 | 3.6378 | 3.5463 | 6.2796 | 3.9802 | 1.7931 | 16.0347 | 13.6438 | 16.0347 | 1
3419 | 3.4461 | 3.8364 | 7.5249 | 4.9038 | 3.659 | 1.5871 | 13.7733 | 16.217 | 16.217 | 0
3420 | 2.2339 | 4.7187 | 6.9563 | 5.2736 | 3.0687 | 2.6151 | 14.8413 | 14.874 | 14.874 | 0
3421 | 4.0116 | 5.8567 | 4.4342 | 5.0608 | 4.2733 | 2.3946 | 17.3237 | 15.1136 | 17.3237 | 1
3422 | 2.9069 | 5.3877 | 4.2643 | 4.8631 | 4.1665 | 1.4974 | 14.6552 | 12.8352 | 14.6552 | 1
3423 | 3.4028 | 5.1277 | 6.2975 | 5.0811 | 3.4725 | 2.0691 | 15.6807 | 15.2419 | 15.6807 | 1
3424 | 2.4059 | 4.3352 | 6.5597 | 4.0514 | 3.5515 | 1.9192 | 12.7116 | 14.4363 | 14.4363 | 0
3425 | 5.3428 | 3.8962 | 5.5772 | 4.8168 | 3.3384 | 2.2998 | 16.3556 | 16.5582 | 16.5582 | 0
3426 | 5.6597 | 6.0119 | 6.9894 | 4.1494 | 4.1037 | 1.4183 | 17.2392 | 18.1709 | 18.1709 | 0
3427 | 3.6063 | 5.0443 | 5.4925 | 4.806 | 5.0362 | 2.4687 | 15.9254 | 16.6038 | 16.6038 | 0
3428 | 4.7425 | 5.566 | 5.8292 | 6.8337 | 4.0945 | 2.4257 | 19.5679 | 17.092 | 19.5679 | 1
3429 | 3.9064 | 5.7599 | 3.5818 | 5.5249 | 3.5532 | 2.4796 | 17.6708 | 13.521 | 17.6708 | 1
3430 | 4.3245 | 6.5528 | 3.991 | 5.5365 | 3.6138 | 2.0272 | 18.4409 | 13.9565 | 18.4409 | 1
3431 | 5.1499 | 5.6234 | 5.8292 | 4.6137 | 5.3684 | 1.9703 | 17.3574 | 18.3178 | 18.3178 | 0
3432 | 5.1616 | 5.4424 | 6.7931 | 5.7928 | 4.3404 | 2.0006 | 18.3974 | 18.2956 | 18.3974 | 1
3433 | 4.2932 | 5.4864 | 5.1996 | 5.0801 | 4.4539 | 2.2158 | 17.0755 | 16.1626 | 17.0755 | 1
3434 | 4.1907 | 5.2486 | 5.9776 | 5.6873 | 4.0551 | 2.1464 | 17.2729 | 16.3697 | 17.2729 | 1
3435 | 4.1614 | 3.3551 | 3.6963 | 4.5636 | 4.8669 | 1.6308 | 13.7109 | 14.3555 | 14.3555 | 0
3436 | 4.3751 | 5.3958 | 5.5733 | 6.5511 | 3.3133 | 1.8142 | 18.1363 | 15.0761 | 18.1363 | 1
3437 | 5.3098 | 8.2593 | 6.0556 | 5.0141 | 4.4519 | 1.9405 | 20.5237 | 17.7577 | 20.5237 | 1
3438 | 3.3756 | 5.5361 | 4.8442 | 6.4188 | 4.6549 | 1.8436 | 17.1741 | 14.7183 | 17.1741 | 1
3439 | 2.9359 | 4.5863 | 5.7661 | 5.2649 | 5.2619 | 2.3163 | 15.1034 | 16.2802 | 16.2802 | 0
3440 | 3.4758 | 6.4607 | 7.0554 | 4.6873 | 4.6918 | 2.0769 | 16.7007 | 17.2998 | 17.2998 | 0
3441 | 4.4043 | 5.9855 | 5.6245 | 4.5315 | 3.5985 | 1.9761 | 16.8975 | 15.6034 | 16.8975 | 1
3442 | 2.8792 | 5.4688 | 5.4331 | 4.6245 | 4.8062 | 1.5683 | 14.5408 | 14.6868 | 14.6868 | 0
3443 | 4.0702 | 5.4625 | 5.8913 | 5.3515 | 4.5145 | 1.9867 | 16.871 | 16.4627 | 16.871 | 1
3444 | 3.3711 | 5.5788 | 5.6476 | 4.5989 | 5.3138 | 2.3834 | 15.9321 | 16.7159 | 16.7159 | 0
3445 | 5.7708 | 6.1923 | 6.5795 | 5.0557 | 4.1524 | 2.0418 | 19.0605 | 18.5444 | 19.0605 | 1
3446 | 4.182 | 7.3478 | 5.969 | 5.5566 | 5.4714 | 1.9049 | 18.9914 | 17.5273 | 18.9914 | 1
3447 | 4.734 | 4.3118 | 4.1642 | 4.8524 | 4.0473 | 1.2506 | 15.1488 | 14.1961 | 15.1488 | 1
3448 | 3.6291 | 4.3 | 4.6901 | 6.5944 | 3.8131 | 2.2183 | 16.7418 | 14.3506 | 16.7418 | 1
3449 | 3.3193 | 5.4496 | 5.8886 | 5.5489 | 4.7877 | 1.5752 | 15.893 | 15.5708 | 15.893 | 1
3450 | 4.4684 | 3.5514 | 6.1528 | 5.1754 | 5.0007 | 2.3853 | 15.5805 | 18.0073 | 18.0073 | 0
3451 | 3.7544 | 3.401 | 3.5561 | 4.3508 | 4.54 | 1.8526 | 13.3587 | 13.7032 | 13.7032 | 0
3452 | 5.1952 | 6.3083 | 4.0583 | 4.1378 | 3.4198 | 2.2003 | 17.8416 | 14.8737 | 17.8416 | 1
3453 | 4.3025 | 4.2233 | 7.0356 | 5.7971 | 5.1607 | 1.9815 | 16.3043 | 18.4802 | 18.4802 | 0
3454 | 4.1126 | 5.0186 | 4.4087 | 4.9226 | 3.9332 | 2.1191 | 16.1729 | 14.5735 | 16.1729 | 1
3455 | 2.7137 | 5.6101 | 4.2462 | 5.0418 | 4.9161 | 1.3281 | 14.6936 | 13.2041 | 14.6936 | 1
3456 | 3.9474 | 4.923 | 6.9604 | 4.7751 | 4.0516 | 2.0416 | 15.6872 | 17.001 | 17.001 | 0
3457 | 4.3142 | 7.0046 | 5.0322 | 4.1206 | 5.1953 | 1.8025 | 17.2418 | 16.3442 | 17.2418 | 1
3458 | 4.8007 | 3.9709 | 5.1976 | 4.4708 | 4.2332 | 1.9921 | 15.2345 | 16.2236 | 16.2236 | 0
3459 | 3.6015 | 4.7658 | 5.2332 | 6.6808 | 3.5294 | 2.0813 | 17.1293 | 14.4453 | 17.1293 | 1
3460 | 3.8079 | 6.0062 | 6.6326 | 4.6659 | 3.8329 | 1.5491 | 16.0291 | 15.8225 | 16.0291 | 1
3461 | 3.9865 | 5.303 | 5.7959 | 5.331 | 4.39 | 1.9307 | 16.5513 | 16.1031 | 16.5513 | 1
3462 | 4.9675 | 4.3989 | 5.1117 | 5.1553 | 3.956 | 1.5225 | 16.0442 | 15.5577 | 16.0442 | 1
3463 | 4.0639 | 7.4804 | 6.578 | 6.3003 | 5.6468 | 1.7232 | 19.5679 | 18.012 | 19.5679 | 1
3464 | 4.1057 | 4.6502 | 5.773 | 5.6047 | 4.8317 | 2.6631 | 17.0238 | 17.3736 | 17.3736 | 0
3465 | 2.9426 | 5.296 | 6.3862 | 5.0885 | 3.6637 | 2.7856 | 16.1127 | 15.7781 | 16.1127 | 1
3466 | 2.9033 | 6.5206 | 4.5712 | 6.0694 | 4.4559 | 2.1192 | 17.6124 | 14.0496 | 17.6124 | 1
3467 | 3.252 | 4.114 | 4.4444 | 4.3804 | 4.6107 | 1.8461 | 13.5924 | 14.1532 | 14.1532 | 0
3468 | 5.194 | 4.0756 | 2.76 | 4.4804 | 4.0602 | 2.2977 | 16.0477 | 14.3118 | 16.0477 | 1
3469 | 4.61 | 3.9171 | 4.1646 | 5.7433 | 5.3888 | 1.4422 | 15.7127 | 15.6056 | 15.7127 | 1
3470 | 4.4589 | 6.0361 | 6.9992 | 4.9731 | 4.758 | 2.1896 | 17.6577 | 18.4057 | 18.4057 | 0
3471 | 4.4994 | 4.042 | 4.5862 | 4.7572 | 3.8886 | 1.3966 | 14.6951 | 14.3707 | 14.6951 | 1
3472 | 3.369 | 6.0707 | 6.7086 | 5.8229 | 4.6965 | 2.605 | 17.8676 | 17.3791 | 17.8676 | 1
3473 | 4.3658 | 6.034 | 5.8006 | 5.6505 | 3.5347 | 1.8204 | 17.8707 | 15.5215 | 17.8707 | 1
3474 | 2.6811 | 6.4166 | 4.4617 | 4.9103 | 5.4569 | 1.1936 | 15.2016 | 13.7934 | 15.2016 | 1
3475 | 4.6907 | 5.199 | 6.43 | 5.6234 | 3.5809 | 2.3607 | 17.8738 | 17.0622 | 17.8738 | 1
3476 | 4.6726 | 5.4763 | 5.4207 | 5.7345 | 3.7617 | 1.8049 | 17.6883 | 15.66 | 17.6883 | 1
3477 | 2.7543 | 4.8379 | 4.3921 | 4.7291 | 3.5117 | 2.8065 | 15.1278 | 13.4645 | 15.1278 | 1
3478 | 3.5607 | 4.2431 | 4.6449 | 5.2303 | 3.3617 | 1.353 | 14.3872 | 12.9204 | 14.3872 | 1
3479 | 4.3076 | 3.7563 | 5.1501 | 4.5557 | 4.3562 | 2.0568 | 14.6765 | 15.8708 | 15.8708 | 0
3480 | 3.5052 | 5.9466 | 5.4709 | 5.6556 | 4.2926 | 1.7227 | 16.8301 | 14.9913 | 16.8301 | 1
3481 | 5.051 | 6.0943 | 5.0778 | 4.3939 | 3.609 | 1.9818 | 17.5211 | 15.7196 | 17.5211 | 1
3482 | 4.7132 | 6.3736 | 4.3735 | 4.3102 | 3.7251 | 1.8283 | 17.2253 | 14.64 | 17.2253 | 1
3483 | 3.6746 | 4.5877 | 7.1273 | 4.8374 | 4.2824 | 2.5239 | 15.6237 | 17.6083 | 17.6083 | 0
3484 | 3.5752 | 3.7958 | 7.7038 | 6.8665 | 4.8022 | 1.9167 | 16.1542 | 17.9979 | 17.9979 | 0
3485 | 3.1953 | 4.3765 | 6.2261 | 5.1144 | 3.9727 | 2.1213 | 14.8075 | 15.5154 | 15.5154 | 0
3486 | 4.5953 | 3.9688 | 5.709 | 5.7724 | 5.2631 | 1.4912 | 15.8278 | 17.0587 | 17.0587 | 0
3487 | 3.8297 | 4.6437 | 4.9031 | 4.6761 | 3.8978 | 1.7304 | 14.8799 | 14.361 | 14.8799 | 1
3488 | 4.2454 | 5.8443 | 3.8944 | 5.227 | 3.2894 | 1.7922 | 17.1088 | 13.2213 | 17.1088 | 1
3489 | 4.7298 | 6.1245 | 3.2195 | 4.4558 | 3.6695 | 2.3222 | 17.6323 | 13.941 | 17.6323 | 1
3490 | 3.2312 | 4.2881 | 5.4741 | 5.0002 | 3.4205 | 2.2352 | 14.7546 | 14.361 | 14.7546 | 1
3491 | 3.4249 | 4.1231 | 6.8006 | 5.877 | 4.6924 | 2.2381 | 15.6632 | 17.1561 | 17.1561 | 0
3492 | 5.2192 | 5.3407 | 4.7569 | 5.265 | 3.59 | 1.9925 | 17.8173 | 15.5587 | 17.8173 | 1
3493 | 3.9204 | 6.3164 | 5.0561 | 4.3293 | 6.4009 | 2.4445 | 17.0107 | 17.822 | 17.822 | 0
3494 | 3.5368 | 5.3811 | 7.14 | 5.5978 | 4.2302 | 1.4199 | 15.9356 | 16.3269 | 16.3269 | 0
3495 | 3.7912 | 6.4118 | 5.9362 | 6.604 | 4.6514 | 2.5125 | 19.3194 | 16.8912 | 19.3194 | 1
3496 | 4.678 | 4.4481 | 5.481 | 4.7301 | 4.861 | 1.4351 | 15.2913 | 16.4551 | 16.4551 | 0
3497 | 5.272 | 3.8909 | 5.6714 | 6.3079 | 5.1205 | 2.5271 | 17.9979 | 18.5909 | 18.5909 | 0
3498 | 4.7422 | 7.6299 | 5.2893 | 4.42 | 3.8592 | 1.8399 | 18.632 | 15.7305 | 18.632 | 1
3499 | 4.2534 | 5.3675 | 7.0232 | 6.3933 | 4.816 | 1.5039 | 17.5181 | 17.5965 | 17.5965 | 0
3500 | 3.6365 | 6.155 | 6.2247 | 7.2301 | 4.8501 | 2.1636 | 19.1852 | 16.875 | 19.1852 | 1
3501 | 3.861 | 6.4851 | 2.9266 | 6.2394 | 4.1067 | 2.0731 | 18.6587 | 12.9674 | 18.6587 | 1
3502 | 4.1373 | 6.2538 | 5.138 | 6.1438 | 4.1111 | 1.4868 | 18.0216 | 14.8731 | 18.0216 | 1
3503 | 4.1657 | 4.2226 | 5.7806 | 4.6307 | 4.516 | 2.2198 | 15.2388 | 16.6821 | 16.6821 | 0
3504 | 4.7519 | 5.3164 | 5.4889 | 4.668 | 3.9445 | 2.0479 | 16.7842 | 16.2332 | 16.7842 | 1
3505 | 4.1598 | 5.2288 | 5.7114 | 5.5858 | 5.6745 | 1.6883 | 16.6627 | 17.234 | 17.234 | 0
3506 | 4.3982 | 4.8362 | 3.7094 | 4.2486 | 4.955 | 2.01 | 15.493 | 15.0726 | 15.493 | 1
3507 | 4.9807 | 5.775 | 6.3502 | 5.6094 | 5.2668 | 1.8889 | 18.254 | 18.4866 | 18.4866 | 0
3508 | 4.6674 | 5.4169 | 5.7431 | 6.0384 | 5.0214 | 1.7082 | 17.8309 | 17.1401 | 17.8309 | 1
3509 | 4.0969 | 4.2073 | 6.2311 | 6.1504 | 5.491 | 2.0256 | 16.4802 | 17.8446 | 17.8446 | 0
3510 | 4.6298 | 5.9594 | 7.5567 | 5.994 | 4.1397 | 1.8446 | 18.4278 | 18.1708 | 18.4278 | 1
3511 | 4.1248 | 6.0273 | 5.2831 | 6.8341 | 3.3905 | 2.5784 | 19.5645 | 15.3768 | 19.5645 | 1
3512 | 3.98 | 6.9097 | 5.3122 | 5.3651 | 5.903 | 1.8656 | 18.1204 | 17.0608 | 18.1204 | 1
3513 | 2.7514 | 5.5602 | 7.2766 | 4.7335 | 5.8826 | 1.6869 | 14.732 | 17.5975 | 17.5975 | 0
3514 | 5.2409 | 5.1205 | 6.6208 | 6.7998 | 4.9149 | 2.2737 | 19.4349 | 19.0502 | 19.4349 | 1
3515 | 4.5729 | 5.0929 | 6.7632 | 6.0056 | 4.0013 | 2.4324 | 18.1039 | 17.7699 | 18.1039 | 1
3516 | 3.3884 | 6.3972 | 2.687 | 5.0129 | 4.6106 | 2.0097 | 16.8082 | 12.6957 | 16.8082 | 1
3517 | 3.2765 | 3.785 | 4.9211 | 4.3457 | 4.5602 | 1.9755 | 13.3826 | 14.7333 | 14.7333 | 0
3518 | 4.1739 | 4.1858 | 6.4296 | 5.9566 | 3.5564 | 1.4115 | 15.7279 | 15.5714 | 15.7279 | 1
3519 | 4.8669 | 5.5125 | 7.2304 | 6.139 | 3.7822 | 2.0233 | 18.5417 | 17.9028 | 18.5417 | 1
3520 | 4.0129 | 5.9917 | 5.3828 | 5.4755 | 3.6669 | 1.7746 | 17.2546 | 14.8372 | 17.2546 | 1
3521 | 5.2518 | 4.4892 | 5.743 | 5.0435 | 3.512 | 1.1606 | 15.9451 | 15.6674 | 15.9451 | 1
3522 | 4.0594 | 7.0189 | 5.4637 | 4.551 | 4.4174 | 2.2522 | 17.8815 | 16.1926 | 17.8815 | 1
3523 | 4.8668 | 4.3578 | 4.6311 | 5.5981 | 3.8661 | 1.5742 | 16.3969 | 14.9382 | 16.3969 | 1
3524 | 5.4751 | 4.2956 | 4.0468 | 5.5268 | 3.1637 | 2.6085 | 17.9059 | 15.2941 | 17.9059 | 1
3525 | 3.4724 | 6.8609 | 6.4704 | 5.1448 | 3.0726 | 2.0588 | 17.5368 | 15.0742 | 17.5368 | 1
3526 | 3.2256 | 4.9465 | 5.3099 | 5.0906 | 3.7453 | 2.1298 | 15.3924 | 14.4105 | 15.3924 | 1
3527 | 3.5527 | 7.4213 | 5.2205 | 6.2225 | 5.2693 | 1.7148 | 18.9113 | 15.7573 | 18.9113 | 1
3528 | 3.5859 | 5.2362 | 4.8969 | 5.6405 | 4.5172 | 1.4992 | 15.9617 | 14.4992 | 15.9617 | 1
3529 | 4.8672 | 6.1063 | 4.4515 | 5.5641 | 4.3557 | 1.9541 | 18.4917 | 15.6285 | 18.4917 | 1
3530 | 3.2514 | 5.6364 | 5.2292 | 4.1337 | 4.417 | 2.0679 | 15.0894 | 14.9654 | 15.0894 | 1
3531 | 3.9848 | 3.4442 | 7.1581 | 5.4472 | 4.2893 | 2.008 | 14.8843 | 17.4403 | 17.4403 | 0
3532 | 5.1391 | 4.7214 | 5.1139 | 5.8025 | 3.4505 | 2.0477 | 17.7108 | 15.7512 | 17.7108 | 1
3533 | 3.9522 | 6.5722 | 4.2 | 5.1731 | 4.6283 | 2.0993 | 17.7967 | 14.8797 | 17.7967 | 1
3534 | 5.6411 | 4.7099 | 3.9712 | 5.3851 | 3.1858 | 2.1509 | 17.8871 | 14.949 | 17.8871 | 1
3535 | 4.1278 | 4.2514 | 6.5864 | 4.7629 | 4.3224 | 1.3779 | 14.5199 | 16.4145 | 16.4145 | 0
3536 | 3.5676 | 5.3622 | 6.0643 | 4.9659 | 4.6473 | 2.511 | 16.4067 | 16.7903 | 16.7903 | 0
3537 | 5.1781 | 4.294 | 7.1262 | 4.6097 | 3.5212 | 2.1904 | 16.2722 | 18.0159 | 18.0159 | 0
3538 | 4.6593 | 3.9225 | 5.947 | 5.2568 | 4.5999 | 2.1249 | 15.9635 | 17.3311 | 17.3311 | 0
3539 | 3.796 | 5.9177 | 7.2067 | 5.0176 | 3.7128 | 2.226 | 16.9574 | 16.9417 | 16.9574 | 1
3540 | 4.205 | 6.325 | 6.6161 | 4.6369 | 4.0779 | 1.8537 | 17.0207 | 16.7527 | 17.0207 | 1
3541 | 5.0266 | 6.4906 | 4.4318 | 4.3376 | 4.48 | 1.7598 | 17.6146 | 15.6982 | 17.6146 | 1
3542 | 4.3417 | 6.2675 | 7.2544 | 6.2612 | 3.8066 | 2.2751 | 19.1455 | 17.6779 | 19.1455 | 1
3543 | 4.4947 | 4.5286 | 5.3758 | 5.5388 | 4.5953 | 2.1758 | 16.7379 | 16.6416 | 16.7379 | 1
3544 | 5.068 | 5.0844 | 7.314 | 4.4863 | 4.6989 | 2.3884 | 17.0271 | 19.4693 | 19.4693 | 0
3545 | 4.7516 | 5.2423 | 4.0178 | 5.8359 | 3.4884 | 2.428 | 18.2579 | 14.6858 | 18.2579 | 1
3546 | 4.8174 | 6.3108 | 6.1527 | 5.8011 | 3.3657 | 1.9759 | 18.9051 | 16.3117 | 18.9051 | 1
3547 | 3.2442 | 5.5288 | 4.6955 | 5.3885 | 4.4123 | 1.2095 | 15.371 | 13.5614 | 15.371 | 1
3548 | 3.1718 | 4.795 | 5.9871 | 6.5932 | 3.9966 | 1.7226 | 16.2826 | 14.8782 | 16.2826 | 1
3549 | 3.3703 | 4.1168 | 4.7178 | 5.1507 | 3.2455 | 1.7248 | 14.3626 | 13.0584 | 14.3626 | 1
3550 | 3.4023 | 4.9349 | 6.2066 | 4.6667 | 3.0969 | 1.8684 | 14.8723 | 14.5742 | 14.8723 | 1
3551 | 5.1858 | 6.8192 | 6.053 | 5.1829 | 4.6601 | 1.8647 | 19.0526 | 17.7637 | 19.0526 | 1
3552 | 4.5744 | 5.5322 | 4.2371 | 5.2734 | 4.0631 | 2.0498 | 17.4297 | 14.9244 | 17.4297 | 1
3553 | 3.2769 | 5.3351 | 7.6826 | 5.5018 | 3.1169 | 2.2865 | 16.4003 | 16.3629 | 16.4003 | 1
3554 | 4.0682 | 8.2626 | 4.9792 | 5.0005 | 3.9816 | 2.333 | 19.6643 | 15.362 | 19.6643 | 1
3555 | 3.7783 | 5.3656 | 5.0535 | 4.6586 | 4.2412 | 2.1402 | 15.9428 | 15.2133 | 15.9428 | 1
3556 | 3.303 | 3.6542 | 5.8697 | 4.154 | 3.2968 | 1.5051 | 12.6164 | 13.9746 | 13.9746 | 0
3557 | 4.3947 | 3.4278 | 7.2983 | 6.3451 | 3.1516 | 1.9299 | 16.0974 | 16.7744 | 16.7744 | 0
3558 | 4.0439 | 5.0576 | 6.3236 | 4.592 | 4.901 | 1.843 | 15.5365 | 17.1114 | 17.1114 | 0
3559 | 4.527 | 5.1149 | 5.9189 | 5.5419 | 5.8427 | 1.8488 | 17.0326 | 18.1373 | 18.1373 | 0
3560 | 4.765 | 6.0056 | 5.7519 | 5.6619 | 3.4502 | 2.6119 | 19.0445 | 16.5791 | 19.0445 | 1
3561 | 3.9978 | 4.0088 | 5.2596 | 4.4382 | 4.0945 | 1.786 | 14.2308 | 15.1379 | 15.1379 | 0
3562 | 4.0626 | 4.2779 | 4.6849 | 4.6548 | 4.5694 | 1.6847 | 14.68 | 15.0015 | 15.0015 | 0
3563 | 5.1126 | 4.5439 | 3.9468 | 4.1632 | 5.7429 | 2.0929 | 15.9126 | 16.8952 | 16.8952 | 0
3564 | 3.7665 | 5.4765 | 4.9599 | 5.8528 | 4.7928 | 2.5099 | 17.6057 | 16.0291 | 17.6057 | 1
3565 | 4.9982 | 5.943 | 5.0099 | 5.7094 | 5.1509 | 1.8416 | 18.4922 | 17.0005 | 18.4922 | 1
3566 | 4.4473 | 7.3246 | 4.0943 | 5.5637 | 4.6346 | 1.8984 | 19.2341 | 15.0746 | 19.2341 | 1
3567 | 3.2651 | 4.2237 | 6.294 | 5.3158 | 4.5911 | 1.6989 | 14.5035 | 15.8491 | 15.8491 | 0
3568 | 3.7434 | 5.9182 | 5.4531 | 5.5752 | 3.6446 | 1.6858 | 16.9227 | 14.527 | 16.9227 | 1
3569 | 2.6141 | 4.2333 | 6.4332 | 5.6009 | 3.5775 | 2.3352 | 14.7835 | 14.96 | 14.96 | 0
3570 | 3.8903 | 4.2013 | 5.1391 | 7.1148 | 4.6997 | 1.7034 | 16.9099 | 15.4325 | 16.9099 | 1
3571 | 3.2173 | 3.202 | 4.6459 | 4.3907 | 5.2241 | 2.2468 | 13.0569 | 15.3342 | 15.3342 | 0
3572 | 4.6748 | 4.2421 | 5.8854 | 5.1303 | 4.7599 | 2.0907 | 16.138 | 17.4108 | 17.4108 | 0
3573 | 2.5759 | 5.4523 | 5.3773 | 4.2169 | 4.3549 | 2.5595 | 14.8047 | 14.8675 | 14.8675 | 0
3574 | 2.8201 | 4.3795 | 7.0706 | 6.0488 | 4.4787 | 2.2562 | 15.5046 | 16.6255 | 16.6255 | 0
3575 | 4.1751 | 6.4974 | 7.3238 | 5.1251 | 3.3939 | 2.1128 | 17.9105 | 17.0056 | 17.9105 | 1
3576 | 3.743 | 4.7697 | 3.701 | 6.0091 | 4.3104 | 1.567 | 16.0887 | 13.3213 | 16.0887 | 1
3577 | 4.5713 | 6.07 | 5.45 | 5.6341 | 4.4768 | 1.9101 | 18.1855 | 16.4082 | 18.1855 | 1
3578 | 5.4042 | 4.3988 | 2.8684 | 4.17 | 3.5225 | 2.521 | 16.4941 | 14.3161 | 16.4941 | 1
3579 | 3.9551 | 4.8169 | 5.2727 | 4.7849 | 4.0549 | 2.19 | 15.7469 | 15.4727 | 15.7469 | 1
3580 | 4.6932 | 5.4203 | 7.2346 | 4.7179 | 5.0798 | 1.8166 | 16.6479 | 18.8242 | 18.8242 | 0
3581 | 4.0105 | 5.5111 | 4.2191 | 5.5295 | 3.1505 | 1.6993 | 16.7504 | 13.0793 | 16.7504 | 1
3582 | 4.0098 | 5.8875 | 6.5485 | 5.9502 | 3.7414 | 1.7994 | 17.647 | 16.0991 | 17.647 | 1
3583 | 3.6794 | 7.5205 | 5.2609 | 4.2377 | 3.524 | 2.1456 | 17.5832 | 14.6098 | 17.5832 | 1
3584 | 3.5989 | 5.1531 | 6.9617 | 4.8739 | 4.9232 | 1.7356 | 15.3615 | 17.2194 | 17.2194 | 0
3585 | 4.1308 | 5.2383 | 6.7843 | 4.7087 | 4.4945 | 2.3451 | 16.4229 | 17.7547 | 17.7547 | 0
3586 | 2.8998 | 6.148 | 6.0345 | 6.3014 | 4.3466 | 1.7575 | 17.1066 | 15.0384 | 17.1066 | 1
3587 | 3.5889 | 5.4552 | 6.5167 | 5.0532 | 5.8944 | 1.8137 | 15.911 | 17.8136 | 17.8136 | 0
3588 | 4.8249 | 5.7368 | 7.0418 | 5.2446 | 4.369 | 2.3334 | 18.1397 | 18.5691 | 18.5691 | 0
3589 | 4.9002 | 5.2269 | 6.7177 | 5.1508 | 4.4682 | 2.0754 | 17.3532 | 18.1615 | 18.1615 | 0
3590 | 3.9409 | 3.8129 | 5.912 | 7.0268 | 3.7407 | 1.6612 | 16.4418 | 15.2547 | 16.4418 | 1
3591 | 3.5588 | 4.9379 | 6.1618 | 4.576 | 5.2471 | 2.2961 | 15.3688 | 17.2638 | 17.2638 | 0
3592 | 4.5112 | 5.4802 | 5.5381 | 6.7421 | 4.4915 | 1.4818 | 18.2153 | 16.0227 | 18.2153 | 1
3593 | 4.6239 | 6.7787 | 4.796 | 5.1907 | 5.5189 | 2.4305 | 19.0238 | 17.3693 | 19.0238 | 1
3594 | 3.0331 | 5.2153 | 4.524 | 5.557 | 4.2585 | 2.6322 | 16.4377 | 14.4479 | 16.4377 | 1
3595 | 3.8008 | 4.671 | 5.486 | 6.3967 | 4.7516 | 1.7333 | 16.6017 | 15.7716 | 16.6017 | 1
3596 | 3.4209 | 6.4641 | 5.9579 | 5.0091 | 4.0778 | 2.5041 | 17.3982 | 15.9607 | 17.3982 | 1
3597 | 4.9969 | 6.0403 | 5.0951 | 4.7811 | 3.8688 | 2.2511 | 18.0694 | 16.2119 | 18.0694 | 1
3598 | 3.4618 | 3.2579 | 5.913 | 5.0747 | 4.4713 | 1.3004 | 13.0949 | 15.1466 | 15.1466 | 0
3599 | 3.3107 | 5.2882 | 6.5869 | 5.0825 | 5.485 | 2.5768 | 16.2582 | 17.9593 | 17.9593 | 0
3600 | 3.1967 | 6.2584 | 6.3312 | 6.1169 | 4.7116 | 1.8619 | 17.4339 | 16.1014 | 17.4339 | 1
3601 | 3.9538 | 3.8099 | 7.1592 | 5.063 | 5.1669 | 2.7239 | 15.5507 | 19.0038 | 19.0038 | 0
3602 | 3.767 | 6.1503 | 4.2341 | 6.7646 | 4.3561 | 1.6356 | 18.3174 | 13.9927 | 18.3174 | 1
3603 | 4.0014 | 5.6631 | 5.4901 | 5.9706 | 5.3534 | 1.9989 | 17.634 | 16.8438 | 17.634 | 1
3604 | 2.7319 | 5.2983 | 5.3224 | 5.2286 | 3.6423 | 1.4799 | 14.7387 | 13.1764 | 14.7387 | 1
3605 | 4.0132 | 5.848 | 6.2422 | 4.8316 | 3.6266 | 2.481 | 17.1738 | 16.363 | 17.1738 | 1
3606 | 5.2101 | 6.58 | 5.1636 | 6.9886 | 4.105 | 1.9553 | 20.7339 | 16.434 | 20.7339 | 1
3607 | 3.9387 | 6.106 | 6.0886 | 5.8548 | 5.0747 | 2.1209 | 18.0203 | 17.2229 | 18.0203 | 1
3608 | 2.988 | 4.7946 | 4.6571 | 4.3274 | 4.1125 | 2.6215 | 14.7315 | 14.379 | 14.7315 | 1
3609 | 3.5921 | 3.6853 | 5.9945 | 4.6183 | 5.6881 | 1.7305 | 13.6262 | 17.0052 | 17.0052 | 0
3610 | 4.4471 | 5.1066 | 6.7847 | 6.0859 | 3.7055 | 1.7013 | 17.3408 | 16.6386 | 17.3408 | 1
3611 | 3.3803 | 4.2549 | 3.6875 | 5.9244 | 5.4797 | 2.1312 | 15.6908 | 14.6787 | 15.6908 | 1
3612 | 2.4694 | 6.2731 | 6.3481 | 5.2683 | 3.8108 | 2.0532 | 16.0641 | 14.6816 | 16.0641 | 1
3613 | 3.1184 | 4.2029 | 5.7444 | 6.0737 | 4.6748 | 2.0275 | 15.4225 | 15.5651 | 15.5651 | 0
3614 | 4.3238 | 5.6327 | 4.2944 | 5.8359 | 3.3736 | 2.4478 | 18.2402 | 14.4396 | 18.2402 | 1
3615 | 4.6478 | 8.0287 | 4.3581 | 6.2994 | 3.8625 | 2.4473 | 21.4232 | 15.3156 | 21.4232 | 1
3616 | 3.4825 | 4.6828 | 5.1271 | 4.391 | 3.8042 | 1.9041 | 14.4603 | 14.3179 | 14.4603 | 1
3617 | 3.6553 | 4.242 | 5.7743 | 4.7696 | 3.7343 | 1.9484 | 14.6153 | 15.1123 | 15.1123 | 0
3618 | 4.8424 | 7.4688 | 2.8141 | 5.5937 | 3.8145 | 2.4983 | 20.4031 | 13.9692 | 20.4031 | 1
3619 | 3.3814 | 4.4907 | 4.839 | 4.7947 | 4.615 | 2.0382 | 14.7051 | 14.8736 | 14.8736 | 0
3620 | 4.2938 | 5.9111 | 6.7861 | 5.1305 | 3.7956 | 2.5517 | 17.8872 | 17.4273 | 17.8872 | 1
3621 | 4.6124 | 4.011 | 5.8169 | 5.2413 | 5.009 | 1.6544 | 15.5191 | 17.0927 | 17.0927 | 0
3622 | 3.7061 | 3.7579 | 6.2591 | 5.063 | 4.4146 | 2.5687 | 15.0959 | 16.9486 | 16.9486 | 0
3623 | 2.6977 | 5.9994 | 7.0215 | 5.7517 | 3.5695 | 1.5898 | 16.0385 | 14.8785 | 16.0385 | 1
3624 | 3.5935 | 4.0493 | 4.6379 | 4.9729 | 5.6865 | 2.0801 | 14.6957 | 15.998 | 15.998 | 0
3625 | 3.9017 | 5.7978 | 3.7925 | 5.692 | 5.1842 | 1.8026 | 17.1941 | 14.6809 | 17.1941 | 1
3626 | 4.2658 | 5.5505 | 4.4503 | 4.5239 | 4.0858 | 2.3297 | 16.6698 | 15.1316 | 16.6698 | 1
3627 | 4.7609 | 5.0612 | 6.7962 | 5.7669 | 5.0986 | 1.7258 | 17.3148 | 18.3816 | 18.3816 | 0
3628 | 3.6579 | 5.4628 | 2.5625 | 4.5296 | 4.1658 | 2.162 | 15.8122 | 12.5482 | 15.8122 | 1
3629 | 4.1896 | 4.4889 | 3.4415 | 4.9722 | 3.3754 | 2.1384 | 15.7891 | 13.1448 | 15.7891 | 1
3630 | 4.1833 | 6.2819 | 7.3843 | 5.8907 | 4.8393 | 1.7815 | 18.1374 | 18.1884 | 18.1884 | 0
3631 | 3.6049 | 6.0019 | 6.4647 | 4.3761 | 4.1961 | 2.5329 | 16.5158 | 16.7986 | 16.7986 | 0
3632 | 4.8733 | 4.6062 | 5.6995 | 5.2317 | 3.7845 | 1.9896 | 16.7007 | 16.3469 | 16.7007 | 1
3633 | 2.811 | 6.6439 | 6.6436 | 5.6622 | 5.4917 | 2.4722 | 17.5893 | 17.4185 | 17.5893 | 1
3634 | 5.4116 | 4.6089 | 4.7652 | 5.8544 | 3.5987 | 2.3182 | 18.1931 | 16.0937 | 18.1931 | 1
3635 | 4.1846 | 3.9569 | 7.6459 | 6.6757 | 3.8969 | 1.8039 | 16.621 | 17.5313 | 17.5313 | 0
3636 | 4.657 | 6.6062 | 3.634 | 4.9609 | 3.4622 | 1.4417 | 17.6658 | 13.1949 | 17.6658 | 1
3637 | 4.4405 | 3.9845 | 5.3697 | 5.6736 | 5.7497 | 2.067 | 16.1656 | 17.6269 | 17.6269 | 0
3638 | 5.2754 | 6.3548 | 4.0764 | 5.6842 | 4.9882 | 1.7189 | 19.0332 | 16.0588 | 19.0332 | 1
3639 | 4.1884 | 5.1131 | 5.1862 | 5.0163 | 4.6192 | 2.0556 | 16.3733 | 16.0494 | 16.3733 | 1
3640 | 5.5401 | 3.8438 | 4.386 | 6.411 | 4.1277 | 2.4347 | 18.2295 | 16.4885 | 18.2295 | 1
3641 | 3.3827 | 4.2926 | 5.0795 | 6.1597 | 3.64 | 2.4874 | 16.3224 | 14.5895 | 16.3224 | 1
3642 | 3.745 | 4.2189 | 6.5771 | 5.786 | 3.3653 | 2.3325 | 16.0825 | 16.0199 | 16.0825 | 1
3643 | 4.9016 | 5.0618 | 5.7456 | 5.5557 | 4.7024 | 1.8063 | 17.3254 | 17.1559 | 17.3254 | 1
3644 | 3.9889 | 5.7427 | 3.4922 | 4.6372 | 4.6652 | 2.3749 | 16.7438 | 14.5212 | 16.7438 | 1
3645 | 3.5155 | 6.6563 | 5.9174 | 5.0136 | 4.8498 | 2.1197 | 17.3051 | 16.4024 | 17.3051 | 1
3646 | 3.6791 | 5.4904 | 5.2806 | 4.9895 | 4.0566 | 1.6306 | 15.7896 | 14.6468 | 15.7896 | 1
3647 | 3.3509 | 5.025 | 5.5533 | 4.718 | 4.1984 | 1.5713 | 14.6652 | 14.6739 | 14.6739 | 0
3648 | 3.7967 | 5.593 | 4.5501 | 6.138 | 5.0212 | 2.4628 | 17.9905 | 15.8307 | 17.9905 | 1
3649 | 4.2051 | 3.9628 | 5.4095 | 6.077 | 4.2556 | 1.8929 | 16.1378 | 15.763 | 16.1378 | 1
3650 | 3.6391 | 6.8848 | 5.0046 | 6.4543 | 3.6224 | 1.8806 | 18.8588 | 14.1466 | 18.8588 | 1
3651 | 2.6664 | 6.6822 | 5.628 | 4.6513 | 3.393 | 2.0472 | 16.047 | 13.7346 | 16.047 | 1
3652 | 4.5458 | 4.1819 | 6.2034 | 6.4554 | 3.4198 | 2.6933 | 17.8764 | 16.8623 | 17.8764 | 1
3653 | 2.9984 | 4.5104 | 5.4246 | 5.0572 | 4.2521 | 1.636 | 14.2021 | 14.3112 | 14.3112 | 0
3654 | 3.4341 | 7.4055 | 5.2681 | 5.0887 | 4.3221 | 1.7639 | 17.6923 | 14.7882 | 17.6923 | 1
3655 | 4.299 | 5.7774 | 3.5905 | 5.7957 | 3.2737 | 1.3443 | 17.2165 | 12.5075 | 17.2165 | 1
3656 | 4.5961 | 5.8087 | 4.7217 | 4.9392 | 3.8003 | 2.5909 | 17.935 | 15.7091 | 17.935 | 1
3657 | 3.4436 | 3.6963 | 5.3362 | 4.5928 | 3.2391 | 2.6064 | 14.3392 | 14.6253 | 14.6253 | 0
3658 | 4.8784 | 6.1038 | 6.0797 | 4.6993 | 5.0769 | 1.6576 | 17.339 | 17.6925 | 17.6925 | 0
3659 | 3.7327 | 5.2699 | 5.3701 | 4.6415 | 5.3892 | 2.4403 | 16.0844 | 16.9324 | 16.9324 | 0
3660 | 2.8981 | 6.6614 | 5.6747 | 5.452 | 3.3153 | 2.145 | 17.1566 | 14.0331 | 17.1566 | 1
3661 | 2.6626 | 4.7718 | 6.28 | 4.8537 | 4.1969 | 2.532 | 14.8201 | 15.6714 | 15.6714 | 0
3662 | 4.7515 | 4.2256 | 5.2598 | 5.709 | 4.3439 | 2.7546 | 17.4407 | 17.1098 | 17.4407 | 1
3663 | 2.8115 | 6.6867 | 5.8738 | 6.1278 | 4.0439 | 1.7433 | 17.3693 | 14.4726 | 17.3693 | 1
3664 | 2.8345 | 7.111 | 6.8341 | 4.7047 | 4.8792 | 2.5087 | 17.1588 | 17.0564 | 17.1588 | 1
3665 | 4.3256 | 3.992 | 4.5943 | 5.5844 | 3.4421 | 1.4685 | 15.3704 | 13.8305 | 15.3704 | 1
3666 | 3.303 | 4.9062 | 7.2727 | 4.8398 | 5.0775 | 1.7802 | 14.8292 | 17.4335 | 17.4335 | 0
3667 | 3.5049 | 4.9887 | 5.2737 | 5.3787 | 4.307 | 1.9651 | 15.8374 | 15.0507 | 15.8374 | 1
3668 | 3.748 | 4.0586 | 5.5689 | 5.725 | 4.6932 | 1.8744 | 15.4061 | 15.8846 | 15.8846 | 0
3669 | 3.8145 | 3.6033 | 6.0746 | 5.761 | 4.5341 | 1.9586 | 15.1375 | 16.3818 | 16.3818 | 0
3670 | 4.4426 | 5.7048 | 6.1557 | 4.4078 | 4.1877 | 1.7622 | 16.3175 | 16.5482 | 16.5482 | 0
3671 | 3.943 | 4.915 | 4.7376 | 4.6069 | 3.1797 | 2.3193 | 15.7841 | 14.1796 | 15.7841 | 1
3672 | 2.9407 | 4.6 | 4.53 | 4.6917 | 4.6676 | 1.4588 | 13.6912 | 13.5972 | 13.6912 | 1
3673 | 3.3205 | 6.5056 | 5.9174 | 4.7863 | 5.0926 | 2.2803 | 16.8927 | 16.6109 | 16.8927 | 1
3674 | 4.8307 | 7.0216 | 7.5614 | 4.5332 | 4.8137 | 2.2375 | 18.6229 | 19.4433 | 19.4433 | 0
3675 | 3.5437 | 6.0197 | 6.525 | 5.9391 | 5.3816 | 1.7647 | 17.2671 | 17.215 | 17.2671 | 1
3676 | 5.4944 | 8.2247 | 5.8287 | 4.5515 | 5.6817 | 1.2704 | 19.5409 | 18.2752 | 19.5409 | 1
3677 | 2.6092 | 6.3701 | 5.1113 | 6.2485 | 3.2909 | 1.8584 | 17.0861 | 12.8698 | 17.0861 | 1
3678 | 3.4539 | 4.7136 | 5.5147 | 5.2559 | 5.6334 | 2.2061 | 15.6294 | 16.8081 | 16.8081 | 0
3679 | 4.1033 | 5.6094 | 6.5822 | 4.7093 | 4.376 | 2.0684 | 16.4904 | 17.1299 | 17.1299 | 0
3680 | 3.6876 | 4.4484 | 4.6369 | 4.6862 | 5.0946 | 1.8949 | 14.7171 | 15.314 | 15.314 | 0
3681 | 4.8731 | 4.6923 | 7.7226 | 5.3202 | 4.9302 | 2.3367 | 17.2222 | 19.8626 | 19.8626 | 0
3682 | 3.219 | 5.4728 | 5.8361 | 4.5513 | 4.4756 | 1.6429 | 14.8859 | 15.1735 | 15.1735 | 0
3683 | 5.2591 | 5.5539 | 6.8317 | 5.2212 | 3.8024 | 1.8149 | 17.8491 | 17.7081 | 17.8491 | 1
3684 | 4.7963 | 5.9684 | 5.415 | 5.6449 | 3.6754 | 2.0825 | 18.492 | 15.9692 | 18.492 | 1
3685 | 5.6345 | 6.98 | 6.8929 | 4.9389 | 4.2546 | 1.5779 | 19.1314 | 18.3599 | 19.1314 | 1
3686 | 4.5885 | 6.6385 | 3.8117 | 4.7363 | 4.6535 | 1.8716 | 17.8349 | 14.9254 | 17.8349 | 1
3687 | 3.9344 | 6.6335 | 6.3721 | 4.785 | 4.5447 | 2.1324 | 17.4853 | 16.9836 | 17.4853 | 1
3688 | 4.2671 | 5.1392 | 6.5198 | 4.3522 | 3.7446 | 2.004 | 15.7625 | 16.5356 | 16.5356 | 0
3689 | 3.9395 | 4.3539 | 6.349 | 5.9438 | 5.0042 | 2.3574 | 16.5946 | 17.6501 | 17.6501 | 0
3690 | 5.4186 | 3.3642 | 5.5542 | 4.9065 | 4.5374 | 2.3908 | 16.0801 | 17.901 | 17.901 | 0
3691 | 4.8834 | 5.8627 | 5.7041 | 4.7659 | 3.3831 | 2.1134 | 17.6255 | 16.0841 | 17.6255 | 1
3692 | 3.8219 | 5.825 | 5.8896 | 5.3441 | 5.2721 | 2.089 | 17.08 | 17.0726 | 17.08 | 1
3693 | 4.5402 | 5.76 | 6.8515 | 5.1376 | 3.6854 | 1.8829 | 17.3208 | 16.96 | 17.3208 | 1
3694 | 3.5019 | 4.5053 | 4.925 | 5.4173 | 4.1183 | 1.7319 | 15.1564 | 14.2771 | 15.1564 | 1
3695 | 3.408 | 7.695 | 6.2035 | 5.0005 | 5.0671 | 1.9086 | 18.0121 | 16.5872 | 18.0121 | 1
3696 | 2.5413 | 4.1056 | 5.4325 | 6.5389 | 3.8721 | 1.4896 | 14.6753 | 13.3354 | 14.6753 | 1
3697 | 2.673 | 4.3789 | 4.7079 | 5.0834 | 4.1738 | 1.7765 | 13.9117 | 13.3312 | 13.9117 | 1
3698 | 4.7426 | 6.4578 | 6.0731 | 5.4937 | 4.3254 | 1.6348 | 18.3289 | 16.7759 | 18.3289 | 1
3699 | 4.4409 | 7.4143 | 3.5824 | 4.3058 | 4.1994 | 2.2596 | 18.4206 | 14.4822 | 18.4206 | 1
3700 | 2.7644 | 7.371 | 6.3949 | 4.741 | 4.5269 | 2.2071 | 17.0835 | 15.8933 | 17.0835 | 1
3701 | 4.9881 | 4.1927 | 6.0017 | 5.7244 | 5.6626 | 2.1382 | 17.0434 | 18.7906 | 18.7906 | 0
3702 | 5.3913 | 4.3924 | 3.6701 | 5.5648 | 4.3648 | 1.7592 | 17.1078 | 15.1855 | 17.1078 | 1
3703 | 4.7566 | 5.6791 | 3.9609 | 6.2298 | 4.5161 | 1.5171 | 18.1826 | 14.7507 | 18.1826 | 1
3704 | 4.2837 | 5.5349 | 5.1052 | 5.9717 | 3.9431 | 1.9505 | 17.7409 | 15.2825 | 17.7409 | 1
3705 | 3.5853 | 3.985 | 4.2056 | 5.9831 | 3.4237 | 1.6165 | 15.1698 | 12.8311 | 15.1698 | 1
3706 | 3.2496 | 4.0597 | 6.1876 | 4.2643 | 5.1871 | 2.0568 | 13.6305 | 16.6812 | 16.6812 | 0
3707 | 2.4566 | 3.904 | 5.8097 | 5.6256 | 3.5589 | 2.2439 | 14.2301 | 14.0691 | 14.2301 | 1
3708 | 5.0155 | 6.3986 | 5.5719 | 5.7546 | 6.2084 | 1.977 | 19.1456 | 18.7727 | 19.1456 | 1
3709 | 4.4405 | 5.6406 | 7.7563 | 5.1413 | 3.8144 | 1.7753 | 16.9977 | 17.7865 | 17.7865 | 0
3710 | 3.0803 | 4.8076 | 6.3027 | 5.1853 | 3.4912 | 2.2233 | 15.2965 | 15.0975 | 15.2965 | 1
3711 | 4.4179 | 4.9842 | 6.4021 | 5.2229 | 3.8726 | 1.6623 | 16.2873 | 16.3549 | 16.3549 | 0
3712 | 3.5912 | 4.281 | 5.8594 | 6.2745 | 3.3705 | 1.5696 | 15.7162 | 14.3907 | 15.7162 | 1
3713 | 4.1547 | 5.5397 | 7.3669 | 5.6798 | 4.039 | 1.5121 | 16.8864 | 17.0727 | 17.0727 | 0
3714 | 3.0831 | 7.6094 | 7.1239 | 5.5941 | 3.8533 | 1.7881 | 18.0748 | 15.8485 | 18.0748 | 1
3715 | 5.1125 | 5.9196 | 6.8255 | 5.3462 | 3.5153 | 2.3002 | 18.6784 | 17.7535 | 18.6784 | 1
3716 | 4.145 | 6.4646 | 5.4977 | 5.5833 | 3.949 | 1.6513 | 17.8443 | 15.243 | 17.8443 | 1
3717 | 3.3721 | 3.6114 | 6.5999 | 5.1695 | 4.6069 | 1.6908 | 13.8437 | 16.2697 | 16.2697 | 0
3718 | 4.916 | 7.8118 | 4.1205 | 6.7236 | 4.5576 | 1.1613 | 20.6127 | 14.7554 | 20.6127 | 1
3719 | 3.5059 | 5.694 | 5.3179 | 4.3234 | 4.0854 | 1.9139 | 15.4371 | 14.823 | 15.4371 | 1
3720 | 4.2195 | 5.3541 | 5.436 | 4.6218 | 4.1387 | 2.0371 | 16.2325 | 15.8313 | 16.2325 | 1
3721 | 4.2231 | 7.4419 | 6.7507 | 6.0891 | 3.4482 | 1.8963 | 19.6504 | 16.3183 | 19.6504 | 1
3722 | 4.0228 | 6.5293 | 5.2381 | 6.8081 | 3.6419 | 1.4866 | 18.8468 | 14.3893 | 18.8468 | 1
3723 | 3.689 | 7.3228 | 6.5006 | 5.3255 | 3.329 | 1.673 | 18.0102 | 15.1916 | 18.0102 | 1
3724 | 3.6009 | 4.3623 | 5.9631 | 5.0876 | 3.9112 | 1.5449 | 14.5957 | 15.0201 | 15.0201 | 0
3725 | 3.5957 | 4.6838 | 4.5799 | 5.3545 | 5.5925 | 1.3193 | 14.9533 | 15.0874 | 15.0874 | 0
3726 | 3.3958 | 3.8952 | 4.1254 | 4.2688 | 3.0979 | 2.6116 | 14.1714 | 13.2307 | 14.1714 | 1
3727 | 3.0472 | 5.078 | 4.7082 | 5.3398 | 4.4314 | 1.9036 | 15.3686 | 14.0903 | 15.3686 | 1
3728 | 4.8516 | 5.2216 | 5.6629 | 6.2636 | 5.7138 | 2.7017 | 19.0385 | 18.9301 | 19.0385 | 1
3729 | 3.9912 | 6.3361 | 7.0919 | 5.5512 | 3.731 | 1.2889 | 17.1675 | 16.1031 | 17.1675 | 1
3730 | 3.4027 | 7.267 | 6.0596 | 4.8213 | 3.9575 | 1.6556 | 17.1465 | 15.0753 | 17.1465 | 1
3731 | 3.9362 | 5.182 | 6.5194 | 4.4342 | 4.1377 | 2.0468 | 15.5992 | 16.6401 | 16.6401 | 0
3732 | 4.9623 | 7.3442 | 5.3316 | 7.2905 | 4.0155 | 1.9136 | 21.5106 | 16.2228 | 21.5106 | 1
3733 | 3.3553 | 4.3201 | 4.591 | 5.1687 | 3.6644 | 2.5499 | 15.394 | 14.1607 | 15.394 | 1
3734 | 4.3894 | 4.7013 | 3.9975 | 4.2518 | 4.5892 | 2.3523 | 15.6948 | 15.3283 | 15.6948 | 1
3735 | 4.3131 | 4.9362 | 7.1475 | 5.7777 | 3.5995 | 2.083 | 17.11 | 17.1431 | 17.1431 | 0
3736 | 4.9674 | 4.7329 | 6.6418 | 6.289 | 5.4575 | 1.4688 | 17.4581 | 18.5355 | 18.5355 | 0
3737 | 5.0372 | 5.1609 | 5.9198 | 5.2318 | 3.5386 | 1.5431 | 16.973 | 16.0387 | 16.973 | 1
3738 | 3.1965 | 3.7579 | 4.2912 | 4.9112 | 3.9969 | 2.3469 | 14.2125 | 13.8315 | 14.2125 | 1
3739 | 3.2188 | 6.1224 | 5.0649 | 5.5627 | 4.0548 | 2.634 | 17.5378 | 14.9724 | 17.5378 | 1
3740 | 4.2931 | 5.3317 | 6.9738 | 5.3128 | 3.6083 | 2.0016 | 16.9392 | 16.8768 | 16.9392 | 1
3741 | 4.3148 | 6.2056 | 7.2032 | 6.2294 | 3.5103 | 2.2148 | 18.9646 | 17.2431 | 18.9646 | 1
3742 | 3.4932 | 5.24 | 5.4114 | 4.8403 | 4.4327 | 2.2261 | 15.7996 | 15.5634 | 15.7996 | 1
3743 | 4.0934 | 5.1494 | 6.1548 | 6.3706 | 3.8416 | 1.6743 | 17.2878 | 15.7641 | 17.2878 | 1
3744 | 3.7116 | 6.5961 | 6.2709 | 6.4464 | 4.497 | 2.2576 | 19.0117 | 16.7371 | 19.0117 | 1
3745 | 3.863 | 6.7507 | 7.4371 | 5.5247 | 3.4055 | 2.0755 | 18.2139 | 16.781 | 18.2139 | 1
3746 | 2.9523 | 7.0752 | 7.1841 | 5.66 | 3.5305 | 1.7303 | 17.4178 | 15.3973 | 17.4178 | 1
3747 | 4.6685 | 5.9009 | 5.2654 | 4.2848 | 4.5334 | 1.5514 | 16.4056 | 16.0187 | 16.4056 | 1
3748 | 4.8688 | 6.3086 | 7.0537 | 7.2369 | 3.7575 | 2.5124 | 20.9269 | 18.1925 | 20.9269 | 1
3749 | 4.3541 | 5.972 | 6.9464 | 6.429 | 4.3641 | 2.3898 | 19.145 | 18.0544 | 19.145 | 1
3750 | 3.7755 | 6.0786 | 4.8002 | 4.8566 | 3.6603 | 2.015 | 16.7258 | 14.251 | 16.7258 | 1
3751 | 4.439 | 6.99 | 5.6843 | 5.5884 | 4.6401 | 1.6428 | 18.6602 | 16.4061 | 18.6602 | 1
3752 | 4.9041 | 4.0684 | 7.3324 | 4.3308 | 4.7848 | 2.0305 | 15.3338 | 19.0518 | 19.0518 | 0
3753 | 4.7933 | 3.7702 | 6.0733 | 6.632 | 4.2446 | 1.4929 | 16.6884 | 16.6042 | 16.6884 | 1
3754 | 3.8504 | 4.3125 | 5.3472 | 5.6118 | 5.1527 | 2.1112 | 15.8858 | 16.4614 | 16.4614 | 0
3755 | 3.946 | 5.5458 | 4.7853 | 4.8998 | 4.6365 | 2.1311 | 16.5227 | 15.499 | 16.5227 | 1
3756 | 3.6971 | 4.1117 | 4.8038 | 5.3222 | 4.4464 | 2.5438 | 15.6748 | 15.4911 | 15.6748 | 1
3757 | 5.0313 | 6.5659 | 7.4056 | 5.9202 | 4.1919 | 1.5622 | 19.0796 | 18.191 | 19.0796 | 1
3758 | 4.2737 | 4.3923 | 6.5085 | 5.43 | 3.827 | 1.4572 | 15.5532 | 16.0664 | 16.0664 | 0
3759 | 2.7375 | 4.953 | 5.3177 | 5.4219 | 4.6604 | 1.7155 | 14.8279 | 14.4312 | 14.8279 | 1
3760 | 4.2524 | 5.9072 | 5.5968 | 4.9421 | 3.5358 | 2.26 | 17.3617 | 15.645 | 17.3617 | 1
3761 | 4.4512 | 4.7728 | 7.6484 | 4.9632 | 3.3583 | 2.3285 | 16.5158 | 17.7864 | 17.7864 | 0
3762 | 4.5092 | 4.6252 | 6.6763 | 5.8924 | 5.1226 | 2.4313 | 17.4581 | 18.7394 | 18.7394 | 0
3763 | 3.7303 | 6.1027 | 5.7037 | 4.2564 | 4.9167 | 1.6686 | 15.758 | 16.0193 | 16.0193 | 0
3764 | 3.4738 | 4.1588 | 5.831 | 4.7276 | 3.6684 | 2.3288 | 14.6891 | 15.3021 | 15.3021 | 0
3765 | 4.2858 | 5.2448 | 6.2065 | 6.1143 | 3.9466 | 2.1717 | 17.8166 | 16.6105 | 17.8166 | 1
3766 | 3.8039 | 4.4494 | 6.1819 | 5.0036 | 3.5238 | 2.3796 | 15.6366 | 15.8893 | 15.8893 | 0
3767 | 3.3528 | 5.7212 | 4.3683 | 6.017 | 4.3337 | 1.6926 | 16.7837 | 13.7475 | 16.7837 | 1
3768 | 3.9489 | 3.8174 | 4.6106 | 4.6235 | 4.6763 | 2.4147 | 14.8045 | 15.6505 | 15.6505 | 0
3769 | 5.4404 | 5.1377 | 4.9971 | 4.296 | 5.0024 | 2.1333 | 17.0074 | 17.5732 | 17.5732 | 0
3770 | 3.6096 | 6.3013 | 4.9882 | 5.6576 | 3.7423 | 1.983 | 17.5514 | 14.323 | 17.5514 | 1
3771 | 4.2094 | 5.2313 | 5.6461 | 5.9304 | 3.7363 | 2.2551 | 17.6262 | 15.8469 | 17.6262 | 1
3772 | 4.5607 | 4.5582 | 5.5066 | 5.8755 | 4.5638 | 2.041 | 17.0354 | 16.6721 | 17.0354 | 1
3773 | 3.0961 | 5.5512 | 6.2817 | 5.0394 | 4.1665 | 2.2685 | 15.9553 | 15.8129 | 15.9553 | 1
3774 | 4.0188 | 4.1741 | 6.6365 | 6.0951 | 3.9461 | 2.2454 | 16.5334 | 16.8468 | 16.8468 | 0
3775 | 4.9779 | 5.746 | 5.35 | 6.7099 | 4.3986 | 1.8598 | 19.2935 | 16.5862 | 19.2935 | 1
3776 | 3.8665 | 5.6494 | 4.9796 | 6.0551 | 4.365 | 1.9533 | 17.5242 | 15.1643 | 17.5242 | 1
3777 | 4.6159 | 5.3662 | 6.8772 | 5.3107 | 4.6213 | 2.1405 | 17.4333 | 18.2548 | 18.2548 | 0
3778 | 3.9715 | 4.3878 | 6.7829 | 6.4642 | 3.9548 | 1.2914 | 16.115 | 16.0006 | 16.115 | 1
3779 | 4.4964 | 3.813 | 6.0624 | 5.5169 | 4.9641 | 1.7969 | 15.6233 | 17.3199 | 17.3199 | 0
3780 | 5.5124 | 5.7643 | 5.7972 | 5.5485 | 3.776 | 1.8574 | 18.6826 | 16.943 | 18.6826 | 1
3781 | 5.0384 | 3.6416 | 3.7793 | 5.2386 | 4.3723 | 2.3595 | 16.2782 | 15.5494 | 16.2782 | 1
3782 | 3.6636 | 4.0482 | 5.7473 | 4.6255 | 4.9037 | 1.2139 | 13.5513 | 15.5286 | 15.5286 | 0
3783 | 4.4564 | 4.6476 | 5.5818 | 5.6665 | 5.1639 | 2.1735 | 16.944 | 17.3756 | 17.3756 | 0
3784 | 4.9578 | 6.0968 | 3.6434 | 5.2326 | 4.4983 | 1.9835 | 18.2708 | 15.0831 | 18.2708 | 1
3785 | 5.6914 | 4.3825 | 6.5396 | 5.2666 | 3.9367 | 2.3728 | 17.7133 | 18.5406 | 18.5406 | 0
3786 | 3.241 | 4.8344 | 4.7725 | 6.0583 | 4.2134 | 2.3122 | 16.4459 | 14.5391 | 16.4459 | 1
3787 | 2.7297 | 5.7001 | 4.6251 | 4.7652 | 4.9779 | 1.5857 | 14.7806 | 13.9184 | 14.7806 | 1
3788 | 4.5017 | 4.3782 | 7.16 | 5.5273 | 5.6466 | 2.127 | 16.5342 | 19.4353 | 19.4353 | 0
3789 | 3.4744 | 6.3574 | 5.4983 | 5.6519 | 4.4827 | 1.5878 | 17.0715 | 15.0431 | 17.0715 | 1
3790 | 4.8678 | 4.184 | 6.5693 | 5.2446 | 3.4947 | 2.3577 | 16.654 | 17.2895 | 17.2895 | 0
3791 | 3.9779 | 4.9883 | 6.0076 | 5.7293 | 5.491 | 2.3226 | 17.0181 | 17.7991 | 17.7991 | 0
3792 | 4.7601 | 4.9929 | 4.2522 | 4.4624 | 3.61 | 1.636 | 15.8514 | 14.2583 | 15.8514 | 1
3793 | 4.4129 | 4.5614 | 6.0334 | 7.0323 | 3.3934 | 1.9665 | 17.9731 | 15.8062 | 17.9731 | 1
3794 | 4.0089 | 5.8001 | 5.3377 | 7.0288 | 4.0461 | 1.3952 | 18.233 | 14.7879 | 18.233 | 1
3795 | 3.2509 | 3.6076 | 6.0037 | 4.8299 | 5.6874 | 2.2904 | 13.9788 | 17.2323 | 17.2323 | 0
3796 | 3.5118 | 5.5074 | 7.4711 | 5.0121 | 4.0566 | 2.3975 | 16.4287 | 17.4369 | 17.4369 | 0
3797 | 3.555 | 3.5603 | 5.5867 | 4.7613 | 4.0793 | 1.7387 | 13.6153 | 14.9597 | 14.9597 | 0
3798 | 3.7283 | 4.1894 | 5.2666 | 4.8482 | 4.3559 | 1.4504 | 14.2163 | 14.8012 | 14.8012 | 0
3799 | 3.8992 | 6.6074 | 4.9066 | 6.0335 | 4.3572 | 2.0281 | 18.5682 | 15.191 | 18.5682 | 1
3800 | 4.3641 | 4.5691 | 4.6814 | 4.2237 | 3.9568 | 1.8186 | 14.9756 | 14.821 | 14.9756 | 1
3801 | 3.9396 | 6.595 | 5.0371 | 4.5921 | 5.2003 | 2.4176 | 17.5442 | 16.5946 | 17.5442 | 1
3802 | 4.8849 | 4.1771 | 5.5831 | 6.7928 | 6.033 | 2.0508 | 17.9056 | 18.5517 | 18.5517 | 0
3803 | 2.9784 | 4.6491 | 7.1109 | 6.3456 | 4.3837 | 2.4677 | 16.4409 | 16.9408 | 16.9408 | 0
3804 | 4.8227 | 6.1264 | 5.2 | 4.6619 | 4.0819 | 1.2202 | 16.8313 | 15.3248 | 16.8313 | 1
3805 | 2.6298 | 5.3888 | 5.7455 | 4.7634 | 3.6943 | 2.3586 | 15.1407 | 14.4282 | 15.1407 | 1
3806 | 3.2004 | 7.2286 | 6.4289 | 4.6556 | 3.4342 | 1.5472 | 16.6319 | 14.6107 | 16.6319 | 1
3807 | 4.0744 | 6.989 | 4.9243 | 5.4976 | 4.0645 | 2.2915 | 18.8525 | 15.3548 | 18.8525 | 1
3808 | 4.1576 | 3.7312 | 5.2063 | 5.4373 | 4.989 | 2.2585 | 15.5847 | 16.6114 | 16.6114 | 0
3809 | 3.4768 | 5.2556 | 5.6878 | 6.0592 | 4.221 | 1.4977 | 16.2893 | 14.8833 | 16.2893 | 1
3810 | 4.0655 | 6.5202 | 7.1271 | 5.1372 | 5.0455 | 1.7301 | 17.4531 | 17.9683 | 17.9683 | 0
3811 | 4.0808 | 3.84 | 5.0118 | 6.1014 | 5.0414 | 1.3577 | 15.38 | 15.4916 | 15.4916 | 0
3812 | 3.8574 | 6.0302 | 6.1647 | 4.7418 | 3.0764 | 1.7598 | 16.3892 | 14.8582 | 16.3892 | 1
3813 | 3.1485 | 5.8953 | 2.7437 | 4.878 | 4.2895 | 2.0484 | 15.9702 | 12.2301 | 15.9702 | 1
3814 | 3.8394 | 6.076 | 5.2856 | 6.5343 | 3.681 | 1.5749 | 18.0246 | 14.381 | 18.0246 | 1
3815 | 3.3116 | 5.3356 | 5.5674 | 4.1999 | 4.2357 | 1.3275 | 14.1747 | 14.4423 | 14.4423 | 0
3816 | 4.3289 | 5.8002 | 4.9746 | 4.8907 | 5.0535 | 1.8132 | 16.833 | 16.1702 | 16.833 | 1
3817 | 3.1979 | 5.9222 | 5.6215 | 5.1346 | 3.3115 | 1.9267 | 16.1814 | 14.0577 | 16.1814 | 1
3818 | 3.805 | 6.785 | 3.4747 | 5.3071 | 4.0883 | 2.3625 | 18.2595 | 13.7304 | 18.2595 | 1
3819 | 3.0139 | 3.3715 | 5.2848 | 5.4976 | 4.177 | 1.3873 | 13.2704 | 13.863 | 13.863 | 0
3820 | 4.495 | 4.1634 | 4.9446 | 6.1386 | 3.5879 | 2.5422 | 17.3392 | 15.5698 | 17.3392 | 1
3821 | 4.4231 | 5.5015 | 5.318 | 5.2398 | 5.4771 | 1.6117 | 16.776 | 16.8298 | 16.8298 | 0
3822 | 3.7791 | 5.4579 | 6.2327 | 5.2823 | 4.0949 | 1.7215 | 16.2408 | 15.8282 | 16.2408 | 1
3823 | 2.953 | 3.3802 | 6.2021 | 4.1725 | 4.4917 | 1.5512 | 12.0568 | 15.1979 | 15.1979 | 0
3824 | 3.9456 | 4.6293 | 5.0612 | 4.8694 | 3.1945 | 2.369 | 15.8133 | 14.5703 | 15.8133 | 1
3825 | 2.8455 | 6.3319 | 5.9936 | 5.5291 | 3.3816 | 1.6547 | 16.3612 | 13.8754 | 16.3612 | 1
3826 | 3.9563 | 6.232 | 6.8815 | 5.4185 | 5.2213 | 2.3443 | 17.9511 | 18.4033 | 18.4033 | 0
3827 | 4.5405 | 5.672 | 3.243 | 6.0669 | 5.0647 | 2.2046 | 18.484 | 15.0528 | 18.484 | 1
3828 | 3.7445 | 6.362 | 5.5548 | 5.5007 | 3.6859 | 1.8235 | 17.4309 | 14.8088 | 17.4309 | 1
3829 | 4.3755 | 6.943 | 4.243 | 4.8825 | 3.8554 | 1.8832 | 18.0843 | 14.3571 | 18.0843 | 1
3830 | 4.0179 | 4.6716 | 5.0822 | 4.9851 | 3.2255 | 2.2348 | 15.9094 | 14.5604 | 15.9094 | 1
3831 | 4.0799 | 5.0632 | 6.5192 | 4.5655 | 5.8385 | 2.2564 | 15.965 | 18.694 | 18.694 | 0
3832 | 3.6074 | 3.9435 | 3.2295 | 5.4074 | 3.9361 | 1.7261 | 14.6844 | 12.4991 | 14.6844 | 1
3833 | 3.0513 | 5.8721 | 4.0257 | 5.6797 | 3.9818 | 1.5088 | 16.1119 | 12.5676 | 16.1119 | 1
3834 | 3.3697 | 4.6357 | 4.5845 | 5.7598 | 4.6712 | 2.3041 | 16.0693 | 14.9295 | 16.0693 | 1
3835 | 3.939 | 6.2327 | 6.4763 | 5.3018 | 4.9421 | 2.09 | 17.5634 | 17.4473 | 17.5634 | 1
3836 | 4.1297 | 4.9893 | 5.9214 | 5.2014 | 4.3519 | 2.0337 | 16.3542 | 16.4367 | 16.4367 | 0
3837 | 4.4465 | 6.4951 | 6.3352 | 4.0442 | 3.7452 | 2.1725 | 17.1583 | 16.6994 | 17.1583 | 1
3838 | 4.7158 | 4.3651 | 3.6714 | 5.0741 | 4.4605 | 1.6399 | 15.795 | 14.4877 | 15.795 | 1
3839 | 3.2022 | 5.9151 | 5.4837 | 6.0539 | 4.1869 | 2.2924 | 17.4637 | 15.1653 | 17.4637 | 1
3840 | 5.2221 | 4.2772 | 6.766 | 5.7145 | 3.4428 | 1.6232 | 16.8369 | 17.0541 | 17.0541 | 0
3841 | 2.8868 | 5.0127 | 6.0532 | 4.7991 | 4.0099 | 1.8979 | 14.5965 | 14.8478 | 14.8478 | 0
3842 | 3.926 | 5.0935 | 6.3583 | 4.8446 | 3.671 | 2.6349 | 16.4991 | 16.5902 | 16.5902 | 0
3843 | 3.0365 | 6.0038 | 5.9515 | 5.4061 | 4.467 | 2.4237 | 16.8702 | 15.8788 | 16.8702 | 1
3844 | 3.2016 | 6.4627 | 5.7583 | 4.8213 | 3.4675 | 1.27 | 15.7556 | 13.6975 | 15.7556 | 1
3845 | 2.8151 | 4.503 | 5.5525 | 4.9966 | 3.1397 | 1.6197 | 13.9344 | 13.127 | 13.9344 | 1
3846 | 3.5621 | 5.8095 | 6.9442 | 5.8214 | 4.2456 | 2.2126 | 17.4056 | 16.9646 | 17.4056 | 1
3847 | 5.376 | 5.0364 | 6.6878 | 4.3357 | 4.4091 | 2.0827 | 16.8308 | 18.5556 | 18.5556 | 0
3848 | 3.3157 | 5.5316 | 4.7419 | 5.0317 | 4.8329 | 2.1739 | 16.0528 | 15.0645 | 16.0528 | 1
3849 | 4.7772 | 5.4796 | 5.2486 | 6.6665 | 3.6829 | 1.7003 | 18.6236 | 15.409 | 18.6236 | 1
3850 | 5.4355 | 5.5222 | 6.6912 | 5.052 | 6.0041 | 2.4847 | 18.4944 | 20.6155 | 20.6155 | 0
3851 | 4.0444 | 6.4019 | 6.0939 | 5.688 | 4.2615 | 2.194 | 18.3283 | 16.5939 | 18.3283 | 1
3852 | 4.9571 | 4.6445 | 5.7482 | 5.6632 | 5.2523 | 2.4382 | 17.7029 | 18.3957 | 18.3957 | 0
3853 | 3.9705 | 3.7956 | 7.0345 | 5.3141 | 3.9691 | 2.4778 | 15.5581 | 17.452 | 17.452 | 0
3854 | 4.5119 | 3.9701 | 5.9507 | 5.5596 | 4.861 | 2.48 | 16.5216 | 17.8036 | 17.8036 | 0
3855 | 2.4843 | 3.947 | 6.4873 | 5.7379 | 4.1218 | 2.3727 | 14.5419 | 15.4661 | 15.4661 | 0
3856 | 4.2209 | 4.1127 | 6.5074 | 4.9946 | 4.0938 | 1.2329 | 14.561 | 16.0549 | 16.0549 | 0
3857 | 3.2194 | 4.0479 | 5.6044 | 5.2272 | 4.3081 | 2.6186 | 15.1132 | 15.7505 | 15.7505 | 0
3858 | 3.1907 | 5.8335 | 6.8404 | 4.2516 | 4.8661 | 2.2768 | 15.5526 | 17.1739 | 17.1739 | 0
3859 | 5.199 | 4.2568 | 6.1509 | 4.9307 | 4.8111 | 2.3289 | 16.7154 | 18.4898 | 18.4898 | 0
3860 | 4.4813 | 3.6916 | 5.9591 | 5.5425 | 5.1473 | 1.7089 | 15.4243 | 17.2966 | 17.2966 | 0
3861 | 2.9198 | 3.6428 | 5.0427 | 5.9356 | 3.908 | 1.809 | 14.3073 | 13.6796 | 14.3073 | 1
3862 | 5.3526 | 4.7403 | 7.3896 | 4.8676 | 3.7514 | 2.3489 | 17.3093 | 18.8425 | 18.8425 | 0
3863 | 4.2291 | 4.8957 | 6.7692 | 4.4485 | 4.1741 | 1.7987 | 15.372 | 16.971 | 16.971 | 0
3864 | 3.0432 | 4.143 | 4.6919 | 5.5508 | 3.6337 | 1.1603 | 13.8973 | 12.5291 | 13.8973 | 1
3865 | 3.0919 | 6.6367 | 6.9207 | 6.3521 | 4.9522 | 1.8551 | 17.9358 | 16.8199 | 17.9358 | 1
3866 | 3.6764 | 3.8676 | 7.1939 | 4.2137 | 4.9786 | 1.9318 | 13.6895 | 17.7807 | 17.7807 | 0
3867 | 4.7399 | 6.4725 | 3.5449 | 6.8348 | 4.3652 | 2.2678 | 20.315 | 14.9178 | 20.315 | 1
3868 | 3.1379 | 4.0449 | 6.6686 | 4.7234 | 3.477 | 2.7032 | 14.6094 | 15.9867 | 15.9867 | 0
3869 | 4.2189 | 6.5399 | 6.6808 | 4.3054 | 4.8022 | 2.222 | 17.2861 | 17.9239 | 17.9239 | 0
3870 | 4.0938 | 3.3608 | 4.2172 | 5.6505 | 4.5852 | 2.1352 | 15.2404 | 15.0315 | 15.2404 | 1
3871 | 3.9549 | 6.9437 | 7.2516 | 6.8783 | 4.7943 | 1.9615 | 19.7384 | 17.9622 | 19.7384 | 1
3872 | 2.9309 | 7.0151 | 7.2457 | 5.158 | 3.6463 | 1.6462 | 16.7502 | 15.4691 | 16.7502 | 1
3873 | 4.4327 | 6.1247 | 6.5348 | 6.8562 | 3.8945 | 1.7657 | 19.1793 | 16.6278 | 19.1793 | 1
3874 | 4.0433 | 5.0695 | 3.8671 | 4.8387 | 4.4355 | 1.9371 | 15.8886 | 14.2831 | 15.8886 | 1
3875 | 2.9246 | 4.5904 | 6.6859 | 5.5821 | 4.4329 | 1.6867 | 14.7838 | 15.7301 | 15.7301 | 0
3876 | 4.3991 | 4.4076 | 7.1309 | 4.4331 | 3.5106 | 2.176 | 15.4158 | 17.2166 | 17.2166 | 0
3877 | 4.8621 | 6.7665 | 4.4329 | 4.7887 | 3.9353 | 1.7009 | 18.1181 | 14.9312 | 18.1181 | 1
3878 | 2.4386 | 4.907 | 4.3347 | 4.5213 | 3.2829 | 1.8504 | 13.7173 | 11.9065 | 13.7173 | 1
3879 | 4.2336 | 4.3185 | 7.5756 | 5.5349 | 4.4077 | 2.4831 | 16.5701 | 18.7 | 18.7 | 0
3880 | 3.4216 | 3.5587 | 5.5908 | 5.2553 | 3.778 | 1.8791 | 14.1147 | 14.6695 | 14.6695 | 0
3881 | 4.3695 | 3.4503 | 4.6655 | 4.5752 | 4.6662 | 1.8605 | 14.2555 | 15.5617 | 15.5617 | 0
3882 | 3.728 | 8.1556 | 5.1978 | 6.2531 | 6.0571 | 2.2994 | 20.4361 | 17.2823 | 20.4361 | 1
3883 | 5.4975 | 5.7016 | 6.6191 | 6.2204 | 4.9629 | 2.124 | 19.5435 | 19.2034 | 19.5435 | 1
3884 | 3.9353 | 6.1334 | 5.4585 | 6.1534 | 3.8459 | 1.8492 | 18.0713 | 15.0889 | 18.0713 | 1
3885 | 4.0049 | 4.9862 | 4.6197 | 4.9166 | 4.5748 | 2.3214 | 16.2291 | 15.5207 | 16.2291 | 1
3886 | 5.0601 | 4.7881 | 5.13 | 4.9072 | 3.6633 | 1.5471 | 16.3026 | 15.4006 | 16.3026 | 1
3887 | 3.7183 | 4.3664 | 4.2581 | 6.9256 | 3.2754 | 1.2629 | 16.2732 | 12.5147 | 16.2732 | 1
3888 | 4.3106 | 6.2781 | 6.3898 | 5.55 | 4.4592 | 1.9247 | 18.0634 | 17.0843 | 18.0634 | 1
3889 | 4.9704 | 4.9207 | 7.2498 | 4.8292 | 4.0192 | 2.4224 | 17.1427 | 18.6618 | 18.6618 | 0
3890 | 3.1606 | 6.998 | 4.2602 | 5.5191 | 4.1147 | 1.7686 | 17.4463 | 13.3041 | 17.4463 | 1
3891 | 2.8784 | 5.9706 | 7.0402 | 4.852 | 5.2576 | 1.7102 | 15.4112 | 16.8864 | 16.8864 | 0
3892 | 5.285 | 5.5598 | 4.5055 | 5.9892 | 3.8043 | 2.4248 | 19.2589 | 16.0196 | 19.2589 | 1
3893 | 2.8994 | 5.42 | 6.2497 | 5.1449 | 3.8735 | 1.5068 | 14.9712 | 14.5294 | 14.9712 | 1
3894 | 3.8849 | 5.4033 | 5.5787 | 4.0802 | 3.3144 | 2.5162 | 15.8846 | 15.2942 | 15.8846 | 1
3895 | 2.8586 | 6.2496 | 7.2674 | 4.9569 | 4.6051 | 1.6013 | 15.6664 | 16.3324 | 16.3324 | 0
3896 | 4.4039 | 3.1174 | 5.7598 | 5.4282 | 3.7563 | 1.9484 | 14.898 | 15.8684 | 15.8684 | 0
3897 | 3.4698 | 4.7116 | 6.8799 | 4.4073 | 3.2588 | 2.0091 | 14.5978 | 15.6177 | 15.6177 | 0
3898 | 2.56 | 5.0535 | 5.1161 | 6.3362 | 4.58 | 1.8227 | 15.7724 | 14.0788 | 15.7724 | 1
3899 | 3.6413 | 5.7171 | 5.4462 | 5.0919 | 4.1955 | 1.0933 | 15.5436 | 14.3763 | 15.5436 | 1
3900 | 2.2803 | 5.0537 | 6.7485 | 4.9225 | 3.8278 | 2.1719 | 14.4284 | 15.0285 | 15.0285 | 0
3901 | 4.8405 | 5.0414 | 5.1714 | 5.9685 | 3.7239 | 2.3442 | 18.1946 | 16.08 | 18.1946 | 1
3902 | 3.6372 | 5.4193 | 3.0557 | 4.452 | 3.8461 | 2.7834 | 16.2919 | 13.3223 | 16.2919 | 1
3903 | 4.7416 | 5.6193 | 5.7145 | 4.4483 | 5.7833 | 1.5176 | 16.3268 | 17.7571 | 17.7571 | 0
3904 | 4.9173 | 6.5722 | 6.9481 | 5.3093 | 3.9507 | 1.9877 | 18.7864 | 17.8037 | 18.7864 | 1
3905 | 4.6485 | 5.9104 | 7.0584 | 5.0744 | 3.8607 | 1.5249 | 17.1583 | 17.0926 | 17.1583 | 1
3906 | 3.5881 | 5.6763 | 3.3893 | 4.4658 | 4.3053 | 2.5995 | 16.3296 | 13.8821 | 16.3296 | 1
3907 | 4.245 | 7.6634 | 7.0368 | 7.441 | 4.8467 | 2.3821 | 21.7315 | 18.5106 | 21.7315 | 1
3908 | 4.889 | 5.0713 | 5.0697 | 4.635 | 5.6026 | 1.5813 | 16.1765 | 17.1425 | 17.1425 | 0
3909 | 4.2015 | 6.355 | 6.6956 | 4.7003 | 3.9961 | 2.0943 | 17.3511 | 16.9875 | 17.3511 | 1
3910 | 3.8786 | 4.4273 | 6.3823 | 4.9255 | 4.424 | 2.0404 | 15.2719 | 16.7253 | 16.7253 | 0
3911 | 5.8869 | 4.2143 | 6.9413 | 5.3958 | 5.5531 | 2.0155 | 17.5126 | 20.3968 | 20.3968 | 0
3912 | 2.3851 | 6.3259 | 6.6355 | 5.7239 | 4.0696 | 2.6123 | 17.0472 | 15.7025 | 17.0472 | 1
3913 | 4.524 | 4.4144 | 5.2926 | 6.3012 | 4.3199 | 2.4835 | 17.7232 | 16.62 | 17.7232 | 1
3914 | 3.9514 | 5.3313 | 5.1836 | 5.2888 | 4.202 | 2.2201 | 16.7915 | 15.557 | 16.7915 | 1
3915 | 5.2566 | 6.1872 | 6.2019 | 4.928 | 4.5451 | 2.1646 | 18.5364 | 18.1681 | 18.5364 | 1
3916 | 5.6974 | 4.7337 | 4.4826 | 4.4633 | 3.9088 | 2.5002 | 17.3946 | 16.5889 | 17.3946 | 1
3917 | 4.2274 | 5.6284 | 7.3088 | 4.7123 | 4.6425 | 2.0683 | 16.6364 | 18.2471 | 18.2471 | 0
3918 | 3.4515 | 6.5179 | 3.5385 | 4.3225 | 5.2809 | 1.86 | 16.1519 | 14.1309 | 16.1519 | 1
3919 | 4.5342 | 5.0179 | 4.4825 | 5.5511 | 3.9514 | 2.118 | 17.2212 | 15.0861 | 17.2212 | 1
3920 | 3.6844 | 7.4823 | 5.9665 | 5.5129 | 5.9916 | 2.5037 | 19.1833 | 18.1461 | 19.1833 | 1
3921 | 3.8566 | 3.6542 | 5.3447 | 5.3258 | 4.4083 | 1.4155 | 14.252 | 15.0251 | 15.0251 | 0
3922 | 2.324 | 3.3893 | 5.6378 | 5.7851 | 4.3975 | 1.7157 | 13.2141 | 14.075 | 14.075 | 0
3923 | 2.6031 | 6.0402 | 6.5567 | 4.924 | 3.9865 | 2.7789 | 16.3463 | 15.9252 | 16.3463 | 1
3924 | 3.0825 | 4.114 | 4.5152 | 4.5008 | 3.5287 | 1.8824 | 13.5797 | 13.0088 | 13.5797 | 1
3925 | 2.6151 | 6.0095 | 7.1029 | 4.7277 | 3.4249 | 1.8718 | 15.2242 | 15.0147 | 15.2242 | 1
3926 | 3.2621 | 3.4942 | 4.8641 | 4.3652 | 4.5245 | 1.7337 | 12.8552 | 14.3843 | 14.3843 | 0
3927 | 5.2698 | 5.7251 | 5.3047 | 5.7985 | 4.245 | 1.6976 | 18.4911 | 16.5171 | 18.4911 | 1
3928 | 3.4565 | 3.7918 | 5.289 | 4.9 | 3.3769 | 2.2157 | 14.3639 | 14.3381 | 14.3639 | 1
3929 | 4.4656 | 6.185 | 6.1293 | 6.7942 | 5.8317 | 2.439 | 19.8838 | 18.8657 | 19.8838 | 1
3930 | 3.7967 | 7.2057 | 4.561 | 5.0838 | 4.449 | 2.0555 | 18.1418 | 14.8623 | 18.1418 | 1
3931 | 4.1014 | 6.3699 | 6.6544 | 4.4085 | 3.9867 | 2.6914 | 17.5712 | 17.4339 | 17.5712 | 1
3932 | 3.7699 | 4.7428 | 5.3999 | 6.2257 | 4.4314 | 2.1734 | 16.9118 | 15.7746 | 16.9118 | 1
3933 | 4.9784 | 5.8596 | 4.8792 | 5.2198 | 4.6152 | 2.1963 | 18.2541 | 16.669 | 18.2541 | 1
3934 | 4.5052 | 4.4515 | 6.8844 | 4.6214 | 4.3869 | 2.0688 | 15.6469 | 17.8454 | 17.8454 | 0
3935 | 3.698 | 7.1198 | 6.9129 | 4.7803 | 3.6704 | 1.8618 | 17.4599 | 16.143 | 17.4599 | 1
3936 | 3.1095 | 5.5473 | 5.7558 | 6.2561 | 3.3872 | 2.128 | 17.0409 | 14.3804 | 17.0409 | 1
3937 | 3.7367 | 6.7201 | 5.6565 | 4.3728 | 3.8884 | 1.6376 | 16.4672 | 14.9192 | 16.4672 | 1
3938 | 2.5776 | 7.9398 | 7.4577 | 6.9411 | 4.3075 | 1.4996 | 18.958 | 15.8424 | 18.958 | 1
3939 | 4.9337 | 5.605 | 5.4598 | 5.3586 | 3.321 | 1.6463 | 17.5435 | 15.3608 | 17.5435 | 1
3940 | 2.9938 | 5.904 | 5.2539 | 4.6166 | 3.2831 | 2.22 | 15.7343 | 13.7508 | 15.7343 | 1
3941 | 4.5955 | 4.813 | 3.424 | 6.4751 | 4.017 | 1.5068 | 17.3905 | 13.5433 | 17.3905 | 1
3942 | 4.4293 | 6.1605 | 5.1568 | 4.3176 | 4.1064 | 1.7786 | 16.6861 | 15.4712 | 16.6861 | 1
3943 | 3.9378 | 4.3645 | 6.347 | 4.818 | 3.96 | 1.9223 | 15.0426 | 16.1672 | 16.1672 | 0
3944 | 4.4566 | 4.6012 | 6.5727 | 5.2695 | 4.6725 | 2.1233 | 16.4506 | 17.8251 | 17.8251 | 0
3945 | 3.3209 | 4.5096 | 6.8782 | 6.3613 | 4.4146 | 2.2338 | 16.4257 | 16.8475 | 16.8475 | 0
3946 | 3.6862 | 5.8452 | 3.5992 | 5.4482 | 3.8359 | 1.951 | 16.9306 | 13.0722 | 16.9306 | 1
3947 | 3.2711 | 5.1173 | 4.9406 | 5.4604 | 3.6722 | 1.974 | 15.8227 | 13.8579 | 15.8227 | 1
3948 | 3.1092 | 5.8565 | 4.1593 | 5.8342 | 4.3877 | 1.4933 | 16.2932 | 13.1495 | 16.2932 | 1
3949 | 3.1566 | 7.8227 | 3.505 | 5.8002 | 4.3372 | 1.9413 | 18.7209 | 12.9401 | 18.7209 | 1
3950 | 4.4094 | 5.5632 | 6.7661 | 4.8621 | 4.6508 | 1.6507 | 16.4854 | 17.477 | 17.477 | 0
3951 | 2.9031 | 4.479 | 5.9312 | 4.9761 | 4.2063 | 2.074 | 14.4321 | 15.1145 | 15.1145 | 0
3952 | 4.3301 | 5.5311 | 2.8557 | 5.6125 | 3.7201 | 2.02 | 17.4938 | 12.9259 | 17.4938 | 1
3953 | 5.2132 | 6.6348 | 7.353 | 4.8677 | 4.5394 | 1.2113 | 17.927 | 18.317 | 18.317 | 0
3954 | 4.134 | 7.3587 | 3.8912 | 4.8249 | 4.0621 | 2.2121 | 18.5297 | 14.2994 | 18.5297 | 1
3955 | 4.7361 | 4.4331 | 6.5618 | 5.4729 | 3.788 | 1.7859 | 16.4279 | 16.8718 | 16.8718 | 0
3956 | 5.2649 | 7.6225 | 4.8106 | 6.2096 | 3.3147 | 2.8942 | 21.9911 | 16.2843 | 21.9911 | 1
3957 | 3.9833 | 5.6675 | 5.9456 | 5.2573 | 3.9914 | 2.4756 | 17.3838 | 16.396 | 17.3838 | 1
3958 | 3.5303 | 5.158 | 4.2596 | 4.8925 | 4.2059 | 1.4675 | 15.0482 | 13.4632 | 15.0482 | 1
3959 | 4.5322 | 5.972 | 5.4637 | 4.3316 | 3.5406 | 2.3315 | 17.1673 | 15.868 | 17.1673 | 1
3960 | 5.3157 | 5.8099 | 6.773 | 4.8179 | 4.4664 | 2.2213 | 18.1648 | 18.7764 | 18.7764 | 0
3961 | 3.1365 | 5.5194 | 7.4521 | 4.4506 | 3.8861 | 1.9615 | 15.0679 | 16.4362 | 16.4362 | 0
3962 | 2.6087 | 5.3381 | 4.7533 | 6.3797 | 4.4234 | 1.8677 | 16.1942 | 13.6531 | 16.1942 | 1
3963 | 4.5237 | 7.2223 | 4.6708 | 5.7945 | 4.3435 | 2.4442 | 19.9846 | 15.9822 | 19.9846 | 1
3964 | 4.4543 | 7.4806 | 6.2959 | 4.5798 | 4.665 | 2.5004 | 19.0152 | 17.9157 | 19.0152 | 1
3965 | 4.0516 | 3.7353 | 5.7788 | 5.4412 | 4.5464 | 1.7097 | 14.9378 | 16.0865 | 16.0865 | 0
3966 | 3.5161 | 6.5773 | 5.0274 | 4.3345 | 3.479 | 2.4525 | 16.8804 | 14.475 | 16.8804 | 1
3967 | 4.7367 | 3.8579 | 4.5546 | 5.1041 | 3.6736 | 1.6634 | 15.3621 | 14.6283 | 15.3621 | 1
3968 | 3.7813 | 4.5853 | 6.5736 | 5.5285 | 4.6437 | 2.6789 | 16.574 | 17.6775 | 17.6775 | 0
3969 | 3.8382 | 5.3038 | 6.1337 | 4.5045 | 3.1807 | 2.0221 | 15.6686 | 15.1747 | 15.6686 | 1
3970 | 3.9345 | 6.0498 | 6.2436 | 5.6303 | 4.6563 | 2.4744 | 18.089 | 17.3087 | 18.089 | 1
3971 | 3.5435 | 4.6452 | 4.1614 | 6.1395 | 4.6749 | 2.372 | 16.7002 | 14.7517 | 16.7002 | 1
3972 | 4.1464 | 6.143 | 5.9277 | 5.7899 | 3.414 | 1.7434 | 17.8227 | 15.2315 | 17.8227 | 1
3973 | 3.3261 | 3.7394 | 4.4574 | 5.045 | 4.1249 | 2.1883 | 14.2989 | 14.0967 | 14.2989 | 1
3974 | 4.0847 | 5.0207 | 5.8952 | 4.7994 | 3.3089 | 2.3306 | 16.2353 | 15.6194 | 16.2353 | 1
3975 | 2.9557 | 7.2705 | 5.0003 | 6.503 | 3.915 | 1.7608 | 18.4901 | 13.6318 | 18.4901 | 1
3976 | 4.9682 | 4.3031 | 4.8873 | 4.7729 | 4.5613 | 1.9633 | 16.0075 | 16.3801 | 16.3801 | 0
3977 | 3.8942 | 5.038 | 6.0368 | 6.4376 | 5.2741 | 1.5755 | 16.9452 | 16.7806 | 16.9452 | 1
3978 | 4.1854 | 7.2217 | 3.9644 | 4.6776 | 4.8496 | 2.5798 | 18.6646 | 15.5793 | 18.6646 | 1
3979 | 5.0748 | 4.3034 | 4.7996 | 4.882 | 4.4407 | 2.2652 | 16.5253 | 16.5803 | 16.5803 | 0
3980 | 3.7688 | 3.8941 | 6.3074 | 6.3662 | 5.0416 | 1.7592 | 15.7883 | 16.8771 | 16.8771 | 0
3981 | 3.9457 | 7.2333 | 6.6341 | 4.4766 | 6.0695 | 1.2476 | 16.9032 | 17.897 | 17.897 | 0
3982 | 3.6824 | 3.4203 | 6.6264 | 5.7034 | 3.8036 | 1.9206 | 14.7268 | 16.033 | 16.033 | 0
3983 | 3.3876 | 4.3592 | 5.629 | 5.2765 | 4.1288 | 1.6558 | 14.6792 | 14.8012 | 14.8012 | 0
3984 | 4.5155 | 7.5973 | 7.1581 | 4.8214 | 3.5781 | 2.8019 | 19.7362 | 18.0536 | 19.7362 | 1
3985 | 3.9613 | 4.0878 | 7.0689 | 5.4886 | 3.5101 | 2.7016 | 16.2392 | 17.2419 | 17.2419 | 0
3986 | 2.7482 | 3.9719 | 3.5462 | 5.0181 | 3.9797 | 2.3263 | 14.0646 | 12.6004 | 14.0646 | 1
3987 | 4.7821 | 4.4716 | 4.8463 | 6.7274 | 3.6668 | 1.4914 | 17.4725 | 14.7866 | 17.4725 | 1
3988 | 4.3455 | 6.4462 | 4.6946 | 5.9586 | 5.0571 | 2.2844 | 19.0348 | 16.3817 | 19.0348 | 1
3989 | 4.966 | 4.209 | 6.0116 | 4.7246 | 4.9272 | 1.8789 | 15.7785 | 17.7837 | 17.7837 | 0
3990 | 4.3459 | 6.9807 | 5.6438 | 4.9568 | 3.2406 | 2.3192 | 18.6026 | 15.5495 | 18.6026 | 1
3991 | 3.6486 | 3.9746 | 3.6371 | 4.3406 | 4.5386 | 2.4179 | 14.3816 | 14.2421 | 14.3816 | 1
3992 | 2.3177 | 4.9645 | 5.2069 | 5.1032 | 3.7588 | 2.0916 | 14.477 | 13.375 | 14.477 | 1
3993 | 3.4234 | 4.7147 | 6.8963 | 5.4076 | 4.1416 | 1.6058 | 15.1514 | 16.0671 | 16.0671 | 0
3994 | 3.4381 | 8.0448 | 5.3109 | 5.4388 | 4.7478 | 1.7079 | 18.6296 | 15.2047 | 18.6296 | 1
3995 | 2.9391 | 4.8471 | 6.6988 | 5.8715 | 4.7566 | 1.6617 | 15.3193 | 16.0562 | 16.0562 | 0
3996 | 3.2792 | 4.6349 | 5.9916 | 5.4513 | 3.4617 | 2.079 | 15.4445 | 14.8115 | 15.4445 | 1
3997 | 3.8234 | 4.4518 | 6.0377 | 4.8348 | 4.3579 | 1.8396 | 14.9495 | 16.0585 | 16.0585 | 0
3998 | 3.7855 | 4.4035 | 6.7671 | 6.6068 | 5.5629 | 1.5641 | 16.3599 | 17.6796 | 17.6796 | 0
3999 | 5.2537 | 4.4469 | 3.894 | 4.2326 | 3.5682 | 1.6672 | 15.6003 | 14.383 | 15.6003 | 1
4000 | 2.9842 | 5.0691 | 5.9976 | 5.6489 | 3.4423 | 2.1003 | 15.8026 | 14.5244 | 15.8026 | 1
4001 | 2.9982 | 4.3005 | 6.4471 | 4.5163 | 4.5152 | 2.6344 | 14.4494 | 16.5949 | 16.5949 | 0
4002 | 4.4812 | 7.8813 | 6.8493 | 4.2204 | 3.2872 | 1.8667 | 18.4497 | 16.4844 | 18.4497 | 1
4003 | 3.76 | 5.2521 | 6.5792 | 6.2135 | 4.0498 | 1.2784 | 16.504 | 15.6674 | 16.504 | 1
4004 | 2.6743 | 6.0468 | 6.0109 | 7.3258 | 4.7184 | 1.5608 | 17.6077 | 14.9644 | 17.6077 | 1
4005 | 3.1649 | 6.2568 | 4.9706 | 5.7483 | 5.448 | 1.6818 | 16.8518 | 15.2653 | 16.8518 | 1
4006 | 5.1658 | 4.7785 | 7.606 | 4.8734 | 3.8586 | 1.9242 | 16.7419 | 18.5546 | 18.5546 | 0
4007 | 4.0647 | 4.6956 | 5.4339 | 5.9417 | 3.1272 | 1.8498 | 16.5518 | 14.4756 | 16.5518 | 1
4008 | 3.9156 | 3.942 | 3.7116 | 4.4833 | 3.8097 | 2.2889 | 14.6298 | 13.7258 | 14.6298 | 1
4009 | 4.726 | 5.2934 | 6.7852 | 4.5918 | 5.0466 | 2.0781 | 16.6892 | 18.6359 | 18.6359 | 0
4010 | 4.2953 | 6.1052 | 5.7728 | 6.3321 | 5.0449 | 1.8213 | 18.5539 | 16.9343 | 18.5539 | 1
4011 | 4.5633 | 6.5536 | 7.1241 | 7.3461 | 3.9505 | 2.0144 | 20.4773 | 17.6524 | 20.4773 | 1
4012 | 4.2976 | 5.7735 | 4.1282 | 4.2861 | 4.2386 | 2.1733 | 16.5305 | 14.8378 | 16.5305 | 1
4013 | 5.0587 | 4.5875 | 6.4141 | 4.5231 | 4.0472 | 1.9484 | 16.1178 | 17.4684 | 17.4684 | 0
4014 | 3.1014 | 4.3953 | 4.0561 | 5.732 | 4.5101 | 1.7649 | 14.9936 | 13.4325 | 14.9936 | 1
4015 | 3.6875 | 5.106 | 5.0507 | 5.6224 | 4.1938 | 1.888 | 16.3039 | 14.8201 | 16.3039 | 1
4016 | 4.272 | 5.7073 | 5.6515 | 5.8444 | 4.7469 | 1.8805 | 17.7043 | 16.5511 | 17.7043 | 1
4017 | 4.0538 | 5.5687 | 6.6799 | 4.4071 | 4.0662 | 2.1304 | 16.16 | 16.9303 | 16.9303 | 0
4018 | 3.7238 | 5.963 | 5.0852 | 5.9886 | 4.4376 | 1.8065 | 17.4819 | 15.0531 | 17.4819 | 1
4019 | 3.8314 | 4.5223 | 7.693 | 4.8452 | 3.1188 | 2.3433 | 15.5423 | 16.9866 | 16.9866 | 0
4020 | 3.2884 | 6.4589 | 6.3442 | 5.0387 | 4.0458 | 2.3934 | 17.1793 | 16.0718 | 17.1793 | 1
4021 | 4.9269 | 3.9199 | 6.7052 | 4.7517 | 4.4733 | 1.2135 | 14.8121 | 17.3189 | 17.3189 | 0
4022 | 3.1737 | 4.1592 | 4.2825 | 4.8894 | 4.9401 | 2.4137 | 14.636 | 14.8101 | 14.8101 | 0
4023 | 3.5317 | 5.2602 | 6.2841 | 5.9271 | 3.4123 | 1.5568 | 16.2757 | 14.7849 | 16.2757 | 1
4024 | 4.3285 | 4.3349 | 4.7415 | 4.7963 | 5.0438 | 1.9371 | 15.3968 | 16.0509 | 16.0509 | 0
4025 | 4.4032 | 5.1143 | 4.409 | 5.7798 | 5.4624 | 1.3933 | 16.6906 | 15.6678 | 16.6906 | 1
4026 | 2.7346 | 6.3169 | 5.2807 | 4.1866 | 4.9744 | 2.014 | 15.2521 | 15.0037 | 15.2521 | 1
4027 | 3.9678 | 5.2488 | 5.6885 | 5.1322 | 4.9139 | 1.9898 | 16.3385 | 16.56 | 16.56 | 0
4028 | 4.1496 | 6.8157 | 4.6504 | 4.3089 | 6.1111 | 1.8297 | 17.104 | 16.7408 | 17.104 | 1
4029 | 5.5063 | 4.2671 | 5.4066 | 4.883 | 3.524 | 1.9651 | 16.6214 | 16.4019 | 16.6214 | 1
4030 | 2.8139 | 5.5445 | 6.5716 | 5.9283 | 5.3221 | 2.3907 | 16.6775 | 17.0984 | 17.0984 | 0
4031 | 3.9667 | 8.3802 | 5.0756 | 5.8859 | 4.0774 | 2.2156 | 20.4484 | 15.3352 | 20.4484 | 1
4032 | 4.3064 | 5.4596 | 4.1748 | 5.9281 | 3.909 | 2.4637 | 18.1579 | 14.854 | 18.1579 | 1
4033 | 4.2473 | 5.4352 | 4.5857 | 5.575 | 4.0881 | 2.8111 | 18.0686 | 15.7323 | 18.0686 | 1
4034 | 4.8374 | 5.8314 | 5.7414 | 5.9013 | 3.3686 | 1.7216 | 18.2917 | 15.669 | 18.2917 | 1
4035 | 4.2342 | 5.5397 | 4.8607 | 4.6473 | 4.9888 | 2.1093 | 16.5305 | 16.193 | 16.5305 | 1
4036 | 4.3854 | 5.8741 | 5.7923 | 4.1927 | 4.1614 | 1.9514 | 16.4036 | 16.2905 | 16.4036 | 1
4037 | 4.3742 | 4.2142 | 5.1447 | 4.8144 | 5.1393 | 2.5089 | 15.9117 | 17.1671 | 17.1671 | 0
4038 | 3.8942 | 5.8703 | 4.1005 | 5.9136 | 4.5784 | 2.1435 | 17.8216 | 14.7166 | 17.8216 | 1
4039 | 3.407 | 6.0556 | 6.6141 | 5.6911 | 4.2267 | 2.4237 | 17.5775 | 16.6715 | 17.5775 | 1
4040 | 2.6339 | 4.1568 | 4.7777 | 6.8516 | 3.685 | 1.3654 | 15.0076 | 12.462 | 15.0076 | 1
4041 | 4.4239 | 6.5641 | 5.8487 | 5.7117 | 4.7826 | 1.9472 | 18.6469 | 17.0024 | 18.6469 | 1
4042 | 4.103 | 4.9445 | 6.7508 | 4.4083 | 5.4973 | 2.6664 | 16.1221 | 19.0174 | 19.0174 | 0
4043 | 3.8377 | 5.5303 | 5.3668 | 4.9385 | 3.6899 | 1.5106 | 15.8171 | 14.4049 | 15.8171 | 1
4044 | 4.5426 | 6.9136 | 7.1123 | 4.7399 | 4.9006 | 2.4945 | 18.6907 | 19.05 | 19.05 | 0
4045 | 4.8991 | 5.6347 | 5.434 | 4.7475 | 5.4992 | 1.2254 | 16.5067 | 17.0577 | 17.0577 | 0
4046 | 3.676 | 5.0949 | 4.5961 | 5.0876 | 4.5401 | 1.9417 | 15.8002 | 14.754 | 15.8002 | 1
4047 | 3.5522 | 6.737 | 6.0455 | 5.1936 | 3.5066 | 1.9254 | 17.4082 | 15.0297 | 17.4082 | 1
4048 | 3.9027 | 3.7372 | 4.6982 | 4.9851 | 4.7295 | 2.1973 | 14.8222 | 15.5277 | 15.5277 | 0
4049 | 5.5089 | 5.2851 | 5.2703 | 5.2606 | 3.8678 | 1.7503 | 17.8048 | 16.3973 | 17.8048 | 1
4050 | 3.0547 | 6.7039 | 4.5615 | 6.0205 | 5.9351 | 2.4778 | 18.2569 | 16.0291 | 18.2569 | 1
4051 | 3.4225 | 6.068 | 4.5794 | 6.3798 | 3.61 | 1.3854 | 17.2557 | 12.9973 | 17.2557 | 1
4052 | 3.6377 | 6.5133 | 6.4087 | 4.4018 | 4.0882 | 1.5081 | 16.0609 | 15.6427 | 16.0609 | 1
4053 | 4.806 | 4.2698 | 4.6759 | 4.2171 | 4.1773 | 2.2967 | 15.5895 | 15.9559 | 15.9559 | 0
4054 | 5.422 | 5.7199 | 4.8819 | 6.9249 | 4.0115 | 2.809 | 20.8758 | 17.1245 | 20.8758 | 1
4055 | 3.7439 | 6.0446 | 5.9377 | 6.4207 | 4.2393 | 1.3448 | 17.5539 | 15.2657 | 17.5539 | 1
4056 | 4.0367 | 3.8209 | 5.5753 | 5.9092 | 3.109 | 2.0319 | 15.7988 | 14.7529 | 15.7988 | 1
4057 | 4.9664 | 5.1136 | 7.6903 | 5.5991 | 3.8512 | 2.0036 | 17.6828 | 18.5116 | 18.5116 | 0
4058 | 3.7489 | 6.5903 | 6.5363 | 4.6176 | 4.2249 | 2.2923 | 17.249 | 16.8024 | 17.249 | 1
4059 | 4.54 | 4.3257 | 4.8628 | 4.5331 | 3.8164 | 2.1301 | 15.5289 | 15.3494 | 15.5289 | 1
4060 | 4.9546 | 5.5242 | 6.3295 | 4.2513 | 4.9972 | 2.4489 | 17.1791 | 18.7302 | 18.7302 | 0
4061 | 4.254 | 4.0783 | 4.2291 | 5.0275 | 4.3145 | 2.4625 | 15.8224 | 15.2601 | 15.8224 | 1
4062 | 2.5298 | 4.2431 | 6.0354 | 5.6699 | 3.9985 | 1.9799 | 14.4227 | 14.5436 | 14.5436 | 0
4063 | 3.1131 | 4.0973 | 5.5257 | 5.6253 | 5.4224 | 1.9817 | 14.8174 | 16.0429 | 16.0429 | 0
4064 | 3.7377 | 4.4198 | 6.0954 | 4.4918 | 3.7545 | 2.6764 | 15.3256 | 16.2639 | 16.2639 | 0
4065 | 3.2247 | 3.5047 | 5.7983 | 4.8818 | 5.5323 | 2.0606 | 13.6719 | 16.616 | 16.616 | 0
4066 | 5.3863 | 5.8221 | 5.8981 | 5.7161 | 3.9791 | 2.1274 | 19.052 | 17.3909 | 19.052 | 1
4067 | 4.2298 | 6.6102 | 3.6597 | 4.9985 | 4.8347 | 2.6219 | 18.4605 | 15.3462 | 18.4605 | 1
4068 | 2.647 | 4.173 | 7.1555 | 5.0389 | 3.2751 | 2.2905 | 14.1494 | 15.3681 | 15.3681 | 0
4069 | 4.3967 | 4.5299 | 5.5192 | 5.2222 | 3.6302 | 1.5381 | 15.6869 | 15.0842 | 15.6869 | 1
4070 | 3.7533 | 5.8272 | 5.396 | 4.9506 | 3.7939 | 1.9302 | 16.4613 | 14.8735 | 16.4613 | 1
4071 | 4.5259 | 4.3238 | 5.9995 | 6.1236 | 4.1947 | 1.3773 | 16.3506 | 16.0974 | 16.3506 | 1
4072 | 4.3305 | 4.465 | 5.8391 | 6.9288 | 4.4013 | 1.3648 | 17.0892 | 15.9357 | 17.0892 | 1
4073 | 2.6364 | 6.5395 | 5.5725 | 4.6648 | 4.7351 | 2.3198 | 16.1605 | 15.2638 | 16.1605 | 1
4074 | 3.0928 | 5.8371 | 6.4289 | 5.9536 | 4.5922 | 2.4896 | 17.373 | 16.6034 | 17.373 | 1
4075 | 4.0851 | 6.7304 | 5.7472 | 5.2035 | 3.5865 | 2.6704 | 18.6894 | 16.0892 | 18.6894 | 1
4076 | 4.9941 | 4.7365 | 4.8183 | 4.6845 | 4.2255 | 1.3462 | 15.7612 | 15.384 | 15.7612 | 1
4077 | 3.8574 | 4.2187 | 5.1191 | 4.2071 | 3.2824 | 1.1381 | 13.4212 | 13.3969 | 13.4212 | 1
4078 | 3.5299 | 4.4754 | 5.801 | 4.5843 | 4.2829 | 2.2147 | 14.8043 | 15.8285 | 15.8285 | 0
4079 | 3.5473 | 3.7946 | 5.9352 | 5.0731 | 4.081 | 1.8305 | 14.2455 | 15.394 | 15.394 | 0
4080 | 2.8533 | 3.9593 | 4.348 | 5.5841 | 4.8835 | 1.7943 | 14.191 | 13.879 | 14.191 | 1
4081 | 2.796 | 4.0938 | 6.8076 | 5.595 | 4.2582 | 2.0614 | 14.5462 | 15.9232 | 15.9232 | 0
4082 | 4.4128 | 4.5972 | 4.8308 | 5.2944 | 3.3315 | 2.4375 | 16.742 | 15.0126 | 16.742 | 1
4083 | 5.0417 | 5.1631 | 5.2641 | 5.4821 | 4.4732 | 1.642 | 17.3289 | 16.421 | 17.3289 | 1
4084 | 5.1428 | 7.0111 | 6.7013 | 4.9188 | 4.9905 | 1.9712 | 19.0439 | 18.8059 | 19.0439 | 1
4085 | 3.4568 | 6.3725 | 6.5945 | 5.0437 | 3.9553 | 1.7696 | 16.6425 | 15.7761 | 16.6425 | 1
4086 | 4.072 | 3.8178 | 4.8021 | 5.5572 | 5.0047 | 1.9281 | 15.3751 | 15.8069 | 15.8069 | 0
4087 | 4.3448 | 3.8395 | 5.4059 | 5.1247 | 3.5613 | 1.8363 | 15.1453 | 15.1483 | 15.1483 | 0
4088 | 3.8183 | 7.6025 | 6.502 | 4.3573 | 4.3293 | 2.3352 | 18.1133 | 16.9848 | 18.1133 | 1
4089 | 3.5163 | 4.7433 | 4.534 | 4.7231 | 5.3858 | 1.8431 | 14.8259 | 15.2793 | 15.2793 | 0
4090 | 3.8394 | 4.7561 | 6.3334 | 5.7245 | 4.0724 | 1.6833 | 16.0033 | 15.9285 | 16.0033 | 1
4091 | 3.3646 | 4.51 | 5.1243 | 5.1554 | 3.9613 | 2.4487 | 15.4787 | 14.8989 | 15.4787 | 1
4092 | 4.1453 | 5.1032 | 5.3534 | 7.4352 | 3.4605 | 1.8387 | 18.5224 | 14.798 | 18.5224 | 1
4093 | 3.1449 | 6.8179 | 5.3992 | 4.4791 | 5.4699 | 1.9656 | 16.4075 | 15.9795 | 16.4075 | 1
4094 | 3.4728 | 6.003 | 4.032 | 5.5362 | 3.4276 | 2.4253 | 17.4373 | 13.3577 | 17.4373 | 1
4095 | 3.7773 | 6.398 | 4.4256 | 5.2688 | 4.5563 | 2.1641 | 17.6081 | 14.9232 | 17.6081 | 1
4096 | 5.2309 | 3.9848 | 7.0716 | 5.1035 | 3.3878 | 2.0383 | 16.3576 | 17.7286 | 17.7286 | 0
4097 | 3.0688 | 3.785 | 6.4679 | 5.3479 | 4.7199 | 2.1642 | 14.3658 | 16.4207 | 16.4207 | 0
4098 | 2.9226 | 5.1465 | 5.351 | 6.3231 | 3.3509 | 2.4231 | 16.8154 | 14.0477 | 16.8154 | 1
4099 | 3.9862 | 5.0221 | 5.1066 | 5.483 | 4.4816 | 1.5334 | 16.0247 | 15.1078 | 16.0247 | 1
4100 | 4.0604 | 3.5737 | 4.6674 | 4.3002 | 5.6586 | 1.9884 | 13.9227 | 16.3749 | 16.3749 | 0
4101 | 3.9972 | 6.9598 | 6.7967 | 4.7113 | 4.6886 | 2.509 | 18.1773 | 17.9915 | 18.1773 | 1
4102 | 3.0577 | 5.6931 | 4.4629 | 4.9197 | 4.4196 | 1.6065 | 15.2771 | 13.5468 | 15.2771 | 1
4103 | 4.4503 | 4.4347 | 3.9414 | 6.0335 | 3.6591 | 1.74 | 16.6586 | 13.7908 | 16.6586 | 1
4104 | 2.8304 | 7.0502 | 5.0197 | 4.6719 | 4.9369 | 1.301 | 15.8536 | 14.088 | 15.8536 | 1
4105 | 4.2957 | 4.5085 | 6.5931 | 4.5079 | 5.1602 | 2.0559 | 15.3679 | 18.1048 | 18.1048 | 0
4106 | 4.0912 | 6.9754 | 4.0533 | 4.3251 | 5.0229 | 2.0777 | 17.4694 | 15.245 | 17.4694 | 1
4107 | 3.2459 | 5.0486 | 4.4047 | 4.3806 | 4.604 | 2.2204 | 14.8954 | 14.475 | 14.8954 | 1
4108 | 3.567 | 5.0115 | 7.197 | 4.4977 | 5.1027 | 2.1877 | 15.2639 | 18.0544 | 18.0544 | 0
4109 | 2.636 | 5.0423 | 3.1734 | 5.0207 | 4.3906 | 1.773 | 14.472 | 11.9731 | 14.472 | 1
4110 | 4.7154 | 5.6799 | 5.4109 | 4.4393 | 4.3965 | 1.5082 | 16.3428 | 16.031 | 16.3428 | 1
4111 | 4.5959 | 5.7092 | 6.1845 | 4.8953 | 4.0702 | 2.2231 | 17.4235 | 17.0737 | 17.4235 | 1
4112 | 4.8996 | 4.2709 | 4.8066 | 6.2632 | 4.1228 | 1.6933 | 17.1271 | 15.5223 | 17.1271 | 1
4113 | 3.1014 | 4.2075 | 5.5163 | 4.6376 | 4.4245 | 1.2295 | 13.176 | 14.2717 | 14.2717 | 0
4114 | 4.3997 | 3.9552 | 6.311 | 4.7823 | 4.4472 | 1.6409 | 14.7781 | 16.7988 | 16.7988 | 0
4115 | 4.1526 | 5.4846 | 6.3441 | 4.9846 | 3.5793 | 1.5567 | 16.1785 | 15.6327 | 16.1785 | 1
4116 | 4.1063 | 5.0478 | 5.7053 | 4.5362 | 5.0004 | 2.1187 | 15.8089 | 16.9307 | 16.9307 | 0
4117 | 4.2421 | 3.4405 | 5.188 | 4.7885 | 3.7864 | 1.474 | 13.9451 | 14.6904 | 14.6904 | 0
4118 | 3.4067 | 6.3784 | 5.9667 | 4.1212 | 3.8453 | 1.7572 | 15.6635 | 14.9759 | 15.6635 | 1
4119 | 3.9021 | 4.3117 | 4.9094 | 6.7388 | 4.3794 | 2.1509 | 17.1035 | 15.3417 | 17.1035 | 1
4120 | 4.7437 | 4.0881 | 3.9858 | 4.5174 | 4.3184 | 1.759 | 15.1083 | 14.8069 | 15.1083 | 1
4121 | 3.0746 | 6.2297 | 4.5558 | 4.5032 | 4.2389 | 2.0977 | 15.9053 | 13.967 | 15.9053 | 1
4122 | 5.575 | 4.949 | 6.8039 | 4.73 | 4.2255 | 1.4855 | 16.7396 | 18.0899 | 18.0899 | 0
4123 | 3.5455 | 5.258 | 7.1443 | 5.0987 | 3.1482 | 1.8223 | 15.7244 | 15.6602 | 15.7244 | 1
4124 | 2.6121 | 4.0847 | 5.0843 | 4.5893 | 3.0657 | 2.3016 | 13.5877 | 13.0636 | 13.5877 | 1
4125 | 4.5898 | 5.1218 | 4.5625 | 5.426 | 4.3337 | 2.0948 | 17.2325 | 15.5808 | 17.2325 | 1
4126 | 4.8213 | 7.4544 | 6.2978 | 4.7809 | 4.3693 | 2.4803 | 19.5369 | 17.9688 | 19.5369 | 1
4127 | 4.3967 | 4.0611 | 6.7312 | 6.4063 | 4.129 | 2.3567 | 17.2208 | 17.6136 | 17.6136 | 0
4128 | 4.0955 | 5.2685 | 5.8149 | 4.6816 | 3.6881 | 1.7191 | 15.7647 | 15.3175 | 15.7647 | 1
4129 | 3.6502 | 4.3877 | 6.5817 | 5.2596 | 3.4973 | 2.623 | 15.9205 | 16.3522 | 16.3522 | 0
4130 | 2.7914 | 6.1155 | 6.3133 | 5.9552 | 3.6991 | 2.3579 | 17.2199 | 15.1617 | 17.2199 | 1
4131 | 4.3194 | 7.7081 | 6.9468 | 4.0855 | 5.5981 | 1.7792 | 17.8922 | 18.6436 | 18.6436 | 0
4132 | 4.9012 | 5.6989 | 6.3575 | 4.8755 | 4.3428 | 1.2268 | 16.7025 | 16.8283 | 16.8283 | 0
4133 | 3.8599 | 4.4064 | 5.1854 | 5.6272 | 4.9114 | 2.0808 | 15.9743 | 16.0375 | 16.0375 | 0
4134 | 4.6584 | 3.9275 | 5.4889 | 5.2133 | 4.7967 | 2.4339 | 16.2332 | 17.378 | 17.378 | 0
4135 | 2.2048 | 4.9157 | 5.527 | 6.4281 | 4.216 | 1.6978 | 15.2462 | 13.6456 | 15.2462 | 1
4136 | 2.8391 | 5.8313 | 5.843 | 5.1941 | 5.6605 | 2.2507 | 16.1152 | 16.5933 | 16.5933 | 0
4137 | 2.7318 | 7.3378 | 4.8012 | 5.8411 | 3.9749 | 1.9081 | 17.8188 | 13.416 | 17.8188 | 1
4138 | 3.8616 | 3.9218 | 5.4891 | 5.9668 | 3.4962 | 2.0435 | 15.7937 | 14.8904 | 15.7937 | 1
4139 | 4.6571 | 6.388 | 6.3893 | 5.0775 | 4.7536 | 1.5907 | 17.7134 | 17.3907 | 17.7134 | 1
4140 | 5.082 | 4.5338 | 5.3655 | 5.1348 | 4.017 | 1.6835 | 16.4341 | 16.1479 | 16.4341 | 1
4141 | 3.857 | 5.8251 | 6.9946 | 5.5441 | 3.9399 | 2.7177 | 17.944 | 17.5092 | 17.944 | 1
4142 | 5.1762 | 6.1217 | 6.6856 | 5.7736 | 4.6114 | 1.9278 | 18.9993 | 18.401 | 18.9993 | 1
4143 | 4.6719 | 3.7968 | 6.7259 | 7.271 | 3.9484 | 2.1849 | 17.9246 | 17.531 | 17.9246 | 1
4144 | 4.6465 | 7.2361 | 5.3084 | 5.1537 | 4.5589 | 1.4965 | 18.5328 | 16.0103 | 18.5328 | 1
4145 | 3.371 | 6.6796 | 7.7114 | 5.8442 | 4.6512 | 1.9228 | 17.8176 | 17.6564 | 17.8176 | 1
4146 | 4.2952 | 7.373 | 6.038 | 5.8083 | 4.5942 | 1.6087 | 19.0851 | 16.5361 | 19.0851 | 1
4147 | 3.5437 | 4.9094 | 4.6952 | 5.4288 | 5.0688 | 2.3613 | 16.2432 | 15.669 | 16.2432 | 1
4148 | 5.3009 | 8.1249 | 6.7169 | 5.7467 | 4.0435 | 1.8246 | 20.997 | 17.8859 | 20.997 | 1
4149 | 4.123 | 6.567 | 6.1287 | 5.0395 | 4.1478 | 1.9589 | 17.6883 | 16.3583 | 17.6883 | 1
4150 | 3.8978 | 4.3725 | 7.2558 | 5.815 | 3.2489 | 2.2349 | 16.3201 | 16.6374 | 16.6374 | 0
4151 | 4.2082 | 3.5521 | 5.2571 | 4.1619 | 5.6382 | 2.1108 | 14.033 | 17.2143 | 17.2143 | 0
4152 | 3.6458 | 4.93 | 7.0147 | 4.6369 | 3.5326 | 2.2067 | 15.4193 | 16.3998 | 16.3998 | 0
4153 | 4.2033 | 3.4102 | 7.3101 | 4.458 | 5.6481 | 1.9299 | 14.0014 | 19.0914 | 19.0914 | 0
4154 | 3.3316 | 6.3251 | 4.081 | 4.6351 | 4.174 | 1.395 | 15.6868 | 12.9816 | 15.6868 | 1
4155 | 2.5679 | 4.6047 | 4.858 | 5.0404 | 4.6474 | 1.8667 | 14.0797 | 13.9401 | 14.0797 | 1
4156 | 3.802 | 5.0496 | 4.7518 | 6.752 | 5.3416 | 2.4939 | 18.0976 | 16.3893 | 18.0976 | 1
4157 | 3.8338 | 6.4753 | 7.4752 | 4.6643 | 4.6013 | 2.1002 | 17.0735 | 18.0104 | 18.0104 | 0
4158 | 3.8731 | 5.6632 | 3.7583 | 5.0667 | 3.9962 | 2.1468 | 16.7498 | 13.7744 | 16.7498 | 1
4159 | 3.4103 | 4.4381 | 6.2988 | 5.5568 | 4.0312 | 1.8711 | 15.2763 | 15.6114 | 15.6114 | 0
4160 | 3.4297 | 6.5564 | 6.502 | 6.1184 | 3.4937 | 1.6122 | 17.7167 | 15.0375 | 17.7167 | 1
4161 | 3.6216 | 5.3404 | 7.687 | 6.4985 | 3.4267 | 1.8401 | 17.3007 | 16.5755 | 17.3007 | 1
4162 | 3.6785 | 4.8644 | 6.0691 | 4.4806 | 5.0465 | 1.935 | 14.9586 | 16.7292 | 16.7292 | 0
4163 | 2.6255 | 6.5328 | 5.6313 | 5.0479 | 4.8729 | 1.5252 | 15.7314 | 14.6549 | 15.7314 | 1
4164 | 4.3892 | 4.9407 | 5.7523 | 6.2901 | 5.0225 | 2.0237 | 17.6438 | 17.1878 | 17.6438 | 1
4165 | 3.9901 | 3.9257 | 6.9298 | 5.1288 | 4.0088 | 2.0201 | 15.0647 | 16.9488 | 16.9488 | 0
4166 | 4.4705 | 6.887 | 6.4447 | 5.3823 | 5.6346 | 2.2077 | 18.9474 | 18.7575 | 18.9474 | 1
4167 | 4.2521 | 6.2118 | 5.6092 | 5.034 | 5.6048 | 2.1593 | 17.6573 | 17.6254 | 17.6573 | 1
4168 | 3.5647 | 5.8085 | 6.9909 | 4.414 | 5.139 | 1.9623 | 15.7495 | 17.6568 | 17.6568 | 0
4169 | 4.3558 | 4.6236 | 5.3378 | 4.9554 | 5.0455 | 1.9539 | 15.8888 | 16.6931 | 16.6931 | 0
4170 | 2.2916 | 5.309 | 5.5257 | 5.4719 | 4.8546 | 1.6999 | 14.7723 | 14.3717 | 14.7723 | 1
4171 | 4.4085 | 4.6447 | 5.3111 | 4.2582 | 4.4266 | 2.6318 | 15.9432 | 16.7779 | 16.7779 | 0
4172 | 4.869 | 4.4777 | 4.3089 | 6.272 | 3.2476 | 2.0607 | 17.6794 | 14.4862 | 17.6794 | 1
4173 | 4.2229 | 5.6283 | 5.5251 | 6.0638 | 3.5272 | 2.138 | 18.0531 | 15.4132 | 18.0531 | 1
4174 | 3.4255 | 4.1449 | 4.7616 | 4.7915 | 3.9425 | 2.058 | 14.4199 | 14.1876 | 14.4199 | 1
4175 | 5.4128 | 5.9903 | 5.9371 | 5.9375 | 4.3036 | 1.9182 | 19.2588 | 17.5717 | 19.2588 | 1
4176 | 3.5949 | 4.8141 | 5.974 | 7.0653 | 3.8831 | 1.9138 | 17.3881 | 15.3657 | 17.3881 | 1
4177 | 4.7113 | 6.7892 | 5.4826 | 6.0287 | 4.7332 | 1.5864 | 19.1157 | 16.5135 | 19.1157 | 1
4178 | 4.1969 | 5.2275 | 7.3774 | 5.6388 | 4.247 | 2.1896 | 17.2528 | 18.0108 | 18.0108 | 0
4179 | 4.8059 | 4.0067 | 7.1061 | 5.5157 | 3.9401 | 2.2975 | 16.6258 | 18.1496 | 18.1496 | 0
4180 | 5.2235 | 7.8171 | 4.9808 | 4.7715 | 4.5217 | 2.3521 | 20.1643 | 17.0782 | 20.1643 | 1
4181 | 2.8667 | 5.3332 | 5.1751 | 5.8054 | 5.0547 | 2.2163 | 16.2216 | 15.3128 | 16.2216 | 1
4182 | 4.7032 | 5.3117 | 3.5455 | 5.9004 | 5.0824 | 2.0455 | 17.9609 | 15.3766 | 17.9609 | 1
4183 | 4.7701 | 4.9383 | 3.5022 | 4.4139 | 4.2405 | 1.766 | 15.8882 | 14.2788 | 15.8882 | 1
4184 | 4.0914 | 8.0236 | 4.9892 | 5.6045 | 3.5977 | 1.971 | 19.6904 | 14.6493 | 19.6904 | 1
4185 | 3.8139 | 6.0936 | 4.0089 | 5.2108 | 4.332 | 2.4354 | 17.5536 | 14.5902 | 17.5536 | 1
4186 | 2.6104 | 7.0176 | 6.3579 | 4.4389 | 4.556 | 2.4182 | 16.4851 | 15.9425 | 16.4851 | 1
4187 | 4.5421 | 4.8631 | 4.7081 | 6.1455 | 3.2836 | 1.7382 | 17.289 | 14.272 | 17.289 | 1
4188 | 4.2571 | 3.2934 | 7.1752 | 4.2799 | 4.6509 | 2.0373 | 13.8677 | 18.1205 | 18.1205 | 0
4189 | 5.1772 | 7.2539 | 3.4477 | 4.4144 | 4.3795 | 1.3934 | 18.2389 | 14.3979 | 18.2389 | 1
4190 | 4.1166 | 3.6425 | 3.771 | 4.9507 | 3.9429 | 1.8102 | 14.52 | 13.6407 | 14.52 | 1
4191 | 5.1986 | 5.0561 | 3.2753 | 4.7682 | 3.8262 | 2.2124 | 17.2354 | 14.5125 | 17.2354 | 1
4192 | 2.4065 | 4.1941 | 6.6979 | 4.9972 | 5.0147 | 2.1838 | 13.7817 | 16.303 | 16.303 | 0
4193 | 3.5655 | 5.1506 | 5.4498 | 5.3951 | 3.8491 | 2.2089 | 16.3201 | 15.0732 | 16.3201 | 1
4194 | 3.8727 | 5.4987 | 6.4093 | 4.8322 | 4.1789 | 2.1416 | 16.3452 | 16.6025 | 16.6025 | 0
4195 | 3.7294 | 4.4724 | 5.8524 | 5.6656 | 4.1997 | 1.6901 | 15.5575 | 15.4717 | 15.5575 | 1
4196 | 4.6667 | 5.0463 | 5.3233 | 5.9501 | 4.5272 | 2.1468 | 17.81 | 16.6641 | 17.81 | 1
4197 | 3.5085 | 6.0793 | 4.9368 | 5.4453 | 4.9211 | 1.9409 | 16.9739 | 15.3073 | 16.9739 | 1
4198 | 3.1393 | 4.8803 | 5.8286 | 4.7203 | 4.0274 | 1.6557 | 14.3955 | 14.6509 | 14.6509 | 0
4199 | 5.2842 | 4.9376 | 3.9932 | 4.9313 | 4.0653 | 2.5044 | 17.6575 | 15.8472 | 17.6575 | 1
4200 | 4.6993 | 3.7281 | 6.0748 | 5.7619 | 4.4889 | 1.3779 | 15.5671 | 16.6408 | 16.6408 | 0
4201 | 3.8188 | 5.169 | 5.0856 | 5.8709 | 4.0315 | 1.8187 | 16.6774 | 14.7546 | 16.6774 | 1
4202 | 4.1804 | 5.3728 | 7.4921 | 6.9543 | 3.3197 | 2.0073 | 18.5147 | 16.9995 | 18.5147 | 1
4203 | 4.1793 | 4.1236 | 3.906 | 5.0738 | 3.85 | 2.099 | 15.4757 | 14.0343 | 15.4757 | 1
4204 | 4.1853 | 5.4963 | 5.6061 | 6.232 | 4.0201 | 2.1563 | 18.0698 | 15.9678 | 18.0698 | 1
4205 | 3.6468 | 6.9684 | 5.6123 | 4.5316 | 3.9427 | 1.6571 | 16.8038 | 14.8589 | 16.8038 | 1
4206 | 4.6045 | 5.0078 | 7.4113 | 4.8445 | 3.1244 | 2.1852 | 16.6419 | 17.3253 | 17.3253 | 0
4207 | 3.9404 | 5.4832 | 6.3197 | 5.6944 | 4.9232 | 1.8516 | 16.9696 | 17.0349 | 17.0349 | 0
4208 | 4.6026 | 4.5806 | 6.4782 | 5.1092 | 3.0644 | 1.2887 | 15.5811 | 15.4339 | 15.5811 | 1
4209 | 3.5058 | 3.8765 | 4.0274 | 4.7978 | 4.3983 | 2.6623 | 14.8424 | 14.5938 | 14.8424 | 1
4210 | 4.4636 | 4.4719 | 5.9354 | 4.7388 | 4.563 | 1.8986 | 15.5729 | 16.8605 | 16.8605 | 0
4211 | 4.835 | 6.5618 | 4.0926 | 4.575 | 4.3243 | 1.3467 | 17.3186 | 14.5986 | 17.3186 | 1
4212 | 4.0313 | 6.0308 | 5.3853 | 5.5547 | 3.0824 | 2.1457 | 17.7625 | 14.6448 | 17.7625 | 1
4213 | 2.1899 | 3.7019 | 4.0203 | 6.5312 | 3.5138 | 2.351 | 14.7741 | 12.075 | 14.7741 | 1
4214 | 3.8203 | 6.0497 | 5.6344 | 6.2926 | 5.873 | 2.2937 | 18.4564 | 17.6214 | 18.4564 | 1
4215 | 4.2845 | 4.653 | 5.4989 | 6.017 | 4.6664 | 1.8387 | 16.7932 | 16.2884 | 16.7932 | 1
4216 | 5.1992 | 3.8273 | 3.9257 | 5.7431 | 4.7464 | 2.6812 | 17.4508 | 16.5525 | 17.4508 | 1
4217 | 3.7449 | 5.8895 | 6.3324 | 5.0972 | 3.5727 | 2.3296 | 17.0612 | 15.9797 | 17.0612 | 1
4218 | 2.8347 | 3.8671 | 6.0505 | 4.3427 | 4.5548 | 2.368 | 13.4125 | 15.8081 | 15.8081 | 0
4219 | 2.4886 | 6.5425 | 5.0809 | 5.3434 | 4.4884 | 1.841 | 16.2155 | 13.8988 | 16.2155 | 1
4220 | 4.3884 | 4.7371 | 4.6426 | 6.0084 | 3.9905 | 2.3668 | 17.5008 | 15.3883 | 17.5008 | 1
4221 | 2.5702 | 5.2563 | 5.272 | 5.3425 | 3.3708 | 1.5583 | 14.7274 | 12.7714 | 14.7274 | 1
4222 | 2.7907 | 4.7184 | 6.2439 | 5.8116 | 5.4721 | 2.1386 | 15.4593 | 16.6453 | 16.6453 | 0
4223 | 4.5112 | 4.4248 | 5.3439 | 4.9711 | 3.2561 | 2.0017 | 15.9088 | 15.113 | 15.9088 | 1
4224 | 4.5736 | 6.7997 | 5.0875 | 6.0637 | 5.8761 | 2.668 | 20.105 | 18.2053 | 20.105 | 1
4225 | 2.578 | 4.1386 | 3.3035 | 6.1346 | 4.9126 | 1.9424 | 14.7937 | 12.7365 | 14.7937 | 1
4226 | 4.17 | 5.4804 | 5.7777 | 5.3394 | 3.2796 | 1.932 | 16.9219 | 15.1593 | 16.9219 | 1
4227 | 2.9808 | 5.9662 | 6.4809 | 4.1922 | 4.3717 | 2.3369 | 15.4761 | 16.1703 | 16.1703 | 0
4228 | 3.9297 | 3.9106 | 7.1463 | 5.3459 | 4.1756 | 1.6149 | 14.8011 | 16.8665 | 16.8665 | 0
4229 | 2.6288 | 3.9969 | 6.8106 | 6.0532 | 4.5534 | 1.5295 | 14.2085 | 15.5223 | 15.5223 | 0
4230 | 3.2082 | 5.9529 | 5.5453 | 4.8955 | 4.0544 | 1.5327 | 15.5892 | 14.3406 | 15.5892 | 1
4231 | 4.2398 | 5.3047 | 5.6392 | 5.4651 | 3.8126 | 2.1236 | 17.1332 | 15.8152 | 17.1332 | 1
4232 | 3.407 | 4.127 | 5.947 | 5.1739 | 3.6555 | 2.5597 | 15.2676 | 15.5692 | 15.5692 | 0
4233 | 3.7939 | 3.5084 | 6.3816 | 6.1161 | 4.8427 | 2.3596 | 15.7779 | 17.3778 | 17.3778 | 0
4234 | 3.1635 | 5.3297 | 6.5262 | 4.3941 | 4.3083 | 2.1235 | 15.0108 | 16.1215 | 16.1215 | 0
4235 | 4.0947 | 6.0593 | 5.459 | 5.048 | 5.7477 | 1.4625 | 16.6646 | 16.764 | 16.764 | 0
4236 | 4.6397 | 4.5107 | 5.1096 | 6.1261 | 3.118 | 2.0283 | 17.3047 | 14.8956 | 17.3047 | 1
4237 | 3.1842 | 5.4246 | 5.1092 | 5.2294 | 4.8684 | 1.9573 | 15.7956 | 15.1192 | 15.7956 | 1
4238 | 4.1725 | 4.932 | 2.8603 | 4.873 | 4.5051 | 1.3136 | 15.2912 | 12.8515 | 15.2912 | 1
4239 | 4.3383 | 4.9878 | 6.1247 | 6.4342 | 5.1739 | 1.3495 | 17.1097 | 16.9863 | 17.1097 | 1
4240 | 3.2007 | 5.546 | 3.9884 | 5.0385 | 4.9072 | 2.3109 | 16.0961 | 14.4073 | 16.0961 | 1
4241 | 4.6609 | 6.5957 | 6.3746 | 5.7408 | 3.6158 | 1.8044 | 18.8018 | 16.4556 | 18.8018 | 1
4242 | 3.9494 | 3.9129 | 6.0504 | 5.4839 | 3.7556 | 2.2771 | 15.6232 | 16.0325 | 16.0325 | 0
4243 | 4.3193 | 5.6512 | 6.8853 | 4.2851 | 4.4098 | 2.042 | 16.2975 | 17.6564 | 17.6564 | 0
4244 | 3.4833 | 5.7097 | 6.2659 | 5.3951 | 3.47 | 2.0216 | 16.6097 | 15.2408 | 16.6097 | 1
4245 | 3.5359 | 5.662 | 5.4601 | 4.9007 | 4.183 | 1.7295 | 15.8281 | 14.9085 | 15.8281 | 1
4246 | 4.652 | 4.6177 | 5.9705 | 5.8999 | 4.1647 | 1.8781 | 17.0476 | 16.6653 | 17.0476 | 1
4247 | 3.7224 | 4.6639 | 4.593 | 6.3413 | 4.7065 | 1.5324 | 16.26 | 14.5542 | 16.26 | 1
4248 | 3.2518 | 4.5679 | 6.4904 | 5.5739 | 4.5024 | 1.6537 | 15.0473 | 15.8983 | 15.8983 | 0
4249 | 4.2743 | 3.7106 | 6.1819 | 6.3809 | 4.9119 | 1.2194 | 15.5853 | 16.5875 | 16.5875 | 0
4250 | 5.4098 | 4.9234 | 5.9829 | 4.5858 | 3.6679 | 2.1275 | 17.0464 | 17.188 | 17.188 | 0
4251 | 2.5761 | 4.0733 | 4.6204 | 4.0983 | 5.0343 | 1.7844 | 12.5321 | 14.0152 | 14.0152 | 0
4252 | 3.9044 | 6.9842 | 5.6999 | 5.6046 | 3.9854 | 2.0337 | 18.5268 | 15.6234 | 18.5268 | 1
4253 | 4.1545 | 7.0691 | 7.0188 | 5.1564 | 4.063 | 2.12 | 18.5001 | 17.3564 | 18.5001 | 1
4254 | 3.9119 | 4.6663 | 4.6392 | 4.0745 | 4.295 | 1.9062 | 14.5589 | 14.7522 | 14.7522 | 0
4255 | 4.6886 | 4.6903 | 4.8329 | 4.3317 | 5.4677 | 2.1381 | 15.8487 | 17.1272 | 17.1272 | 0
4256 | 3.3266 | 3.3665 | 6.0103 | 4.5199 | 4.6161 | 1.8906 | 13.1036 | 15.8436 | 15.8436 | 0
4257 | 2.4623 | 3.2663 | 5.1262 | 4.2998 | 3.216 | 1.5413 | 11.5697 | 12.3458 | 12.3458 | 0
4258 | 4.838 | 5.5506 | 7.4203 | 4.5699 | 4.1332 | 1.8963 | 16.8547 | 18.2877 | 18.2877 | 0
4259 | 4.2728 | 4.8455 | 6.2381 | 4.493 | 4.5049 | 2.7421 | 16.3534 | 17.758 | 17.758 | 0
4260 | 3.5171 | 4.5712 | 4.7763 | 5.658 | 3.8719 | 2.11 | 15.8562 | 14.2753 | 15.8562 | 1
4261 | 5.5739 | 6.6663 | 5.4838 | 5.6124 | 3.7338 | 2.1867 | 20.0392 | 16.9782 | 20.0392 | 1
4262 | 3.7298 | 4.3376 | 5.4361 | 6.8379 | 4.049 | 2.1185 | 17.0239 | 15.3333 | 17.0239 | 1
4263 | 5.2495 | 4.6145 | 7.3847 | 4.7638 | 5.1384 | 1.3065 | 15.9343 | 19.0791 | 19.0791 | 0
4264 | 2.9356 | 5.9435 | 7.1216 | 6.2731 | 3.5418 | 2.1071 | 17.2594 | 15.7061 | 17.2594 | 1
4265 | 4.0673 | 6.5315 | 5.118 | 5.4475 | 4.447 | 2.7 | 18.7463 | 16.3323 | 18.7463 | 1
4266 | 3.8402 | 4.8611 | 7.0846 | 5.3951 | 4.3341 | 2.1637 | 16.2602 | 17.4226 | 17.4226 | 0
4267 | 4.0782 | 5.0402 | 6.8669 | 5.4008 | 3.3612 | 2.5952 | 17.1144 | 16.9015 | 17.1144 | 1
4268 | 4.1038 | 4.6966 | 5.4954 | 4.6739 | 3.7253 | 2.8487 | 16.3229 | 16.1732 | 16.3229 | 1
4269 | 3.8649 | 5.0163 | 6.2 | 5.2235 | 3.5198 | 1.5904 | 15.6951 | 15.1751 | 15.6951 | 1
4270 | 4.2167 | 4.646 | 4.7924 | 6.8595 | 4.1081 | 1.2091 | 16.9313 | 14.3262 | 16.9313 | 1
4271 | 5.2745 | 4.2004 | 5.2765 | 4.8872 | 3.5905 | 1.6083 | 15.9703 | 15.7497 | 15.9703 | 1
4272 | 3.7923 | 6.6283 | 4.1219 | 5.4169 | 4.6575 | 1.7718 | 17.6092 | 14.3436 | 17.6092 | 1
4273 | 4.583 | 5.8783 | 5.8936 | 5.0705 | 4.5678 | 2.2878 | 17.8196 | 17.3322 | 17.8196 | 1
4274 | 4.7195 | 6.2106 | 5.0679 | 5.4971 | 3.3432 | 1.7185 | 18.1457 | 14.8491 | 18.1457 | 1
4275 | 4.7304 | 6.7649 | 4.2169 | 4.8712 | 3.6714 | 1.9007 | 18.2672 | 14.5193 | 18.2672 | 1
4276 | 4.4644 | 5.8113 | 5.5672 | 6.0208 | 5.5272 | 2.2883 | 18.5848 | 17.8472 | 18.5848 | 1
4277 | 3.4157 | 6.1527 | 5.816 | 5.3677 | 4.2186 | 1.5923 | 16.5284 | 15.0426 | 16.5284 | 1
4278 | 4.7015 | 4.1781 | 6.5926 | 5.0753 | 4.7059 | 1.9794 | 15.9342 | 17.9793 | 17.9793 | 0
4279 | 4.3577 | 4.8059 | 5.3383 | 4.4088 | 4.6315 | 2.0015 | 15.5739 | 16.329 | 16.329 | 0
4280 | 4.0182 | 5.3998 | 6.3161 | 6.006 | 4.3836 | 2.8321 | 18.2561 | 17.5499 | 18.2561 | 1
4281 | 2.9386 | 6.6409 | 6.3113 | 4.7717 | 5.1849 | 1.4861 | 15.8373 | 15.9209 | 15.9209 | 0
4282 | 3.4634 | 6.4451 | 7.2267 | 5.4731 | 3.9778 | 1.5737 | 16.9553 | 16.2416 | 16.9553 | 1
4283 | 3.3366 | 4.3298 | 6.3954 | 4.7894 | 3.207 | 1.7646 | 14.2203 | 14.7035 | 14.7035 | 0
4284 | 2.8883 | 4.7976 | 5.2905 | 5.5934 | 4.3927 | 1.5932 | 14.8726 | 14.1648 | 14.8726 | 1
4285 | 5.4763 | 6.1941 | 5.6649 | 4.6305 | 3.8101 | 1.622 | 17.923 | 16.5734 | 17.923 | 1
4286 | 2.7175 | 4.4716 | 7.1011 | 6.8001 | 5.1848 | 1.7435 | 15.7326 | 16.7469 | 16.7469 | 0
4287 | 3.889 | 6.3868 | 4.9531 | 6.9978 | 6.0787 | 1.8118 | 19.0854 | 16.7326 | 19.0854 | 1
4288 | 5.0592 | 6.5567 | 4.2161 | 5.8979 | 5.1639 | 1.5347 | 19.0485 | 15.9739 | 19.0485 | 1
4289 | 3.3272 | 6.2586 | 6.752 | 4.7899 | 5.03 | 1.7054 | 16.0811 | 16.8146 | 16.8146 | 0
4290 | 5.1721 | 4.8556 | 5.14 | 4.3824 | 4.7578 | 1.9555 | 16.3656 | 17.0255 | 17.0255 | 0
4291 | 5.3682 | 5.5418 | 4.1003 | 6.549 | 4.5202 | 2.5422 | 20.0012 | 16.5309 | 20.0012 | 1
4292 | 4.2316 | 5.2601 | 6.18 | 4.2677 | 4.1571 | 1.6847 | 15.4441 | 16.2534 | 16.2534 | 0
4293 | 3.7434 | 3.413 | 6.3771 | 5.472 | 5.1836 | 1.7645 | 14.3929 | 17.0686 | 17.0686 | 0
4294 | 4.1035 | 5.5836 | 7.7022 | 5.871 | 5.6722 | 1.7982 | 17.3562 | 19.2761 | 19.2761 | 0
4295 | 4.0543 | 7.039 | 7.315 | 4.7329 | 5.0736 | 2.5066 | 18.3329 | 18.9496 | 18.9496 | 0
4296 | 5.2985 | 3.9862 | 6.0619 | 6.155 | 3.8328 | 2.3987 | 17.8385 | 17.5919 | 17.8385 | 1
4297 | 4.1622 | 5.4564 | 5.1848 | 6.2143 | 5.47 | 1.3559 | 17.1887 | 16.1727 | 17.1887 | 1
4298 | 3.0937 | 5.0565 | 5.2944 | 4.182 | 4.1421 | 2.2998 | 14.6321 | 14.83 | 14.83 | 0
4299 | 4.7197 | 6.8636 | 6.186 | 5.6498 | 4.1734 | 1.5496 | 18.7827 | 16.6288 | 18.7827 | 1
4300 | 3.4546 | 6.6126 | 6.596 | 5.4824 | 4.1163 | 2.3185 | 17.8681 | 16.4854 | 17.8681 | 1
4301 | 5.0326 | 5.1061 | 3.505 | 5.0026 | 4.3762 | 1.8935 | 17.0349 | 14.8074 | 17.0349 | 1
4302 | 4.9333 | 4.9249 | 5.4032 | 4.6393 | 4.1139 | 1.9536 | 16.4512 | 16.404 | 16.4512 | 1
4303 | 3.2662 | 4.7573 | 4.4071 | 5.27 | 4.989 | 2.0872 | 15.3808 | 14.7496 | 15.3808 | 1
4304 | 4.0605 | 4.374 | 4.208 | 4.55 | 3.3655 | 1.3732 | 14.3577 | 13.0072 | 14.3577 | 1
4305 | 4.7484 | 5.2153 | 2.63 | 4.5337 | 5.1511 | 2.1405 | 16.6378 | 14.67 | 16.6378 | 1
4306 | 4.3605 | 5.3645 | 3.4987 | 6.1404 | 3.8927 | 2.0142 | 17.8796 | 13.7661 | 17.8796 | 1
4307 | 4.119 | 6.3174 | 7.3874 | 6.219 | 5.7638 | 2.4639 | 19.1193 | 19.7341 | 19.7341 | 0
4308 | 4.8371 | 4.6534 | 4.7459 | 4.3512 | 3.8449 | 2.2716 | 16.1133 | 15.6994 | 16.1133 | 1
4309 | 4.6769 | 6.49 | 6.0634 | 5.9971 | 4.3921 | 1.5575 | 18.7214 | 16.6898 | 18.7214 | 1
4310 | 3.6946 | 4.9339 | 6.1391 | 4.4552 | 3.444 | 2.1349 | 15.2186 | 15.4126 | 15.4126 | 0
4311 | 3.7148 | 4.1454 | 5.7906 | 5.152 | 5.1491 | 1.8948 | 14.9069 | 16.5492 | 16.5492 | 0
4312 | 3.7301 | 4.953 | 5.8362 | 5.1057 | 5.1079 | 2.0405 | 15.8293 | 16.7148 | 16.7148 | 0
4313 | 4.8523 | 3.4378 | 5.9246 | 4.7236 | 4.8673 | 1.9006 | 14.9143 | 17.5448 | 17.5448 | 0
4314 | 3.2123 | 4.0291 | 5.0724 | 6.1666 | 4.3653 | 1.9938 | 15.4018 | 14.6438 | 15.4018 | 1
4315 | 3.0907 | 5.7299 | 7.5768 | 5.0623 | 3.721 | 1.4798 | 15.3627 | 15.8684 | 15.8684 | 0
4316 | 3.5225 | 4.1237 | 5.1437 | 5.873 | 3.5432 | 1.7502 | 15.2693 | 13.9596 | 15.2693 | 1
4317 | 3.2311 | 4.4158 | 3.955 | 4.6289 | 4.7399 | 2.0905 | 14.3662 | 14.0165 | 14.3662 | 1
4318 | 5.1124 | 7.3015 | 6.3896 | 5.0636 | 3.6478 | 2.2342 | 19.7117 | 17.3841 | 19.7117 | 1
4319 | 3.8973 | 5.5252 | 4.4252 | 4.7682 | 3.4976 | 1.4142 | 15.6048 | 13.2342 | 15.6048 | 1
4320 | 3.482 | 4.9817 | 4.153 | 5.4954 | 6.0666 | 2.2579 | 16.217 | 15.9596 | 16.217 | 1
4321 | 2.6651 | 4.6803 | 4.4432 | 5.1957 | 5.0724 | 1.4867 | 14.0278 | 13.6674 | 14.0278 | 1
4322 | 3.7829 | 3.794 | 6.5872 | 4.863 | 4.3967 | 1.7749 | 14.2149 | 16.5418 | 16.5418 | 0
4323 | 3.1043 | 5.1222 | 5.5756 | 5.9893 | 3.7678 | 2.2395 | 16.4553 | 14.6872 | 16.4553 | 1
4324 | 3.0255 | 5.7359 | 7.6148 | 4.2956 | 4.8236 | 1.3404 | 14.3975 | 16.8044 | 16.8044 | 0
4325 | 2.494 | 4.7513 | 6.5323 | 5.6408 | 3.5965 | 2.1333 | 15.0194 | 14.7561 | 15.0194 | 1
4326 | 4.3772 | 5.4954 | 5.991 | 4.0488 | 4.7619 | 2.1617 | 16.0831 | 17.2918 | 17.2918 | 0
4327 | 3.5019 | 4.0451 | 7.1539 | 6.6424 | 5.8728 | 2.5941 | 16.7835 | 19.1227 | 19.1227 | 0
4328 | 3.4859 | 7.9443 | 6.923 | 4.2872 | 4.1168 | 2.2974 | 18.0148 | 16.8231 | 18.0148 | 1
4329 | 4.1678 | 4.551 | 6.5209 | 5.1271 | 5.2017 | 2.0337 | 15.8797 | 17.924 | 17.924 | 0
4330 | 3.4496 | 5.318 | 6.0549 | 4.7522 | 3.7648 | 2.2936 | 15.8132 | 15.5628 | 15.8132 | 1
4331 | 3.6762 | 6.7736 | 4.7495 | 5.2068 | 5.2839 | 2.3469 | 18.0035 | 16.0565 | 18.0035 | 1
4332 | 3.4898 | 5.4153 | 7.559 | 5.6343 | 3.4107 | 1.9771 | 16.5165 | 16.4366 | 16.5165 | 1
4333 | 4.1259 | 6.2335 | 6.1718 | 4.9782 | 4.9505 | 1.6235 | 16.9611 | 16.8716 | 16.9611 | 1
4334 | 2.9685 | 6.541 | 5.7493 | 4.2844 | 4.0681 | 1.6034 | 15.3973 | 14.3893 | 15.3973 | 1
4335 | 3.2208 | 6.5946 | 4.9304 | 5.3498 | 4.6216 | 1.6391 | 16.8043 | 14.4118 | 16.8043 | 1
4336 | 4.2977 | 6.1128 | 5.535 | 5.7232 | 4.7321 | 2.2375 | 18.3713 | 16.8023 | 18.3713 | 1
4337 | 3.0101 | 5.1899 | 3.1911 | 4.5576 | 5.5492 | 1.9647 | 14.7223 | 13.7151 | 14.7223 | 1
4338 | 2.9855 | 6.1957 | 4.8889 | 5.247 | 4.6077 | 2.2664 | 16.6946 | 14.7484 | 16.6946 | 1
4339 | 4.0468 | 3.518 | 6.4707 | 6.292 | 4.6131 | 1.9729 | 15.8297 | 17.1035 | 17.1035 | 0
4340 | 3.9195 | 4.5904 | 6.5986 | 5.2206 | 3.3772 | 2.1853 | 15.9157 | 16.0805 | 16.0805 | 0
4341 | 4.6687 | 5.5421 | 5.83 | 4.7098 | 3.5226 | 1.3633 | 16.2838 | 15.3845 | 16.2838 | 1
4342 | 3.7172 | 5.3136 | 6.1274 | 5.7037 | 3.628 | 2.322 | 17.0565 | 15.7945 | 17.0565 | 1
4343 | 3.9748 | 5.5401 | 5.8461 | 6.2363 | 3.9134 | 1.9828 | 17.7339 | 15.717 | 17.7339 | 1
4344 | 5.2957 | 4.7369 | 5.8268 | 4.6225 | 3.5249 | 1.3965 | 16.0514 | 16.0438 | 16.0514 | 1
4345 | 2.69 | 5.2083 | 6.0984 | 4.861 | 4.6396 | 1.856 | 14.6153 | 15.284 | 15.284 | 0
4346 | 2.6666 | 5.8757 | 7.6626 | 6.871 | 3.6351 | 2.1739 | 17.5872 | 16.1383 | 17.5872 | 1
4347 | 3.2995 | 4.552 | 6.361 | 5.3951 | 5.0162 | 1.3256 | 14.5722 | 16.0023 | 16.0023 | 0
4348 | 3.2077 | 4.9871 | 6.4451 | 5.8178 | 3.4974 | 1.8016 | 15.8142 | 14.9519 | 15.8142 | 1
4349 | 4.3796 | 6.7507 | 5.2637 | 6.5895 | 4.9953 | 2.7057 | 20.4256 | 17.3444 | 20.4256 | 1
4350 | 3.4121 | 6.9932 | 4.8864 | 4.7958 | 3.6002 | 2.04 | 17.241 | 13.9386 | 17.241 | 1
4351 | 4.322 | 3.7797 | 5.3789 | 5.4016 | 5.1098 | 2.3247 | 15.8279 | 17.1354 | 17.1354 | 0
4352 | 4.5211 | 7.8245 | 6.0851 | 4.5976 | 3.1973 | 2.5617 | 19.5049 | 16.3652 | 19.5049 | 1
4353 | 4.7431 | 4.4769 | 6.8703 | 4.7802 | 5.369 | 1.8517 | 15.8519 | 18.8341 | 18.8341 | 0
4354 | 4.6565 | 3.5893 | 5.4968 | 4.5584 | 5.6679 | 2.6198 | 15.4241 | 18.441 | 18.441 | 0
4355 | 5.0031 | 4.7263 | 5.4288 | 5.6638 | 4.6165 | 1.4719 | 16.8652 | 16.5203 | 16.8652 | 1
4356 | 2.7233 | 5.2997 | 6.6429 | 5.7021 | 3.8862 | 2.3404 | 16.0655 | 15.5928 | 16.0655 | 1
4357 | 4.9282 | 6.0486 | 4.6907 | 5.2872 | 3.3337 | 1.4642 | 17.7283 | 14.4169 | 17.7283 | 1
4358 | 5.3089 | 5.3502 | 6.998 | 6.2992 | 3.9028 | 1.5413 | 18.4996 | 17.751 | 18.4996 | 1
4359 | 3.7904 | 7.0853 | 5.0936 | 4.418 | 4.8524 | 1.8169 | 17.1106 | 15.5532 | 17.1106 | 1
4360 | 3.7294 | 5.1732 | 5.688 | 5.1478 | 4.0032 | 1.9875 | 16.0379 | 15.4081 | 16.0379 | 1
4361 | 3.6077 | 4.1657 | 5.2482 | 4.9276 | 4.0356 | 2.2648 | 14.9658 | 15.1563 | 15.1563 | 0
4362 | 3.3166 | 4.7907 | 7.2385 | 5.1344 | 3.7613 | 1.3449 | 14.5865 | 15.6613 | 15.6613 | 0
4363 | 5.1551 | 5.4333 | 3.1079 | 7.314 | 4.5689 | 1.2341 | 19.1364 | 14.0659 | 19.1364 | 1
4364 | 3.8703 | 6.6813 | 5.7392 | 4.7976 | 3.4385 | 1.8267 | 17.1759 | 14.8746 | 17.1759 | 1
4365 | 3.7753 | 3.5598 | 4.6691 | 5.0583 | 4.2426 | 2.1897 | 14.5831 | 14.8766 | 14.8766 | 0
4366 | 4.7912 | 5.8064 | 3.9641 | 5.6002 | 3.7759 | 1.8039 | 18.0017 | 14.3352 | 18.0017 | 1
4367 | 3.8081 | 6.4441 | 3.9622 | 6.7891 | 3.67 | 1.6491 | 18.6904 | 13.0894 | 18.6904 | 1
4368 | 3.0685 | 4.0057 | 5.4956 | 5.8168 | 3.5819 | 1.785 | 14.6761 | 13.931 | 14.6761 | 1
4369 | 4.727 | 5.538 | 4.0106 | 5.1883 | 4.3912 | 1.8415 | 17.2947 | 14.9703 | 17.2947 | 1
4370 | 4.3838 | 4.2111 | 6.1843 | 5.2008 | 5.8943 | 2.136 | 15.9317 | 18.5983 | 18.5983 | 0
4371 | 3.7148 | 5.2505 | 6.8567 | 5.6452 | 4.6763 | 1.7967 | 16.4071 | 17.0444 | 17.0444 | 0
4372 | 3.3041 | 3.7885 | 5.8614 | 4.8462 | 6.0024 | 1.2885 | 13.2274 | 16.4565 | 16.4565 | 0
4373 | 3.3739 | 7.2004 | 4.5624 | 4.9502 | 5.4355 | 1.4091 | 16.9336 | 14.7809 | 16.9336 | 1
4374 | 4.0423 | 5.8977 | 6.5433 | 4.7801 | 5.2682 | 2.3194 | 17.0395 | 18.1731 | 18.1731 | 0
4375 | 5.6006 | 6.2189 | 4.7846 | 5.1847 | 3.379 | 2.3869 | 19.3912 | 16.1511 | 19.3912 | 1
4376 | 3.0017 | 6.2366 | 6.3262 | 5.4849 | 5.1041 | 2.4875 | 17.2106 | 16.9194 | 17.2106 | 1
4377 | 4.2858 | 5.0651 | 5.1992 | 4.2854 | 4.708 | 2.3064 | 15.9428 | 16.4994 | 16.4994 | 0
4378 | 5.1977 | 4.0154 | 4.0474 | 6.1943 | 5.428 | 1.3736 | 16.781 | 16.0466 | 16.781 | 1
4379 | 3.8388 | 7.4608 | 6.9769 | 5.0756 | 3.1465 | 2.5284 | 18.9036 | 16.4906 | 18.9036 | 1
4380 | 3.1392 | 7.4192 | 5.1363 | 4.2772 | 3.549 | 2.0603 | 16.8958 | 13.8846 | 16.8958 | 1
4381 | 3.0783 | 6.209 | 5.1164 | 5.6002 | 3.5923 | 2.5316 | 17.419 | 14.3185 | 17.419 | 1
4382 | 3.6836 | 5.1983 | 4.4364 | 6.1657 | 3.4856 | 1.7147 | 16.7624 | 13.3203 | 16.7624 | 1
4383 | 4.8947 | 6.9975 | 6.8412 | 5.0842 | 3.8679 | 2.0221 | 18.9986 | 17.626 | 18.9986 | 1
4384 | 4.8762 | 4.9827 | 5.4878 | 5.4488 | 3.3089 | 1.4755 | 16.7833 | 15.1485 | 16.7833 | 1
4385 | 4.2469 | 7.1641 | 5.2511 | 5.9211 | 5.2209 | 2.1894 | 19.5215 | 16.9083 | 19.5215 | 1
4386 | 2.8018 | 6.5341 | 7.4465 | 5.6217 | 3.2367 | 2.0538 | 17.0114 | 15.5388 | 17.0114 | 1
4387 | 5.5422 | 4.3048 | 5.8368 | 4.6411 | 5.4058 | 2.773 | 17.2611 | 19.5579 | 19.5579 | 0
4388 | 4.5678 | 3.6657 | 7.0356 | 5.3379 | 4.4578 | 1.5673 | 15.1387 | 17.6285 | 17.6285 | 0
4389 | 3.3053 | 4.8176 | 6.1587 | 7.5124 | 4.6161 | 1.8805 | 17.5157 | 15.9605 | 17.5157 | 1
4390 | 3.4572 | 4.1039 | 6.2523 | 4.1281 | 4.9051 | 1.1991 | 12.8883 | 15.8138 | 15.8138 | 0
4391 | 4.0913 | 6.5545 | 5.139 | 5.8388 | 4.5281 | 1.9679 | 18.4524 | 15.7263 | 18.4524 | 1
4392 | 3.3609 | 4.3518 | 5.3431 | 4.2192 | 5.0462 | 1.1509 | 13.0829 | 14.9011 | 14.9011 | 0
4393 | 3.8272 | 3.694 | 5.7423 | 6.3372 | 4.5622 | 1.63 | 15.4883 | 15.7617 | 15.7617 | 0
4394 | 4.5153 | 6.0354 | 5.1584 | 4.069 | 3.4427 | 1.3135 | 15.9331 | 14.4298 | 15.9331 | 1
4395 | 4.0542 | 5.1485 | 5.7222 | 7.5805 | 6.1468 | 2.7377 | 19.5209 | 18.661 | 19.5209 | 1
4396 | 4.5738 | 6.7053 | 4.9861 | 4.9627 | 3.5869 | 2.7467 | 18.9885 | 15.8934 | 18.9885 | 1
4397 | 4.5222 | 5.1334 | 7.4632 | 4.3778 | 3.2673 | 2.2929 | 16.3264 | 17.5457 | 17.5457 | 0
4398 | 5.0235 | 7.3757 | 3.3325 | 5.1626 | 3.7787 | 1.9243 | 19.4861 | 14.0591 | 19.4861 | 1
4399 | 4.57 | 5.9647 | 5.9711 | 6.084 | 4.073 | 1.5837 | 18.2024 | 16.1978 | 18.2024 | 1
4400 | 3.1679 | 6.3094 | 6.0732 | 5.8791 | 4.4404 | 1.8515 | 17.2078 | 15.533 | 17.2078 | 1
4401 | 4.4161 | 4.0743 | 5.6715 | 5.4432 | 4.6568 | 1.8148 | 15.7485 | 16.5594 | 16.5594 | 0
4402 | 2.5202 | 5.1415 | 6.8447 | 6.4593 | 4.8461 | 1.979 | 16.1 | 16.19 | 16.19 | 0
4403 | 3.3405 | 5.4874 | 4.7777 | 5.1462 | 4.2304 | 2.513 | 16.4871 | 14.8616 | 16.4871 | 1
4404 | 4.1269 | 4.005 | 4.364 | 4.4775 | 5.1811 | 1.6659 | 14.2753 | 15.338 | 15.338 | 0
4405 | 3.3064 | 4.1329 | 7.5384 | 5.4739 | 4.2275 | 2.0831 | 14.9963 | 17.1555 | 17.1555 | 0
4406 | 3.6416 | 5.4421 | 7.3502 | 4.6927 | 3.1198 | 1.5988 | 15.3752 | 15.7105 | 15.7105 | 0
4407 | 3.3451 | 5.4849 | 5.8473 | 4.3515 | 3.6473 | 1.2868 | 14.4683 | 14.1265 | 14.4683 | 1
4408 | 3.4993 | 4.5168 | 6.3102 | 5.3327 | 4.7878 | 1.2614 | 14.6101 | 15.8587 | 15.8587 | 0
4409 | 5.5154 | 3.6818 | 6.7376 | 6.8486 | 6.3464 | 2.1009 | 18.1468 | 20.7003 | 20.7003 | 0
4410 | 3.9747 | 7.0669 | 7.3118 | 5.2402 | 4.1715 | 1.9927 | 18.2745 | 17.4507 | 18.2745 | 1
4411 | 4.2988 | 5.7737 | 7.8813 | 6.3624 | 5.143 | 2.0302 | 18.4651 | 19.3533 | 19.3533 | 0
4412 | 3.0366 | 5.4529 | 7.2882 | 4.6281 | 5.0033 | 1.9052 | 15.0228 | 17.2332 | 17.2332 | 0
4413 | 5.2254 | 4.8161 | 4.6858 | 6.2934 | 4.4632 | 1.7406 | 18.0754 | 16.1149 | 18.0754 | 1
4414 | 5.5012 | 4.2644 | 6.1482 | 4.7041 | 4.1566 | 2.2854 | 16.7551 | 18.0914 | 18.0914 | 0
4415 | 4.599 | 4.2992 | 6.8729 | 5.7046 | 4.372 | 2.4953 | 17.0981 | 18.3392 | 18.3392 | 0
4416 | 5.2055 | 6.1282 | 5.6988 | 5.5779 | 3.3643 | 1.791 | 18.7026 | 16.0596 | 18.7026 | 1
4417 | 3.0979 | 6.2806 | 5.5199 | 4.0713 | 4.3723 | 2.6441 | 16.094 | 15.6342 | 16.094 | 1
4418 | 3.6854 | 6.2984 | 5.2532 | 5.1437 | 3.743 | 2.0851 | 17.2126 | 14.7667 | 17.2126 | 1
4419 | 3.1995 | 4.332 | 3.6238 | 4.864 | 3.2971 | 2.7765 | 15.172 | 12.8969 | 15.172 | 1
4420 | 4.5484 | 5.354 | 2.9839 | 6.0084 | 3.7103 | 2.0125 | 17.9233 | 13.2551 | 17.9233 | 1
4421 | 4.5161 | 5.0942 | 6.6773 | 4.816 | 5.0811 | 2.4965 | 16.9228 | 18.771 | 18.771 | 0
4422 | 3.4898 | 4.8331 | 5.4282 | 4.9471 | 3.4561 | 2.8008 | 16.0708 | 15.1749 | 16.0708 | 1
4423 | 4.3975 | 5.8031 | 7.1564 | 5.4993 | 5.6706 | 2.4799 | 18.1798 | 19.7044 | 19.7044 | 0
4424 | 4.6859 | 4.9714 | 5.7964 | 6.3564 | 5.3133 | 1.7333 | 17.7471 | 17.529 | 17.7471 | 1
4425 | 5.061 | 4.1936 | 4.9322 | 4.8456 | 3.7905 | 1.8926 | 15.9928 | 15.6764 | 15.9928 | 1
4426 | 4.3837 | 6.3402 | 3.9421 | 4.2613 | 4.4445 | 2.3877 | 17.3729 | 15.158 | 17.3729 | 1
4427 | 3.8896 | 6.3675 | 6.5582 | 4.4885 | 3.9636 | 1.9914 | 16.7371 | 16.4029 | 16.7371 | 1
4428 | 3.7487 | 5.9863 | 6.1023 | 4.7824 | 3.9193 | 1.7636 | 16.2809 | 15.5339 | 16.2809 | 1
4429 | 3.8019 | 5.6225 | 7.5637 | 4.3976 | 3.7236 | 1.792 | 15.6139 | 16.8812 | 16.8812 | 0
4430 | 5.0858 | 3.8757 | 6.774 | 6.3442 | 3.9133 | 1.2501 | 16.5559 | 17.0232 | 17.0232 | 0
4431 | 4.1754 | 3.9498 | 5.5411 | 6.0563 | 3.3948 | 2.0451 | 16.2265 | 15.1563 | 16.2265 | 1
4432 | 3.0971 | 5.3173 | 5.8604 | 4.0886 | 4.447 | 2.3791 | 14.8821 | 15.7835 | 15.7835 | 0
4433 | 3.2688 | 5.6144 | 6.2704 | 4.388 | 4.3959 | 2.6433 | 15.9145 | 16.5784 | 16.5784 | 0
4434 | 3.8387 | 5.1004 | 5.2764 | 6.1603 | 4.1621 | 2.1494 | 17.2488 | 15.4266 | 17.2488 | 1
4435 | 5.2936 | 4.5847 | 4.6224 | 5.8592 | 4.067 | 2.2411 | 17.9785 | 16.2241 | 17.9785 | 1
4436 | 3.9708 | 7.1926 | 3.3453 | 4.5859 | 4.0451 | 2.2085 | 17.9578 | 13.5696 | 17.9578 | 1
4437 | 4.1204 | 4.812 | 4.532 | 4.8062 | 4.2532 | 1.6689 | 15.4075 | 14.5745 | 15.4075 | 1
4438 | 3.6674 | 6.6463 | 5.4153 | 4.6014 | 5.106 | 1.5135 | 16.4286 | 15.7022 | 16.4286 | 1
4439 | 5.1789 | 7.0224 | 6.8852 | 5.8035 | 5.6817 | 2.2298 | 20.2346 | 19.9756 | 20.2346 | 1
4440 | 4.0269 | 5.72 | 3.2767 | 6.3099 | 4.691 | 1.65 | 17.7069 | 13.6446 | 17.7069 | 1
4441 | 5.2624 | 6.6046 | 5.5324 | 4.8929 | 3.9858 | 2.0558 | 18.8158 | 16.8365 | 18.8158 | 1
4442 | 3.3327 | 6.1206 | 6.7226 | 6.0332 | 3.9506 | 2.3751 | 17.8616 | 16.381 | 17.8616 | 1
4443 | 4.0281 | 6.4703 | 5.438 | 4.1804 | 4.3864 | 1.5604 | 16.2392 | 15.4129 | 16.2392 | 1
4444 | 3.8122 | 4.4656 | 5.7321 | 5.0175 | 5.2426 | 1.7429 | 15.0382 | 16.5298 | 16.5298 | 0
4445 | 4.0129 | 6.2779 | 7.1779 | 5.433 | 3.8822 | 1.4569 | 17.1807 | 16.5298 | 17.1807 | 1
4446 | 4.6665 | 3.8745 | 6.2754 | 4.1865 | 4.3526 | 1.8411 | 14.5686 | 17.1356 | 17.1356 | 0
4447 | 3.7053 | 6.2187 | 4.852 | 5.882 | 3.1887 | 1.6672 | 17.4731 | 13.4132 | 17.4731 | 1
4448 | 3.8048 | 4.9696 | 5.7649 | 4.8677 | 3.1034 | 1.6413 | 15.2833 | 14.3143 | 15.2833 | 1
4449 | 3.939 | 7.1804 | 3.6575 | 5.3337 | 4.0643 | 1.6465 | 18.0997 | 13.3073 | 18.0997 | 1
4450 | 2.6816 | 4.6175 | 5.508 | 4.5909 | 5.2416 | 1.3501 | 13.2401 | 14.7812 | 14.7812 | 0
4451 | 4.3803 | 6.3797 | 7.3887 | 4.9114 | 3.6874 | 2.5125 | 18.1839 | 17.9689 | 18.1839 | 1
4452 | 2.934 | 5.0624 | 5.8019 | 4.5416 | 3.804 | 1.8909 | 14.4289 | 14.4308 | 14.4308 | 0
4453 | 4.6279 | 6.0427 | 5.6395 | 5.5473 | 3.472 | 1.8853 | 18.1032 | 15.6247 | 18.1032 | 1
4454 | 3.2697 | 4.3782 | 4.7154 | 4.8067 | 6.1217 | 1.7679 | 14.2224 | 15.8746 | 15.8746 | 0
4455 | 2.9909 | 7.7054 | 6.9597 | 5.0439 | 3.3662 | 1.5729 | 17.3132 | 14.8898 | 17.3132 | 1
4456 | 2.9796 | 5.484 | 4.9053 | 5.925 | 4.6719 | 2.316 | 16.7045 | 14.8728 | 16.7045 | 1
4457 | 2.93 | 5.6409 | 5.5131 | 5.7785 | 4.7492 | 1.804 | 16.1534 | 14.9964 | 16.1534 | 1
4458 | 4.0634 | 4.9746 | 6.1693 | 5.0887 | 4.1407 | 1.7063 | 15.8329 | 16.0796 | 16.0796 | 0
4459 | 4.8426 | 5.1622 | 6.5786 | 4.5105 | 3.7246 | 1.6799 | 16.1952 | 16.8257 | 16.8257 | 0
4460 | 2.8932 | 4.8528 | 6.8024 | 6.757 | 5.3768 | 1.9915 | 16.4946 | 17.0639 | 17.0639 | 0
4461 | 4.2691 | 6.7615 | 5.6745 | 5.5674 | 4.035 | 2.2344 | 18.8324 | 16.2131 | 18.8324 | 1
4462 | 2.2123 | 3.7798 | 3.6704 | 6.3435 | 4.0969 | 1.5289 | 13.8646 | 11.5086 | 13.8646 | 1
4463 | 4.2358 | 3.534 | 5.0831 | 4.8091 | 5.0312 | 2.2008 | 14.7798 | 16.5509 | 16.5509 | 0
4464 | 4.8287 | 5.7523 | 7.0097 | 5.3959 | 3.7263 | 2.2686 | 18.2455 | 17.8333 | 18.2455 | 1
4465 | 4.7078 | 7.3255 | 6.1228 | 5.9519 | 3.7718 | 1.7392 | 19.7243 | 16.3415 | 19.7243 | 1
4466 | 3.333 | 3.9577 | 6.5802 | 6.3525 | 6.0697 | 1.9712 | 15.6144 | 17.9542 | 17.9542 | 0
4467 | 3.3847 | 4.1453 | 6.2984 | 6.0639 | 3.6318 | 2.5322 | 16.1261 | 15.8472 | 16.1261 | 1
4468 | 3.4025 | 5.5366 | 4.8644 | 4.9402 | 5.0166 | 2.1558 | 16.0351 | 15.4393 | 16.0351 | 1
4469 | 5.0299 | 4.3719 | 3.8576 | 6.5934 | 3.5591 | 2.7516 | 18.7468 | 15.1982 | 18.7468 | 1
4470 | 4.0486 | 5.5252 | 6.8052 | 6.8302 | 4.3191 | 2.5537 | 18.9577 | 17.7267 | 18.9577 | 1
4471 | 4.0751 | 5.9145 | 5.6251 | 7.1247 | 4.8122 | 1.3387 | 18.453 | 15.8511 | 18.453 | 1
4472 | 3.0316 | 4.0083 | 5.0318 | 4.8353 | 4.5819 | 2.0561 | 13.9312 | 14.7014 | 14.7014 | 0
4473 | 5.635 | 5.4399 | 6.7086 | 5.5644 | 3.8365 | 1.9307 | 18.5701 | 18.1109 | 18.5701 | 1
4474 | 3.8531 | 4.3973 | 4.1038 | 5.3279 | 6.0171 | 1.4076 | 14.986 | 15.3817 | 15.3817 | 0
4475 | 4.3374 | 3.6592 | 5.1437 | 4.3789 | 3.4692 | 2.023 | 14.3985 | 14.9733 | 14.9733 | 0
4476 | 2.8444 | 3.4755 | 5.6197 | 5.3571 | 4.3891 | 2.3806 | 14.0576 | 15.2339 | 15.2339 | 0
4477 | 5.1562 | 5.4366 | 4.7964 | 5.6911 | 4.2091 | 1.7503 | 18.0342 | 15.9119 | 18.0342 | 1
4478 | 2.7755 | 4.7071 | 4.2389 | 6.2483 | 4.299 | 1.7934 | 15.5244 | 13.1069 | 15.5244 | 1
4479 | 5.0235 | 5.9974 | 5.7012 | 5.5888 | 3.7573 | 2.1821 | 18.7917 | 16.664 | 18.7917 | 1
4480 | 3.471 | 4.1334 | 5.3107 | 4.5609 | 5.846 | 2.6553 | 14.8207 | 17.2831 | 17.2831 | 0
4481 | 3.901 | 4.1852 | 4.2808 | 5.8308 | 5.6726 | 2.3825 | 16.2995 | 16.2369 | 16.2995 | 1
4482 | 3.4196 | 5.2998 | 6.9448 | 6.3848 | 3.9215 | 1.7392 | 16.8434 | 16.0251 | 16.8434 | 1
4483 | 2.6837 | 6.8297 | 6.5387 | 6.8237 | 6.1583 | 2.3519 | 18.6891 | 17.7327 | 18.6891 | 1
4484 | 3.0826 | 4.71 | 6.4725 | 4.1998 | 4.1891 | 1.6456 | 13.6379 | 15.3898 | 15.3898 | 0
4485 | 5.0573 | 6.4726 | 6.7752 | 4.5445 | 6.2376 | 2.1331 | 18.2075 | 20.2032 | 20.2032 | 0
4486 | 4.0162 | 5.4006 | 4.8195 | 6.1622 | 4.8152 | 2.6747 | 18.2538 | 16.3257 | 18.2538 | 1
4487 | 2.3943 | 4.1031 | 5.3145 | 4.5952 | 3.39 | 1.6967 | 12.7893 | 12.7956 | 12.7956 | 0
4488 | 4.3538 | 7.1435 | 7.0089 | 4.0789 | 3.2266 | 1.8211 | 17.3972 | 16.4103 | 17.3972 | 1
4489 | 3.8522 | 3.4903 | 6.1607 | 5.4817 | 4.8708 | 2.7088 | 15.5329 | 17.5924 | 17.5924 | 0
4490 | 4.2858 | 6.8837 | 7.3351 | 4.3081 | 6.0446 | 2.3779 | 17.8554 | 20.0434 | 20.0434 | 0
4491 | 3.3534 | 5.0904 | 4.8377 | 4.3595 | 4.2657 | 1.6484 | 14.4517 | 14.1052 | 14.4517 | 1
4492 | 3.4627 | 5.8508 | 5.829 | 5.3438 | 5.4988 | 2.5846 | 17.2419 | 17.3751 | 17.3751 | 0
4493 | 4.3815 | 4.8608 | 6.1517 | 4.6689 | 3.7676 | 1.87 | 15.7812 | 16.1709 | 16.1709 | 0
4494 | 3.9791 | 5.3788 | 5.9776 | 6.6937 | 3.4585 | 2.5285 | 18.5801 | 15.9436 | 18.5801 | 1
4495 | 3.9224 | 4.7964 | 4.4266 | 6.8794 | 3.5715 | 2.4202 | 18.0184 | 14.3407 | 18.0184 | 1
4496 | 3.933 | 5.3374 | 5.7401 | 6.0136 | 3.6442 | 2.6248 | 17.9088 | 15.9421 | 17.9088 | 1
4497 | 4.617 | 6.3326 | 5.7087 | 4.9306 | 6.4737 | 1.8073 | 17.6875 | 18.6067 | 18.6067 | 0
4498 | 4.5478 | 5.0884 | 5.3769 | 4.6606 | 4.102 | 2.1809 | 16.4776 | 16.2076 | 16.4776 | 1
4499 | 4.532 | 5.977 | 6.0362 | 4.8679 | 3.0788 | 2.3255 | 17.7025 | 15.9725 | 17.7025 | 1
4500 | 3.3015 | 4.5717 | 6.1143 | 5.0071 | 3.4415 | 1.9781 | 14.8585 | 14.8355 | 14.8585 | 1
4501 | 3.3025 | 5.3159 | 3.1856 | 5.5932 | 4.1546 | 1.9313 | 16.1429 | 12.5739 | 16.1429 | 1
4502 | 4.8826 | 6.1386 | 5.2811 | 5.3834 | 3.5871 | 2.3705 | 18.775 | 16.1212 | 18.775 | 1
4503 | 3.3424 | 4.7547 | 5.2572 | 6.9823 | 3.7628 | 2.8537 | 17.9331 | 15.2161 | 17.9331 | 1
4504 | 4.5376 | 6.9735 | 3.0536 | 4.9004 | 3.1614 | 1.524 | 17.9355 | 12.2766 | 17.9355 | 1
4505 | 2.9871 | 7.3779 | 6.3459 | 5.4505 | 4.5475 | 1.5253 | 17.3408 | 15.4058 | 17.3408 | 1
4506 | 3.4886 | 6.3536 | 4.1252 | 5.0687 | 4.5475 | 2.8255 | 17.7364 | 14.9868 | 17.7364 | 1
4507 | 3.4271 | 6.5316 | 6.5376 | 6.3766 | 3.1854 | 1.5779 | 17.9132 | 14.7279 | 17.9132 | 1
4508 | 4.3203 | 5.8823 | 3.9386 | 5.042 | 5.848 | 2.0328 | 17.2774 | 16.1397 | 17.2774 | 1
4509 | 3.04 | 4.0642 | 3.3703 | 5.9485 | 4.3655 | 2.0286 | 15.0813 | 12.8044 | 15.0813 | 1
4510 | 4.966 | 5.162 | 7.0411 | 4.5352 | 4.9288 | 2.0867 | 16.7499 | 19.0226 | 19.0226 | 0
4511 | 5.1259 | 5.0863 | 6.1051 | 5.4239 | 4.4969 | 1.8874 | 17.5235 | 17.6153 | 17.6153 | 0
4512 | 5.1414 | 7.1427 | 5.2989 | 4.9728 | 3.7371 | 1.4207 | 18.6776 | 15.5981 | 18.6776 | 1
4513 | 4.6749 | 4.9324 | 5.4285 | 4.9505 | 4.2522 | 1.7997 | 16.3576 | 16.1554 | 16.3576 | 1
4514 | 5.1306 | 4.8301 | 3.1486 | 5.3729 | 5.4123 | 1.4898 | 16.8234 | 15.1813 | 16.8234 | 1
4515 | 2.8696 | 4.0183 | 6.169 | 5.664 | 4.5871 | 1.3296 | 13.8816 | 14.9553 | 14.9553 | 0
4516 | 3.7617 | 6.5612 | 7.5532 | 5.2725 | 3.5561 | 2.2047 | 17.8 | 17.0755 | 17.8 | 1
4517 | 3.0551 | 4.4787 | 6.3883 | 5.5764 | 4.5936 | 2.6787 | 15.7889 | 16.7158 | 16.7158 | 0
4518 | 4.2219 | 5.684 | 4.2043 | 6.1833 | 3.7439 | 1.6884 | 17.7776 | 13.8585 | 17.7776 | 1
4519 | 4.1559 | 4.308 | 6.4379 | 5.0059 | 3.2761 | 1.5459 | 15.0157 | 15.4158 | 15.4158 | 0
4520 | 5.0188 | 5.1766 | 6.0715 | 5.4073 | 3.5019 | 2.1615 | 17.7642 | 16.7537 | 17.7642 | 1
4521 | 3.7911 | 4.8446 | 7.0195 | 5.206 | 5.2994 | 2.3078 | 16.1494 | 18.4177 | 18.4177 | 0
4522 | 4.7279 | 3.7627 | 4.5853 | 4.7259 | 3.6038 | 2.1481 | 15.3647 | 15.0651 | 15.3647 | 1
4523 | 5.3154 | 3.4321 | 6.9341 | 4.8685 | 4.3072 | 1.6865 | 15.3025 | 18.2433 | 18.2433 | 0
4524 | 4.3781 | 5.5732 | 4.2186 | 5.7598 | 4.0255 | 1.824 | 17.5352 | 14.4463 | 17.5352 | 1
4525 | 3.996 | 4.7497 | 5.3306 | 5.3465 | 4.1375 | 1.5942 | 15.6865 | 15.0584 | 15.6865 | 1
4526 | 3.9801 | 4.2694 | 6.8723 | 4.6 | 3.832 | 2.2071 | 15.0565 | 16.8914 | 16.8914 | 0
4527 | 2.8802 | 5.5135 | 6.0392 | 6.4623 | 4.0543 | 1.334 | 16.19 | 14.3077 | 16.19 | 1
4528 | 3.9925 | 4.1611 | 3.6399 | 4.7796 | 4.6151 | 1.947 | 14.8802 | 14.1945 | 14.8802 | 1
4529 | 5.283 | 6.9413 | 5.2517 | 4.6576 | 4.2903 | 1.9689 | 18.8508 | 16.794 | 18.8508 | 1
4530 | 3.6244 | 6.3089 | 3.2569 | 4.9899 | 5.1427 | 1.5827 | 16.5059 | 13.6067 | 16.5059 | 1
4531 | 4.7008 | 5.5319 | 4.6752 | 4.3401 | 4.9103 | 1.1697 | 15.7425 | 15.456 | 15.7425 | 1
4532 | 4.2601 | 6.1072 | 3.9947 | 5.1866 | 4.7297 | 1.8606 | 17.4145 | 14.8451 | 17.4145 | 1
4533 | 2.9439 | 5.7666 | 6.9678 | 5.1764 | 4.3114 | 1.9755 | 15.8624 | 16.1987 | 16.1987 | 0
4534 | 5.1573 | 5.3507 | 4.5601 | 4.9103 | 4.2913 | 2.2647 | 17.6831 | 16.2734 | 17.6831 | 1
4535 | 2.7683 | 7.1503 | 5.8089 | 4.6699 | 3.3174 | 1.722 | 16.3106 | 13.6167 | 16.3106 | 1
4536 | 2.7048 | 4.6615 | 7.1255 | 5.3147 | 3.3942 | 2.2466 | 14.9276 | 15.471 | 15.471 | 0
4537 | 5.0197 | 5.527 | 5.1712 | 4.9205 | 3.625 | 2.0035 | 17.4707 | 15.8193 | 17.4707 | 1
4538 | 3.324 | 7.1491 | 5.2819 | 5.0595 | 4.0116 | 1.862 | 17.3947 | 14.4795 | 17.3947 | 1
4539 | 3.9112 | 6.8591 | 6.9218 | 4.7754 | 3.8692 | 1.832 | 17.3777 | 16.5342 | 17.3777 | 1
4540 | 5.148 | 5.2418 | 6.0592 | 4.4305 | 3.6448 | 2.3845 | 17.2048 | 17.2365 | 17.2365 | 0
4541 | 4.4734 | 6.2055 | 6.5614 | 4.635 | 3.4649 | 2.1588 | 17.4727 | 16.6584 | 17.4727 | 1
4542 | 3.5713 | 3.6213 | 4.5754 | 5.6429 | 4.2019 | 1.5156 | 14.351 | 13.8642 | 14.351 | 1
4543 | 4.4637 | 7.3699 | 5.9256 | 5.7442 | 4.4878 | 1.9841 | 19.5619 | 16.8613 | 19.5619 | 1
4544 | 3.5872 | 3.7613 | 5.3002 | 4.2097 | 4.7075 | 2.3058 | 13.864 | 15.9008 | 15.9008 | 0
4545 | 4.7097 | 4.7107 | 5.9981 | 5.885 | 5.5566 | 2.5672 | 17.8725 | 18.8316 | 18.8316 | 0
4546 | 2.8488 | 4.6612 | 6.3228 | 5.3311 | 4.3726 | 2.232 | 15.073 | 15.7762 | 15.7762 | 0
4547 | 4.3299 | 5.2104 | 5.2763 | 5.7257 | 5.9078 | 1.9819 | 17.248 | 17.496 | 17.496 | 0
4548 | 5.0109 | 5.6598 | 4.276 | 4.2663 | 5.3299 | 1.6055 | 16.5425 | 16.2222 | 16.5425 | 1
4549 | 3.7343 | 4.4142 | 6.6353 | 5.381 | 4.1522 | 2.3744 | 15.9039 | 16.8962 | 16.8962 | 0
4550 | 3.8507 | 6.3631 | 4.9144 | 5.7775 | 4.7691 | 2.7888 | 18.7802 | 16.323 | 18.7802 | 1
4551 | 3.9555 | 5.4894 | 7.363 | 6.3276 | 4.9143 | 1.5093 | 17.2818 | 17.7421 | 17.7421 | 0
4552 | 3.2743 | 4.8725 | 7.1816 | 5.7754 | 3.2894 | 2.1123 | 16.0346 | 15.8577 | 16.0346 | 1
4553 | 3.427 | 3.9561 | 5.4862 | 6.6037 | 4.2979 | 2.1964 | 16.1832 | 15.4076 | 16.1832 | 1
4554 | 3.0484 | 3.794 | 4.0482 | 6.6479 | 3.8266 | 2.1219 | 15.6121 | 13.045 | 15.6121 | 1
4555 | 3.9339 | 4.7387 | 4.6459 | 6.2909 | 3.3517 | 2.3367 | 17.3002 | 14.2682 | 17.3002 | 1
4556 | 4.8647 | 5.2494 | 4.4817 | 6.4542 | 4.92 | 1.6053 | 18.1736 | 15.8717 | 18.1736 | 1
4557 | 3.6905 | 5.0709 | 4.4721 | 6.4048 | 5.7777 | 1.8628 | 17.0291 | 15.8031 | 17.0291 | 1
4558 | 3.9645 | 6.094 | 7.1025 | 5.2191 | 3.4197 | 1.8111 | 17.0887 | 16.2979 | 17.0887 | 1
4559 | 3.1652 | 6.0098 | 5.3777 | 5.3933 | 3.5237 | 1.6066 | 16.1748 | 13.6732 | 16.1748 | 1
4560 | 3.5349 | 5.7008 | 5.8902 | 6.3866 | 4.6286 | 1.4806 | 17.1029 | 15.5343 | 17.1029 | 1
4561 | 3.3453 | 3.5957 | 6.1457 | 6.4914 | 5.0411 | 1.3463 | 14.7786 | 15.8783 | 15.8783 | 0
4562 | 5.1739 | 4.8389 | 6.5747 | 6.4029 | 3.3191 | 1.5823 | 17.998 | 16.65 | 17.998 | 1
4563 | 3.5287 | 5.496 | 4.6908 | 5.3864 | 4.0265 | 1.6234 | 16.0345 | 13.8694 | 16.0345 | 1
4564 | 3.646 | 4.8703 | 5.4944 | 6.1904 | 3.8351 | 2.038 | 16.7447 | 15.0135 | 16.7447 | 1
4565 | 3.4376 | 5.4193 | 6.041 | 4.978 | 5.1047 | 2.1476 | 15.9825 | 16.7309 | 16.7309 | 0
4566 | 4.235 | 6.465 | 7.0247 | 5.0165 | 4.3672 | 2.2523 | 17.9688 | 17.8792 | 17.9688 | 1
4567 | 3.5759 | 6.2621 | 4.1184 | 6.5749 | 5.3539 | 1.8496 | 18.2625 | 14.8979 | 18.2625 | 1
4568 | 3.6801 | 7.1382 | 5.9509 | 5.9771 | 4.0618 | 1.8457 | 18.641 | 15.5385 | 18.641 | 1
4569 | 2.489 | 6.0961 | 5.9846 | 5.5259 | 6.1458 | 2.1941 | 16.3051 | 16.8134 | 16.8134 | 0
4570 | 4.1619 | 4.0684 | 4.4551 | 5.1686 | 3.7781 | 1.598 | 14.997 | 13.9932 | 14.997 | 1
4571 | 4.2043 | 7.5705 | 5.2921 | 5.3977 | 3.2767 | 1.9747 | 19.1473 | 14.7477 | 19.1473 | 1
4572 | 4.5831 | 4.1595 | 5.0444 | 5.3941 | 4.3357 | 1.8846 | 16.0213 | 15.8478 | 16.0213 | 1
4573 | 3.1118 | 5.4768 | 6.684 | 5.7444 | 3.68 | 2.1063 | 16.4393 | 15.5821 | 16.4393 | 1
4574 | 3.943 | 5.491 | 6.3747 | 4.4419 | 4.1909 | 1.7785 | 15.6544 | 16.2871 | 16.2871 | 0
4575 | 4.4111 | 5.4721 | 4.3413 | 4.8396 | 5.2993 | 2.2276 | 16.9504 | 16.2794 | 16.9504 | 1
4576 | 5.5409 | 5.4335 | 6.4904 | 5.5362 | 4.0257 | 2.7377 | 19.2484 | 18.7947 | 19.2484 | 1
4577 | 2.8247 | 6.1888 | 5.1838 | 4.2269 | 4.5161 | 1.2318 | 14.4722 | 13.7564 | 14.4722 | 1
4578 | 4.8609 | 3.4054 | 4.1269 | 4.681 | 4.5796 | 1.5044 | 14.4517 | 15.0719 | 15.0719 | 0
4579 | 3.9476 | 6.6756 | 6.4335 | 4.8572 | 4.1595 | 2.0427 | 17.5231 | 16.5834 | 17.5231 | 1
4580 | 4.2143 | 4.0266 | 4.8932 | 6.0004 | 4.4435 | 1.8154 | 16.0567 | 15.3664 | 16.0567 | 1
4581 | 3.3567 | 3.2398 | 5.4223 | 5.0479 | 5.8203 | 1.7822 | 13.4267 | 16.3816 | 16.3816 | 0
4582 | 4.3181 | 3.8315 | 7.0035 | 5.371 | 6.2246 | 1.7652 | 15.2858 | 19.3114 | 19.3114 | 0
4583 | 3.5761 | 4.5528 | 7.1404 | 6.0969 | 3.7007 | 1.7745 | 16.0003 | 16.1917 | 16.1917 | 0
4584 | 4.7591 | 5.8896 | 4.5467 | 5.5154 | 5.5475 | 2.6316 | 18.7956 | 17.4849 | 18.7956 | 1
4585 | 5.0372 | 4.0831 | 5.7375 | 5.3056 | 3.878 | 1.4336 | 15.8595 | 16.0863 | 16.0863 | 0
4586 | 4.8381 | 5.1357 | 6.2257 | 4.5872 | 4.6117 | 2.3438 | 16.9049 | 18.0193 | 18.0193 | 0
4587 | 4.4119 | 4.4898 | 6.1639 | 4.3616 | 4.7035 | 1.7201 | 14.9835 | 16.9994 | 16.9994 | 0
4588 | 3.6877 | 6.2147 | 7.2196 | 5.8703 | 3.9024 | 2.1475 | 17.9202 | 16.9572 | 17.9202 | 1
4589 | 3.5424 | 3.9818 | 6.4127 | 5.5246 | 4.2376 | 2.4709 | 15.5197 | 16.6636 | 16.6636 | 0
4590 | 4.3314 | 4.5879 | 3.2747 | 4.7303 | 3.9763 | 2.8506 | 16.5001 | 14.433 | 16.5001 | 1
4591 | 3.7638 | 5.7603 | 6.1423 | 5.5098 | 4.4271 | 2.4517 | 17.4857 | 16.7849 | 17.4857 | 1
4592 | 3.1725 | 3.5458 | 5.4839 | 6.5799 | 3.5287 | 2.187 | 15.4852 | 14.3721 | 15.4852 | 1
4593 | 5.1234 | 5.0452 | 6.0862 | 6.0579 | 4.6902 | 1.9096 | 18.1362 | 17.8094 | 18.1362 | 1
4594 | 3.459 | 6.109 | 7.6472 | 4.5326 | 4.51 | 1.6613 | 15.7619 | 17.2775 | 17.2775 | 0
4595 | 3.2744 | 7.1762 | 5.147 | 6.5 | 3.2444 | 1.9786 | 18.9293 | 13.6445 | 18.9293 | 1
4596 | 2.4653 | 6.5117 | 4.9026 | 5.3741 | 5.6329 | 2.0182 | 16.3693 | 15.019 | 16.3693 | 1
4597 | 4.5564 | 7.7395 | 3.2744 | 5.7795 | 5.7541 | 1.2727 | 19.3481 | 14.8575 | 19.3481 | 1
4598 | 3.9842 | 4.4301 | 5.2288 | 4.68 | 4.2075 | 1.8798 | 14.9741 | 15.3004 | 15.3004 | 0
4599 | 3.6744 | 4.6035 | 6.0251 | 5.6522 | 4.8504 | 2.7637 | 16.6938 | 17.3136 | 17.3136 | 0
4600 | 3.2695 | 3.7951 | 4.5811 | 5.3377 | 4.0356 | 1.7692 | 14.1715 | 13.6553 | 14.1715 | 1
4601 | 4.8547 | 5.889 | 5.6946 | 6.1363 | 5.4658 | 1.4855 | 18.3655 | 17.5006 | 18.3655 | 1
4602 | 5.3833 | 7.769 | 6.0875 | 4.8181 | 4.4406 | 1.6112 | 19.5816 | 17.5225 | 19.5816 | 1
4603 | 4.3889 | 5.0652 | 4.0879 | 4.9274 | 5.3644 | 1.5442 | 15.9257 | 15.3854 | 15.9257 | 1
4604 | 5.1069 | 5.6007 | 6.9916 | 5.4144 | 4.1999 | 1.5732 | 17.6951 | 17.8716 | 17.8716 | 0
4605 | 4.2873 | 5.3675 | 4.8063 | 4.306 | 3.0827 | 2.5956 | 16.5563 | 14.7719 | 16.5563 | 1
4606 | 3.8445 | 4.6595 | 4.1914 | 5.4251 | 5.4583 | 2.0931 | 16.0222 | 15.5873 | 16.0222 | 1
4607 | 2.7521 | 5.7848 | 7.5241 | 5.4044 | 4.6519 | 2.0859 | 16.0272 | 17.0139 | 17.0139 | 0
4608 | 4.34 | 5.8704 | 5.673 | 4.7317 | 4.1559 | 2.1024 | 17.0445 | 16.2714 | 17.0445 | 1
4609 | 2.5534 | 5.146 | 6.035 | 6.2089 | 3.982 | 1.9914 | 15.8998 | 14.5619 | 15.8998 | 1
4610 | 3.8128 | 5.3704 | 5.8577 | 5.5291 | 4.3394 | 2.084 | 16.7963 | 16.0939 | 16.7963 | 1
4611 | 2.9433 | 5.5792 | 6.2399 | 4.4846 | 4.2153 | 2.7196 | 15.7266 | 16.1181 | 16.1181 | 0
4612 | 2.9273 | 6.6344 | 3.996 | 6.6396 | 5.1406 | 1.8732 | 18.0745 | 13.937 | 18.0745 | 1
4613 | 4.3139 | 5.3877 | 4.6766 | 5.4895 | 3.9526 | 2.3301 | 17.5212 | 15.2732 | 17.5212 | 1
4614 | 4.4829 | 5.727 | 6.4433 | 5.2365 | 4.3091 | 2.6252 | 18.0716 | 17.8605 | 18.0716 | 1
4615 | 2.7991 | 5.322 | 7.0055 | 5.0543 | 4.7029 | 1.7828 | 14.9582 | 16.2903 | 16.2903 | 0
4616 | 3.3112 | 4.0599 | 7.5184 | 4.6024 | 3.5352 | 2.1983 | 14.1717 | 16.5632 | 16.5632 | 0
4617 | 3.8795 | 5.5591 | 5.5054 | 4.1966 | 4.3448 | 2.8108 | 16.4459 | 16.5404 | 16.5404 | 0
4618 | 4.7683 | 3.5357 | 4.7418 | 5.5409 | 3.8982 | 1.8181 | 15.6629 | 15.2264 | 15.6629 | 1
4619 | 4.5095 | 5.4287 | 5.0196 | 5.227 | 4.1645 | 2.1608 | 17.326 | 15.8545 | 17.326 | 1
4620 | 3.8076 | 5.9994 | 4.253 | 4.5247 | 3.5796 | 2.5909 | 16.9226 | 14.2311 | 16.9226 | 1
4621 | 4.0567 | 6.6272 | 6.0986 | 5.5544 | 4.0798 | 1.8821 | 18.1205 | 16.1173 | 18.1205 | 1
4622 | 5.5004 | 6.372 | 6.9743 | 5.3059 | 5.4725 | 1.2909 | 18.4692 | 19.238 | 19.238 | 0
4623 | 5.1549 | 4.4185 | 5.4811 | 4.991 | 4.4898 | 2.0318 | 16.5962 | 17.1576 | 17.1576 | 0
4624 | 4.9294 | 4.902 | 7.2685 | 5.4007 | 5.2234 | 1.862 | 17.0941 | 19.2832 | 19.2832 | 0
4625 | 4.7465 | 5.1133 | 5.2127 | 4.3444 | 3.7422 | 1.9162 | 16.1203 | 15.6174 | 16.1203 | 1
4626 | 4.2671 | 4.8307 | 6.64 | 6.443 | 3.7721 | 1.8175 | 17.3582 | 16.4967 | 17.3582 | 1
4627 | 3.4778 | 5.6731 | 6.6056 | 6.2607 | 3.8654 | 2.4529 | 17.8645 | 16.4016 | 17.8645 | 1
4628 | 4.1441 | 4.6499 | 5.5635 | 6.6279 | 3.2393 | 2.2662 | 17.6881 | 15.2131 | 17.6881 | 1
4629 | 4.1304 | 5.1583 | 5.3034 | 5.6488 | 3.7065 | 2.212 | 17.1496 | 15.3522 | 17.1496 | 1
4630 | 2.5867 | 5.3283 | 6.6352 | 5.9766 | 4.1014 | 2.2775 | 16.1691 | 15.6008 | 16.1691 | 1
4631 | 2.8065 | 6.545 | 3.0193 | 4.5216 | 4.9292 | 2.3969 | 16.27 | 13.1519 | 16.27 | 1
4632 | 3.4291 | 5.186 | 4.257 | 5.0727 | 4.1172 | 1.4173 | 15.1052 | 13.2206 | 15.1052 | 1
4633 | 2.7651 | 4.4422 | 5.404 | 5.1307 | 5.9241 | 2.3155 | 14.6535 | 16.4088 | 16.4088 | 0
4634 | 4.0816 | 4.7576 | 7.0462 | 4.9081 | 4.8183 | 1.7897 | 15.537 | 17.7357 | 17.7357 | 0
4635 | 4.5258 | 3.7147 | 5.8909 | 4.5548 | 3.4445 | 2.4961 | 15.2915 | 16.3573 | 16.3573 | 0
4636 | 3.855 | 4.9927 | 5.6854 | 5.3456 | 3.9385 | 2.6662 | 16.8594 | 16.145 | 16.8594 | 1
4637 | 2.6355 | 6.1165 | 6.1741 | 5.2758 | 5.259 | 2.2183 | 16.2461 | 16.2869 | 16.2869 | 0
4638 | 4.2047 | 7.1776 | 5.1536 | 5.1717 | 3.9256 | 1.994 | 18.5481 | 15.2779 | 18.5481 | 1
4639 | 3.0963 | 3.4834 | 6.6447 | 4.968 | 3.6352 | 1.7982 | 13.346 | 15.1745 | 15.1745 | 0
4640 | 4.0169 | 6.3384 | 2.7964 | 5.2288 | 3.4195 | 2.2205 | 17.8046 | 12.4533 | 17.8046 | 1
4641 | 3.727 | 3.8507 | 4.5406 | 6.3335 | 3.5928 | 1.2002 | 15.1114 | 13.0605 | 15.1114 | 1
4642 | 3.4441 | 6.2568 | 6.6519 | 6.0652 | 4.797 | 2.5121 | 18.2781 | 17.4051 | 18.2781 | 1
4643 | 3.5886 | 3.7477 | 4.3142 | 5.0164 | 4.7822 | 2.0057 | 14.3583 | 14.6908 | 14.6908 | 0
4644 | 3.5024 | 4.3934 | 5.2294 | 6.9136 | 4.3353 | 2.0702 | 16.8795 | 15.1373 | 16.8795 | 1
4645 | 3.9269 | 6.4607 | 5.8302 | 5.499 | 3.5029 | 1.9771 | 17.8636 | 15.2371 | 17.8636 | 1
4646 | 4.4866 | 5.132 | 4.4845 | 4.9895 | 3.5594 | 1.3709 | 15.979 | 13.9013 | 15.979 | 1
4647 | 5.3449 | 5.2466 | 4.6527 | 5.3507 | 4.6024 | 1.9745 | 17.9167 | 16.5745 | 17.9167 | 1
4648 | 3.2603 | 5.76 | 5.1712 | 6.2011 | 3.3377 | 2.1256 | 17.347 | 13.8949 | 17.347 | 1
4649 | 3.4997 | 6.0765 | 5.98 | 5.8596 | 4.463 | 1.5676 | 17.0033 | 15.5103 | 17.0033 | 1
4650 | 4.255 | 5.5799 | 7.6234 | 5.6023 | 3.6213 | 1.6172 | 17.0543 | 17.1169 | 17.1169 | 0
4651 | 5.6459 | 4.9852 | 4.9952 | 6.1699 | 4.5281 | 2.3269 | 19.1281 | 17.4962 | 19.1281 | 1
4652 | 3.3879 | 6.0846 | 6.7823 | 5.7186 | 3.4872 | 1.5963 | 16.7875 | 15.2537 | 16.7875 | 1
4653 | 4.058 | 5.0488 | 6.3819 | 4.4624 | 3.9704 | 2.4334 | 16.0026 | 16.8437 | 16.8437 | 0
4654 | 4.164 | 6.7878 | 6.3047 | 4.3849 | 4.189 | 1.8784 | 17.2151 | 16.5361 | 17.2151 | 1
4655 | 5.4112 | 5.924 | 7.606 | 6.5702 | 4.1212 | 1.8592 | 19.7646 | 18.9976 | 19.7646 | 1
4656 | 4.0445 | 5.0047 | 5.0825 | 4.8833 | 3.1042 | 2.7685 | 16.701 | 14.9997 | 16.701 | 1
4657 | 3.1716 | 4.9053 | 5.9622 | 5.448 | 3.5199 | 1.5322 | 15.057 | 14.1859 | 15.057 | 1
4658 | 2.8398 | 4.4668 | 6.4346 | 5.7678 | 4.2655 | 2.5444 | 15.6188 | 16.0842 | 16.0842 | 0
4659 | 2.831 | 4.6216 | 4.9943 | 4.3902 | 5.3422 | 2.0361 | 13.879 | 15.2037 | 15.2037 | 0
4660 | 3.6439 | 3.5265 | 5.5862 | 5.5035 | 5.0934 | 1.9931 | 14.6671 | 16.3166 | 16.3166 | 0
4661 | 4.3846 | 3.47 | 6.2738 | 6.6762 | 4.9819 | 2.1176 | 16.6485 | 17.7579 | 17.7579 | 0
4662 | 3.9445 | 6.8459 | 5.056 | 6.3264 | 4.4289 | 1.4101 | 18.527 | 14.8395 | 18.527 | 1
4663 | 5.2362 | 6.4293 | 5.7872 | 6.0082 | 3.5867 | 1.5742 | 19.2479 | 16.1843 | 19.2479 | 1
4664 | 4.0917 | 5.8795 | 6.3993 | 5.3873 | 4.8898 | 1.7565 | 17.1151 | 17.1373 | 17.1373 | 0
4665 | 4.503 | 6.8679 | 4.4947 | 4.7925 | 3.4839 | 1.973 | 18.1364 | 14.4546 | 18.1364 | 1
4666 | 4.4795 | 4.7947 | 3.958 | 4.8527 | 3.6889 | 1.5363 | 15.6633 | 13.6627 | 15.6633 | 1
4667 | 3.4302 | 4.6702 | 7.5237 | 6.1915 | 3.6528 | 2.0864 | 16.3782 | 16.6931 | 16.6931 | 0
4668 | 3.9464 | 5.3076 | 6.6019 | 6.2655 | 5.1809 | 1.5737 | 17.0932 | 17.3029 | 17.3029 | 0
4669 | 3.7115 | 4.3455 | 4.4257 | 5.2778 | 5.125 | 1.7657 | 15.1005 | 15.0278 | 15.1005 | 1
4670 | 4.0132 | 8.0311 | 5.9618 | 4.5436 | 5.1718 | 1.9244 | 18.5123 | 17.0713 | 18.5123 | 1
4671 | 4.9529 | 3.7617 | 5.9584 | 5.4454 | 4.4737 | 2.1455 | 16.3054 | 17.5304 | 17.5304 | 0
4672 | 3.8819 | 6.6632 | 5.4891 | 6.6763 | 4.5248 | 1.8113 | 19.0327 | 15.7071 | 19.0327 | 1
4673 | 5.0607 | 4.0598 | 4.9622 | 5.6905 | 4.9123 | 1.733 | 16.544 | 16.6682 | 16.6682 | 0
4674 | 5.226 | 4.853 | 6.7495 | 4.8514 | 6.0546 | 2.4036 | 17.3339 | 20.4336 | 20.4336 | 0
4675 | 3.8758 | 6.8044 | 5.6799 | 4.7184 | 5.1425 | 1.7624 | 17.161 | 16.4606 | 17.161 | 1
4676 | 4.6064 | 5.9244 | 5.8363 | 5.8972 | 5.4194 | 2.4792 | 18.9072 | 18.3413 | 18.9072 | 1
4677 | 4.3696 | 5.2129 | 5.8319 | 5.0086 | 3.2652 | 2.2277 | 16.8187 | 15.6944 | 16.8187 | 1
4678 | 3.7724 | 5.3589 | 7.4868 | 5.5749 | 5.5491 | 1.7226 | 16.4288 | 18.5309 | 18.5309 | 0
4679 | 2.8373 | 6.1484 | 6.2194 | 5.7122 | 6.1903 | 2.4726 | 17.1705 | 17.7195 | 17.7195 | 0
4680 | 4.1357 | 5.1276 | 7.1637 | 5.6217 | 4.5147 | 1.7749 | 16.66 | 17.5891 | 17.5891 | 0
4681 | 3.9367 | 4.4198 | 5.5467 | 7.171 | 4.7279 | 2.2952 | 17.8227 | 16.5066 | 17.8227 | 1
4682 | 3.1057 | 4.2602 | 7.0753 | 4.2647 | 3.4936 | 2.4919 | 14.1225 | 16.1665 | 16.1665 | 0
4683 | 5.2969 | 5.3588 | 6.4522 | 5.2086 | 4.2443 | 1.6599 | 17.5242 | 17.6533 | 17.6533 | 0
4684 | 3.3566 | 4.4381 | 5.8968 | 5.8377 | 4.3319 | 2.5027 | 16.1351 | 16.088 | 16.1351 | 1
4685 | 4.1892 | 4.0553 | 6.0831 | 4.9668 | 4.84 | 1.6097 | 14.821 | 16.722 | 16.722 | 0
4686 | 2.8904 | 4.0585 | 5.5956 | 4.2906 | 5.1024 | 1.9093 | 13.1488 | 15.4977 | 15.4977 | 0
4687 | 2.8741 | 5.198 | 7.5202 | 6.3641 | 4.2407 | 1.9698 | 16.406 | 16.6048 | 16.6048 | 0
4688 | 3.7411 | 4.3343 | 2.6303 | 4.8748 | 3.6912 | 1.9851 | 14.9352 | 12.0477 | 14.9352 | 1
4689 | 4.5474 | 4.6877 | 6.9694 | 4.9842 | 4.4319 | 2.6031 | 16.8225 | 18.5519 | 18.5519 | 0
4690 | 3.6847 | 4.3554 | 5.3917 | 5.5234 | 4.2132 | 2.5473 | 16.1108 | 15.8369 | 16.1108 | 1
4691 | 3.7921 | 4.321 | 4.9693 | 6.4534 | 4.498 | 2.3466 | 16.9131 | 15.606 | 16.9131 | 1
4692 | 3.1034 | 4.3689 | 6.1469 | 4.9747 | 4.6323 | 2.36 | 14.8071 | 16.2426 | 16.2426 | 0
4693 | 4.4899 | 5.9935 | 6.2911 | 5.8521 | 4.4746 | 1.5559 | 17.8913 | 16.8114 | 17.8913 | 1
4694 | 2.6044 | 6.0414 | 5.1921 | 6.9777 | 5.3273 | 2.4963 | 18.1198 | 15.62 | 18.1198 | 1
4695 | 4.7027 | 3.77 | 6.1082 | 7.1186 | 4.1796 | 1.4025 | 16.9937 | 16.393 | 16.9937 | 1
4696 | 3.244 | 3.2735 | 3.0147 | 4.6158 | 5.0158 | 1.9538 | 13.0871 | 13.2283 | 13.2283 | 0
4697 | 4.3716 | 6.528 | 6.5729 | 5.3511 | 4.0283 | 2.0952 | 18.3458 | 17.068 | 18.3458 | 1
4698 | 5.195 | 7.0022 | 5.5831 | 4.7825 | 4.8281 | 2.458 | 19.4377 | 18.0642 | 19.4377 | 1
4699 | 5.0775 | 4.0486 | 7.3933 | 4.7646 | 4.6212 | 1.9121 | 15.8028 | 19.0041 | 19.0041 | 0
4700 | 3.4518 | 6.8981 | 4.2996 | 5.3243 | 5.6865 | 2.3073 | 17.9815 | 15.7452 | 17.9815 | 1
4701 | 3.2013 | 5.1935 | 5.0064 | 5.7185 | 3.2169 | 2.509 | 16.6224 | 13.9337 | 16.6224 | 1
4702 | 3.6805 | 5.5878 | 7.7827 | 6.3164 | 4.7131 | 2.587 | 18.1716 | 18.7633 | 18.7633 | 0
4703 | 4.7094 | 5.3629 | 5.0652 | 4.319 | 3.9034 | 1.4775 | 15.8687 | 15.1554 | 15.8687 | 1
4704 | 4.676 | 5.8216 | 6.1855 | 4.6016 | 5.0548 | 1.4075 | 16.5067 | 17.3237 | 17.3237 | 0
4705 | 3.5021 | 7.3694 | 6.2627 | 4.7479 | 4.3231 | 1.9614 | 17.5809 | 16.0493 | 17.5809 | 1
4706 | 2.9777 | 5.5315 | 4.5842 | 4.7263 | 4.1763 | 2.3883 | 15.6238 | 14.1266 | 15.6238 | 1
4707 | 4.2113 | 4.0905 | 3.2524 | 5.0135 | 3.1797 | 2.2553 | 15.5707 | 12.8987 | 15.5707 | 1
4708 | 4.0171 | 4.8759 | 6.5249 | 6.0671 | 4.2655 | 2.3824 | 17.3424 | 17.1899 | 17.3424 | 1
4709 | 4.7847 | 4.3849 | 6.2571 | 6.1734 | 5.3351 | 1.4463 | 16.7893 | 17.8231 | 17.8231 | 0
4710 | 4.5263 | 5.4694 | 4.0652 | 4.8603 | 3.2324 | 2.321 | 17.177 | 14.1449 | 17.177 | 1
4711 | 3.2998 | 4.8518 | 4.9268 | 6.0987 | 4.093 | 1.7588 | 16.0091 | 14.0785 | 16.0091 | 1
4712 | 3.5076 | 7.157 | 6.0803 | 6.77 | 3.5395 | 1.4996 | 18.9342 | 14.6271 | 18.9342 | 1
4713 | 4.5208 | 5.8983 | 6.6968 | 5.624 | 3.5045 | 1.6591 | 17.7022 | 16.3812 | 17.7022 | 1
4714 | 3.6652 | 4.0874 | 6.6066 | 4.8251 | 3.4009 | 2.2348 | 14.8126 | 15.9075 | 15.9075 | 0
4715 | 4.545 | 5.0502 | 4.3873 | 6.4394 | 3.2141 | 2.1582 | 18.1928 | 14.3047 | 18.1928 | 1
4716 | 2.8442 | 6.6131 | 6.7428 | 6.1734 | 3.7896 | 1.7129 | 17.3436 | 15.0895 | 17.3436 | 1
4717 | 3.105 | 6.6313 | 6.5006 | 6.6379 | 5.1472 | 1.9045 | 18.2786 | 16.6573 | 18.2786 | 1
4718 | 4.9922 | 7.1214 | 6.3343 | 4.4094 | 4.6434 | 1.9345 | 18.4573 | 17.9044 | 18.4573 | 1
4719 | 3.0293 | 4.0195 | 6.7322 | 4.2314 | 3.4377 | 2.0297 | 13.31 | 15.229 | 15.229 | 0
4720 | 3.8945 | 5.0291 | 6.3771 | 4.3457 | 3.5389 | 1.6871 | 14.9564 | 15.4976 | 15.4976 | 0
4721 | 3.7602 | 4.6886 | 5.5549 | 5.3511 | 5.0065 | 2.4811 | 16.281 | 16.8026 | 16.8026 | 0
4722 | 4.8639 | 7.6782 | 6.1086 | 5.2304 | 4.4278 | 1.5917 | 19.3643 | 16.9922 | 19.3643 | 1
4723 | 5.5181 | 5.4304 | 6.9318 | 5.6403 | 5.4935 | 2.7891 | 19.378 | 20.7325 | 20.7325 | 0
4724 | 2.3072 | 4.4541 | 4.6982 | 5.8983 | 3.7382 | 2.5293 | 15.1889 | 13.273 | 15.1889 | 1
4725 | 3.9108 | 4.6331 | 6.2836 | 4.9917 | 3.2284 | 2.4962 | 16.0319 | 15.9191 | 16.0319 | 1
4726 | 2.7667 | 6.5174 | 5.4012 | 5.1121 | 4.3392 | 1.3685 | 15.7647 | 13.8756 | 15.7647 | 1
4727 | 3.5993 | 3.9081 | 6.9832 | 6.2159 | 5.6255 | 1.5882 | 15.3115 | 17.7963 | 17.7963 | 0
4728 | 4.2211 | 6.638 | 5.3902 | 5.4029 | 4.2682 | 2.0772 | 18.3392 | 15.9567 | 18.3392 | 1
4729 | 5.2675 | 4.7962 | 7.0319 | 5.5973 | 3.4323 | 2.1907 | 17.8518 | 17.9224 | 17.9224 | 0
4730 | 4.2834 | 5.6078 | 6.7422 | 4.7719 | 4.7177 | 1.1693 | 15.8324 | 16.9126 | 16.9126 | 0
4731 | 4.4959 | 6.1739 | 6.1845 | 5.7198 | 4.1551 | 2.4013 | 18.7909 | 17.2369 | 18.7909 | 1
4732 | 3.9921 | 6.4179 | 6.1093 | 4.9597 | 4.2381 | 1.9959 | 17.3656 | 16.3355 | 17.3656 | 1
4733 | 5.1618 | 4.6283 | 4.8855 | 5.7776 | 4.4647 | 2.0695 | 17.6371 | 16.5813 | 17.6371 | 1
4734 | 4.4227 | 4.0831 | 6.6252 | 4.8757 | 3.8176 | 2.0872 | 15.4687 | 16.9527 | 16.9527 | 0
4735 | 4.6303 | 4.0527 | 5.7357 | 5.6154 | 5.3886 | 1.9309 | 16.2293 | 17.6854 | 17.6854 | 0
4736 | 3.976 | 5.0597 | 7.3743 | 4.1365 | 4.2968 | 2.5732 | 15.7455 | 18.2203 | 18.2203 | 0
4737 | 2.8602 | 5.2653 | 5.5787 | 5.3808 | 4.4274 | 1.8536 | 15.3599 | 14.7199 | 15.3599 | 1
4738 | 3.8233 | 6.3028 | 6.4377 | 4.7478 | 5.1348 | 2.3404 | 17.2143 | 17.7362 | 17.7362 | 0
4739 | 4.2456 | 5.4665 | 5.9048 | 6.1432 | 3.7887 | 1.9165 | 17.7718 | 15.8556 | 17.7718 | 1
4740 | 3.6235 | 6.1223 | 6.7728 | 4.8858 | 3.541 | 2.8152 | 17.4468 | 16.7525 | 17.4468 | 1
4741 | 5.1591 | 5.9384 | 5.5958 | 5.1957 | 3.0142 | 1.9828 | 18.2761 | 15.752 | 18.2761 | 1
4742 | 5.5863 | 6.0106 | 5.0292 | 5.1209 | 4.6016 | 1.7753 | 18.4932 | 16.9924 | 18.4932 | 1
4743 | 5.2052 | 5.9146 | 7.5704 | 6.1629 | 3.8227 | 2.0794 | 19.362 | 18.6777 | 19.362 | 1
4744 | 3.6516 | 4.3398 | 6.2513 | 4.6394 | 4.2844 | 1.8091 | 14.44 | 15.9965 | 15.9965 | 0
4745 | 4.6177 | 6.3467 | 6.0291 | 4.6166 | 4.0685 | 2.0747 | 17.6557 | 16.7899 | 17.6557 | 1
4746 | 3.8418 | 7.0362 | 6.7781 | 4.2778 | 3.9925 | 2.2433 | 17.3992 | 16.8557 | 17.3992 | 1
4747 | 4.4729 | 6.4653 | 5.9808 | 5.2007 | 4.5591 | 1.902 | 18.0409 | 16.9148 | 18.0409 | 1
4748 | 5.0727 | 5.0891 | 4.509 | 5.6607 | 4.377 | 1.9279 | 17.7504 | 15.8867 | 17.7504 | 1
4749 | 3.2964 | 5.4441 | 7.5825 | 6.0294 | 4.5397 | 2.4005 | 17.1704 | 17.8191 | 17.8191 | 0
4750 | 3.6619 | 3.868 | 4.302 | 6.0672 | 4.2357 | 1.3177 | 14.9147 | 13.5172 | 14.9147 | 1
4751 | 4.6313 | 5.1056 | 3.1242 | 5.5355 | 4.7708 | 2.0737 | 17.3461 | 14.6 | 17.3461 | 1
4752 | 4.1822 | 8.3317 | 5.8575 | 5.4848 | 4.4073 | 1.6372 | 19.6359 | 16.0841 | 19.6359 | 1
4753 | 3.1777 | 6.6461 | 5.1059 | 4.5506 | 4.1019 | 1.8957 | 16.2701 | 14.2811 | 16.2701 | 1
4754 | 4.1601 | 4.562 | 6.2521 | 6.0796 | 4.5549 | 2.0803 | 16.882 | 17.0474 | 17.0474 | 0
4755 | 5.1336 | 4.0968 | 7.0219 | 4.8806 | 5.1526 | 2.8287 | 16.9396 | 20.1368 | 20.1368 | 0
4756 | 4.7732 | 6.6886 | 4.6225 | 5.1433 | 3.7943 | 1.8827 | 18.4878 | 15.0728 | 18.4878 | 1
4757 | 3.8243 | 5.2374 | 6.3518 | 4.868 | 3.9181 | 2.0371 | 15.9668 | 16.1313 | 16.1313 | 0
4758 | 4.1845 | 7.2496 | 4.4951 | 5.536 | 3.6693 | 2.3523 | 19.3225 | 14.7013 | 19.3225 | 1
4759 | 3.9916 | 4.8779 | 5.8814 | 5.8499 | 3.4308 | 2.1014 | 16.8207 | 15.4052 | 16.8207 | 1
4760 | 4.0701 | 4.1522 | 4.3754 | 4.3549 | 4.6933 | 1.6832 | 14.2604 | 14.8219 | 14.8219 | 0
4761 | 4.3591 | 6.4059 | 7.1239 | 5.7471 | 5.5887 | 2.0441 | 18.5562 | 19.1158 | 19.1158 | 0
4762 | 3.3442 | 5.9526 | 6.1722 | 6.5033 | 3.4954 | 2.162 | 17.9622 | 15.1738 | 17.9622 | 1
4763 | 3.7302 | 4.8382 | 4.9161 | 4.1892 | 5.3544 | 2.7617 | 15.5193 | 16.7623 | 16.7623 | 0
4764 | 3.7547 | 6.1083 | 6.186 | 4.2549 | 3.6552 | 1.7546 | 15.8726 | 15.3506 | 15.8726 | 1
4765 | 4.8809 | 4.5009 | 6.4589 | 4.8694 | 3.6676 | 2.1803 | 16.4315 | 17.1877 | 17.1877 | 0
4766 | 3.749 | 6.7711 | 3.9793 | 5.4983 | 4.0589 | 1.6721 | 17.6904 | 13.4593 | 17.6904 | 1
4767 | 4.7283 | 4.1854 | 6.1345 | 5.9633 | 3.2219 | 2.3321 | 17.2091 | 16.4168 | 17.2091 | 1
4768 | 3.7518 | 4.1663 | 5.5068 | 6.5989 | 4.4743 | 2.0708 | 16.5878 | 15.8036 | 16.5878 | 1
4769 | 4.955 | 5.5057 | 4.4078 | 4.6087 | 4.3391 | 1.8213 | 16.8908 | 15.5232 | 16.8908 | 1
4770 | 4.8985 | 3.5196 | 7.642 | 5.2848 | 3.9301 | 2.24 | 15.9429 | 18.7106 | 18.7106 | 0
4771 | 4.4769 | 6.7737 | 6.8321 | 6.8718 | 3.4139 | 2.3003 | 20.4227 | 17.0233 | 20.4227 | 1
4772 | 4.6599 | 4.3038 | 7.0827 | 5.1429 | 3.7314 | 1.6499 | 15.7565 | 17.1239 | 17.1239 | 0
4773 | 3.3953 | 5.5179 | 6.2754 | 4.4422 | 4.7244 | 2.24 | 15.5954 | 16.6352 | 16.6352 | 0
4774 | 4.2713 | 6.8833 | 4.522 | 5.7988 | 4.4124 | 2.3548 | 19.3082 | 15.5604 | 19.3082 | 1
4775 | 4.5095 | 4.7277 | 3.9608 | 5.6769 | 4.685 | 2.3283 | 17.2424 | 15.4836 | 17.2424 | 1
4776 | 4.4526 | 5.3209 | 5.1334 | 5.8262 | 4.1869 | 2.464 | 18.0636 | 16.2369 | 18.0636 | 1
4777 | 4.5066 | 5.946 | 6.6175 | 5.3632 | 4.7481 | 2.0314 | 17.8472 | 17.9036 | 17.9036 | 0
4778 | 2.8278 | 3.923 | 6.266 | 4.4733 | 4.9253 | 2.456 | 13.6802 | 16.4752 | 16.4752 | 0
4779 | 4.6905 | 6.3492 | 5.0812 | 5.0009 | 5.025 | 1.2153 | 17.2558 | 16.0119 | 17.2558 | 1
4780 | 3.8747 | 7.5081 | 6.1546 | 5.7831 | 3.8308 | 1.3636 | 18.5295 | 15.2237 | 18.5295 | 1
4781 | 2.737 | 5.8098 | 4.3862 | 5.0986 | 5.8374 | 1.8763 | 15.5218 | 14.837 | 15.5218 | 1
4782 | 2.5893 | 7.2326 | 6.1638 | 4.5788 | 3.8218 | 1.9092 | 16.3098 | 14.484 | 16.3098 | 1
4783 | 3.1503 | 4.2203 | 7.4867 | 4.5324 | 5.1834 | 2.1269 | 14.0299 | 17.9473 | 17.9473 | 0
4784 | 3.3168 | 5.6276 | 5.937 | 4.8093 | 3.6657 | 2.14 | 15.8937 | 15.0595 | 15.8937 | 1
4785 | 5.4356 | 7.3248 | 4.1682 | 4.908 | 4.277 | 1.9978 | 19.6661 | 15.8785 | 19.6661 | 1
4786 | 3.4414 | 5.5411 | 5.8509 | 5.3659 | 3.904 | 1.7309 | 16.0792 | 14.9272 | 16.0792 | 1
4787 | 5.4225 | 3.715 | 6.7129 | 6.0177 | 3.8001 | 2.4597 | 17.6148 | 18.3952 | 18.3952 | 0
4788 | 4.7008 | 7.3504 | 6.006 | 5.0197 | 3.1418 | 2.1657 | 19.2366 | 16.0142 | 19.2366 | 1
4789 | 2.8962 | 7.1494 | 5.2009 | 4.4623 | 4.9588 | 1.6992 | 16.207 | 14.755 | 16.207 | 1
4790 | 2.8958 | 6.1172 | 6.6041 | 4.7684 | 4.0335 | 2.0645 | 15.8459 | 15.5979 | 15.8459 | 1
4791 | 3.7884 | 5.2191 | 4.4159 | 6.2965 | 4.9031 | 1.8477 | 17.1517 | 14.9551 | 17.1517 | 1
4792 | 5.1376 | 5.4407 | 4.2033 | 6.1127 | 4.6545 | 2.6031 | 19.2941 | 16.5984 | 19.2941 | 1
4793 | 3.1024 | 4.376 | 4.7903 | 5.5377 | 5.4482 | 2.8785 | 15.8947 | 16.2193 | 16.2193 | 0
4794 | 3.6969 | 7.4396 | 7.7821 | 4.6378 | 4.1542 | 1.7886 | 17.5629 | 17.4218 | 17.5629 | 1
4795 | 4.033 | 6.3575 | 2.9895 | 5.9906 | 4.1245 | 1.3995 | 17.7805 | 12.5465 | 17.7805 | 1
4796 | 4.0952 | 5.208 | 3.5533 | 5.284 | 4.0233 | 2.7663 | 17.3534 | 14.4381 | 17.3534 | 1
4797 | 4.1499 | 6.2338 | 6.2944 | 5.1997 | 3.3817 | 2.2463 | 17.8297 | 16.0723 | 17.8297 | 1
4798 | 4.4801 | 6.0674 | 5.2725 | 4.3993 | 4.5432 | 1.4428 | 16.3897 | 15.7386 | 16.3897 | 1
4799 | 5.0197 | 3.7182 | 3.4892 | 4.8173 | 3.6966 | 2.0119 | 15.5671 | 14.2174 | 15.5671 | 1
4800 | 3.9911 | 7.0752 | 4.8036 | 4.2688 | 4.8743 | 2.4014 | 17.7365 | 16.0705 | 17.7365 | 1
4801 | 4.641 | 4.7049 | 6.3401 | 6.1625 | 4.7325 | 2.0261 | 17.5345 | 17.7397 | 17.7397 | 0
4802 | 4.0264 | 4.5436 | 5.5096 | 6.3412 | 4.152 | 2.7753 | 17.6865 | 16.4633 | 17.6865 | 1
4803 | 5.4915 | 6.0334 | 4.3072 | 4.9349 | 3.7226 | 1.3022 | 17.762 | 14.8235 | 17.762 | 1
4804 | 3.9182 | 5.5981 | 5.5673 | 5.406 | 4.8875 | 2.0336 | 16.9559 | 16.4067 | 16.9559 | 1
4805 | 3.0421 | 3.993 | 6.2029 | 4.998 | 4.7089 | 1.704 | 13.7371 | 15.6579 | 15.6579 | 0
4806 | 3.6429 | 5.4417 | 5.8393 | 5.2488 | 3.7911 | 1.7935 | 16.1268 | 15.0668 | 16.1268 | 1
4807 | 4.1522 | 4.8825 | 4.7 | 4.5963 | 4.4336 | 1.8037 | 15.4347 | 15.0894 | 15.4347 | 1
4808 | 3.8314 | 6.2527 | 6.3545 | 4.7711 | 5.2355 | 1.544 | 16.3993 | 16.9655 | 16.9655 | 0
4809 | 3.1647 | 4.3493 | 4.634 | 5.2205 | 3.4918 | 1.9689 | 14.7034 | 13.2594 | 14.7034 | 1
4810 | 4.1103 | 5.5447 | 5.5072 | 4.7061 | 3.3812 | 1.9835 | 16.3447 | 14.9822 | 16.3447 | 1
4811 | 4.0761 | 4.933 | 4.7691 | 5.4179 | 3.8658 | 2.5017 | 16.9288 | 15.2128 | 16.9288 | 1
4812 | 3.2389 | 5.3294 | 5.1082 | 5.8283 | 3.5355 | 1.9218 | 16.3184 | 13.8044 | 16.3184 | 1
4813 | 3.392 | 7.1538 | 4.241 | 6.2409 | 4.2535 | 1.9574 | 18.7441 | 13.8439 | 18.7441 | 1
4814 | 3.8178 | 5.1942 | 6.1533 | 4.4633 | 4.3048 | 1.7366 | 15.212 | 16.0125 | 16.0125 | 0
4815 | 3.6681 | 6.2869 | 7.0925 | 6.3943 | 4.2107 | 2.487 | 18.8363 | 17.4584 | 18.8363 | 1
4816 | 4.5029 | 5.1614 | 5.9478 | 5.496 | 3.4424 | 1.7685 | 16.9288 | 15.6616 | 16.9288 | 1
4817 | 4.9795 | 5.6406 | 4.2979 | 6.3179 | 4.5166 | 2.0966 | 19.0345 | 15.8906 | 19.0345 | 1
4818 | 3.2024 | 6.8273 | 4.8386 | 4.4373 | 5.1492 | 1.909 | 16.3759 | 15.0991 | 16.3759 | 1
4819 | 5.3872 | 4.6879 | 4.2906 | 5.0305 | 5.1696 | 1.8183 | 16.9239 | 16.6657 | 16.9239 | 1
4820 | 4.0655 | 3.9428 | 3.5596 | 5.7558 | 3.3867 | 1.6271 | 15.3912 | 12.6389 | 15.3912 | 1
4821 | 4.5357 | 4.9964 | 6.2267 | 5.2366 | 4.4548 | 2.6912 | 17.4599 | 17.9085 | 17.9085 | 0
4822 | 2.5049 | 6.7612 | 5.211 | 5.2239 | 3.7833 | 2.1794 | 16.6694 | 13.6786 | 16.6694 | 1
4823 | 4.1514 | 5.745 | 4.8615 | 5.276 | 4.3342 | 2.4353 | 17.6077 | 15.7824 | 17.6077 | 1
4824 | 4.547 | 4.6586 | 5.781 | 5.8556 | 4.126 | 1.5404 | 16.6017 | 15.9945 | 16.6017 | 1
4825 | 3.4684 | 5.4333 | 4.4344 | 6.9393 | 5.1328 | 1.7879 | 17.6289 | 14.8235 | 17.6289 | 1
4826 | 3.334 | 3.6405 | 6.6838 | 5.9813 | 4.7264 | 1.6036 | 14.5595 | 16.3477 | 16.3477 | 0
4827 | 3.9198 | 4.1311 | 4.5517 | 5.1377 | 3.5723 | 1.7943 | 14.9828 | 13.8381 | 14.9828 | 1
4828 | 4.9459 | 5.2165 | 5.8505 | 4.1624 | 3.7978 | 1.6694 | 15.9942 | 16.2635 | 16.2635 | 0
4829 | 3.1114 | 4.864 | 5.2738 | 4.8782 | 4.7213 | 2.1835 | 15.0372 | 15.29 | 15.29 | 0
4830 | 3.3524 | 5.0511 | 5.516 | 4.9419 | 4.5897 | 2.4016 | 15.7469 | 15.8597 | 15.8597 | 0
4831 | 4.7455 | 4.1637 | 4.6548 | 5.7118 | 5.5516 | 2.1548 | 16.7759 | 17.1068 | 17.1068 | 0
4832 | 4.6051 | 5.6338 | 7.0631 | 7.2219 | 3.7631 | 1.5932 | 19.054 | 17.0245 | 19.054 | 1
4833 | 4.2384 | 3.5339 | 4.9539 | 4.9642 | 4.5121 | 2.2059 | 14.9424 | 15.9103 | 15.9103 | 0
4834 | 4.7975 | 5.3023 | 3.3554 | 5.3877 | 4.9279 | 1.3991 | 16.8865 | 14.4799 | 16.8865 | 1
4835 | 4.9182 | 5.3477 | 7.4808 | 4.7975 | 5.0575 | 1.259 | 16.3224 | 18.7155 | 18.7155 | 0
4836 | 5.091 | 4.0975 | 5.887 | 5.6701 | 5.0088 | 2.0779 | 16.9365 | 18.0646 | 18.0646 | 0
4837 | 4.5723 | 5.4724 | 6.4144 | 4.2543 | 4.1111 | 1.7985 | 16.0976 | 16.8962 | 16.8962 | 0
4838 | 3.8811 | 5.5433 | 2.5922 | 4.4397 | 4.1399 | 1.4673 | 15.3314 | 12.0805 | 15.3314 | 1
4839 | 4.5099 | 5.2132 | 4.9872 | 5.4752 | 3.6219 | 2.6937 | 17.892 | 15.8126 | 17.892 | 1
4840 | 3.9698 | 8.0809 | 5.4251 | 4.8066 | 5.481 | 1.9143 | 18.7716 | 16.7902 | 18.7716 | 1
4841 | 3.4412 | 5.2907 | 4.4643 | 5.0456 | 4.515 | 2.0473 | 15.8248 | 14.4677 | 15.8248 | 1
4842 | 3.2031 | 4.3603 | 5.1294 | 6.8275 | 4.1569 | 2.2982 | 16.689 | 14.7876 | 16.689 | 1
4843 | 4.2369 | 3.6469 | 5.4211 | 6.1534 | 5.1975 | 2.2943 | 16.3316 | 17.15 | 17.15 | 0
4844 | 4.1589 | 4.2706 | 4.9419 | 4.9497 | 5.4873 | 2.435 | 15.8141 | 17.0231 | 17.0231 | 0
4845 | 4.7566 | 4.8654 | 4.9876 | 6.4441 | 4.0799 | 2.7211 | 18.7873 | 16.5453 | 18.7873 | 1
4846 | 2.9606 | 6.7955 | 6.3248 | 5.5814 | 4.079 | 2.742 | 18.0796 | 16.1064 | 18.0796 | 1
4847 | 4.7111 | 5.4798 | 3.6606 | 6.9045 | 3.7655 | 1.5451 | 18.6405 | 13.6824 | 18.6405 | 1
4848 | 4.4574 | 6.5698 | 4.9506 | 6.8906 | 4.4624 | 1.7395 | 19.6573 | 15.6099 | 19.6573 | 1
4849 | 3.5917 | 4.5886 | 6.1196 | 5.4778 | 3.7071 | 2.7813 | 16.4394 | 16.1997 | 16.4394 | 1
4850 | 3.005 | 4.4789 | 4.7729 | 4.5035 | 5.5173 | 1.4158 | 13.4033 | 14.711 | 14.711 | 0
4851 | 2.257 | 3.7006 | 3.3408 | 5.319 | 4.168 | 1.6583 | 12.9349 | 11.4241 | 12.9349 | 1
4852 | 4.3521 | 4.8655 | 6.1406 | 6.2161 | 3.6481 | 1.8732 | 17.3069 | 16.014 | 17.3069 | 1
4853 | 3.6204 | 5.6796 | 4.44 | 5.3238 | 3.4633 | 2.442 | 17.0658 | 13.9657 | 17.0658 | 1
4854 | 3.1931 | 5.6566 | 5.8998 | 4.9942 | 3.2604 | 1.983 | 15.8269 | 14.3363 | 15.8269 | 1
4855 | 5.4721 | 4.6629 | 4.8518 | 6.389 | 4.8597 | 1.6075 | 18.1315 | 16.7911 | 18.1315 | 1
4856 | 3.1478 | 4.646 | 6.6736 | 6.3983 | 3.7201 | 1.402 | 15.594 | 14.9434 | 15.594 | 1
4857 | 4.9268 | 4.8423 | 6.3529 | 4.8068 | 3.3627 | 1.298 | 15.8738 | 15.9404 | 15.9404 | 0
4858 | 5.0016 | 4.1417 | 6.1026 | 6.3752 | 4.2293 | 1.8495 | 17.3681 | 17.183 | 17.3681 | 1
4859 | 5.2237 | 7.1986 | 6.3008 | 5.1668 | 4.256 | 2.5564 | 20.1455 | 18.337 | 20.1455 | 1
4860 | 2.9009 | 4.6128 | 5.9577 | 5.0276 | 3.5323 | 1.413 | 13.9543 | 13.8038 | 13.9543 | 1
4861 | 4.9145 | 5.6226 | 5.089 | 5.7976 | 5.0339 | 2.7573 | 19.092 | 17.7947 | 19.092 | 1
4862 | 4.4504 | 4.3128 | 6.8685 | 5.1185 | 4.7743 | 1.7745 | 15.6562 | 17.8677 | 17.8677 | 0
4863 | 3.7586 | 5.1789 | 4.078 | 5.1774 | 3.9386 | 2.3672 | 16.4821 | 14.1425 | 16.4821 | 1
4864 | 4.8721 | 4.9748 | 4.3581 | 4.8934 | 4.0745 | 1.4966 | 16.2368 | 14.8013 | 16.2368 | 1
4865 | 3.5065 | 4.2867 | 6.1139 | 6.499 | 5.2171 | 2.1587 | 16.4508 | 16.9961 | 16.9961 | 0
4866 | 3.8807 | 5.4915 | 6.7767 | 5.108 | 5.1963 | 1.4708 | 15.951 | 17.3247 | 17.3247 | 0
4867 | 4.0936 | 3.9356 | 3.483 | 5.383 | 4.3444 | 1.7206 | 15.1328 | 13.6416 | 15.1328 | 1
4868 | 4.2948 | 4.5485 | 6.4044 | 6.0036 | 4.39 | 2.0784 | 16.9253 | 17.1676 | 17.1676 | 0
4869 | 4.7332 | 6.8244 | 4.9618 | 5.342 | 5.6367 | 2.0537 | 18.9533 | 17.3855 | 18.9533 | 1
4870 | 3.2457 | 5.8119 | 5.2216 | 5.2054 | 4.5342 | 1.5879 | 15.851 | 14.5895 | 15.851 | 1
4871 | 4.082 | 5.6283 | 5.5638 | 4.6607 | 3.4605 | 1.8511 | 16.2221 | 14.9574 | 16.2221 | 1
4872 | 4.3583 | 4.1188 | 5.2838 | 6.056 | 3.4515 | 1.7657 | 16.2989 | 14.8594 | 16.2989 | 1
4873 | 3.6827 | 5.5979 | 6.9583 | 5.9109 | 3.4257 | 2.0737 | 17.2652 | 16.1405 | 17.2652 | 1
4874 | 2.8834 | 7.3615 | 3.2076 | 4.6431 | 4.4134 | 2.3891 | 17.2771 | 12.8935 | 17.2771 | 1
4875 | 3.3604 | 4.3444 | 7.0275 | 4.8759 | 3.9898 | 1.8073 | 14.3879 | 16.1849 | 16.1849 | 0
4876 | 4.1033 | 7.7022 | 6.994 | 4.3251 | 4.0139 | 2.2028 | 18.3334 | 17.3139 | 18.3334 | 1
4877 | 4.0021 | 7.3682 | 5.951 | 4.4072 | 4.826 | 1.5758 | 17.3534 | 16.3549 | 17.3534 | 1
4878 | 4.4323 | 4.8241 | 4.9775 | 4.8732 | 3.6892 | 2.2844 | 16.4141 | 15.3835 | 16.4141 | 1
4879 | 4.3662 | 4.4433 | 4.9733 | 4.4887 | 3.5377 | 2.1219 | 15.4201 | 14.999 | 15.4201 | 1
4880 | 3.7281 | 6.1436 | 6.9301 | 5.927 | 4.2132 | 2.8842 | 18.6828 | 17.7555 | 18.6828 | 1
4881 | 4.6283 | 6.3452 | 7.5852 | 4.7934 | 3.6999 | 2.4625 | 18.2294 | 18.3758 | 18.3758 | 0
4882 | 3.8389 | 4.6311 | 6.0311 | 5.5322 | 3.8748 | 2.0718 | 16.0739 | 15.8166 | 16.0739 | 1
4883 | 4.1258 | 4.8225 | 5.5897 | 6.0537 | 5.2522 | 2.6978 | 17.6998 | 17.6655 | 17.6998 | 1
4884 | 3.994 | 4.7659 | 4.6504 | 4.3529 | 5.3238 | 1.5683 | 14.6811 | 15.5365 | 15.5365 | 0
4885 | 5.206 | 4.6798 | 6.1931 | 4.9509 | 4.8111 | 2.7583 | 17.595 | 18.9685 | 18.9685 | 0
4886 | 2.885 | 6.9858 | 6.9053 | 5.6149 | 3.9177 | 1.6507 | 17.1364 | 15.3587 | 17.1364 | 1
4887 | 3.562 | 5.7814 | 4.6482 | 6.161 | 3.9353 | 2.6352 | 18.1395 | 14.7807 | 18.1395 | 1
4888 | 3.6321 | 5.2784 | 7.5389 | 5.4094 | 4.5344 | 1.6369 | 15.9568 | 17.3422 | 17.3422 | 0
4889 | 4.9254 | 6.5621 | 4.9111 | 4.7985 | 3.9247 | 1.8784 | 18.1644 | 15.6396 | 18.1644 | 1
4890 | 4.5329 | 4.5952 | 7.5755 | 4.477 | 4.3097 | 2.053 | 15.6582 | 18.4711 | 18.4711 | 0
4891 | 3.4176 | 4.8878 | 6.1898 | 4.4194 | 3.4138 | 2.3893 | 15.1141 | 15.4106 | 15.4106 | 0
4892 | 3.1933 | 5.9095 | 7.2425 | 4.7107 | 3.9853 | 2.1814 | 15.9948 | 16.6025 | 16.6025 | 0
4893 | 3.3733 | 6.6526 | 6.4999 | 4.1288 | 4.6133 | 2.0639 | 16.2186 | 16.5504 | 16.5504 | 0
4894 | 3.3186 | 3.7168 | 7.1713 | 5.0842 | 3.48 | 1.8254 | 13.945 | 15.7952 | 15.7952 | 0
4895 | 4.4373 | 7.4137 | 5.2779 | 6.2983 | 3.4991 | 2.3688 | 20.518 | 15.5831 | 20.518 | 1
4896 | 4.973 | 4.4187 | 5.9188 | 4.8188 | 4.4369 | 1.6946 | 15.9051 | 17.0233 | 17.0233 | 0
4897 | 5.2839 | 5.2479 | 6.8217 | 5.0069 | 4.9116 | 2.02 | 17.5588 | 19.0373 | 19.0373 | 0
4898 | 4.9192 | 5.3007 | 6.1679 | 7.0572 | 4.1183 | 1.8089 | 19.086 | 17.0144 | 19.086 | 1
4899 | 3.1643 | 5.4186 | 4.6155 | 5.046 | 5.2564 | 2.2405 | 15.8694 | 15.2767 | 15.8694 | 1
4900 | 5.4674 | 4.8444 | 6.3577 | 6.1507 | 3.4984 | 1.4555 | 17.918 | 16.7789 | 17.918 | 1
4901 | 3.6515 | 5.4805 | 6.1614 | 4.4271 | 5.0302 | 2.539 | 16.0982 | 17.3822 | 17.3822 | 0
4902 | 4.4104 | 5.4048 | 5.9178 | 6.7116 | 4.9684 | 1.5858 | 18.1126 | 16.8824 | 18.1126 | 1
4903 | 3.723 | 5.6519 | 6.5157 | 4.9568 | 5.2764 | 2.1998 | 16.5316 | 17.7149 | 17.7149 | 0
4904 | 2.9326 | 5.2557 | 2.5051 | 5.4957 | 3.4006 | 1.3369 | 15.0209 | 10.1752 | 15.0209 | 1
4905 | 4.5472 | 3.9897 | 5.9799 | 7.1464 | 4.981 | 2.0808 | 17.7641 | 17.5889 | 17.7641 | 1
4906 | 3.6362 | 4.702 | 5.1109 | 5.7194 | 4.3272 | 1.9177 | 15.9753 | 14.992 | 15.9753 | 1
4907 | 3.6902 | 6.3258 | 6.3488 | 4.4542 | 3.8375 | 2.1229 | 16.593 | 15.9994 | 16.593 | 1
4908 | 3.8014 | 7.2765 | 5.4006 | 5.522 | 3.7765 | 1.412 | 18.0119 | 14.3905 | 18.0119 | 1
4909 | 3.7969 | 4.1875 | 7.5445 | 5.0677 | 4.3647 | 1.5984 | 14.6506 | 17.3046 | 17.3046 | 0
4910 | 3.5974 | 6.1921 | 5.4278 | 6.2458 | 3.605 | 1.8886 | 17.9239 | 14.5188 | 17.9239 | 1
4911 | 4.4912 | 5.2399 | 6.5049 | 5.9222 | 4.195 | 1.981 | 17.6343 | 17.1721 | 17.6343 | 1
4912 | 3.8947 | 7.5406 | 6.2948 | 5.2535 | 3.8651 | 1.5926 | 18.2813 | 15.6471 | 18.2813 | 1
4913 | 3.2986 | 5.774 | 5.9099 | 4.392 | 4.0965 | 1.6858 | 15.1504 | 14.9908 | 15.1504 | 1
4914 | 4.6916 | 3.6096 | 3.8374 | 5.1789 | 5.5781 | 2.595 | 16.0751 | 16.7022 | 16.7022 | 0
4915 | 4.2291 | 6.1233 | 6.76 | 5.4707 | 3.2379 | 1.8962 | 17.7193 | 16.1231 | 17.7193 | 1
4916 | 4.3064 | 5.0311 | 6.122 | 6.0548 | 5.728 | 1.4339 | 16.8263 | 17.5903 | 17.5903 | 0
4917 | 5.1327 | 5.9867 | 5.1752 | 5.192 | 4.9348 | 2.0251 | 18.3366 | 17.2678 | 18.3366 | 1
4918 | 3.2594 | 4.054 | 6.8359 | 6.122 | 3.4575 | 1.3384 | 14.7738 | 14.8912 | 14.8912 | 0
4919 | 4.7265 | 4.2461 | 6.852 | 5.8784 | 3.4486 | 1.63 | 16.481 | 16.657 | 16.657 | 0
4920 | 4.4425 | 3.7387 | 5.8796 | 5.5458 | 4.8012 | 2.4951 | 16.2221 | 17.6184 | 17.6184 | 0
4921 | 4.4344 | 7.3032 | 3.6549 | 4.3974 | 4.8795 | 1.6507 | 17.7856 | 14.6194 | 17.7856 | 1
4922 | 2.601 | 4.1994 | 6.1224 | 4.9243 | 4.855 | 2.4942 | 14.219 | 16.0727 | 16.0727 | 0
4923 | 3.4197 | 3.3969 | 6.2119 | 5.9394 | 4.0626 | 1.8129 | 14.5689 | 15.5072 | 15.5072 | 0
4924 | 3.6999 | 4.8455 | 6.5041 | 5.2226 | 5.8379 | 2.0261 | 15.7942 | 18.0681 | 18.0681 | 0
4925 | 3.5764 | 4.4299 | 4.4215 | 5.23 | 5.1631 | 1.6869 | 14.9232 | 14.8479 | 14.9232 | 1
4926 | 4.3492 | 4.7259 | 4.3032 | 5.0518 | 4.1994 | 2.1188 | 16.2456 | 14.9706 | 16.2456 | 1
4927 | 5.1591 | 5.418 | 4.2749 | 4.7713 | 5.085 | 2.2662 | 17.6147 | 16.7853 | 17.6147 | 1
4928 | 3.8145 | 5.2456 | 6.4973 | 5.6318 | 3.5672 | 1.8073 | 16.4992 | 15.6864 | 16.4992 | 1
4929 | 5.1775 | 6.7493 | 6.9767 | 6.5085 | 4.3917 | 1.6365 | 20.0718 | 18.1824 | 20.0718 | 1
4930 | 3.2496 | 3.8046 | 6.751 | 6.5103 | 3.2171 | 2.2321 | 15.7966 | 15.4499 | 15.7966 | 1
4931 | 3.5386 | 5.8783 | 3.6309 | 5.0182 | 5.0953 | 2.0725 | 16.5076 | 14.3373 | 16.5076 | 1
4932 | 3.579 | 4.3042 | 5.6702 | 5.127 | 5.4453 | 1.944 | 14.9542 | 16.6385 | 16.6385 | 0
4933 | 3.8275 | 5.2146 | 5.1015 | 4.3763 | 3.8258 | 1.5812 | 14.9995 | 14.336 | 14.9995 | 1
4934 | 4.6456 | 5.6618 | 4.8109 | 4.2645 | 4.9443 | 1.9724 | 16.5443 | 16.3731 | 16.5443 | 1
4935 | 4.9565 | 4.8051 | 5.4941 | 4.799 | 4.1014 | 2.3187 | 16.8792 | 16.8707 | 16.8792 | 1
4936 | 2.3858 | 4.6853 | 4.7319 | 6.4442 | 3.3715 | 2.1627 | 15.678 | 12.6518 | 15.678 | 1
4937 | 4.2085 | 4.0689 | 6.1372 | 5.1965 | 3.6841 | 1.6189 | 15.0929 | 15.6488 | 15.6488 | 0
4938 | 3.5724 | 6.8285 | 7.2311 | 5.7841 | 4.9582 | 1.6873 | 17.8723 | 17.449 | 17.8723 | 1
4939 | 4.8279 | 4.5979 | 3.2582 | 5.3724 | 3.8797 | 1.73 | 16.5282 | 13.6958 | 16.5282 | 1
4940 | 3.4641 | 5.6693 | 4.5743 | 7.1725 | 3.9074 | 2.245 | 18.5509 | 14.1907 | 18.5509 | 1
4941 | 4.6604 | 3.5443 | 6.4867 | 6.249 | 3.0256 | 1.8657 | 16.3194 | 16.0385 | 16.3194 | 1
4942 | 4.4274 | 5.7288 | 6.4806 | 5.0995 | 4.4113 | 1.6148 | 16.8704 | 16.934 | 16.934 | 0
4943 | 5.0447 | 7.0667 | 4.9299 | 4.9825 | 4.0231 | 2.0468 | 19.1407 | 16.0445 | 19.1407 | 1
4944 | 4.1329 | 6.6286 | 4.5678 | 5.5874 | 3.7124 | 2.2479 | 18.5968 | 14.6611 | 18.5968 | 1
4945 | 4.4355 | 6.4371 | 5.4516 | 5.2276 | 4.4829 | 2.3199 | 18.4201 | 16.6899 | 18.4201 | 1
4946 | 4.3299 | 5.4342 | 6.4352 | 4.9024 | 5.1679 | 1.8212 | 16.4877 | 17.7542 | 17.7542 | 0
4947 | 4.1588 | 5.9515 | 7.2031 | 5.2905 | 3.5055 | 1.9716 | 17.3723 | 16.839 | 17.3723 | 1
4948 | 3.5193 | 5.4428 | 5.6694 | 4.5325 | 6.5176 | 1.6762 | 15.1708 | 17.3825 | 17.3825 | 0
4949 | 3.743 | 3.3524 | 3.7682 | 5.6701 | 5.8591 | 1.3879 | 14.1535 | 14.7582 | 14.7582 | 0
4950 | 3.7468 | 5.6301 | 5.2555 | 4.8397 | 4.6782 | 1.8675 | 16.0842 | 15.548 | 16.0842 | 1
4951 | 4.3685 | 7.8533 | 5.8281 | 6.8556 | 3.9173 | 1.2989 | 20.3764 | 15.4129 | 20.3764 | 1
4952 | 4.3042 | 7.0765 | 5.6236 | 5.0281 | 4.2491 | 1.3177 | 17.7265 | 15.4946 | 17.7265 | 1
4953 | 3.6352 | 5.075 | 6.9984 | 5.6484 | 6.1332 | 1.8588 | 16.2173 | 18.6255 | 18.6255 | 0
4954 | 3.5152 | 5.2677 | 3.6372 | 4.5432 | 6.157 | 2.3905 | 15.7166 | 15.6999 | 15.7166 | 1
4955 | 3.8406 | 5.9188 | 6.7018 | 5.8564 | 4.1916 | 1.4189 | 17.0347 | 16.153 | 17.0347 | 1
4956 | 3.9306 | 5.6157 | 5.7568 | 4.7868 | 4.9914 | 1.7033 | 16.0363 | 16.3821 | 16.3821 | 0
4957 | 3.5191 | 5.7762 | 5.4548 | 4.7918 | 4.4804 | 2.3993 | 16.4865 | 15.8536 | 16.4865 | 1
4958 | 4.5832 | 3.3164 | 4.3261 | 4.627 | 3.2563 | 1.6975 | 14.2242 | 13.8632 | 14.2242 | 1
4959 | 3.8638 | 4.1205 | 4.9172 | 4.4087 | 3.6499 | 2.3057 | 14.6986 | 14.7366 | 14.7366 | 0
4960 | 3.2719 | 6.8048 | 3.9106 | 4.0805 | 4.7968 | 1.41 | 15.5672 | 13.3893 | 15.5672 | 1
4961 | 3.7922 | 5.2879 | 6.2726 | 4.7154 | 3.2198 | 2.0518 | 15.8472 | 15.3363 | 15.8472 | 1
4962 | 5.2286 | 3.2508 | 5.8413 | 4.651 | 4.5602 | 1.7078 | 14.8382 | 17.3379 | 17.3379 | 0
4963 | 4.9655 | 4.7774 | 4.0763 | 4.7025 | 5.0509 | 2.0315 | 16.4769 | 16.1242 | 16.4769 | 1
4964 | 2.8491 | 4.0384 | 5.1339 | 5.7984 | 5.5704 | 2.5326 | 15.2185 | 16.086 | 16.086 | 0
4965 | 3.6615 | 4.2878 | 5.49 | 5.1014 | 4.502 | 2.0808 | 15.1315 | 15.7343 | 15.7343 | 0
4966 | 2.3817 | 5.5827 | 6.8893 | 6.3896 | 4.429 | 2.1863 | 16.5404 | 15.8864 | 16.5404 | 1
4967 | 3.9611 | 4.3989 | 3.0038 | 4.4745 | 4.5115 | 1.5493 | 14.3838 | 13.0257 | 14.3838 | 1
4968 | 3.0431 | 5.2088 | 6.7132 | 5.087 | 5.337 | 1.7926 | 15.1315 | 16.886 | 16.886 | 0
4969 | 4.0213 | 3.8429 | 2.9607 | 5.9869 | 5.1299 | 1.8025 | 15.6536 | 13.9145 | 15.6536 | 1
4970 | 3.5704 | 3.937 | 6.3699 | 6.8318 | 5.1767 | 1.5589 | 15.8981 | 16.6759 | 16.6759 | 0
4971 | 4.5719 | 7.8466 | 4.0348 | 4.4825 | 4.866 | 1.7281 | 18.629 | 15.2008 | 18.629 | 1
4972 | 3.8952 | 3.9318 | 5.2218 | 4.9923 | 3.6114 | 1.5816 | 14.4009 | 14.3099 | 14.4009 | 1
4973 | 2.7836 | 5.6719 | 4.1599 | 5.2814 | 4.5855 | 1.9503 | 15.6872 | 13.4793 | 15.6872 | 1
4974 | 2.8981 | 6.6409 | 6.4181 | 4.2113 | 5.0319 | 2.7588 | 16.5091 | 17.1069 | 17.1069 | 0
4975 | 3.7672 | 6.3737 | 3.8287 | 6.9226 | 3.2746 | 1.3913 | 18.4548 | 12.2618 | 18.4548 | 1
4976 | 3.8959 | 5.3463 | 5.2877 | 5.0742 | 4.497 | 1.3106 | 15.6269 | 14.9913 | 15.6269 | 1
4977 | 3.4264 | 7.5223 | 5.023 | 4.9932 | 3.7648 | 1.9988 | 17.9407 | 14.213 | 17.9407 | 1
4978 | 4.7225 | 4.7061 | 5.4459 | 4.8058 | 3.4118 | 1.8348 | 16.0693 | 15.415 | 16.0693 | 1
4979 | 5.0256 | 4.8991 | 5.655 | 6.6039 | 4.9194 | 1.7716 | 18.3003 | 17.3716 | 18.3003 | 1
4980 | 2.7226 | 5.8264 | 3.75 | 5.02 | 3.9894 | 2.085 | 15.6541 | 12.547 | 15.6541 | 1
4981 | 3.4499 | 4.7898 | 6.9317 | 4.3249 | 5.0538 | 1.9219 | 14.4866 | 17.3572 | 17.3572 | 0
4982 | 4.4562 | 3.9419 | 5.7189 | 5.8636 | 4.3185 | 2.6278 | 16.8895 | 17.1214 | 17.1214 | 0
4983 | 4.6877 | 5.9251 | 5.7091 | 5.9192 | 4.619 | 2.3566 | 18.8886 | 17.3724 | 18.8886 | 1
4984 | 3.9276 | 6.2689 | 4.9522 | 4.3993 | 3.4889 | 2.1042 | 16.6999 | 14.4728 | 16.6999 | 1
4985 | 3.0596 | 3.9059 | 5.4738 | 5.0461 | 5.3018 | 2.0363 | 14.048 | 15.8715 | 15.8715 | 0
4986 | 4.4258 | 5.8672 | 5.6331 | 6.065 | 5.6923 | 2.2361 | 18.594 | 17.9873 | 18.594 | 1
4987 | 4.48 | 3.7528 | 6.1543 | 4.9476 | 4.2736 | 1.6282 | 14.8086 | 16.5361 | 16.5361 | 0
4988 | 3.7285 | 3.5909 | 2.5873 | 4.5956 | 3.9982 | 1.9196 | 13.8346 | 12.2336 | 13.8346 | 1
4989 | 4.3005 | 4.7909 | 5.5796 | 4.6412 | 4.4802 | 2.1862 | 15.9187 | 16.5464 | 16.5464 | 0
4990 | 3.176 | 3.9922 | 6.2869 | 4.6318 | 4.4267 | 2.0436 | 13.8436 | 15.9332 | 15.9332 | 0
4991 | 5.3181 | 6.767 | 4.9399 | 4.3791 | 3.6205 | 1.7102 | 18.1744 | 15.5887 | 18.1744 | 1
4992 | 2.8526 | 4.5687 | 7.5295 | 5.3359 | 4.1553 | 1.7856 | 14.5429 | 16.323 | 16.323 | 0
4993 | 4.3718 | 3.5408 | 7.5178 | 4.698 | 3.9261 | 1.5892 | 14.1998 | 17.4049 | 17.4049 | 0
4994 | 4.4532 | 6.5775 | 5.8106 | 6.8247 | 3.9338 | 1.5128 | 19.3682 | 15.7103 | 19.3682 | 1
4995 | 3.9431 | 7.9524 | 6.6394 | 5.2425 | 4.275 | 1.5223 | 18.6603 | 16.3798 | 18.6603 | 1
4996 | 2.4273 | 4.8365 | 7.1206 | 4.407 | 5.8223 | 2.7147 | 14.3854 | 18.0849 | 18.0849 | 0
4997 | 3.3368 | 5.8434 | 3.935 | 5.3562 | 4.7788 | 2.0168 | 16.5532 | 14.0674 | 16.5532 | 1
4998 | 4.0705 | 5.1391 | 6.1815 | 5.9487 | 4.2522 | 1.8528 | 17.0111 | 16.357 | 17.0111 | 1
4999 | 3.7621 | 3.8917 | 5.9608 | 6.4244 | 4.0081 | 2.0546 | 16.1328 | 15.7857 | 16.1328 | 1
5000 | 4.7503 | 5.0101 | 4.7323 | 4.7957 | 5.6203 | 2.0374 | 16.5935 | 17.1403 | 17.1403 | 0

## T4_Correlated
T09: Correlation check (optional): B and D correlated, hand-built Cholesky step
z1 = NORMSINV(RAND()); z2 = rho*z1 + SQRT(1-rho^2)*NORMSINV(RAND()); u = NORMSDIST(z); duration = BETAINV(u, ...). Other activities independent.
| Correlation rho (B with D) | 0.6
Test | Measure | Excel | Tool | Difference | Tolerance | Result
T09 | Rank correlation of B and D (CORREL of their uniforms) | 0.5841 | 0.5826 | 0.0015003 | 0.03 | Pass
T09b | Mean project duration | 17.2286 | 17.2125 | 0.016079 | 0.1 | Pass
T09c | P80 project duration | 18.5809 | 18.5305 | 0.050409 | 0.15 | Pass
| Theory: (6/pi) x asin(rho/2) | 0.58192
| P80 with B, D independent (from T3) | 18.301
| Effect of correlation on P80 (days) | 0.2799
B and D are on the same path, so correlating them widens the spread and raises P80.
Run | z1 | z2 | u for B | u for D | A | B | C | D | E | F | Path A-B-D-F | Path A-C-E-F | Project
1 | 1.3123 | 1.2843 | 0.9053 | 0.90048 | 3.1685 | 6.9032 | 3.638 | 6.3379 | 5.4688 | 1.3235 | 17.733 | 13.5987 | 17.733
2 | -0.17109 | -0.91638 | 0.43208 | 0.17973 | 4.1003 | 5.0466 | 5.4293 | 4.6321 | 5.1356 | 1.9905 | 15.7694 | 16.6557 | 16.6557
3 | -1.8992 | -0.42947 | 0.028769 | 0.33379 | 4.6346 | 3.5076 | 5.0936 | 4.9366 | 4.5701 | 1.6823 | 14.7611 | 15.9806 | 15.9806
4 | -0.32092 | -2.3047 | 0.37413 | 0.01059 | 2.5542 | 4.8698 | 5.1104 | 4.1347 | 5.3506 | 2.0562 | 13.6149 | 15.0714 | 15.0714
5 | 0.0034738 | -0.25177 | 0.50139 | 0.40061 | 3.8714 | 5.2592 | 5.2441 | 5.0634 | 4.9117 | 1.8665 | 16.0605 | 15.8937 | 16.0605
6 | -1.0274 | -1.1695 | 0.15212 | 0.1211 | 3.873 | 4.1347 | 4.8402 | 4.5009 | 3.2667 | 2.2351 | 14.7437 | 14.215 | 14.7437
7 | -1.9987 | -1.1413 | 0.022822 | 0.12687 | 4.5915 | 3.4564 | 4.9543 | 4.5145 | 6.3419 | 1.8302 | 14.3927 | 17.7179 | 17.7179
8 | -0.046688 | -1.3634 | 0.48138 | 0.086373 | 4.741 | 5.1974 | 3.8871 | 4.4133 | 4.0244 | 2.0562 | 16.408 | 14.7088 | 16.408
9 | -0.28576 | 0.80669 | 0.38753 | 0.79008 | 4.5629 | 4.9108 | 7.3873 | 5.9307 | 4.3944 | 2.1836 | 17.588 | 18.5283 | 18.5283
10 | -0.37009 | -2.0528 | 0.35566 | 0.020047 | 4.0716 | 4.8132 | 5.3495 | 4.1878 | 4.524 | 2.1064 | 15.1791 | 16.0515 | 16.0515
11 | -0.9307 | -0.39364 | 0.176 | 0.34692 | 3.7415 | 4.2242 | 5.5441 | 4.9616 | 3.4421 | 2.0425 | 14.9698 | 14.7702 | 14.9698
12 | 1.5023 | 1.3467 | 0.93349 | 0.91096 | 4.669 | 7.1223 | 5.3651 | 6.3897 | 4.2312 | 1.8885 | 20.0694 | 16.1538 | 20.0694
13 | 0.49106 | -0.64958 | 0.68831 | 0.25798 | 4.5411 | 5.8767 | 6.0875 | 4.7907 | 3.5276 | 2.2067 | 17.4152 | 16.3629 | 17.4152
14 | -0.61906 | -0.50899 | 0.26794 | 0.30538 | 4.2946 | 4.5378 | 6.101 | 4.8824 | 3.9836 | 1.5484 | 15.2632 | 15.9277 | 15.9277
15 | 0.58677 | 1.1055 | 0.72132 | 0.86554 | 3.9743 | 5.9995 | 5.5305 | 6.1872 | 4.0177 | 2.4079 | 18.5689 | 15.9303 | 18.5689
16 | 0.11971 | -0.72887 | 0.54764 | 0.23304 | 3.6449 | 5.4039 | 6.679 | 4.7414 | 3.5636 | 1.9964 | 15.7867 | 15.8839 | 15.8839
17 | -0.80304 | -1.1594 | 0.21098 | 0.12314 | 4.4871 | 4.3481 | 6.7704 | 4.5057 | 4.6967 | 2.0973 | 15.4383 | 18.0515 | 18.0515
18 | 0.077299 | 0.96941 | 0.53081 | 0.83383 | 5.2757 | 5.3508 | 4.6153 | 6.0708 | 3.7638 | 2.1536 | 18.8509 | 15.8084 | 18.8509
19 | -0.30044 | -0.47326 | 0.38192 | 0.31801 | 2.9617 | 4.8937 | 6.6948 | 4.9066 | 4.8581 | 1.9935 | 14.7554 | 16.508 | 16.508
20 | -0.12175 | -0.23934 | 0.45155 | 0.40542 | 4.539 | 5.106 | 5.4606 | 5.0726 | 3.1981 | 1.9823 | 16.6999 | 15.18 | 16.6999
21 | 1.501 | 1.7725 | 0.93332 | 0.96184 | 3.5599 | 7.1208 | 5.8948 | 6.7277 | 5.2364 | 2.1292 | 19.5377 | 16.8204 | 19.5377
22 | 1.115 | 1.6708 | 0.86756 | 0.95262 | 3.868 | 6.6658 | 5.6268 | 6.6498 | 4.0037 | 2.5115 | 19.6951 | 16.0099 | 19.6951
23 | 1.3593 | -1.0557 | 0.91298 | 0.14555 | 3.5832 | 6.9583 | 6.6452 | 4.5575 | 3.5776 | 2.0987 | 17.1977 | 15.9047 | 17.1977
24 | 0.49223 | -0.26654 | 0.68872 | 0.39491 | 4.3751 | 5.8782 | 6.1706 | 5.0526 | 3.7146 | 1.5951 | 16.901 | 15.8554 | 16.901
25 | 2.1566 | 2.1782 | 0.98448 | 0.9853 | 4.1815 | 7.7864 | 5.3066 | 7.0162 | 4.1135 | 2.6997 | 21.6837 | 16.3012 | 21.6837
26 | 1.7089 | 0.45161 | 0.95626 | 0.67423 | 3.5637 | 7.3483 | 6.4192 | 5.6261 | 3.1209 | 1.832 | 18.3701 | 14.9358 | 18.3701
27 | -1.4351 | -1.8048 | 0.075635 | 0.035552 | 4.935 | 3.8008 | 6.0602 | 4.2544 | 4.7546 | 2.3686 | 15.3588 | 18.1184 | 18.1184
28 | -0.95042 | 0.13093 | 0.17095 | 0.55208 | 4.5742 | 4.2056 | 7.5751 | 5.3598 | 4.484 | 2.4583 | 16.5979 | 19.0916 | 19.0916
29 | 0.70424 | 0.13549 | 0.75936 | 0.55389 | 5.4467 | 6.15 | 4.4147 | 5.3635 | 5.5698 | 1.8168 | 18.777 | 17.2481 | 18.777
30 | 1.4854 | 1.1347 | 0.93128 | 0.87176 | 2.8126 | 7.1032 | 7.1126 | 6.212 | 3.6697 | 1.4096 | 17.5373 | 15.0045 | 17.5373
31 | 1.5024 | 0.58651 | 0.93351 | 0.72123 | 2.3772 | 7.1225 | 4.0547 | 5.7412 | 3.3362 | 2.1477 | 17.3885 | 11.9158 | 17.3885
32 | 0.072472 | 0.59177 | 0.52889 | 0.723 | 4.0803 | 5.3448 | 6.1817 | 5.7457 | 5.707 | 1.9881 | 17.1589 | 17.9571 | 17.9571
33 | -1.3416 | -1.5965 | 0.089866 | 0.055187 | 5.1295 | 3.8711 | 6.2285 | 4.3226 | 4.0268 | 1.8705 | 15.1937 | 17.2552 | 17.2552
34 | -1.0836 | 1.6897 | 0.13927 | 0.95445 | 4.868 | 4.0845 | 4.6099 | 6.6644 | 4.1783 | 2.0929 | 17.7097 | 15.7491 | 17.7097
35 | -0.38426 | -1.0561 | 0.35039 | 0.14546 | 3.7614 | 4.797 | 5.7101 | 4.5573 | 3.5552 | 2.2182 | 15.3338 | 15.2449 | 15.3338
36 | -1.1962 | 0.76901 | 0.11581 | 0.77906 | 3.6153 | 3.9878 | 5.1168 | 5.8982 | 4.0392 | 1.2524 | 14.7537 | 14.0237 | 14.7537
37 | 0.54542 | 0.98765 | 0.70727 | 0.83834 | 3.7423 | 5.9465 | 5.7673 | 6.0864 | 4.7623 | 1.4213 | 17.1965 | 15.6932 | 17.1965
38 | 0.5479 | -0.76732 | 0.70812 | 0.22144 | 2.6472 | 5.9496 | 7.2968 | 4.7182 | 5.6313 | 1.9554 | 15.2705 | 17.5307 | 17.5307
39 | 0.36299 | 0.6045 | 0.6417 | 0.72724 | 4.3022 | 5.7125 | 5.2346 | 5.7566 | 4.0434 | 2.0849 | 17.8562 | 15.6651 | 17.8562
40 | -2.0379 | -2.6145 | 0.020781 | 0.0044674 | 3.382 | 3.4372 | 5.5156 | 4.0864 | 3.4068 | 1.7944 | 12.7 | 14.0987 | 14.0987
41 | 1.8793 | 0.34765 | 0.96989 | 0.63595 | 4.0883 | 7.5238 | 6.2478 | 5.5385 | 4.2642 | 1.5381 | 18.6886 | 16.1384 | 18.6886
42 | -1.2914 | -0.0097512 | 0.098275 | 0.49611 | 3.1548 | 3.9103 | 5.1356 | 5.2476 | 5.7703 | 2.1255 | 14.4382 | 16.1862 | 16.1862
43 | 1.0128 | -0.1605 | 0.84443 | 0.43624 | 2.9092 | 6.5398 | 6.9355 | 5.1314 | 3.9351 | 1.7263 | 16.3068 | 15.5061 | 16.3068
44 | -0.51663 | -0.27411 | 0.30271 | 0.392 | 3.3926 | 4.6486 | 6.3189 | 5.0471 | 3.6266 | 1.6914 | 14.7797 | 15.0295 | 15.0295
45 | -0.45778 | -0.18296 | 0.32356 | 0.42742 | 3.4083 | 4.7139 | 6.4459 | 5.1145 | 3.7908 | 2.3255 | 15.5623 | 15.9705 | 15.9705
46 | 0.9626 | 0.9281 | 0.83213 | 0.82332 | 4.93 | 6.4772 | 6.4633 | 6.0352 | 5.0425 | 2.6588 | 20.1012 | 19.0945 | 20.1012
47 | 1.6743 | 1.9826 | 0.95296 | 0.97629 | 4.0216 | 7.3114 | 6.03 | 6.8818 | 3.5441 | 1.9349 | 20.1497 | 15.5305 | 20.1497
48 | 0.39587 | 1.417 | 0.6539 | 0.92176 | 5.2762 | 5.7546 | 4.3869 | 6.4475 | 4.8686 | 1.703 | 19.1813 | 16.2347 | 19.1813
49 | 1.2852 | -0.38537 | 0.90064 | 0.34998 | 5.6024 | 6.8711 | 5.1791 | 4.9674 | 4.3069 | 2.4381 | 19.8789 | 17.5264 | 19.8789
50 | -0.772 | -0.67096 | 0.22006 | 0.25112 | 5.2104 | 4.3792 | 4.2597 | 4.7773 | 5.5494 | 1.4616 | 15.8285 | 16.4811 | 16.4811
51 | 0.16283 | -0.46519 | 0.56467 | 0.3209 | 4.9765 | 5.4581 | 5.1235 | 4.9121 | 4.2228 | 1.4926 | 16.8393 | 15.8154 | 16.8393
52 | -0.50552 | -0.20607 | 0.3066 | 0.41837 | 3.2335 | 4.6609 | 6.3431 | 5.0973 | 4.4512 | 1.4288 | 14.4204 | 15.4565 | 15.4565
53 | -0.039462 | 0.76399 | 0.48426 | 0.77756 | 4.7652 | 5.2063 | 7.0954 | 5.8938 | 5.4095 | 2.6409 | 18.5062 | 19.9109 | 19.9109
54 | -0.42244 | -1.1511 | 0.33635 | 0.12484 | 3.8631 | 4.7536 | 6.2721 | 4.5098 | 3.5481 | 1.7059 | 14.8324 | 15.3892 | 15.3892
55 | 0.27797 | -0.80238 | 0.60948 | 0.21117 | 4.4841 | 5.604 | 3.8893 | 4.6973 | 4.2709 | 2.0002 | 16.7856 | 14.6444 | 16.7856
56 | -0.27482 | -0.61357 | 0.39173 | 0.26975 | 3.3433 | 4.9236 | 5.5569 | 4.8137 | 3.8886 | 2.3968 | 15.4774 | 15.1856 | 15.4774
57 | -0.10341 | -0.23797 | 0.45882 | 0.40595 | 3.1387 | 5.1282 | 6.7731 | 5.0736 | 4.7437 | 2.2486 | 15.5891 | 16.9041 | 16.9041
58 | 1.2336 | 1.7479 | 0.89132 | 0.95976 | 3.7698 | 6.8095 | 6.4028 | 6.7091 | 4.6195 | 1.7699 | 19.0583 | 16.562 | 19.0583
59 | 0.073324 | 0.44988 | 0.52923 | 0.6736 | 3.8277 | 5.3459 | 4.3853 | 5.6246 | 4.9937 | 1.5432 | 16.3414 | 14.7499 | 16.3414
60 | -0.33347 | 0.92769 | 0.36939 | 0.82322 | 5.5627 | 4.8553 | 7.5348 | 6.0349 | 5.4651 | 2.0463 | 18.4992 | 20.6089 | 20.6089
61 | -0.39684 | -1.7623 | 0.34574 | 0.039007 | 4.7662 | 4.7826 | 7.2935 | 4.2674 | 4.8515 | 1.9206 | 15.7368 | 18.8317 | 18.8317
62 | 0.98678 | 0.0074974 | 0.83813 | 0.50299 | 5.4811 | 6.5074 | 5.0328 | 5.2611 | 3.6442 | 2.366 | 19.6157 | 16.5241 | 19.6157
63 | 1.4401 | -0.40486 | 0.92508 | 0.34279 | 4.8685 | 7.0516 | 5.514 | 4.9537 | 3.538 | 2.6866 | 19.5604 | 16.607 | 19.5604
64 | 0.99876 | 1.0995 | 0.84105 | 0.86422 | 4.2782 | 6.5223 | 3.9315 | 6.182 | 5.719 | 1.7343 | 18.7167 | 15.6629 | 18.7167
65 | 0.70158 | 0.82783 | 0.75853 | 0.79612 | 5.2161 | 6.1466 | 5.0052 | 5.9489 | 3.81 | 2.5358 | 19.8473 | 16.5671 | 19.8473
66 | -0.29461 | -2.2747 | 0.38414 | 0.011461 | 4.2916 | 4.9004 | 5.4328 | 4.1403 | 4.064 | 1.7352 | 15.0675 | 15.5235 | 15.5235
67 | 1.098 | 0.58324 | 0.8639 | 0.72013 | 2.8923 | 6.645 | 5.2877 | 5.7384 | 4.2719 | 1.5108 | 16.7865 | 13.9627 | 16.7865
68 | -0.38091 | 0.263 | 0.35163 | 0.60373 | 4.802 | 4.8008 | 4.0303 | 5.4679 | 4.487 | 1.8009 | 16.8716 | 15.1202 | 16.8716
69 | -0.056169 | -0.72442 | 0.4776 | 0.2344 | 5.6849 | 5.1858 | 6.5798 | 4.7442 | 5.1786 | 2.0184 | 17.6334 | 19.4618 | 19.4618
70 | -1.2275 | -0.46898 | 0.10981 | 0.31954 | 3.8605 | 3.9619 | 5.0674 | 4.9095 | 4.9743 | 1.8042 | 14.536 | 15.7063 | 15.7063
71 | 0.73323 | 0.97712 | 0.76829 | 0.83574 | 3.9332 | 6.1871 | 5.3971 | 6.0774 | 4.1279 | 1.4573 | 17.6549 | 14.9155 | 17.6549
72 | -0.93747 | -0.49851 | 0.17426 | 0.30906 | 3.2989 | 4.2178 | 6.838 | 4.8895 | 5.1705 | 1.9798 | 14.386 | 17.2873 | 17.2873
73 | 0.86691 | 0.41053 | 0.807 | 0.65929 | 3.7896 | 6.3569 | 4.3692 | 5.5913 | 3.5261 | 1.9029 | 17.6408 | 13.5879 | 17.6408
74 | 0.060272 | 0.61783 | 0.52403 | 0.73166 | 4.2269 | 5.3296 | 5.7772 | 5.768 | 5.2879 | 2.3396 | 17.6641 | 17.6317 | 17.6641
75 | 0.07195 | 0.44175 | 0.52868 | 0.67066 | 3.4523 | 5.3442 | 6.3749 | 5.6177 | 4.8876 | 1.6082 | 16.0224 | 16.323 | 16.323
76 | 0.48399 | -1.3715 | 0.6858 | 0.08511 | 3.77 | 5.8676 | 4.7533 | 4.4099 | 3.7505 | 1.9688 | 16.0163 | 14.2426 | 16.0163
77 | 1.5137 | 0.6956 | 0.93495 | 0.75666 | 4.7357 | 7.1352 | 5.8529 | 5.8349 | 3.629 | 2.3416 | 20.0473 | 16.5592 | 20.0473
78 | -0.2661 | -0.89311 | 0.39508 | 0.1859 | 4.3295 | 4.9338 | 3.8871 | 4.6451 | 3.1551 | 1.9031 | 15.8115 | 13.2748 | 15.8115
79 | -2.0969 | -1.1742 | 0.018 | 0.12016 | 5.0987 | 3.4095 | 5.4554 | 4.4986 | 3.8213 | 2.2195 | 15.2264 | 16.5948 | 16.5948
80 | 0.11119 | -0.72655 | 0.54427 | 0.23375 | 5.3001 | 5.3932 | 6.4613 | 4.7429 | 3.7386 | 2.1763 | 17.6124 | 17.6762 | 17.6762
81 | 0.49305 | 1.7334 | 0.68901 | 0.95849 | 3.2838 | 5.8792 | 6.8477 | 6.698 | 6.088 | 1.4658 | 17.3269 | 17.6854 | 17.6854
82 | -1.8822 | -2.3391 | 0.029908 | 0.0096651 | 5.0864 | 3.5168 | 2.6489 | 4.1284 | 4.7643 | 2.0419 | 14.7736 | 14.5416 | 14.7736
83 | -0.46637 | -0.30955 | 0.32047 | 0.37845 | 3.1485 | 4.7043 | 6.4367 | 5.0214 | 3.7591 | 1.6548 | 14.529 | 14.9991 | 14.9991
84 | 0.38535 | -0.52345 | 0.65001 | 0.30033 | 4.031 | 5.7411 | 5.5901 | 4.8727 | 4.0015 | 1.3983 | 16.0432 | 15.0209 | 16.0432
85 | 1.2474 | -0.037615 | 0.89388 | 0.485 | 4.092 | 6.8261 | 7.1158 | 5.2258 | 3.311 | 2.125 | 18.2689 | 16.6438 | 18.2689
86 | -1.2725 | -1.1817 | 0.1016 | 0.11866 | 3.0878 | 3.9254 | 3.0113 | 4.4951 | 4.4137 | 1.6289 | 13.1372 | 12.1417 | 13.1372
87 | -2.1676 | -0.23643 | 0.015095 | 0.40655 | 3.8068 | 3.3781 | 4.8971 | 5.0747 | 5.0941 | 2.1462 | 14.4058 | 15.9441 | 15.9441
88 | 1.6558 | 0.062871 | 0.95111 | 0.52507 | 4.3071 | 7.2915 | 6.96 | 5.3051 | 4.5305 | 1.7686 | 18.6723 | 17.5662 | 18.6723
89 | 0.43925 | 1.6841 | 0.66976 | 0.95392 | 3.3608 | 5.8102 | 7.0795 | 6.6601 | 5.646 | 2.3505 | 18.1816 | 18.4367 | 18.4367
90 | 0.093897 | -0.18832 | 0.5374 | 0.42531 | 4.8136 | 5.3716 | 5.9734 | 5.1105 | 3.6038 | 2.7289 | 18.0246 | 17.1197 | 18.0246
91 | -0.023949 | 0.28816 | 0.49045 | 0.61339 | 4.4338 | 5.2254 | 6.5629 | 5.4888 | 4.3775 | 1.4159 | 16.5639 | 16.7901 | 16.7901
92 | -1.797 | -1.0155 | 0.036167 | 0.15493 | 2.982 | 3.5644 | 4.8914 | 4.5784 | 3.6591 | 2.0594 | 13.1843 | 13.5919 | 13.5919
93 | -0.51475 | -0.70742 | 0.30337 | 0.23965 | 3.5715 | 4.6507 | 4.2351 | 4.7546 | 3.8086 | 1.6516 | 14.6284 | 13.2667 | 14.6284
94 | 0.47183 | -1.206 | 0.68148 | 0.1139 | 3.6079 | 5.852 | 7.0451 | 4.4835 | 5.9693 | 2.2493 | 16.1928 | 18.8717 | 18.8717
95 | 1.6827 | -0.16303 | 0.95378 | 0.43525 | 3.0132 | 7.3204 | 5.852 | 5.1295 | 5.8671 | 2.8785 | 18.3416 | 17.6108 | 18.3416
96 | 1.3454 | 0.13389 | 0.91076 | 0.55326 | 3.3061 | 6.942 | 5.2676 | 5.3622 | 3.9437 | 2.3455 | 17.9557 | 14.8628 | 17.9557
97 | -0.011532 | 0.58502 | 0.4954 | 0.72073 | 4.7036 | 5.2406 | 6.9309 | 5.7399 | 4.7612 | 2.716 | 18.4001 | 19.1117 | 19.1117
98 | 0.66751 | 0.31799 | 0.74778 | 0.62475 | 3.1456 | 6.103 | 5.6077 | 5.5136 | 4.4873 | 2.5605 | 17.3229 | 15.8012 | 17.3229
99 | -0.70281 | 0.066266 | 0.24109 | 0.52642 | 4.1517 | 4.4499 | 5.6073 | 5.3078 | 3.7991 | 1.9064 | 15.8158 | 15.4645 | 15.8158
100 | -1.08 | 0.68095 | 0.14006 | 0.75205 | 3.5214 | 4.0876 | 7.1209 | 5.8223 | 4.4018 | 1.7046 | 15.1358 | 16.7486 | 16.7486
101 | 1.899 | 0.37544 | 0.97122 | 0.64633 | 3.4648 | 7.5434 | 5.7194 | 5.5618 | 4.3475 | 1.5471 | 18.117 | 15.0788 | 18.117
102 | 1.6371 | 1.177 | 0.9492 | 0.88041 | 2.4158 | 7.2713 | 4.1606 | 6.2478 | 4.5267 | 2.1763 | 18.1112 | 13.2794 | 18.1112
103 | -0.75868 | 0.21103 | 0.22402 | 0.58357 | 4.5788 | 4.3927 | 4.497 | 5.4251 | 3.9671 | 2.8131 | 17.2097 | 15.856 | 17.2097
104 | -0.33762 | 0.27659 | 0.36783 | 0.60895 | 4.7897 | 4.8505 | 5.8238 | 5.4792 | 5.1921 | 2.4602 | 17.5796 | 18.2657 | 18.2657
105 | 1.6633 | -0.14446 | 0.95187 | 0.44257 | 5.8667 | 7.2996 | 7.1898 | 5.1436 | 5.1066 | 2.053 | 20.3629 | 20.2161 | 20.3629
106 | -0.63967 | 2.3834 | 0.26119 | 0.99142 | 4.0256 | 4.5159 | 6.8416 | 7.147 | 4.8963 | 2.51 | 18.1985 | 18.2736 | 18.2736
107 | 0.47493 | 1.5437 | 0.68258 | 0.93867 | 2.6032 | 5.856 | 7.0078 | 6.5498 | 4.2934 | 1.5834 | 16.5923 | 15.4878 | 16.5923
108 | 0.21565 | 0.29933 | 0.58537 | 0.61766 | 5.3578 | 5.5249 | 5.6664 | 5.4981 | 6.2417 | 1.8952 | 18.276 | 19.1611 | 19.1611
109 | 2.3937 | 0.91462 | 0.99166 | 0.81981 | 5.1418 | 7.9867 | 7.2024 | 6.0237 | 4.8035 | 1.9903 | 21.1425 | 19.138 | 21.1425
110 | -0.35941 | -0.15578 | 0.35964 | 0.4381 | 4.2308 | 4.8254 | 5.3948 | 5.135 | 5.3592 | 1.4748 | 15.666 | 16.4596 | 16.4596
111 | 0.41906 | 0.75653 | 0.66241 | 0.77533 | 3.6867 | 5.7843 | 5.0277 | 5.8874 | 4.8031 | 1.7099 | 17.0683 | 15.2274 | 17.0683
112 | -0.026039 | 0.46354 | 0.48961 | 0.67851 | 3.7253 | 5.2228 | 7.7947 | 5.6362 | 3.728 | 1.9934 | 16.5777 | 17.2414 | 17.2414
113 | 1.3953 | 1.6542 | 0.91854 | 0.95095 | 4.3347 | 7.0001 | 5.4836 | 6.6369 | 5.3489 | 2.5621 | 20.5338 | 17.7293 | 20.5338
114 | -0.044326 | 0.36528 | 0.48232 | 0.64255 | 3.617 | 5.2003 | 6.5215 | 5.5532 | 5.3827 | 2.3074 | 16.678 | 17.8286 | 17.8286
115 | -0.61394 | 0.52187 | 0.26963 | 0.69912 | 4.3402 | 4.5432 | 5.0401 | 5.6859 | 6.6323 | 2.0501 | 16.6194 | 18.0627 | 18.0627
116 | -0.42833 | -0.8077 | 0.33421 | 0.20963 | 4.2244 | 4.747 | 4.5199 | 4.6942 | 4.495 | 1.232 | 14.8976 | 14.4713 | 14.8976
117 | -0.34254 | -0.52106 | 0.36597 | 0.30116 | 2.7931 | 4.8448 | 5.8344 | 4.8743 | 4.2019 | 2.1919 | 14.7042 | 15.0212 | 15.0212
118 | 1.939 | 1.3714 | 0.97375 | 0.91488 | 3.2254 | 7.5828 | 6.8407 | 6.4101 | 4.2326 | 2.61 | 19.8282 | 16.9087 | 19.8282
119 | 0.47613 | -0.23329 | 0.68301 | 0.40777 | 4.4527 | 5.8575 | 5.1845 | 5.0771 | 4.1681 | 2.5985 | 17.9857 | 16.4038 | 17.9857
120 | 0.26288 | -0.58752 | 0.60368 | 0.27843 | 3.2164 | 5.5848 | 5.8696 | 4.8305 | 4.2499 | 2.1295 | 15.7613 | 15.4654 | 15.7613
121 | 2.1654 | 1.0361 | 0.98482 | 0.84993 | 5.5075 | 7.7941 | 3.9367 | 6.128 | 5.047 | 1.5319 | 20.9615 | 16.0231 | 20.9615
122 | 0.018752 | -0.23771 | 0.50748 | 0.40605 | 3.0975 | 5.2781 | 7.2014 | 5.0738 | 3.3694 | 1.6054 | 15.0547 | 15.2737 | 15.2737
123 | 0.45615 | 0.9444 | 0.67586 | 0.82752 | 3.0218 | 5.8319 | 6.4609 | 6.0493 | 5.1506 | 2.6076 | 17.5105 | 17.2409 | 17.5105
124 | -0.61753 | -0.48603 | 0.26844 | 0.31347 | 5.2061 | 4.5394 | 4.2637 | 4.8979 | 4.172 | 1.9253 | 16.5687 | 15.5671 | 16.5687
125 | 0.69984 | 1.1144 | 0.75799 | 0.86746 | 3.932 | 6.1444 | 6.3613 | 6.1947 | 3.7581 | 1.6706 | 17.9417 | 15.722 | 17.9417
126 | -0.64587 | 1.1014 | 0.25918 | 0.86464 | 4.2409 | 4.5094 | 5.4467 | 6.1837 | 3.5212 | 1.4334 | 16.3673 | 14.6422 | 16.3673
127 | 2.189 | 0.20726 | 0.9857 | 0.5821 | 4.7453 | 7.8151 | 4.4344 | 5.422 | 4.7777 | 1.8743 | 19.8567 | 15.8317 | 19.8567
128 | -0.10208 | 0.99652 | 0.45935 | 0.8405 | 3.8078 | 5.1299 | 5.1766 | 6.094 | 3.7148 | 1.7899 | 16.8215 | 14.489 | 16.8215
129 | 0.70157 | 0.3812 | 0.75853 | 0.64847 | 4.4958 | 6.1466 | 6.3659 | 5.5666 | 5.4674 | 2.0289 | 18.2379 | 18.358 | 18.358
130 | 1.4597 | 0.39856 | 0.92781 | 0.65489 | 4.6115 | 7.074 | 4.4614 | 5.5812 | 4.4377 | 1.7639 | 19.0307 | 15.2745 | 19.0307
131 | 2.6674 | 1.6431 | 0.99618 | 0.94982 | 4.485 | 8.1899 | 5.3996 | 6.6283 | 3.5611 | 1.7063 | 21.0095 | 15.1519 | 21.0095
132 | 1.6777 | 1.4037 | 0.9533 | 0.91979 | 3.2478 | 7.3151 | 6.9168 | 6.4365 | 4.4469 | 1.5161 | 18.5155 | 16.1276 | 18.5155
133 | 1.6877 | 1.255 | 0.95426 | 0.89525 | 3.8331 | 7.3257 | 7.0011 | 6.3133 | 4.255 | 2.2205 | 19.6926 | 17.3097 | 19.6926
134 | -0.15993 | 0.035109 | 0.43647 | 0.514 | 4.9057 | 5.06 | 7.1616 | 5.283 | 4.791 | 2.0362 | 17.2848 | 18.8945 | 18.8945
135 | 1.3521 | 2.6253 | 0.91182 | 0.99567 | 4.4731 | 6.9498 | 4.3402 | 7.287 | 5.7298 | 2.5437 | 21.2536 | 17.0869 | 21.2536
136 | 0.37976 | -0.15091 | 0.64794 | 0.44002 | 3.5339 | 5.734 | 6.2539 | 5.1387 | 3.9001 | 1.6059 | 16.0124 | 15.2938 | 16.0124
137 | 0.50571 | 1.3435 | 0.69347 | 0.91044 | 3.8957 | 5.8955 | 4.7913 | 6.387 | 4.1824 | 2.782 | 18.9602 | 15.6514 | 18.9602
138 | 0.64 | 0.16854 | 0.73891 | 0.56692 | 4.7241 | 6.0678 | 6.7492 | 5.3903 | 4.7491 | 2.2593 | 18.4415 | 18.4817 | 18.4817
139 | 2.1072 | 1.3551 | 0.98245 | 0.91231 | 3.8841 | 7.7417 | 5.871 | 6.3966 | 4.6485 | 2.3142 | 20.3366 | 16.7178 | 20.3366
140 | 0.33706 | 0.92324 | 0.63196 | 0.82206 | 3.4778 | 5.6794 | 5.0304 | 6.0311 | 4.5534 | 2.0573 | 17.2455 | 15.1189 | 17.2455
141 | -0.00050083 | 0.075072 | 0.4998 | 0.52992 | 4.5387 | 5.2543 | 3.8585 | 5.3148 | 4.5855 | 1.6312 | 16.7389 | 14.6139 | 16.7389
142 | 0.53295 | -1.6369 | 0.70296 | 0.050822 | 4.1391 | 5.9304 | 5.895 | 4.3085 | 4.1444 | 1.6198 | 15.9979 | 15.7983 | 15.9979
143 | -0.21572 | -1.3943 | 0.4146 | 0.081611 | 5.403 | 4.9933 | 6.9248 | 4.4004 | 4.2729 | 1.851 | 16.6477 | 18.4518 | 18.4518
144 | 0.90851 | 0.66304 | 0.8182 | 0.74635 | 3.2543 | 6.4093 | 6.0185 | 5.8069 | 5.5736 | 1.6509 | 17.1214 | 16.4972 | 17.1214
145 | -0.56707 | -0.35625 | 0.28533 | 0.36083 | 3.174 | 4.5936 | 5.8098 | 4.9879 | 3.7129 | 1.8024 | 14.5579 | 14.4991 | 14.5579
146 | 1.1694 | -0.050554 | 0.87889 | 0.47984 | 3.1871 | 6.7322 | 4.0717 | 5.2157 | 4.834 | 2.1531 | 17.2881 | 14.2459 | 17.2881
147 | 0.015946 | -0.15926 | 0.50636 | 0.43673 | 3.1997 | 5.2746 | 4.1902 | 5.1324 | 3.4025 | 2.3225 | 15.9292 | 13.1149 | 15.9292
148 | 0.91962 | 0.55036 | 0.82111 | 0.70897 | 4.5735 | 6.4233 | 6.3147 | 5.7102 | 4.5324 | 1.4557 | 18.1628 | 16.8764 | 18.1628
149 | -0.49996 | -1.3472 | 0.30855 | 0.088965 | 4.5435 | 4.667 | 4.2113 | 4.4203 | 3.9555 | 2.1395 | 15.7702 | 14.8497 | 15.7702
150 | 1.131 | -0.045802 | 0.87097 | 0.48173 | 4.5013 | 6.6854 | 4.8446 | 5.2194 | 3.6782 | 1.9305 | 18.3365 | 14.9546 | 18.3365
151 | -0.22755 | 0.14597 | 0.41 | 0.55803 | 3.6708 | 4.9793 | 5.0324 | 5.372 | 4.0661 | 2.1303 | 16.1523 | 14.8996 | 16.1523
152 | -0.76241 | 1.102 | 0.22291 | 0.86476 | 3.3366 | 4.3889 | 6.6176 | 6.1841 | 4.6014 | 2.1357 | 16.0454 | 16.6913 | 16.6913
153 | 1.5507 | 1.4 | 0.93951 | 0.91925 | 4.4288 | 7.1764 | 5.6796 | 6.4336 | 3.5012 | 2.2927 | 20.3315 | 15.9023 | 20.3315
154 | -0.7186 | -0.25937 | 0.23619 | 0.39768 | 3.5454 | 4.4336 | 5.0074 | 5.0579 | 4.4934 | 1.9503 | 14.9872 | 14.9965 | 14.9965
155 | 0.74705 | 2.1916 | 0.77248 | 0.9858 | 3.2711 | 6.2047 | 6.1937 | 7.0251 | 4.2084 | 1.6835 | 18.1844 | 15.3568 | 18.1844
156 | 0.18362 | 0.34506 | 0.57284 | 0.63498 | 4.2281 | 5.4844 | 6.2867 | 5.5363 | 5.736 | 1.8253 | 17.074 | 18.076 | 18.076
157 | 0.39607 | -0.45576 | 0.65397 | 0.32428 | 3.5145 | 5.7548 | 5.6019 | 4.9185 | 5.09 | 1.4192 | 15.607 | 15.6256 | 15.6256
158 | 1.113 | 0.15312 | 0.86715 | 0.56085 | 4.7961 | 6.6634 | 5.7868 | 5.3778 | 4.6256 | 2.5716 | 19.4089 | 17.7802 | 19.4089
159 | 0.72318 | 1.2919 | 0.76522 | 0.90181 | 4.155 | 6.1742 | 6.1797 | 6.3442 | 5.322 | 2.2783 | 18.9518 | 17.935 | 18.9518
160 | 0.32855 | 1.5626 | 0.62875 | 0.94093 | 3.4651 | 5.6685 | 4.5287 | 6.5648 | 5.3399 | 1.9748 | 17.6732 | 15.3084 | 17.6732
161 | 0.069262 | -0.53802 | 0.52761 | 0.29528 | 3.2805 | 5.3408 | 7.316 | 4.8631 | 3.2746 | 2.5828 | 16.0672 | 16.454 | 16.454
162 | 0.26536 | 0.6376 | 0.60463 | 0.73813 | 3.8776 | 5.588 | 4.9414 | 5.785 | 3.8721 | 2.6171 | 17.8677 | 15.3083 | 17.8677
163 | 0.40907 | -1.2843 | 0.65876 | 0.099518 | 5.4307 | 5.7715 | 6.5143 | 4.4477 | 5.6374 | 2.319 | 17.9689 | 19.9014 | 19.9014
164 | -0.94153 | 0.23287 | 0.17322 | 0.59207 | 4.0025 | 4.214 | 5.357 | 5.443 | 3.5039 | 1.2469 | 14.9064 | 14.1102 | 14.9064
165 | -1.0102 | 0.30584 | 0.1562 | 0.62014 | 2.8216 | 4.1503 | 5.2338 | 5.5035 | 4.6096 | 1.8508 | 14.3262 | 14.5157 | 14.5157
166 | -0.7057 | -0.23483 | 0.24019 | 0.40717 | 3.7444 | 4.4469 | 6.0079 | 5.0759 | 3.6917 | 2.003 | 15.2702 | 15.447 | 15.447
167 | 1.7788 | 0.26427 | 0.96237 | 0.60422 | 2.5866 | 7.4216 | 4.9924 | 5.469 | 4.0849 | 2.4022 | 17.8793 | 14.0661 | 17.8793
168 | 1.6343 | 1.1672 | 0.94891 | 0.87844 | 4.6631 | 7.2683 | 4.4949 | 6.2395 | 5.7054 | 1.5005 | 19.6714 | 16.3639 | 19.6714
169 | 0.20156 | -0.43414 | 0.57987 | 0.33209 | 3.7472 | 5.507 | 6.8959 | 4.9334 | 4.4592 | 2.0572 | 16.2448 | 17.1595 | 17.1595
170 | -0.48921 | -0.40748 | 0.31235 | 0.34183 | 3.5944 | 4.6789 | 4.477 | 4.9519 | 4.7724 | 1.6548 | 14.88 | 14.4986 | 14.88
171 | 0.67985 | 0.90211 | 0.7517 | 0.8165 | 3.4072 | 6.1188 | 4.4947 | 6.0129 | 3.6683 | 1.9373 | 17.4762 | 13.5075 | 17.4762
172 | -1.3927 | -1.5047 | 0.081849 | 0.066199 | 4.2814 | 3.8322 | 4.4354 | 4.3565 | 3.4408 | 1.124 | 13.594 | 13.2816 | 13.594
173 | 0.24431 | -0.74577 | 0.59651 | 0.2279 | 3.2858 | 5.5612 | 6.3532 | 4.7312 | 3.5021 | 2.3697 | 15.948 | 15.5109 | 15.948
174 | -1.0838 | -1.29 | 0.13924 | 0.098525 | 3.9273 | 4.0843 | 2.7845 | 4.4452 | 3.7611 | 1.7866 | 14.2433 | 12.2595 | 14.2433
175 | 1.1414 | 1.2354 | 0.87316 | 0.89165 | 2.6236 | 6.6982 | 5.2747 | 6.2969 | 5.5098 | 1.9262 | 17.5449 | 15.3343 | 17.5449
176 | -0.94305 | 0.68087 | 0.17283 | 0.75202 | 4.464 | 4.2126 | 4.5461 | 5.8222 | 4.0925 | 2.3327 | 16.8315 | 15.4354 | 16.8315
177 | 0.79273 | 1.6184 | 0.78603 | 0.94721 | 5.8247 | 6.2629 | 5.3731 | 6.6089 | 3.6583 | 2.9192 | 21.6157 | 17.7753 | 21.6157
178 | 2.237 | 1.4125 | 0.98736 | 0.92109 | 4.8318 | 7.8568 | 6.4649 | 6.4437 | 4.2585 | 2.2374 | 21.3699 | 17.7927 | 21.3699
179 | 2.8515 | 3.0854 | 0.99782 | 0.99898 | 3.7277 | 8.3096 | 4.2517 | 7.5099 | 3.316 | 2.3931 | 21.9403 | 13.6884 | 21.9403
180 | -0.71351 | 0.13213 | 0.23776 | 0.55256 | 4.0816 | 4.4389 | 4.2763 | 5.3607 | 3.675 | 2.1329 | 16.014 | 14.1658 | 16.014
181 | 0.41971 | 0.35275 | 0.66265 | 0.63786 | 4.1927 | 5.7851 | 5.0124 | 5.5427 | 4.381 | 1.819 | 17.3395 | 15.4051 | 17.3395
182 | -0.85193 | -1.6057 | 0.19713 | 0.054165 | 4.2906 | 4.2999 | 6.0347 | 4.3194 | 4.5434 | 1.8258 | 14.7358 | 16.6945 | 16.6945
183 | 0.28654 | -0.3038 | 0.61277 | 0.38064 | 4.1504 | 5.6149 | 4.0369 | 5.0255 | 3.5589 | 2.5498 | 17.3407 | 14.2961 | 17.3407
184 | -1.0077 | -0.94893 | 0.1568 | 0.17133 | 3.8315 | 4.1526 | 6.3431 | 4.6141 | 3.7261 | 2.1461 | 14.7443 | 16.0468 | 16.0468
185 | -0.097817 | 0.95565 | 0.46104 | 0.83038 | 4.6468 | 5.135 | 5.2686 | 6.0589 | 3.2654 | 2.5199 | 18.3606 | 15.7007 | 18.3606
186 | 0.21151 | 0.69767 | 0.58376 | 0.75731 | 4.4557 | 5.5196 | 6.6436 | 5.8367 | 4.418 | 2.3185 | 18.1305 | 17.8358 | 18.1305
187 | -2.2334 | -1.1069 | 0.01276 | 0.13416 | 4.609 | 3.3505 | 6.0891 | 4.5315 | 5.4645 | 2.5019 | 14.993 | 18.6645 | 18.6645
188 | 1.1474 | 1.1471 | 0.8744 | 0.87433 | 4.3336 | 6.7055 | 5.1617 | 6.2225 | 3.1647 | 1.4103 | 18.6719 | 14.0703 | 18.6719
189 | 0.48404 | -0.067092 | 0.68582 | 0.47325 | 4.5988 | 5.8677 | 6.7583 | 5.2029 | 4.2124 | 1.9808 | 17.6501 | 17.5503 | 17.6501
190 | -1.9282 | -1.5923 | 0.026913 | 0.055655 | 4.1269 | 3.4922 | 6.597 | 4.3241 | 4.304 | 2.1432 | 14.0865 | 17.171 | 17.171
191 | -1.293 | -0.70154 | 0.098008 | 0.24148 | 4.2614 | 3.9091 | 6.9104 | 4.7582 | 3.4164 | 1.7618 | 14.6905 | 16.35 | 16.35
192 | 0.55707 | 0.74226 | 0.71126 | 0.77103 | 4.8254 | 5.9614 | 4.5166 | 5.8751 | 3.939 | 2.0776 | 18.7395 | 15.3585 | 18.7395
193 | 1.2022 | 1.424 | 0.88536 | 0.92277 | 4.1106 | 6.7718 | 5.3875 | 6.4531 | 3.8755 | 2.2683 | 19.6039 | 15.6419 | 19.6039
194 | 1.5579 | 1.0119 | 0.94037 | 0.8442 | 3.0404 | 7.1844 | 4.0565 | 6.1072 | 4.4641 | 2.3658 | 18.6978 | 13.9268 | 18.6978
195 | 0.30764 | -0.33127 | 0.62082 | 0.37022 | 3.8938 | 5.6418 | 5.4322 | 5.0058 | 3.8738 | 2.1085 | 16.6498 | 15.3083 | 16.6498
196 | -0.67577 | -0.75246 | 0.24959 | 0.22589 | 3.4915 | 4.478 | 6.0184 | 4.7271 | 4.5835 | 2.5065 | 15.2031 | 16.5999 | 16.5999
197 | 0.4827 | 0.98867 | 0.68534 | 0.83859 | 3.8079 | 5.8659 | 4.4355 | 6.0873 | 4.5773 | 2.1784 | 17.9395 | 14.9991 | 17.9395
198 | 1.4782 | 0.61123 | 0.93032 | 0.72948 | 4.5821 | 7.0951 | 4.8059 | 5.7624 | 4.2251 | 2.4812 | 19.9207 | 16.0943 | 19.9207
199 | -2.2048 | -1.7204 | 0.013734 | 0.042684 | 2.7674 | 3.3623 | 5.2453 | 4.2807 | 4.7871 | 1.859 | 12.2694 | 14.6587 | 14.6587
200 | -1.0117 | -0.90933 | 0.15584 | 0.18159 | 4.4306 | 4.149 | 6.2866 | 4.636 | 4.4525 | 1.7849 | 15.0005 | 16.9546 | 16.9546
201 | -0.53844 | -0.876 | 0.29514 | 0.19051 | 2.2621 | 4.6247 | 5.9961 | 4.6547 | 5.1756 | 2.1037 | 13.6452 | 15.5375 | 15.5375
202 | 0.092029 | -0.51545 | 0.53666 | 0.30312 | 3.9856 | 5.3692 | 6.7552 | 4.8781 | 3.4125 | 2.2065 | 16.4395 | 16.3598 | 16.4395
203 | -0.1673 | 1.2686 | 0.43357 | 0.8977 | 3.4946 | 5.0511 | 4.8209 | 6.3247 | 5.8714 | 1.2755 | 16.1459 | 15.4623 | 16.1459
204 | 0.3829 | 0.24884 | 0.6491 | 0.59826 | 4.5308 | 5.738 | 4.7728 | 5.4562 | 4.6886 | 1.9467 | 17.6717 | 15.9389 | 17.6717
205 | 0.68565 | 0.098593 | 0.75353 | 0.53927 | 2.542 | 6.1263 | 6.171 | 5.3337 | 4.7733 | 1.6882 | 15.6901 | 15.1745 | 15.6901
206 | 1.081 | -0.13447 | 0.86016 | 0.44652 | 4.2414 | 6.6242 | 4.1374 | 5.1512 | 3.3107 | 1.7433 | 17.76 | 13.4327 | 17.76
207 | 0.47014 | 1.3527 | 0.68087 | 0.91192 | 2.6046 | 5.8498 | 5.7459 | 6.3946 | 4.0719 | 1.6878 | 16.5369 | 14.1103 | 16.5369
208 | 0.94878 | 0.10793 | 0.82863 | 0.54297 | 3.1443 | 6.4599 | 6.777 | 5.3412 | 4.0852 | 2.12 | 17.0654 | 16.1266 | 17.0654
209 | 1.9612 | 2.0032 | 0.97507 | 0.97742 | 3.6715 | 7.6044 | 6.0923 | 6.8964 | 4.7018 | 1.99 | 20.1622 | 16.4556 | 20.1622
210 | -0.64151 | 0.41018 | 0.2606 | 0.65916 | 3.5241 | 4.514 | 5.9955 | 5.5911 | 3.8513 | 1.7353 | 15.3644 | 15.1062 | 15.3644
211 | -1.4753 | -1.1986 | 0.070063 | 0.11534 | 4.0396 | 3.7718 | 6.94 | 4.487 | 3.8127 | 2.5949 | 14.8933 | 17.3872 | 17.3872
212 | -0.55008 | -0.56385 | 0.29113 | 0.28643 | 4.7817 | 4.612 | 5.9384 | 4.846 | 3.2959 | 2.1354 | 16.3752 | 16.1513 | 16.3752
213 | 0.28567 | 0.24311 | 0.61244 | 0.59604 | 3.6598 | 5.6138 | 2.7984 | 5.4515 | 4.9244 | 2.3899 | 17.115 | 13.7725 | 17.115
214 | 0.39905 | 0.48067 | 0.65507 | 0.68462 | 5.3125 | 5.7587 | 7.4409 | 5.6508 | 5.6412 | 1.679 | 18.4009 | 20.0736 | 20.0736
215 | 1.5429 | 2.457 | 0.93858 | 0.993 | 3.3119 | 7.1678 | 5.1864 | 7.1912 | 5.447 | 1.8086 | 19.4796 | 15.754 | 19.4796
216 | -0.86521 | -1.6239 | 0.19346 | 0.052202 | 5.2689 | 4.287 | 6.6201 | 4.313 | 3.9654 | 1.7136 | 15.5825 | 17.568 | 17.568
217 | -0.48069 | -0.66316 | 0.31537 | 0.25362 | 3.5303 | 4.6884 | 5.8398 | 4.7822 | 4.71 | 1.9577 | 14.9585 | 16.0378 | 16.0378
218 | 0.0014633 | -0.21687 | 0.50058 | 0.41415 | 3.5067 | 5.2567 | 6.4552 | 5.0892 | 4.606 | 1.5114 | 15.3641 | 16.0794 | 16.0794
219 | 0.54682 | -0.29942 | 0.70775 | 0.38231 | 4.3932 | 5.9483 | 6.4971 | 5.0287 | 4.2747 | 1.5466 | 16.9168 | 16.7116 | 16.9168
220 | 0.28289 | 0.65568 | 0.61137 | 0.74399 | 3.8491 | 5.6103 | 6.6207 | 5.8005 | 3.3832 | 2.1686 | 17.4285 | 16.0215 | 17.4285
221 | 0.21467 | 0.39913 | 0.58499 | 0.6551 | 4.5937 | 5.5236 | 5.6878 | 5.5817 | 3.5491 | 2.3681 | 18.0671 | 16.1987 | 18.0671
222 | -1.4626 | -2.0059 | 0.071782 | 0.022434 | 3.3799 | 3.7808 | 6.0495 | 4.1993 | 6.2579 | 2.3999 | 13.7599 | 18.0872 | 18.0872
223 | -0.39706 | 0.5498 | 0.34566 | 0.70877 | 3.4376 | 4.7824 | 6.2886 | 5.7097 | 3.8151 | 2.3537 | 16.2834 | 15.8951 | 16.2834
224 | -0.72132 | 0.18649 | 0.23535 | 0.57397 | 4.0386 | 4.4308 | 5.71 | 5.405 | 5.3983 | 2.3746 | 16.249 | 17.5214 | 17.5214
225 | 0.84771 | 0.33734 | 0.8017 | 0.63207 | 2.6732 | 6.3326 | 7.049 | 5.5298 | 4.2394 | 1.6423 | 16.1779 | 15.6039 | 16.1779
226 | 1.5625 | 0.76819 | 0.94091 | 0.77881 | 2.7396 | 7.1895 | 4.6996 | 5.8975 | 5.3158 | 1.8582 | 17.6848 | 14.6132 | 17.6848
227 | 0.003547 | 0.77975 | 0.50142 | 0.78223 | 4.8481 | 5.2593 | 5.5323 | 5.9074 | 4.3823 | 2.4292 | 18.444 | 17.192 | 18.444
228 | 0.13724 | -0.27986 | 0.55458 | 0.38979 | 3.2446 | 5.4259 | 6.7832 | 5.0429 | 4.8074 | 1.9481 | 15.6615 | 16.7833 | 16.7833
229 | 1.0053 | 0.30752 | 0.84263 | 0.62078 | 3.9426 | 6.5305 | 5.1879 | 5.5049 | 3.7799 | 1.7308 | 17.7088 | 14.6412 | 17.7088
230 | 1.0065 | 0.92727 | 0.8429 | 0.82311 | 3.4744 | 6.5319 | 7.4005 | 6.0345 | 5.1769 | 1.972 | 18.0129 | 18.0238 | 18.0238
231 | 1.0559 | 1.0791 | 0.85448 | 0.85973 | 4.028 | 6.5931 | 5.6174 | 6.1646 | 3.6093 | 2.4175 | 19.2033 | 15.6722 | 19.2033
232 | 0.17445 | -0.0067327 | 0.56924 | 0.49731 | 2.6829 | 5.4728 | 5.8227 | 5.2499 | 3.9995 | 2.4482 | 15.8538 | 14.9533 | 15.8538
233 | -1.3115 | 0.13493 | 0.094837 | 0.55366 | 4.7092 | 3.8944 | 7.1628 | 5.363 | 3.7937 | 2.4541 | 16.4207 | 18.1197 | 18.1197
234 | -1.1802 | 0.73106 | 0.11897 | 0.76763 | 3.86 | 4.0012 | 5.6003 | 5.8654 | 3.0754 | 2.3493 | 16.076 | 14.885 | 16.076
235 | -1.3404 | -1.5577 | 0.090066 | 0.059656 | 4.0275 | 3.872 | 6.0711 | 4.3367 | 3.427 | 2.3745 | 14.6106 | 15.9001 | 15.9001
236 | -0.96757 | 1.1185 | 0.16663 | 0.86833 | 3.7926 | 4.1896 | 5.6914 | 6.1982 | 5.966 | 1.6445 | 15.8249 | 17.0944 | 17.0944
237 | -0.10082 | 0.3766 | 0.45985 | 0.64676 | 2.9119 | 5.1314 | 6.5138 | 5.5628 | 3.7854 | 2.0054 | 15.6114 | 15.2166 | 15.6114
238 | 1.0767 | 1.881 | 0.8592 | 0.97001 | 4.156 | 6.6189 | 4.4464 | 6.8085 | 4.9254 | 1.9366 | 19.5199 | 15.4643 | 19.5199
239 | -0.042762 | -0.089773 | 0.48295 | 0.46423 | 4.762 | 5.2022 | 6.4562 | 5.1854 | 4.0879 | 1.5573 | 16.7069 | 16.8634 | 16.8634
240 | -1.0625 | -0.65946 | 0.14401 | 0.2548 | 4.088 | 4.1032 | 6.5129 | 4.7845 | 4.0343 | 1.4987 | 14.4743 | 16.1338 | 16.1338
241 | -1.4853 | -1.8522 | 0.068737 | 0.031998 | 4.1656 | 3.7647 | 7.3897 | 4.2405 | 4.4029 | 2.3746 | 14.5454 | 18.3328 | 18.3328
242 | -0.031128 | -0.95799 | 0.48758 | 0.16903 | 3.5073 | 5.2165 | 6.3935 | 4.6092 | 3.4662 | 1.9064 | 15.2394 | 15.2734 | 15.2734
243 | 1.1862 | 0.95913 | 0.88224 | 0.83125 | 3.0918 | 6.7525 | 5.8768 | 6.0619 | 3.6385 | 1.8594 | 17.7657 | 14.4666 | 17.7657
244 | -0.1227 | -0.28306 | 0.45117 | 0.38857 | 4.3401 | 5.1049 | 4.5764 | 5.0406 | 4.8149 | 1.6323 | 16.1178 | 15.3637 | 16.1178
245 | -1.6306 | -1.6097 | 0.051487 | 0.053737 | 4.6589 | 3.6662 | 5.8334 | 4.318 | 4.1712 | 2.1483 | 14.7914 | 16.8118 | 16.8118
246 | 0.81328 | -1.0905 | 0.79197 | 0.13774 | 2.9477 | 6.289 | 7.0138 | 4.5398 | 5.0361 | 2.2464 | 16.0228 | 17.244 | 17.244
247 | -1.5011 | -0.14704 | 0.066668 | 0.44155 | 3.5266 | 3.7535 | 3.8948 | 5.1416 | 5.0541 | 1.6876 | 14.1093 | 14.163 | 14.163
248 | 0.061251 | -0.75872 | 0.52442 | 0.22401 | 3.6278 | 5.3308 | 6.4586 | 4.7233 | 3.9224 | 2.2647 | 15.9467 | 16.2734 | 16.2734
249 | -1.2717 | 0.52087 | 0.10173 | 0.69877 | 5.1789 | 3.926 | 5.2618 | 5.685 | 5.8582 | 1.9161 | 16.706 | 18.2149 | 18.2149
250 | -0.62895 | -1.0105 | 0.26469 | 0.15612 | 4.5939 | 4.5273 | 5.1622 | 4.581 | 3.3569 | 2.6227 | 16.3249 | 15.7357 | 16.3249
251 | -0.065749 | 0.72232 | 0.47379 | 0.76495 | 3.5303 | 5.1741 | 5.3404 | 5.8579 | 3.9323 | 1.9055 | 16.4678 | 14.7086 | 16.4678
252 | 0.96853 | -0.70355 | 0.83361 | 0.24086 | 4.0903 | 6.4846 | 6.6042 | 4.757 | 4.6634 | 2.2455 | 17.5774 | 17.6034 | 17.6034
253 | 0.9329 | 0.63506 | 0.82457 | 0.7373 | 4.8192 | 6.44 | 7.2856 | 5.7828 | 3.589 | 2.6719 | 19.714 | 18.3657 | 19.714
254 | -0.88374 | -0.42439 | 0.18842 | 0.33564 | 4.2796 | 4.269 | 5.3909 | 4.9401 | 3.782 | 1.6193 | 15.1081 | 15.0719 | 15.1081
255 | 1.4873 | 1.8044 | 0.93154 | 0.96442 | 5.1788 | 7.1054 | 5.6068 | 6.7517 | 3.8876 | 1.9169 | 20.9528 | 16.59 | 20.9528
256 | 0.18831 | 0.89661 | 0.57468 | 0.81504 | 4.1406 | 5.4903 | 5.4833 | 6.0081 | 3.1871 | 1.6979 | 17.3369 | 14.5089 | 17.3369
257 | -0.90278 | -0.5206 | 0.18332 | 0.30132 | 3.8454 | 4.2507 | 5.2725 | 4.8746 | 4.9848 | 1.7274 | 14.6983 | 15.8302 | 15.8302
258 | 1.6389 | 1.3664 | 0.94938 | 0.9141 | 4.7697 | 7.2733 | 7.2884 | 6.406 | 4.9882 | 2.4357 | 20.8846 | 19.482 | 20.8846
259 | -0.8076 | 0.40185 | 0.20966 | 0.6561 | 3.136 | 4.3436 | 6.3149 | 5.584 | 5.0024 | 2.3718 | 15.4355 | 16.8252 | 16.8252
260 | -0.01699 | -1.0374 | 0.49322 | 0.14977 | 3.8248 | 5.2339 | 3.8604 | 4.5669 | 4.9308 | 1.9033 | 15.529 | 14.5193 | 15.529
261 | -1.3716 | -1.0928 | 0.085096 | 0.13724 | 4.2224 | 3.8481 | 5.242 | 4.5386 | 4.5672 | 1.7955 | 14.4047 | 15.8272 | 15.8272
262 | 0.46019 | -0.0050561 | 0.67731 | 0.49798 | 5.2545 | 5.837 | 5.6151 | 5.2513 | 3.6687 | 1.7902 | 18.133 | 16.3285 | 18.133
263 | -1.1786 | 0.61376 | 0.11928 | 0.73031 | 3.7252 | 4.0025 | 6.8657 | 5.7645 | 3.4013 | 1.5957 | 15.088 | 15.588 | 15.588
264 | -0.80329 | -1.72 | 0.2109 | 0.042716 | 3.6598 | 4.3479 | 6.4458 | 4.2808 | 5.0533 | 1.7942 | 14.0828 | 16.9532 | 16.9532
265 | 0.073421 | 0.87446 | 0.52926 | 0.80907 | 3.034 | 5.346 | 7.273 | 5.9891 | 4.827 | 1.7547 | 16.1237 | 16.8887 | 16.8887
266 | -1.7718 | -0.80255 | 0.038213 | 0.21112 | 3.6386 | 3.5791 | 6.7683 | 4.6972 | 3.9379 | 2.2948 | 14.2098 | 16.6397 | 16.6397
267 | -0.18678 | -0.11247 | 0.42592 | 0.45523 | 3.7702 | 5.0278 | 4.6078 | 5.1679 | 3.8331 | 2.4802 | 16.4461 | 14.6912 | 16.4461
268 | -0.55685 | -0.66714 | 0.28881 | 0.25234 | 3.6479 | 4.6047 | 4.7509 | 4.7797 | 4.0652 | 2.5542 | 15.5864 | 15.0181 | 15.5864
269 | -0.82849 | -0.24413 | 0.2037 | 0.40356 | 4.2959 | 4.3229 | 5.0336 | 5.0691 | 4.1713 | 1.8065 | 15.4943 | 15.3072 | 15.4943
270 | 1.0134 | 1.7994 | 0.84456 | 0.96402 | 4.6307 | 6.5405 | 4.5653 | 6.7479 | 3.7608 | 2.0929 | 20.012 | 15.0497 | 20.012
271 | 1.4172 | 0.8224 | 0.92179 | 0.79458 | 4.4243 | 7.0254 | 4.2254 | 5.9442 | 3.5399 | 1.184 | 18.5779 | 13.3735 | 18.5779
272 | -0.4411 | -1.8698 | 0.32957 | 0.030758 | 4.0571 | 4.7326 | 6.6958 | 4.2355 | 5.3123 | 2.1644 | 15.1896 | 18.2296 | 18.2296
273 | -0.66076 | -0.93903 | 0.25438 | 0.17386 | 4.6988 | 4.4937 | 6.3893 | 4.6195 | 3.9216 | 2.3548 | 16.1668 | 17.3645 | 17.3645
274 | 1.2364 | -0.54169 | 0.89184 | 0.29401 | 4.6101 | 6.8129 | 4.0129 | 4.8606 | 4.4722 | 2.6715 | 18.9551 | 15.7667 | 18.9551
275 | -0.88673 | -0.71938 | 0.18761 | 0.23595 | 3.4228 | 4.2662 | 4.9255 | 4.7472 | 4.5561 | 2.1589 | 14.5951 | 15.0633 | 15.0633
276 | -0.053479 | 0.28843 | 0.47868 | 0.61349 | 3.6177 | 5.1891 | 6.5585 | 5.489 | 5.1368 | 2.1683 | 16.4641 | 17.4813 | 17.4813
277 | -0.38632 | -0.43969 | 0.34963 | 0.33008 | 3.0708 | 4.7946 | 5.1022 | 4.9296 | 4.2774 | 1.8454 | 14.6404 | 14.2958 | 14.6404
278 | -0.33396 | -0.096274 | 0.3692 | 0.46165 | 5.0532 | 4.8547 | 6.2553 | 5.1804 | 5.0271 | 1.8445 | 16.9328 | 18.18 | 18.18
279 | -1.509 | -1.6058 | 0.065645 | 0.054161 | 3.9409 | 3.748 | 4.6655 | 4.3194 | 3.239 | 2.3201 | 14.3283 | 14.1655 | 14.3283
280 | 0.1832 | -0.12934 | 0.57268 | 0.44854 | 4.6708 | 5.4838 | 4.9582 | 5.1551 | 3.8469 | 1.6301 | 16.9399 | 15.106 | 16.9399
281 | -0.49133 | -0.90432 | 0.3116 | 0.18291 | 2.681 | 4.6766 | 7.3661 | 4.6388 | 4.5655 | 2.0541 | 14.0504 | 16.6667 | 16.6667
282 | 0.054108 | 0.44444 | 0.52158 | 0.67164 | 5.718 | 5.3219 | 5.2787 | 5.62 | 5.2973 | 2.2465 | 18.9065 | 18.5405 | 18.9065
283 | 1.5347 | 0.21272 | 0.93757 | 0.58423 | 3.5334 | 7.1587 | 5.7875 | 5.4265 | 5.1529 | 2.3223 | 18.4409 | 16.7961 | 18.4409
284 | 0.47153 | -0.028758 | 0.68137 | 0.48853 | 3.6363 | 5.8516 | 3.5795 | 5.2327 | 4.2665 | 2.5492 | 17.2698 | 14.0314 | 17.2698
285 | -0.56821 | 0.41742 | 0.28495 | 0.66181 | 3.6975 | 4.5924 | 6.8974 | 5.5972 | 5.9319 | 1.3387 | 15.2258 | 17.8656 | 17.8656
286 | -0.92486 | -1.6888 | 0.17752 | 0.045628 | 3.9967 | 4.2297 | 4.9273 | 4.291 | 4.6867 | 1.4005 | 13.9179 | 15.0111 | 15.0111
287 | 0.096824 | -0.59287 | 0.53857 | 0.27663 | 4.1684 | 5.3752 | 5.1337 | 4.8271 | 3.8947 | 2.0286 | 16.3993 | 15.2254 | 16.3993
288 | -0.51176 | -0.45362 | 0.30441 | 0.32505 | 3.7668 | 4.654 | 4.3698 | 4.92 | 3.5169 | 1.7495 | 15.0903 | 13.4029 | 15.0903
289 | -0.49791 | 0.10571 | 0.30927 | 0.54209 | 5.1065 | 4.6693 | 6.9099 | 5.3394 | 5.1402 | 1.8266 | 16.9417 | 18.9831 | 18.9831
290 | -0.4998 | -0.56176 | 0.30861 | 0.28714 | 3.7615 | 4.6672 | 4.8776 | 4.8474 | 3.8903 | 2.3258 | 15.6019 | 14.8552 | 15.6019
291 | 1.0681 | 0.47075 | 0.85727 | 0.68109 | 4.1114 | 6.6083 | 6.1824 | 5.6423 | 3.6763 | 1.8626 | 18.2246 | 15.8327 | 18.2246
292 | 0.76892 | 1.2765 | 0.77903 | 0.89911 | 3.0971 | 6.2326 | 5.0832 | 6.3314 | 4.1022 | 2.2199 | 17.8809 | 14.5024 | 17.8809
293 | 0.11414 | 0.17021 | 0.54544 | 0.56758 | 3.4334 | 5.3969 | 6.141 | 5.3917 | 3.8676 | 1.86 | 16.082 | 15.302 | 16.082
294 | 0.37679 | 1.3919 | 0.64683 | 0.91802 | 4.3649 | 5.7302 | 5.7801 | 6.4269 | 4.5776 | 2.2431 | 18.765 | 16.9657 | 18.765
295 | -0.41416 | 0.94213 | 0.33938 | 0.82694 | 4.9714 | 4.763 | 6.947 | 6.0473 | 5.7308 | 2.1605 | 17.9422 | 19.8096 | 19.8096
296 | -0.60997 | 0.54953 | 0.27094 | 0.70868 | 4.3802 | 4.5475 | 6.5897 | 5.7095 | 4.5974 | 2.151 | 16.7881 | 17.7183 | 17.7183
297 | -0.86571 | 0.57555 | 0.19332 | 0.71754 | 3.9102 | 4.2865 | 4.523 | 5.7318 | 3.6998 | 2.3698 | 16.2983 | 14.5029 | 16.2983
298 | 0.11245 | -1.0264 | 0.54477 | 0.15235 | 5.0534 | 5.3948 | 4.9957 | 4.5727 | 3.576 | 1.6012 | 16.6222 | 15.2264 | 16.6222
299 | -0.23994 | 0.63928 | 0.40519 | 0.73868 | 3.8989 | 4.9646 | 4.7369 | 5.7864 | 3.8256 | 2.3916 | 17.0416 | 14.853 | 17.0416
300 | -1.433 | -0.12106 | 0.075923 | 0.45182 | 4.0675 | 3.8023 | 6.511 | 5.1614 | 4.4439 | 2.0432 | 15.0745 | 17.0657 | 17.0657
301 | -2.4687 | -0.98481 | 0.0067809 | 0.16236 | 4.3006 | 3.2642 | 6.4534 | 4.5947 | 3.7186 | 1.9289 | 14.0884 | 16.4015 | 16.4015
302 | -0.46266 | 0.98722 | 0.3218 | 0.83823 | 4.571 | 4.7084 | 6.5776 | 6.086 | 4.2672 | 2.3665 | 17.732 | 17.7823 | 17.7823
303 | 1.3797 | 0.8127 | 0.91617 | 0.7918 | 3.7083 | 6.9821 | 5.7562 | 5.9358 | 5.1578 | 1.8539 | 18.4801 | 16.4762 | 18.4801
304 | -1.1388 | -0.43536 | 0.12739 | 0.33165 | 3.8825 | 4.0364 | 6.4733 | 4.9325 | 3.7123 | 1.2674 | 14.1188 | 15.3355 | 15.3355
305 | 1.1867 | 1.2628 | 0.88233 | 0.89667 | 4.185 | 6.7531 | 6.4477 | 6.3199 | 4.8794 | 2.2535 | 19.5115 | 17.7657 | 19.5115
306 | 0.88465 | -0.35409 | 0.81183 | 0.36164 | 3.276 | 6.3793 | 5.3634 | 4.9895 | 4.0829 | 1.985 | 16.6298 | 14.7074 | 16.6298
307 | 0.30416 | 0.33736 | 0.6195 | 0.63208 | 5.7524 | 5.6374 | 5.0057 | 5.5298 | 3.2615 | 1.9562 | 18.8759 | 15.9758 | 18.8759
308 | 0.52955 | 1.4009 | 0.70179 | 0.91938 | 5.1986 | 5.9261 | 4.3493 | 6.4343 | 5.1026 | 2.0758 | 19.6348 | 16.7262 | 19.6348
309 | 0.70759 | 0.68768 | 0.7604 | 0.75417 | 4.6617 | 6.1543 | 5.7784 | 5.8281 | 6.1722 | 2.0443 | 18.6884 | 18.6565 | 18.6884
310 | -0.27176 | -0.2732 | 0.3929 | 0.39235 | 5.2553 | 4.9272 | 5.862 | 5.0477 | 4.1528 | 1.3872 | 16.6174 | 16.6573 | 16.6573
311 | 0.1617 | 0.45405 | 0.56423 | 0.6751 | 4.4923 | 5.4567 | 6.9441 | 5.6282 | 4.5092 | 2.4674 | 18.0446 | 18.4129 | 18.4129
312 | -1.5914 | -0.59252 | 0.055763 | 0.27675 | 3.2524 | 3.6919 | 5.2916 | 4.8273 | 3.8227 | 1.4286 | 13.2002 | 13.7953 | 13.7953
313 | 1.3321 | 1.048 | 0.90859 | 0.85268 | 4.7166 | 6.9264 | 4.7445 | 6.1381 | 4.9161 | 2.5922 | 20.3733 | 16.9695 | 20.3733
314 | -0.43224 | -0.4424 | 0.33278 | 0.3291 | 3.0404 | 4.7426 | 5.0571 | 4.9277 | 3.3456 | 1.7483 | 14.459 | 13.1914 | 14.459
315 | -2.5413 | 0.054822 | 0.0055215 | 0.52186 | 2.9603 | 3.2412 | 4.9742 | 5.2987 | 4.5705 | 1.8512 | 13.3514 | 14.3562 | 14.3562
316 | -0.59186 | -1.9855 | 0.27697 | 0.023544 | 4.3048 | 4.5669 | 5.4005 | 4.2044 | 3.6946 | 1.411 | 14.4871 | 14.8109 | 14.8109
317 | 2.087 | 1.3058 | 0.98156 | 0.9042 | 2.5242 | 7.7232 | 6.8605 | 6.3558 | 3.7299 | 1.7467 | 18.3499 | 14.8613 | 18.3499
318 | 1.2144 | 1.3299 | 0.8877 | 0.90823 | 3.4856 | 6.7865 | 6.3799 | 6.3758 | 5.9113 | 1.5618 | 18.2096 | 17.3385 | 18.2096
319 | -2.3955 | -2.3979 | 0.0082996 | 0.0082448 | 3.4383 | 3.2891 | 7.2647 | 4.1183 | 3.1817 | 2.0099 | 12.8556 | 15.8946 | 15.8946
320 | -1.1847 | -1.396 | 0.11807 | 0.081352 | 3.6558 | 3.9974 | 6.1266 | 4.3997 | 5.1392 | 2.122 | 14.1749 | 17.0436 | 17.0436
321 | 0.036067 | 0.073419 | 0.51439 | 0.52926 | 3.9127 | 5.2995 | 5.1989 | 5.3135 | 3.9757 | 2.0057 | 16.5313 | 15.0929 | 16.5313
322 | -0.3532 | 0.12681 | 0.36197 | 0.55046 | 2.9082 | 4.8326 | 4.7329 | 5.3564 | 3.4999 | 2.3168 | 15.4139 | 13.4577 | 15.4139
323 | -0.18377 | 0.8649 | 0.4271 | 0.80645 | 4.5267 | 5.0314 | 3.5781 | 5.9808 | 5.9285 | 1.3134 | 16.8523 | 15.3467 | 16.8523
324 | 0.53114 | 0.59838 | 0.70234 | 0.72521 | 4.7398 | 5.9281 | 7.363 | 5.7513 | 3.3552 | 1.636 | 18.0553 | 17.094 | 18.0553
325 | -0.99387 | 0.42327 | 0.16014 | 0.66395 | 4.0639 | 4.1653 | 4.1063 | 5.6021 | 3.4946 | 1.5218 | 15.3531 | 13.1866 | 15.3531
326 | 0.15178 | -0.30402 | 0.56032 | 0.38055 | 4.751 | 5.4442 | 3.919 | 5.0254 | 5.3775 | 2.5448 | 17.7654 | 16.5923 | 17.7654
327 | 0.40077 | 0.014084 | 0.65571 | 0.50562 | 3.3579 | 5.7609 | 6.9053 | 5.2663 | 4.3798 | 1.8737 | 16.2588 | 16.5167 | 16.5167
328 | -0.97739 | -0.81862 | 0.16419 | 0.2065 | 4.8838 | 4.1805 | 6.7815 | 4.6878 | 3.2571 | 1.4667 | 15.2188 | 16.3891 | 16.3891
329 | 0.41272 | 1.3133 | 0.66009 | 0.90545 | 3.366 | 5.7762 | 6.9202 | 6.362 | 5.102 | 1.7515 | 17.2556 | 17.1397 | 17.2556
330 | -0.72946 | -0.99647 | 0.23286 | 0.15951 | 4.615 | 4.4225 | 4.6635 | 4.5885 | 4.2827 | 1.7288 | 15.3548 | 15.29 | 15.3548
331 | -0.068318 | -0.89731 | 0.47277 | 0.18478 | 4.8135 | 5.171 | 5.4637 | 4.6427 | 4.3678 | 2.0862 | 16.7134 | 16.7312 | 16.7312
332 | 2.0997 | 1.1812 | 0.98212 | 0.88124 | 3.7391 | 7.7348 | 4.591 | 6.2513 | 5.1111 | 1.8078 | 19.5331 | 15.2491 | 19.5331
333 | -0.38366 | -0.85489 | 0.35061 | 0.19631 | 4.4575 | 4.7977 | 6.5022 | 4.6668 | 3.46 | 1.362 | 15.284 | 15.7817 | 15.7817
334 | 1.4592 | 1.5672 | 0.92774 | 0.94147 | 3.7676 | 7.0735 | 4.5442 | 6.5685 | 3.5439 | 1.3885 | 18.7981 | 13.2443 | 18.7981
335 | -0.71677 | -0.79327 | 0.23676 | 0.21381 | 4.1909 | 4.4355 | 4.3859 | 4.7027 | 3.7137 | 1.503 | 14.8321 | 13.7935 | 14.8321
336 | 1.009 | -0.2436 | 0.8435 | 0.40377 | 4.2086 | 6.535 | 6.5379 | 5.0694 | 3.3827 | 2.5538 | 18.3669 | 16.683 | 18.3669
337 | 0.78471 | -0.24631 | 0.78369 | 0.40272 | 4.0434 | 6.2527 | 5.3538 | 5.0674 | 4.4426 | 2.0412 | 17.4047 | 15.8809 | 17.4047
338 | -0.24171 | -0.6357 | 0.4045 | 0.26249 | 4.1318 | 4.9626 | 6.707 | 4.7995 | 3.7624 | 1.8363 | 15.7302 | 16.4375 | 16.4375
339 | 0.026226 | 0.2342 | 0.51046 | 0.59258 | 3.16 | 5.2873 | 4.9213 | 5.4441 | 3.4007 | 2.4934 | 16.3849 | 13.9754 | 16.3849
340 | 0.033725 | -0.67734 | 0.51345 | 0.2491 | 4.0005 | 5.2966 | 6.3873 | 4.7733 | 3.2154 | 1.9248 | 15.9952 | 15.528 | 15.9952
341 | -0.14051 | 0.23327 | 0.44413 | 0.59222 | 4.643 | 5.0833 | 6.7621 | 5.4434 | 4.1102 | 1.6773 | 16.847 | 17.1926 | 17.1926
342 | -0.43771 | 0.30009 | 0.3308 | 0.61794 | 3.061 | 4.7364 | 4.6161 | 5.4987 | 5.0346 | 2.5946 | 15.8908 | 15.3063 | 15.8908
343 | -1.3462 | -1.5058 | 0.089113 | 0.066064 | 4.8561 | 3.8675 | 6.1237 | 4.3561 | 4.5306 | 1.8514 | 14.9311 | 17.3618 | 17.3618
344 | -1.4826 | -1.2854 | 0.069084 | 0.099324 | 2.8361 | 3.7666 | 6.1937 | 4.4472 | 4.546 | 2.6157 | 13.6655 | 16.1914 | 16.1914
345 | -0.49003 | -0.31307 | 0.31206 | 0.37711 | 2.3893 | 4.678 | 6.7537 | 5.0188 | 4.5725 | 1.9189 | 14.005 | 15.6344 | 15.6344
346 | 1.0781 | 0.97166 | 0.8595 | 0.83439 | 2.9964 | 6.6205 | 6.9149 | 6.0727 | 3.6745 | 2.6873 | 18.3769 | 16.273 | 18.3769
347 | -1.3202 | -0.86787 | 0.093379 | 0.19273 | 2.5678 | 3.8876 | 6.7083 | 4.6594 | 3.94 | 2.5583 | 13.6731 | 15.7745 | 15.7745
348 | 0.13853 | 0.38416 | 0.55509 | 0.64957 | 4.1978 | 5.4275 | 5.283 | 5.5691 | 4.086 | 1.8953 | 17.0897 | 15.462 | 17.0897
349 | -0.46376 | 0.98315 | 0.32141 | 0.83723 | 3.5704 | 4.7072 | 6.9297 | 6.0826 | 4.6965 | 1.6973 | 16.0574 | 16.8938 | 16.8938
350 | -2.4815 | -3.083 | 0.0065411 | 0.0010248 | 2.534 | 3.26 | 6.1209 | 4.0409 | 4.6346 | 2.2653 | 12.1002 | 15.5548 | 15.5548
351 | -0.053701 | -0.47788 | 0.47859 | 0.31637 | 3.8551 | 5.1888 | 5.7973 | 4.9034 | 4.0266 | 1.6818 | 15.6292 | 15.3609 | 15.6292
352 | -0.035985 | -1.0143 | 0.48565 | 0.15522 | 4.4966 | 5.2106 | 4.0596 | 4.579 | 4.241 | 2.5283 | 16.8145 | 15.3255 | 16.8145
353 | -0.44729 | -0.98539 | 0.32733 | 0.16222 | 3.9482 | 4.7256 | 5.8039 | 4.5944 | 3.6124 | 1.811 | 15.0792 | 15.1755 | 15.1755
354 | 0.12928 | 1.4059 | 0.55143 | 0.92013 | 4.7853 | 5.4159 | 6.352 | 6.4384 | 4.5986 | 1.336 | 17.9755 | 17.0718 | 17.9755
355 | 0.030655 | -1.2964 | 0.51223 | 0.097415 | 4.0186 | 5.2928 | 5.7105 | 4.4423 | 4.388 | 1.6971 | 15.4509 | 15.8142 | 15.8142
356 | 0.4662 | -0.32224 | 0.67946 | 0.37363 | 5.5387 | 5.8448 | 3.6106 | 5.0122 | 4.8946 | 2.13 | 18.5257 | 16.1739 | 18.5257
357 | -0.20549 | 0.16944 | 0.4186 | 0.56728 | 4.7671 | 5.0055 | 5.6873 | 5.3911 | 5.9918 | 2.7434 | 17.907 | 19.1896 | 19.1896
358 | -1.4108 | -1.1339 | 0.079145 | 0.12843 | 3.9084 | 3.8187 | 6.614 | 4.5182 | 5.6534 | 2.2548 | 14.5 | 18.4305 | 18.4305
359 | 0.01407 | 0.39153 | 0.50561 | 0.6523 | 4.4905 | 5.2723 | 7.4083 | 5.5753 | 3.8287 | 2.4116 | 17.7497 | 18.139 | 18.139
360 | 1.3313 | 0.53417 | 0.90846 | 0.70339 | 4.6042 | 6.9255 | 5.0084 | 5.6964 | 3.6966 | 2.4489 | 19.675 | 15.7581 | 19.675
361 | -0.88974 | 0.0522 | 0.1868 | 0.52082 | 3.3125 | 4.2633 | 4.89 | 5.2966 | 3.8024 | 2.1014 | 14.9737 | 14.1062 | 14.9737
362 | 1.3364 | 1.0994 | 0.90928 | 0.8642 | 3.7446 | 6.9314 | 6.5488 | 6.1819 | 5.3289 | 1.7482 | 18.6062 | 17.3705 | 18.6062
363 | 0.17357 | -0.11852 | 0.5689 | 0.45283 | 3.6815 | 5.4717 | 5.2655 | 5.1633 | 4.406 | 1.8219 | 16.1383 | 15.1748 | 16.1383
364 | 0.10116 | -0.30263 | 0.54029 | 0.38109 | 4.666 | 5.3807 | 5.4487 | 5.0264 | 4.7075 | 2.3513 | 17.4244 | 17.1736 | 17.4244
365 | -0.66522 | 0.48551 | 0.25296 | 0.68634 | 3.8031 | 4.489 | 6.4843 | 5.6549 | 5.3784 | 2.5242 | 16.4712 | 18.19 | 18.19
366 | 1.3864 | 1.235 | 0.91719 | 0.89159 | 5.286 | 6.9898 | 6.3324 | 6.2966 | 3.4961 | 1.8204 | 20.3928 | 16.935 | 20.3928
367 | 0.82815 | 1.1322 | 0.79621 | 0.87122 | 3.2366 | 6.3078 | 6.7315 | 6.2098 | 5.1785 | 1.8746 | 17.6288 | 17.0211 | 17.6288
368 | 0.36402 | 0.41774 | 0.64208 | 0.66193 | 3.1541 | 5.7138 | 5.8997 | 5.5974 | 4.4058 | 1.2695 | 15.7348 | 14.7291 | 15.7348
369 | -0.040205 | 0.52643 | 0.48396 | 0.70071 | 3.1545 | 5.2054 | 4.9066 | 5.6898 | 5.3232 | 2.2258 | 16.2755 | 15.6102 | 16.2755
370 | -0.33331 | -0.92003 | 0.36945 | 0.17878 | 4.1354 | 4.8555 | 5.6865 | 4.63 | 3.9415 | 1.7565 | 15.3774 | 15.5198 | 15.5198
371 | 0.40762 | 0.92948 | 0.65822 | 0.82368 | 4.6913 | 5.7696 | 6.5317 | 6.0364 | 4.0123 | 2.1288 | 18.6261 | 17.364 | 18.6261
372 | 0.045462 | 0.034212 | 0.51813 | 0.51365 | 4.2077 | 5.3112 | 6.8807 | 5.2823 | 3.5135 | 1.203 | 16.0042 | 15.805 | 16.0042
373 | -0.071363 | 0.58958 | 0.47155 | 0.72226 | 3.9312 | 5.1672 | 6.9488 | 5.7438 | 5.5673 | 2.154 | 16.9962 | 18.6012 | 18.6012
374 | 0.0011512 | 1.155 | 0.50046 | 0.87595 | 4.2551 | 5.2563 | 6.6793 | 6.2291 | 3.4904 | 2.5211 | 18.2616 | 16.9458 | 18.2616
375 | -0.053425 | 0.24296 | 0.4787 | 0.59598 | 4.0402 | 5.1892 | 7.1748 | 5.4514 | 4.3807 | 2.0534 | 16.7341 | 17.6491 | 17.6491
376 | -1.9322 | 0.21219 | 0.026667 | 0.58402 | 5.7397 | 3.4902 | 4.8683 | 5.426 | 5.3002 | 1.8985 | 16.5544 | 17.8066 | 17.8066
377 | 2.5215 | 1.7563 | 0.99416 | 0.96048 | 4.3633 | 8.0854 | 6.9203 | 6.7154 | 3.412 | 1.9588 | 21.1229 | 16.6543 | 21.1229
378 | -0.70466 | -0.78578 | 0.24051 | 0.216 | 4.7754 | 4.448 | 4.3581 | 4.7072 | 5.1026 | 2.171 | 16.1015 | 16.4071 | 16.4071
379 | -1.2121 | -0.91683 | 0.11273 | 0.17962 | 4.3269 | 3.9746 | 5.0783 | 4.6318 | 4.0142 | 2.0847 | 15.018 | 15.5041 | 15.5041
380 | -0.74129 | -0.48358 | 0.22926 | 0.31434 | 4.1469 | 4.4104 | 4.547 | 4.8996 | 4.3906 | 2.2558 | 15.7126 | 15.3403 | 15.7126
381 | 0.68971 | 0.3186 | 0.75481 | 0.62498 | 4.5564 | 6.1315 | 5.512 | 5.5142 | 4.8217 | 2.5571 | 18.7591 | 17.4472 | 18.7591
382 | 1.3413 | 0.12871 | 0.91009 | 0.5512 | 2.9308 | 6.9372 | 5.1642 | 5.358 | 4.1703 | 2.322 | 17.5481 | 14.5873 | 17.5481
383 | 0.64586 | -0.11698 | 0.74081 | 0.45344 | 3.0287 | 6.0753 | 4.5161 | 5.1645 | 4.5902 | 1.797 | 16.0655 | 13.932 | 16.0655
384 | 0.55447 | 1.4689 | 0.71037 | 0.92907 | 3.9978 | 5.9581 | 6.2037 | 6.4897 | 3.2553 | 2.6443 | 19.0899 | 16.1011 | 19.0899
385 | 0.087767 | -0.61461 | 0.53497 | 0.26941 | 3.4789 | 5.3639 | 6.3818 | 4.813 | 5.0673 | 2.0196 | 15.6754 | 16.9476 | 16.9476
386 | 0.14662 | -1.006 | 0.55829 | 0.15721 | 4.2103 | 5.4377 | 4.6171 | 4.5834 | 4.6456 | 1.8544 | 16.0859 | 15.3274 | 16.0859
387 | 0.58596 | -0.80179 | 0.72105 | 0.21134 | 3.2125 | 5.9985 | 6.843 | 4.6977 | 4.0274 | 2.0899 | 15.9986 | 16.1728 | 16.1728
388 | 0.11514 | 0.065275 | 0.54583 | 0.52602 | 4.2572 | 5.3982 | 4.7068 | 5.307 | 5.7874 | 2.4592 | 17.4215 | 17.2105 | 17.4215
389 | -1.2593 | -1.1886 | 0.10397 | 0.11731 | 4.0604 | 3.9361 | 4.6083 | 4.4918 | 5.4347 | 1.7787 | 14.267 | 15.8821 | 15.8821
390 | -1.1733 | -0.47211 | 0.12034 | 0.31842 | 3.8804 | 4.007 | 7.3627 | 4.9073 | 4.4049 | 1.6272 | 14.422 | 17.2752 | 17.2752
391 | 0.48707 | 0.80303 | 0.68689 | 0.78902 | 3.8043 | 5.8715 | 6.3663 | 5.9275 | 5.148 | 2.6581 | 18.2615 | 17.9767 | 18.2615
392 | -2.0353 | 0.49949 | 0.020909 | 0.69128 | 3.1794 | 3.4385 | 4.8507 | 5.6668 | 3.3989 | 1.685 | 13.9697 | 13.1141 | 13.9697
393 | 1.615 | 0.14292 | 0.94685 | 0.55682 | 4.1908 | 7.2473 | 6.4979 | 5.3695 | 3.5781 | 1.8002 | 18.6078 | 16.067 | 18.6078
394 | -0.11291 | -0.39978 | 0.45505 | 0.34466 | 3.7649 | 5.1167 | 5.3215 | 4.9573 | 6.0646 | 1.9473 | 15.7862 | 17.0984 | 17.0984
395 | -0.052438 | 1.3557 | 0.47909 | 0.9124 | 4.6008 | 5.1904 | 6.5573 | 6.3971 | 3.3376 | 1.8076 | 17.9959 | 16.3033 | 17.9959
396 | 0.018508 | 0.77148 | 0.50738 | 0.77979 | 3.3791 | 5.2778 | 6.2826 | 5.9003 | 4.5965 | 1.9675 | 16.5247 | 16.2257 | 16.5247
397 | -0.15086 | -0.097491 | 0.44004 | 0.46117 | 3.134 | 5.0709 | 5.9672 | 5.1794 | 3.8664 | 2.5568 | 15.941 | 15.5243 | 15.941
398 | -1.0933 | -0.97801 | 0.13714 | 0.16403 | 3.5967 | 4.0759 | 2.9875 | 4.5984 | 5.1398 | 1.9228 | 14.1938 | 13.6469 | 14.1938
399 | 1.3754 | 1.8726 | 0.9155 | 0.96944 | 3.048 | 6.9771 | 6.2437 | 6.8023 | 4.6517 | 2.829 | 19.6564 | 16.7724 | 19.6564
400 | 1.435 | 0.32996 | 0.92435 | 0.62929 | 3.5684 | 7.0458 | 5.7061 | 5.5236 | 5.2693 | 1.9665 | 18.1044 | 16.5103 | 18.1044
401 | 0.90083 | 0.35469 | 0.81616 | 0.63859 | 3.6984 | 6.3997 | 7.2627 | 5.5443 | 3.6475 | 2.0099 | 17.6523 | 16.6185 | 17.6523
402 | -2.0535 | -0.84067 | 0.020014 | 0.20027 | 4.4895 | 3.4298 | 4.7353 | 4.675 | 4.4154 | 2.1353 | 14.7296 | 15.7755 | 15.7755
403 | 0.67454 | 1.248 | 0.75002 | 0.89398 | 3.5272 | 6.112 | 5.5565 | 6.3075 | 4.6464 | 2.1382 | 18.0849 | 15.8683 | 18.0849
404 | 0.21541 | 0.097265 | 0.58528 | 0.53874 | 3.1943 | 5.5246 | 6.0716 | 5.3326 | 4.5712 | 2.5221 | 16.5736 | 16.3592 | 16.5736
405 | -0.11431 | -0.4578 | 0.4545 | 0.32355 | 5.0218 | 5.115 | 7.5345 | 4.9171 | 4.5908 | 2.1926 | 17.2465 | 19.3397 | 19.3397
406 | -0.5068 | 1.2653 | 0.30615 | 0.89712 | 4.626 | 4.6595 | 5.4438 | 6.322 | 3.6884 | 2.4321 | 18.0396 | 16.1904 | 18.0396
407 | 0.77835 | 1.9181 | 0.78182 | 0.97245 | 4.4558 | 6.2446 | 6.5658 | 6.8355 | 4.253 | 1.9931 | 19.529 | 17.2678 | 19.529
408 | 1.1787 | 0.33315 | 0.88075 | 0.63049 | 3.6998 | 6.7435 | 5.2929 | 5.5263 | 4.0454 | 1.9519 | 17.9214 | 14.99 | 17.9214
409 | -1.501 | -0.99063 | 0.066676 | 0.16093 | 3.4022 | 3.7536 | 4.5803 | 4.5916 | 4.0548 | 2.5211 | 14.2685 | 14.5583 | 14.5583
410 | -0.046571 | -0.59678 | 0.48143 | 0.27533 | 3.6146 | 5.1976 | 4.9837 | 4.8245 | 4.6664 | 2.4446 | 16.0813 | 15.7093 | 16.0813
411 | -0.79887 | -1.1596 | 0.21218 | 0.1231 | 4.0639 | 4.3523 | 4.7528 | 4.5057 | 3.5494 | 1.6587 | 14.5805 | 14.0248 | 14.5805
412 | -0.2238 | 0.066595 | 0.41146 | 0.52655 | 4.3283 | 4.9838 | 7.2513 | 5.308 | 3.3094 | 2.1146 | 16.7347 | 17.0036 | 17.0036
413 | -1.1077 | -0.98356 | 0.134 | 0.16267 | 3.5986 | 4.0633 | 4.4591 | 4.5954 | 3.5946 | 1.8248 | 14.0821 | 13.4772 | 14.0821
414 | -1.4795 | -2.5724 | 0.069501 | 0.0050503 | 3.8258 | 3.7688 | 6.1875 | 4.092 | 4.1247 | 2.497 | 14.1836 | 16.6351 | 16.6351
415 | -1.4848 | 0.37926 | 0.0688 | 0.64775 | 4.0867 | 3.765 | 5.534 | 5.565 | 4.3056 | 2.1664 | 15.5831 | 16.0926 | 16.0926
416 | 0.23561 | 0.037408 | 0.59313 | 0.51492 | 4.8341 | 5.5502 | 5.0863 | 5.2848 | 3.4323 | 2.325 | 17.9941 | 15.6778 | 17.9941
417 | -1.5378 | -1.9334 | 0.062048 | 0.026592 | 3.4622 | 3.728 | 6.0811 | 4.218 | 5.3524 | 1.5354 | 12.9436 | 16.4311 | 16.4311
418 | -0.11209 | -0.23891 | 0.45538 | 0.40559 | 3.2335 | 5.1177 | 6.417 | 5.0729 | 3.989 | 1.4454 | 14.8695 | 15.0849 | 15.0849
419 | 0.24043 | 1.2042 | 0.595 | 0.88575 | 4.6942 | 5.5563 | 5.5903 | 6.2707 | 5.3499 | 1.274 | 17.7952 | 16.9084 | 17.7952
420 | 0.3108 | -0.20345 | 0.62202 | 0.41939 | 3.545 | 5.6458 | 5.6942 | 5.0992 | 6.4285 | 2.2575 | 16.5475 | 17.9252 | 17.9252
421 | 0.065425 | 0.7913 | 0.52608 | 0.78562 | 4.8235 | 5.336 | 5.5834 | 5.9174 | 3.6587 | 1.3361 | 17.413 | 15.4016 | 17.413
422 | 0.73808 | -0.576 | 0.76977 | 0.28231 | 3.024 | 6.1932 | 7.0177 | 4.838 | 3.4152 | 1.6278 | 15.6831 | 15.0847 | 15.6831
423 | 0.12398 | -0.68525 | 0.54933 | 0.24659 | 3.4651 | 5.4093 | 6.8562 | 4.7683 | 3.8102 | 1.9666 | 15.6094 | 16.0981 | 16.0981
424 | -0.27196 | 0.0018149 | 0.39283 | 0.50072 | 3.2918 | 4.9269 | 6.2536 | 5.2567 | 4.8439 | 1.7249 | 15.2003 | 16.1141 | 16.1141
425 | 1.1315 | 1.2663 | 0.87108 | 0.89731 | 3.3464 | 6.686 | 7.3168 | 6.3229 | 3.8115 | 2.1246 | 18.4798 | 16.5993 | 18.4798
426 | -1.1064 | -1.7782 | 0.13427 | 0.037685 | 4.0816 | 4.0644 | 6.084 | 4.2625 | 4.3981 | 2.5509 | 14.9593 | 17.1145 | 17.1145
427 | 0.12753 | 0.89609 | 0.55074 | 0.8149 | 5.0158 | 5.4137 | 4.9472 | 6.0077 | 4.1604 | 1.7121 | 18.1493 | 15.8355 | 18.1493
428 | -0.33063 | -0.38693 | 0.37046 | 0.3494 | 4.0662 | 4.8586 | 6.5299 | 4.9663 | 4.0587 | 2.3348 | 16.2259 | 16.9896 | 16.9896
429 | 2.1728 | 1.7049 | 0.9851 | 0.95589 | 4.4138 | 7.8007 | 6.7264 | 6.6761 | 4.5308 | 2.4487 | 21.3394 | 18.1197 | 21.3394
430 | 0.68076 | 0.65835 | 0.75199 | 0.74484 | 3.9222 | 6.12 | 5.7032 | 5.8028 | 3.4354 | 2.3822 | 18.2272 | 15.443 | 18.2272
431 | 0.57161 | 1.2304 | 0.71621 | 0.89073 | 4.4696 | 5.9801 | 6.6941 | 6.2928 | 3.4281 | 1.9935 | 18.7359 | 16.5852 | 18.7359
432 | 0.52117 | -0.59337 | 0.69888 | 0.27647 | 3.9311 | 5.9153 | 4.864 | 4.8267 | 4.0867 | 1.7682 | 16.4414 | 14.65 | 16.4414
433 | -0.76688 | 0.84656 | 0.22158 | 0.80138 | 5.4494 | 4.3844 | 3.1885 | 5.965 | 4.4279 | 2.2202 | 18.0191 | 15.286 | 18.0191
434 | 0.79354 | 1.1683 | 0.78627 | 0.87865 | 4.4524 | 6.2639 | 7.424 | 6.2404 | 3.6346 | 2.7186 | 19.6752 | 18.2297 | 19.6752
435 | 0.042496 | 0.056532 | 0.51695 | 0.52254 | 3.9442 | 5.3075 | 3.4431 | 5.3 | 4.124 | 1.9601 | 16.5118 | 13.4713 | 16.5118
436 | -1.1433 | -1.1543 | 0.12646 | 0.12419 | 3.969 | 4.0325 | 5.7634 | 4.5082 | 3.0659 | 2.2444 | 14.7541 | 15.0427 | 15.0427
437 | 0.099313 | 0.71832 | 0.53956 | 0.76372 | 5.4002 | 5.3784 | 5.276 | 5.8545 | 4.5861 | 1.8663 | 18.4993 | 17.1286 | 18.4993
438 | -0.62071 | -0.57895 | 0.2674 | 0.28131 | 4.0024 | 4.536 | 6.3278 | 4.8361 | 3.2741 | 1.7329 | 15.1075 | 15.3372 | 15.3372
439 | 0.62364 | -0.34321 | 0.73357 | 0.36572 | 4.8505 | 6.0468 | 7.1107 | 4.9972 | 3.4023 | 2.5151 | 18.4096 | 17.8785 | 18.4096
440 | -0.14366 | 0.40795 | 0.44288 | 0.65835 | 3.5784 | 5.0796 | 5.8933 | 5.5892 | 5.7921 | 2.0732 | 16.3203 | 17.337 | 17.337
441 | -0.19287 | -0.34105 | 0.42353 | 0.36653 | 4.3219 | 5.0205 | 5.14 | 4.9988 | 4.6675 | 1.6765 | 16.0177 | 15.8059 | 16.0177
442 | 0.45578 | 0.15052 | 0.67573 | 0.55982 | 3.0652 | 5.8314 | 5.2309 | 5.3757 | 4.7955 | 2.2251 | 16.4973 | 15.3167 | 16.4973
443 | -0.8338 | 0.56924 | 0.2022 | 0.7154 | 4.1684 | 4.3177 | 5.4758 | 5.7264 | 3.4244 | 1.9058 | 16.1182 | 14.9744 | 16.1182
444 | 1.949 | 0.92264 | 0.97435 | 0.8219 | 3.0808 | 7.5926 | 7.3557 | 6.0306 | 4.4258 | 1.7863 | 18.4902 | 16.6487 | 18.4902
445 | 0.16364 | 0.85459 | 0.56499 | 0.80361 | 4.2362 | 5.4592 | 3.365 | 5.9719 | 3.6078 | 1.7735 | 17.4408 | 12.9825 | 17.4408
446 | -1.2648 | -0.40703 | 0.10297 | 0.34199 | 4.202 | 3.9316 | 6.4343 | 4.9522 | 5.0203 | 2.0414 | 15.1271 | 17.6978 | 17.6978
447 | 1.5676 | 0.24035 | 0.94151 | 0.59497 | 4.0224 | 7.1952 | 7.1865 | 5.4492 | 4.2217 | 2.2583 | 18.9251 | 17.689 | 18.9251
448 | 0.39063 | -0.027685 | 0.65196 | 0.48896 | 4.5035 | 5.7479 | 6.7927 | 5.2335 | 6.4299 | 2.3254 | 17.8103 | 20.0515 | 20.0515
449 | -0.64934 | -0.19939 | 0.25806 | 0.42098 | 5.2865 | 4.5057 | 5.0236 | 5.1022 | 5.0585 | 2.6075 | 17.502 | 17.9762 | 17.9762
450 | 0.79385 | 0.68196 | 0.78636 | 0.75237 | 2.9911 | 6.2643 | 6.4576 | 5.8231 | 3.9408 | 1.8919 | 16.9705 | 15.2814 | 16.9705
451 | -0.68514 | -0.11148 | 0.24663 | 0.45562 | 5.0706 | 4.4682 | 4.6536 | 5.1687 | 4.1018 | 2.0307 | 16.7383 | 15.8568 | 16.7383
452 | -0.24127 | -0.30309 | 0.40467 | 0.38091 | 3.9067 | 4.9631 | 4.8074 | 5.026 | 5.5805 | 1.7308 | 15.6266 | 16.0254 | 16.0254
453 | 0.32549 | -1.0591 | 0.62759 | 0.14477 | 3.5766 | 5.6646 | 5.3505 | 4.5557 | 4.087 | 1.4372 | 15.2341 | 14.4512 | 15.2341
454 | 1.0046 | -0.93276 | 0.84246 | 0.17547 | 4.5723 | 6.5296 | 5.6776 | 4.623 | 5.1775 | 2.4832 | 18.2081 | 17.9106 | 18.2081
455 | 0.38477 | -1.9312 | 0.6498 | 0.026731 | 3.9464 | 5.7404 | 5.8977 | 4.2186 | 4.0679 | 1.8399 | 15.7452 | 15.7519 | 15.7519
456 | -0.083551 | 0.59573 | 0.46671 | 0.72432 | 5.1441 | 5.1524 | 6.703 | 5.7491 | 3.3942 | 2.0768 | 18.1223 | 17.318 | 18.1223
457 | 0.96681 | 0.77193 | 0.83318 | 0.77992 | 3.9783 | 6.4825 | 6.3183 | 5.9007 | 4.3573 | 2.0307 | 18.3921 | 16.6846 | 18.3921
458 | -1.2957 | -0.90259 | 0.097532 | 0.18337 | 3.9649 | 3.9069 | 5.3954 | 4.6397 | 4.0584 | 2.0864 | 14.5979 | 15.505 | 15.505
459 | 1.7116 | 2.4201 | 0.95651 | 0.99224 | 4.1384 | 7.3511 | 7.1213 | 7.1692 | 4.3624 | 2.6126 | 21.2713 | 18.2346 | 21.2713
460 | 0.16354 | 0.18025 | 0.56495 | 0.57152 | 3.585 | 5.459 | 3.7406 | 5.3999 | 4.4924 | 2.468 | 16.9119 | 14.286 | 16.9119
461 | -0.13397 | -1.4046 | 0.44671 | 0.080063 | 3.9997 | 5.0912 | 5.7402 | 4.3962 | 5.0161 | 2.5188 | 16.0059 | 17.2748 | 17.2748
462 | 1.9814 | -0.0080818 | 0.97623 | 0.49678 | 4.4086 | 7.6239 | 6.1321 | 5.2489 | 4.9774 | 1.5817 | 18.8631 | 17.0999 | 18.8631
463 | 0.17348 | -1.1059 | 0.56886 | 0.13439 | 4.9707 | 5.4716 | 6.3052 | 4.532 | 4.1892 | 1.6207 | 16.595 | 17.0858 | 17.0858
464 | -0.88459 | -0.21514 | 0.18819 | 0.41483 | 3.5792 | 4.2682 | 6.5357 | 5.0905 | 3.1942 | 1.5654 | 14.5033 | 14.8745 | 14.8745
465 | 0.35981 | 0.5065 | 0.64051 | 0.69375 | 3.0592 | 5.7084 | 3.9271 | 5.6728 | 4.5817 | 1.8404 | 16.2808 | 13.4084 | 16.2808
466 | -0.15143 | 0.3914 | 0.43982 | 0.65225 | 3.0926 | 5.0702 | 4.6107 | 5.5752 | 3.9878 | 2.4059 | 16.1439 | 14.0969 | 16.1439
467 | -2.0702 | 0.0089501 | 0.019216 | 0.50357 | 4.2555 | 3.4219 | 6.0138 | 5.2623 | 5.4405 | 2.3858 | 15.3255 | 18.0956 | 18.0956
468 | 0.89297 | -0.90354 | 0.81406 | 0.18312 | 3.3538 | 6.3898 | 5.8063 | 4.6392 | 3.8915 | 1.4449 | 15.8277 | 14.4965 | 15.8277
469 | 0.0083307 | -1.0916 | 0.50332 | 0.13749 | 4.0301 | 5.2652 | 5.7933 | 4.5392 | 3.7354 | 2.0407 | 15.8751 | 15.5994 | 15.8751
470 | -0.56941 | -0.25071 | 0.28454 | 0.40102 | 4.3238 | 4.5911 | 5.8811 | 5.0642 | 5.071 | 2.5509 | 16.5299 | 17.8268 | 17.8268
471 | 0.39694 | -1.0873 | 0.65429 | 0.13845 | 4.0456 | 5.756 | 5.4399 | 4.5414 | 4.2797 | 1.9915 | 16.3344 | 15.7566 | 16.3344
472 | -0.036926 | -0.22945 | 0.48527 | 0.40926 | 4.2289 | 5.2094 | 4.5321 | 5.0799 | 4.168 | 2.3839 | 16.9022 | 15.313 | 16.9022
473 | 0.21438 | 0.4857 | 0.58488 | 0.68641 | 3.7747 | 5.5233 | 5.1987 | 5.6551 | 5.0853 | 2.1151 | 17.0681 | 16.1738 | 17.0681
474 | -0.68266 | -2.125 | 0.24741 | 0.016794 | 3.6681 | 4.4708 | 3.3975 | 4.1712 | 4.2013 | 1.7312 | 14.0412 | 12.9981 | 14.0412
475 | 0.21074 | 0.26865 | 0.58346 | 0.6059 | 4.5609 | 5.5187 | 4.0924 | 5.4726 | 4.1563 | 2.1586 | 17.7107 | 14.9682 | 17.7107
476 | -0.47296 | -0.15476 | 0.31812 | 0.4385 | 4.0776 | 4.697 | 4.9604 | 5.1358 | 4.2136 | 2.1859 | 16.0961 | 15.4374 | 16.0961
477 | -0.65245 | -1.3401 | 0.25706 | 0.090099 | 4.5156 | 4.5024 | 5.527 | 4.4233 | 5.7848 | 2.1228 | 15.5641 | 17.9502 | 17.9502
478 | -1.0607 | -1.9893 | 0.14441 | 0.023334 | 5.3309 | 4.1048 | 4.3794 | 4.2034 | 4.5909 | 1.1114 | 14.7505 | 15.4127 | 15.4127
479 | 0.36378 | -1.4589 | 0.64199 | 0.07229 | 4.3083 | 5.7135 | 6.5335 | 4.3743 | 3.3755 | 2.3818 | 16.7779 | 16.5991 | 16.7779
480 | 0.61342 | 1.1196 | 0.7302 | 0.86857 | 4.0287 | 6.0337 | 5.1999 | 6.1991 | 4.5331 | 2.0744 | 18.336 | 15.8361 | 18.336
481 | -0.47065 | -0.44385 | 0.31895 | 0.32858 | 3.0958 | 4.6995 | 5.9416 | 4.9267 | 3.953 | 1.7988 | 14.5208 | 14.7891 | 14.7891
482 | 1.1041 | 1.3832 | 0.86522 | 0.9167 | 4.6937 | 6.6525 | 4.0337 | 6.4198 | 3.4002 | 2.6619 | 20.4279 | 14.7895 | 20.4279
483 | -0.69062 | -1.4924 | 0.2449 | 0.067801 | 3.691 | 4.4625 | 6.2179 | 4.3612 | 3.3647 | 2.3293 | 14.8441 | 15.6029 | 15.6029
484 | 0.33399 | -0.37861 | 0.63081 | 0.35249 | 4.4697 | 5.6754 | 5.3868 | 4.9721 | 4.2289 | 1.3674 | 16.4846 | 15.4527 | 16.4846
485 | 0.33925 | -0.16827 | 0.63279 | 0.43318 | 4.6662 | 5.6822 | 5.7371 | 5.1256 | 3.5266 | 1.7037 | 17.1777 | 15.6337 | 17.1777
486 | 0.89263 | 0.63095 | 0.81397 | 0.73596 | 3.718 | 6.3894 | 3.0898 | 5.7793 | 4.4457 | 1.8205 | 17.7071 | 13.074 | 17.7071
487 | 1.1098 | 0.20921 | 0.86646 | 0.58286 | 4.2742 | 6.6595 | 4.8445 | 5.4236 | 4.2032 | 2.2453 | 18.6026 | 15.5673 | 18.6026
488 | 0.8478 | 0.8497 | 0.80172 | 0.80226 | 5.087 | 6.3327 | 6.4247 | 5.9677 | 3.5418 | 1.7085 | 19.0959 | 16.7619 | 19.0959
489 | -0.15145 | -1.2314 | 0.43981 | 0.10909 | 4.027 | 5.0702 | 5.0614 | 4.4717 | 5.0094 | 2.0898 | 15.6587 | 16.1876 | 16.1876
490 | -0.81209 | 0.37495 | 0.20837 | 0.64615 | 5.2365 | 4.3391 | 3.9967 | 5.5614 | 3.1004 | 2.2162 | 17.3533 | 14.5498 | 17.3533
491 | 0.5146 | 1.2943 | 0.69658 | 0.90222 | 3.5252 | 5.9069 | 5.6178 | 6.3462 | 3.8655 | 1.452 | 17.2303 | 14.4605 | 17.2303
492 | -0.68378 | -1.3205 | 0.24706 | 0.093339 | 2.8969 | 4.4696 | 7.6423 | 4.4318 | 5.7372 | 1.797 | 13.5953 | 18.0734 | 18.0734
493 | -0.10361 | 0.55921 | 0.45874 | 0.71199 | 3.8931 | 5.128 | 6.4275 | 5.7178 | 4.1396 | 1.706 | 16.4449 | 16.1663 | 16.4449
494 | 0.87339 | 0.1088 | 0.80877 | 0.54332 | 2.73 | 6.3651 | 6.6016 | 5.3419 | 4.4139 | 1.9373 | 16.3743 | 15.6828 | 16.3743
495 | -0.67735 | -1.7237 | 0.24909 | 0.042381 | 4.6959 | 4.4763 | 2.9515 | 4.2796 | 4.4523 | 1.5327 | 14.9846 | 13.6324 | 14.9846
496 | 0.61533 | 0.73654 | 0.73083 | 0.7693 | 2.9689 | 6.0362 | 5.4667 | 5.8702 | 3.858 | 1.48 | 16.3552 | 13.7736 | 16.3552
497 | 0.43003 | -0.9512 | 0.66641 | 0.17075 | 2.964 | 5.7984 | 6.215 | 4.6129 | 4.9569 | 1.7909 | 15.1661 | 15.9267 | 15.9267
498 | 1.02 | 0.58306 | 0.84614 | 0.72007 | 4.8283 | 6.5487 | 6.0211 | 5.7382 | 4.5415 | 1.2061 | 18.3213 | 16.597 | 18.3213
499 | -0.97922 | -0.50033 | 0.16374 | 0.30842 | 3.2208 | 4.1788 | 5.9365 | 4.8882 | 5.6762 | 1.7484 | 14.0363 | 16.582 | 16.582
500 | -0.64715 | -1.0918 | 0.25877 | 0.13747 | 4.0335 | 4.508 | 5.1245 | 4.5391 | 4.2787 | 1.6254 | 14.706 | 15.062 | 15.062
501 | -1.0458 | -0.88581 | 0.14783 | 0.18786 | 3.0452 | 4.1181 | 3.0767 | 4.6492 | 5.6548 | 1.8726 | 13.6852 | 13.6493 | 13.6852
502 | -0.18417 | 0.52019 | 0.42694 | 0.69853 | 4.2652 | 5.0309 | 6.0463 | 5.6844 | 3.531 | 1.5802 | 16.5608 | 15.4227 | 16.5608
503 | -1.2548 | -0.61996 | 0.10478 | 0.26764 | 3.3686 | 3.9397 | 5.2983 | 4.8096 | 5.043 | 2.2773 | 14.3952 | 15.9871 | 15.9871
504 | -1.8883 | -0.29063 | 0.029494 | 0.38567 | 4.2093 | 3.5135 | 7.0566 | 5.0351 | 4.1247 | 1.8389 | 14.5967 | 17.2295 | 17.2295
505 | 1.4787 | 0.42678 | 0.9304 | 0.66523 | 4.9555 | 7.0957 | 4.3788 | 5.6051 | 4.0876 | 1.7059 | 19.3622 | 15.1279 | 19.3622
506 | -0.55268 | 0.90213 | 0.29024 | 0.8165 | 5.3958 | 4.6092 | 6.126 | 6.0129 | 3.39 | 1.9421 | 17.96 | 16.8539 | 17.96
507 | 1.7083 | 0.49677 | 0.95621 | 0.69032 | 4.3744 | 7.3476 | 7.0808 | 5.6645 | 3.6374 | 1.3093 | 18.6958 | 16.4018 | 18.6958
508 | -0.33814 | -0.25268 | 0.36763 | 0.40026 | 4.2209 | 4.8499 | 4.9745 | 5.0628 | 3.4944 | 1.6743 | 15.8079 | 14.3641 | 15.8079
509 | 0.35294 | -0.44521 | 0.63793 | 0.32808 | 4.4636 | 5.6996 | 3.9127 | 4.9258 | 5.1859 | 1.8925 | 16.9815 | 15.4548 | 16.9815
510 | 1.2226 | 0.33348 | 0.88925 | 0.63061 | 3.5542 | 6.7963 | 6.6897 | 5.5266 | 4.311 | 1.6218 | 17.4989 | 16.1767 | 17.4989
511 | 1.2221 | 1.2259 | 0.88916 | 0.88988 | 3.8178 | 6.7957 | 7.225 | 6.2889 | 3.5258 | 2.078 | 18.9804 | 16.6465 | 18.9804
512 | 1.3497 | 0.54053 | 0.91144 | 0.70558 | 4.7539 | 6.947 | 6.9123 | 5.7018 | 4.611 | 2.5681 | 19.9708 | 18.8453 | 19.9708
513 | 0.43693 | 1.1128 | 0.66892 | 0.8671 | 2.9764 | 5.8072 | 5.9778 | 6.1933 | 4.5607 | 2.3353 | 17.3122 | 15.8502 | 17.3122
514 | 1.4652 | 0.08257 | 0.92856 | 0.5329 | 2.8197 | 7.0803 | 6.2476 | 5.3208 | 3.6834 | 1.8373 | 17.0581 | 14.588 | 17.0581
515 | -1.7065 | -1.2089 | 0.04396 | 0.11334 | 3.6665 | 3.6183 | 6.8216 | 4.4822 | 3.9272 | 2.7242 | 14.4912 | 17.1395 | 17.1395
516 | 0.20892 | 0.95632 | 0.58275 | 0.83054 | 4.7061 | 5.5163 | 6.3182 | 6.0595 | 3.9672 | 2.7774 | 19.0593 | 17.7688 | 19.0593
517 | -0.36371 | 0.80218 | 0.35804 | 0.78878 | 4.8481 | 4.8205 | 6.1577 | 5.9268 | 3.9133 | 1.7171 | 17.3125 | 16.6362 | 17.3125
518 | -0.043025 | 0.34878 | 0.48284 | 0.63637 | 3.88 | 5.2019 | 6.0176 | 5.5394 | 4.3763 | 2.2389 | 16.8602 | 16.5128 | 16.8602
519 | 0.38011 | 1.2099 | 0.64807 | 0.88684 | 4.3244 | 5.7344 | 6.5027 | 6.2755 | 4.471 | 1.7274 | 18.0617 | 17.0255 | 18.0617
520 | 1.5304 | 1.5223 | 0.93704 | 0.93603 | 3.8227 | 7.1539 | 5.9523 | 6.5327 | 4.0239 | 1.5553 | 19.0645 | 15.3542 | 19.0645
521 | 1.0195 | 0.050364 | 0.84602 | 0.52008 | 4.9198 | 6.5481 | 4.4695 | 5.2951 | 4.4741 | 2.447 | 19.21 | 16.3103 | 19.21
522 | -1.7771 | -1.8741 | 0.037777 | 0.030457 | 2.3662 | 3.576 | 4.0379 | 4.2343 | 4.862 | 2.5474 | 12.7238 | 13.8135 | 13.8135
523 | -1.1743 | 1.0946 | 0.12014 | 0.86315 | 5.5501 | 4.0062 | 6.9984 | 6.1778 | 4.2101 | 1.9056 | 17.6398 | 18.6642 | 18.6642
524 | -0.088649 | -0.29474 | 0.46468 | 0.3841 | 4.1154 | 5.1462 | 6.2547 | 5.0321 | 4.2512 | 1.568 | 15.8616 | 16.1892 | 16.1892
525 | 3.2259 | 2.2971 | 0.99937 | 0.98919 | 4.5936 | 8.5133 | 6.5496 | 7.0933 | 5.7967 | 1.5094 | 21.7095 | 18.4493 | 21.7095
526 | 1.5983 | 0.66582 | 0.94501 | 0.74724 | 5.1451 | 7.229 | 3.9683 | 5.8093 | 4.2059 | 1.9528 | 20.1362 | 15.272 | 20.1362
527 | 0.55801 | 0.30422 | 0.71158 | 0.61952 | 2.8689 | 5.9626 | 5.4088 | 5.5022 | 3.2399 | 1.7724 | 16.1061 | 13.29 | 16.1061
528 | 0.10678 | 0.88301 | 0.54252 | 0.81139 | 3.3078 | 5.3877 | 6.5147 | 5.9964 | 4.3982 | 1.7971 | 16.4891 | 16.0179 | 16.4891
529 | -0.63017 | -0.93575 | 0.26429 | 0.1747 | 2.9908 | 4.526 | 5.3211 | 4.6213 | 4.7199 | 1.6186 | 13.7568 | 14.6504 | 14.6504
530 | 0.47662 | 1.5004 | 0.68318 | 0.93325 | 4.6212 | 5.8581 | 5.2065 | 6.5151 | 3.8698 | 2.0904 | 19.0848 | 15.7878 | 19.0848
531 | -1.2135 | -0.1758 | 0.11247 | 0.43022 | 3.5017 | 3.9735 | 5.2348 | 5.1199 | 4.5839 | 2.1634 | 14.7584 | 15.4838 | 15.4838
532 | 0.95709 | 2.1842 | 0.83074 | 0.98553 | 3.5646 | 6.4703 | 5.1346 | 7.0202 | 3.4607 | 1.4312 | 18.4862 | 13.591 | 18.4862
533 | 0.78369 | 1.1007 | 0.78339 | 0.86448 | 2.83 | 6.2514 | 4.9859 | 6.183 | 3.7245 | 1.9501 | 17.2145 | 13.4905 | 17.2145
534 | 0.23435 | 0.57301 | 0.59264 | 0.71668 | 4.5043 | 5.5486 | 7.2358 | 5.7296 | 5.6499 | 1.5049 | 17.2873 | 18.8948 | 18.8948
535 | -0.4177 | -0.14825 | 0.33808 | 0.44107 | 3.7792 | 4.759 | 4.423 | 5.1407 | 3.7068 | 2.3215 | 16.0004 | 14.2306 | 16.0004
536 | -1.9169 | -1.4621 | 0.027628 | 0.071861 | 2.8181 | 3.4982 | 5.9918 | 4.373 | 4.9342 | 1.3227 | 12.0121 | 15.0668 | 15.0668
537 | -0.82146 | 0.022029 | 0.20569 | 0.50879 | 3.2017 | 4.3299 | 7.6938 | 5.2726 | 3.8351 | 1.947 | 14.7512 | 16.6775 | 16.6775
538 | -0.73497 | -0.23828 | 0.23118 | 0.40583 | 3.7921 | 4.4168 | 4.9099 | 5.0734 | 3.8219 | 1.6697 | 14.952 | 14.1935 | 14.952
539 | -0.039279 | -0.034486 | 0.48433 | 0.48624 | 3.4214 | 5.2065 | 4.3756 | 5.2282 | 5.3866 | 2.205 | 16.0612 | 15.3887 | 16.0612
540 | 0.46231 | 0.41294 | 0.67807 | 0.66017 | 3.4704 | 5.8398 | 4.8212 | 5.5934 | 4.1636 | 1.6896 | 16.5931 | 14.1447 | 16.5931
541 | -0.71157 | -2.029 | 0.23836 | 0.021227 | 3.2675 | 4.4409 | 5.8614 | 4.1935 | 4.0279 | 2.3064 | 14.2083 | 15.4632 | 15.4632
542 | -1.4099 | -0.41508 | 0.079285 | 0.33904 | 5.0849 | 3.8194 | 5.5971 | 4.9466 | 5.3731 | 2.1075 | 15.9584 | 18.1626 | 18.1626
543 | 0.37274 | -0.263 | 0.64533 | 0.39627 | 4.1917 | 5.725 | 5.5024 | 5.0552 | 4.6118 | 1.2827 | 16.2545 | 15.5886 | 16.2545
544 | -0.59094 | -0.91172 | 0.27728 | 0.18096 | 4.4748 | 4.5679 | 5.8404 | 4.6347 | 3.2932 | 2.2881 | 15.9654 | 15.8965 | 15.9654
545 | -1.0598 | 1.1384 | 0.14462 | 0.87252 | 3.9868 | 4.1056 | 5.7804 | 6.2151 | 3.8875 | 1.3911 | 15.6985 | 15.0458 | 15.6985
546 | -0.043348 | 0.84138 | 0.48271 | 0.79993 | 4.1821 | 5.2015 | 3.6008 | 5.9606 | 3.2294 | 2.254 | 17.5982 | 13.2664 | 17.5982
547 | 1.3362 | 1.377 | 0.90925 | 0.91574 | 3.534 | 6.9312 | 7.1571 | 6.4146 | 5.0304 | 2.3683 | 19.2481 | 18.0898 | 19.2481
548 | 0.44732 | 1.37 | 0.67268 | 0.91466 | 4.0721 | 5.8205 | 3.7485 | 6.4089 | 4.1269 | 2.1042 | 18.4058 | 14.0517 | 18.4058
549 | 0.52703 | 0.072666 | 0.70091 | 0.52896 | 4.3624 | 5.9228 | 6.5502 | 5.3129 | 3.4584 | 1.7463 | 17.3444 | 16.1173 | 17.3444
550 | 1.2547 | 1.4261 | 0.8952 | 0.92308 | 5.354 | 6.8347 | 5.0808 | 6.4549 | 3.8628 | 2.2609 | 20.9045 | 16.5585 | 20.9045
551 | -0.25372 | -1.0601 | 0.39986 | 0.14455 | 4.2791 | 4.9484 | 6.4447 | 4.5552 | 3.9871 | 1.5913 | 15.374 | 16.3022 | 16.3022
552 | -1.9676 | -1.7725 | 0.024554 | 0.038155 | 4.1729 | 3.4719 | 4.9292 | 4.2642 | 3.5138 | 1.332 | 13.241 | 13.9478 | 13.9478
553 | 1.4724 | 0.84077 | 0.92954 | 0.79976 | 3.6581 | 7.0885 | 4.4708 | 5.96 | 4.1833 | 2.5782 | 19.2848 | 14.8905 | 19.2848
554 | -0.28295 | -1.8295 | 0.38861 | 0.033666 | 5.2063 | 4.9141 | 4.234 | 4.2471 | 5.5672 | 2.1282 | 16.4956 | 17.1356 | 17.1356
555 | 1.0358 | 0.78129 | 0.84986 | 0.78268 | 4.7892 | 6.5683 | 5.3374 | 5.9087 | 4.5845 | 2.3786 | 19.6448 | 17.0895 | 19.6448
556 | -0.75748 | -0.5021 | 0.22438 | 0.3078 | 4.6659 | 4.3939 | 4.0133 | 4.887 | 4.8063 | 2.1343 | 16.0812 | 15.6198 | 16.0812
557 | 0.39705 | 2.5788 | 0.65434 | 0.99504 | 4.5095 | 5.7561 | 3.6811 | 7.2613 | 4.1875 | 2.3823 | 19.9092 | 14.7604 | 19.9092
558 | -0.88712 | -0.61696 | 0.18751 | 0.26863 | 4.3505 | 4.2658 | 4.4503 | 4.8115 | 4.2294 | 2.203 | 15.6308 | 15.2333 | 15.6308
559 | 1.4323 | 0.60413 | 0.92397 | 0.72712 | 3.8795 | 7.0427 | 4.287 | 5.7563 | 4.9363 | 1.6486 | 18.3271 | 14.7514 | 18.3271
560 | -0.67266 | 0.37359 | 0.25058 | 0.64565 | 3.6781 | 4.4812 | 3.6898 | 5.5602 | 3.864 | 1.7143 | 15.4339 | 12.9461 | 15.4339
561 | 0.2855 | -0.94128 | 0.61237 | 0.17328 | 4.0136 | 5.6136 | 4.5792 | 4.6183 | 3.7762 | 1.8502 | 16.0957 | 14.2192 | 16.0957
562 | -0.049028 | -1.4491 | 0.48045 | 0.073652 | 5.3016 | 5.1946 | 5.7146 | 4.3782 | 3.5431 | 1.9366 | 16.8109 | 16.4959 | 16.8109
563 | 1.6518 | 0.8566 | 0.95072 | 0.80417 | 4.5403 | 7.2873 | 5.6413 | 5.9737 | 4.573 | 1.976 | 19.7772 | 16.7305 | 19.7772
564 | 0.1298 | 1.4491 | 0.55164 | 0.92635 | 3.8889 | 5.4166 | 3.8956 | 6.4736 | 4.5641 | 1.7868 | 17.5659 | 14.1354 | 17.5659
565 | 0.86667 | 1.0312 | 0.80694 | 0.84878 | 4.4965 | 6.3566 | 3.3866 | 6.1237 | 4.5641 | 2.5028 | 19.4797 | 14.95 | 19.4797
566 | -2.3172 | -1.4061 | 0.010248 | 0.079854 | 5.4642 | 3.3176 | 5.9712 | 4.3956 | 4.8858 | 2.6304 | 15.8078 | 18.9515 | 18.9515
567 | -0.052944 | -1.422 | 0.47889 | 0.077517 | 4.6773 | 5.1898 | 5.9485 | 4.3891 | 3.5729 | 2.3792 | 16.6353 | 16.5779 | 16.6353
568 | -1.2401 | -2.2945 | 0.10746 | 0.010881 | 3.0229 | 3.9516 | 7.3177 | 4.1366 | 4.2496 | 2.0231 | 13.1341 | 16.6132 | 16.6132
569 | -1.8226 | -1.581 | 0.034179 | 0.056935 | 4.0573 | 3.5498 | 6.0675 | 4.3282 | 3.3591 | 2.0284 | 13.9637 | 15.5124 | 15.5124
570 | 1.1436 | 0.2805 | 0.8736 | 0.61045 | 3.8706 | 6.7007 | 5.3118 | 5.4824 | 3.8232 | 2.5301 | 18.5838 | 15.5357 | 18.5838
571 | 1.0608 | -0.7107 | 0.85562 | 0.23863 | 4.5926 | 6.5993 | 4.8941 | 4.7526 | 4.6268 | 1.8381 | 17.7826 | 15.9517 | 17.7826
572 | 0.86003 | -2.5873 | 0.80511 | 0.0048364 | 3.4715 | 6.3482 | 5.246 | 4.09 | 3.843 | 1.7115 | 15.6212 | 14.272 | 15.6212
573 | 0.2285 | -0.42209 | 0.59037 | 0.33648 | 2.915 | 5.5411 | 7.726 | 4.9417 | 3.5355 | 2.4835 | 15.8814 | 16.66 | 16.66
574 | 0.53961 | -0.031547 | 0.70527 | 0.48742 | 2.6082 | 5.939 | 7.5072 | 5.2305 | 5.5562 | 2.311 | 16.0887 | 17.9825 | 17.9825
575 | 0.59675 | 0.33248 | 0.72466 | 0.63024 | 5.5386 | 6.0123 | 6.4505 | 5.5258 | 4.7778 | 1.3964 | 18.473 | 18.1633 | 18.473
576 | -0.84998 | -0.8074 | 0.19767 | 0.20972 | 3.8443 | 4.3018 | 4.4422 | 4.6944 | 5.4511 | 1.7439 | 14.5844 | 15.4816 | 15.4816
577 | -2.135 | -0.61362 | 0.016381 | 0.26973 | 3.2919 | 3.3924 | 7.2293 | 4.8137 | 4.7007 | 1.4928 | 12.9907 | 16.7147 | 16.7147
578 | 0.61828 | -0.010884 | 0.73181 | 0.49566 | 3.3878 | 6.04 | 5.6418 | 5.2467 | 5.9052 | 2.4342 | 17.1087 | 17.369 | 17.369
579 | -0.81943 | 0.91502 | 0.20627 | 0.81991 | 3.4267 | 4.3319 | 6.4432 | 6.024 | 4.5684 | 2.2608 | 16.0434 | 16.699 | 16.699
580 | 1.7398 | 1.0194 | 0.95905 | 0.846 | 4.7503 | 7.3809 | 5.23 | 6.1137 | 3.817 | 2.4228 | 20.6677 | 16.2201 | 20.6677
581 | -0.26385 | -0.47133 | 0.39595 | 0.3187 | 4.7758 | 4.9365 | 5.9953 | 4.9079 | 3.3747 | 2.8683 | 17.4885 | 17.0141 | 17.4885
582 | 1.4921 | 2.6799 | 0.93216 | 0.99632 | 2.656 | 7.1108 | 4.799 | 7.3164 | 4.9845 | 1.9208 | 19.004 | 14.3603 | 19.004
583 | 0.12921 | -0.22555 | 0.55141 | 0.41077 | 4.2759 | 5.4158 | 6.5565 | 5.0828 | 4.3707 | 1.8672 | 16.6417 | 17.0703 | 17.0703
584 | -0.24526 | 0.04451 | 0.40313 | 0.51775 | 4.4037 | 4.9584 | 5.0325 | 5.2904 | 3.5161 | 2.2875 | 16.9401 | 15.2398 | 16.9401
585 | -0.6357 | -0.59879 | 0.26249 | 0.27466 | 3.0527 | 4.5201 | 6.4499 | 4.8232 | 4.1539 | 1.825 | 14.2211 | 15.4815 | 15.4815
586 | 0.71052 | 0.76393 | 0.76131 | 0.77754 | 5.0753 | 6.1581 | 6.7879 | 5.8938 | 4.216 | 1.5666 | 18.6937 | 17.6458 | 18.6937
587 | -0.90286 | -0.75815 | 0.1833 | 0.22418 | 4.5258 | 4.2507 | 5.364 | 4.7237 | 3.9618 | 2.0146 | 15.5148 | 15.8663 | 15.8663
588 | -1.1894 | -0.58338 | 0.11714 | 0.27982 | 5.1461 | 3.9935 | 6.2831 | 4.8332 | 3.8679 | 2.3973 | 16.37 | 17.6943 | 17.6943
589 | 0.36763 | -0.5818 | 0.64343 | 0.28035 | 4.7097 | 5.7184 | 6.3144 | 4.8343 | 3.9686 | 2.714 | 17.9764 | 17.7067 | 17.9764
590 | 0.97672 | 0.20162 | 0.83565 | 0.57989 | 4.5592 | 6.4948 | 5.1049 | 5.4174 | 3.7847 | 1.7825 | 18.2539 | 15.2312 | 18.2539
591 | 0.18831 | -1.0069 | 0.57468 | 0.157 | 5.2645 | 5.4903 | 6.9751 | 4.583 | 5.5235 | 2.0645 | 17.4023 | 19.8276 | 19.8276
592 | 0.15352 | 1.2138 | 0.56101 | 0.88759 | 3.2841 | 5.4464 | 6.0529 | 6.2788 | 4.5957 | 1.7371 | 16.7464 | 15.6699 | 16.7464
593 | 0.66702 | -0.20532 | 0.74762 | 0.41866 | 3.6932 | 6.1024 | 6.7334 | 5.0978 | 3.8484 | 2.2508 | 17.1442 | 16.5259 | 17.1442
594 | -0.35275 | -1.882 | 0.36214 | 0.029919 | 3.5711 | 4.8331 | 5.3149 | 4.2321 | 3.399 | 1.9633 | 14.5996 | 14.2483 | 14.5996
595 | -0.19998 | 0.64179 | 0.42075 | 0.7395 | 3.8363 | 5.0121 | 6.2542 | 5.7886 | 3.7976 | 2.6552 | 17.2921 | 16.5432 | 17.2921
596 | 0.80291 | -1.1298 | 0.78899 | 0.12928 | 4.3936 | 6.2758 | 4.8857 | 4.5202 | 4.0102 | 1.5707 | 16.7603 | 14.8602 | 16.7603
597 | 0.25086 | -0.19525 | 0.59904 | 0.4226 | 3.4779 | 5.5695 | 6.0813 | 5.1053 | 5.3525 | 2.269 | 16.4218 | 17.1807 | 17.1807
598 | 0.95008 | 0.5609 | 0.82896 | 0.71257 | 3.6924 | 6.4615 | 6.5455 | 5.7192 | 3.2184 | 1.97 | 17.8431 | 15.4262 | 17.8431
599 | -1.6777 | -1.3886 | 0.046702 | 0.082475 | 4.9738 | 3.6362 | 3.311 | 4.4028 | 5.5825 | 1.557 | 14.5698 | 15.4243 | 15.4243
600 | -0.41996 | -0.99012 | 0.33726 | 0.16106 | 2.7549 | 4.7564 | 4.914 | 4.5919 | 4.2164 | 1.8976 | 14.0008 | 13.783 | 14.0008
601 | 0.47824 | -0.22337 | 0.68376 | 0.41162 | 4.1364 | 5.8602 | 5.9373 | 5.0844 | 5.0232 | 1.6153 | 16.6963 | 16.7122 | 16.7122
602 | 0.038917 | 0.6159 | 0.51552 | 0.73102 | 2.683 | 5.3031 | 6.0634 | 5.7664 | 3.6284 | 2.3148 | 16.0672 | 14.6895 | 16.0672
603 | 0.13065 | 0.8841 | 0.55197 | 0.81168 | 3.3269 | 5.4176 | 5.2777 | 5.9974 | 3.4241 | 1.5985 | 16.3404 | 13.6272 | 16.3404
604 | 0.32328 | 0.51894 | 0.62676 | 0.6981 | 4.8564 | 5.6618 | 7.2586 | 5.6834 | 3.7312 | 2.139 | 18.3405 | 17.9852 | 18.3405
605 | -0.69182 | -0.24774 | 0.24453 | 0.40217 | 2.8037 | 4.4613 | 7.1233 | 5.0664 | 4.7517 | 1.974 | 14.3054 | 16.6526 | 16.6526
606 | 0.84621 | 0.29658 | 0.80128 | 0.61661 | 3.8496 | 6.3307 | 4.1932 | 5.4958 | 3.2236 | 2.6642 | 18.3403 | 13.9306 | 18.3403
607 | -1.1453 | -0.51655 | 0.12604 | 0.30274 | 5.0572 | 4.0308 | 4.7569 | 4.8774 | 3.8323 | 1.7667 | 15.7321 | 15.4132 | 15.7321
608 | -0.64221 | 0.19624 | 0.26037 | 0.57779 | 4.2272 | 4.5132 | 3.4001 | 5.4129 | 3.1514 | 1.6072 | 15.7606 | 12.3859 | 15.7606
609 | 1.2007 | 1.0624 | 0.88507 | 0.85598 | 4.2617 | 6.77 | 5.8787 | 6.1504 | 4.4238 | 2.317 | 19.4992 | 16.8813 | 19.4992
610 | 1.1789 | 0.092582 | 0.88079 | 0.53688 | 4.2576 | 6.7437 | 7.1652 | 5.3289 | 5.977 | 2.021 | 18.3511 | 19.4207 | 19.4207
611 | 0.31019 | -0.50151 | 0.62179 | 0.30801 | 4.0658 | 5.6451 | 4.2958 | 4.8874 | 5.1798 | 2.0051 | 16.6034 | 15.5465 | 16.6034
612 | -0.11839 | -0.32292 | 0.45288 | 0.37338 | 4.1313 | 5.1101 | 5.9573 | 5.0117 | 4.3953 | 1.5836 | 15.8367 | 16.0675 | 16.0675
613 | -0.77571 | 0.58535 | 0.21896 | 0.72084 | 3.3025 | 4.3755 | 7.0279 | 5.7402 | 4.6576 | 1.8801 | 15.2983 | 16.8682 | 16.8682
614 | 0.50371 | -0.51746 | 0.69277 | 0.30242 | 3.3464 | 5.8929 | 5.9175 | 4.8767 | 4.5768 | 2.0893 | 16.2053 | 15.93 | 16.2053
615 | -0.67355 | -0.80535 | 0.2503 | 0.21031 | 3.04 | 4.4803 | 3.864 | 4.6956 | 5.0719 | 1.7664 | 13.9823 | 13.7423 | 13.9823
616 | -0.1715 | -0.52501 | 0.43191 | 0.29979 | 3.5471 | 5.0461 | 6.4619 | 4.8717 | 5.6853 | 1.6505 | 15.1154 | 17.3447 | 17.3447
617 | -1.4811 | -0.89015 | 0.069283 | 0.18669 | 2.9012 | 3.7676 | 6.6298 | 4.6467 | 3.5131 | 2.0651 | 13.3807 | 15.1092 | 15.1092
618 | -1.588 | -1.1696 | 0.056141 | 0.12108 | 3.816 | 3.6941 | 6.9421 | 4.5008 | 3.2146 | 2.3465 | 14.3574 | 16.3192 | 16.3192
619 | 1.7345 | 0.78268 | 0.95858 | 0.78309 | 3.7145 | 7.3753 | 6.776 | 5.9099 | 6.5214 | 2.4631 | 19.4628 | 19.475 | 19.475
620 | -1.5959 | -1.023 | 0.055258 | 0.15316 | 4.2977 | 3.6889 | 5.4926 | 4.5745 | 5.8311 | 1.5766 | 14.1377 | 17.198 | 17.198
621 | 0.43244 | -0.92806 | 0.66729 | 0.17669 | 4.1447 | 5.8015 | 3.5497 | 4.6256 | 3.5612 | 2.0229 | 16.5947 | 13.2785 | 16.5947
622 | -1.1068 | -1.552 | 0.13418 | 0.06033 | 3.6287 | 4.0641 | 5.1926 | 4.3388 | 3.5561 | 2.3367 | 14.3682 | 14.714 | 14.714
623 | 0.74808 | 0.2433 | 0.77279 | 0.59611 | 5.3138 | 6.206 | 7.4069 | 5.4516 | 4.1604 | 1.9563 | 18.9277 | 18.8374 | 18.9277
624 | 1.5869 | 1.809 | 0.94373 | 0.96477 | 3.4815 | 7.2165 | 5.1442 | 6.7552 | 5.6098 | 1.6019 | 19.055 | 15.8374 | 19.055
625 | -0.63186 | -0.92366 | 0.26374 | 0.17783 | 5.4616 | 4.5242 | 6.1199 | 4.628 | 3.7939 | 2.3424 | 16.9562 | 17.7178 | 17.7178
626 | -0.67782 | -0.023307 | 0.24894 | 0.4907 | 3.783 | 4.4759 | 6.2281 | 5.2369 | 3.8559 | 1.7004 | 15.1963 | 15.5675 | 15.5675
627 | 0.19292 | 0.0014242 | 0.57649 | 0.50057 | 3.6007 | 5.4961 | 6.0937 | 5.2564 | 4.7137 | 2.2636 | 16.6167 | 16.6716 | 16.6716
628 | -0.20645 | -0.026339 | 0.41822 | 0.48949 | 3.5071 | 5.0044 | 6.441 | 5.2346 | 3.9789 | 2.2931 | 16.0392 | 16.2201 | 16.2201
629 | 1.1106 | -0.17542 | 0.86662 | 0.43037 | 3.38 | 6.6604 | 4.3446 | 5.1202 | 4.8912 | 2.3679 | 17.5285 | 14.9837 | 17.5285
630 | -1.262 | -0.1941 | 0.10348 | 0.42305 | 3.7882 | 3.9338 | 6.445 | 5.1062 | 6.1277 | 2.1691 | 14.9974 | 18.53 | 18.53
631 | -1.3554 | -2.0731 | 0.087641 | 0.019084 | 4.3362 | 3.8604 | 6.9242 | 4.183 | 4.71 | 2.698 | 15.0776 | 18.6683 | 18.6683
632 | -0.14064 | -0.80925 | 0.44408 | 0.20918 | 4.8303 | 5.0832 | 4.0127 | 4.6933 | 3.8023 | 2.2181 | 16.8249 | 14.8633 | 16.8249
633 | 0.83916 | 1.013 | 0.79931 | 0.84448 | 3.6208 | 6.3218 | 3.2301 | 6.1082 | 4.9218 | 2.1917 | 18.2425 | 13.9643 | 18.2425
634 | 0.0087079 | 0.29427 | 0.50347 | 0.61573 | 3.4828 | 5.2656 | 7.5737 | 5.4939 | 5.052 | 1.1724 | 15.4146 | 17.2809 | 17.2809
635 | 0.51852 | -1.424 | 0.69795 | 0.077221 | 3.9101 | 5.9119 | 6.9589 | 4.3883 | 4.3807 | 1.9507 | 16.161 | 17.2004 | 17.2004
636 | 1.1749 | 0.53213 | 0.87999 | 0.70268 | 5.2024 | 6.7388 | 6.7448 | 5.6946 | 3.486 | 2.0838 | 19.7197 | 17.5169 | 19.7197
637 | 0.45147 | -0.041135 | 0.67417 | 0.48359 | 3.5715 | 5.8259 | 5.7883 | 5.223 | 4.6626 | 2.1109 | 16.7313 | 16.1333 | 16.7313
638 | 0.022239 | -1.4446 | 0.50887 | 0.074281 | 2.6753 | 5.2824 | 4.9583 | 4.38 | 5.1445 | 1.5438 | 13.8814 | 14.3219 | 14.3219
639 | 0.82004 | 1.3727 | 0.7939 | 0.91507 | 3.3357 | 6.2975 | 5.4622 | 6.4111 | 4.382 | 2.5494 | 18.5937 | 15.7293 | 18.5937
640 | 0.21162 | 0.12041 | 0.5838 | 0.54792 | 3.9115 | 5.5198 | 7.7425 | 5.3513 | 5.8083 | 1.4249 | 16.2074 | 18.8872 | 18.8872
641 | 0.20004 | 0.051384 | 0.57927 | 0.52049 | 3.9785 | 5.5051 | 4.1082 | 5.2959 | 3.768 | 1.3962 | 16.1757 | 13.2509 | 16.1757
642 | 0.15067 | 0.066276 | 0.55988 | 0.52642 | 4.758 | 5.4428 | 6.9448 | 5.3078 | 4.0387 | 2.5879 | 18.0965 | 18.3293 | 18.3293
643 | -0.31593 | 0.77345 | 0.37603 | 0.78037 | 3.537 | 4.8756 | 3.9693 | 5.902 | 3.557 | 2.3246 | 16.6392 | 13.3879 | 16.6392
644 | 0.56494 | 2.1563 | 0.71394 | 0.98447 | 4.2193 | 5.9715 | 3.6414 | 7.0016 | 6.1221 | 2.0773 | 19.2697 | 16.0601 | 19.2697
645 | -0.57737 | -0.19466 | 0.28184 | 0.42283 | 4.6126 | 4.5825 | 3.1014 | 5.1058 | 4.8667 | 2.316 | 16.6168 | 14.8967 | 16.6168
646 | -1.1575 | -0.37707 | 0.12354 | 0.35306 | 3.984 | 4.0204 | 5.1401 | 4.9732 | 4.1889 | 2.3567 | 15.3344 | 15.6697 | 15.6697
647 | -0.56181 | -0.83542 | 0.28712 | 0.20174 | 5.0651 | 4.5993 | 6.4116 | 4.678 | 4.2407 | 1.4485 | 15.7909 | 17.1659 | 17.1659
648 | -0.20051 | 0.04171 | 0.42054 | 0.51664 | 3.5042 | 5.0114 | 6.6752 | 5.2882 | 3.5318 | 1.8409 | 15.6448 | 15.552 | 15.6448
649 | 1.2296 | -0.040798 | 0.89058 | 0.48373 | 3.5304 | 6.8048 | 5.6775 | 5.2233 | 5.47 | 2.1535 | 17.712 | 16.8314 | 17.712
650 | 1.0842 | 0.43761 | 0.86087 | 0.66916 | 2.8486 | 6.6281 | 5.6176 | 5.6142 | 4.5591 | 1.5059 | 16.5969 | 14.5312 | 16.5969
651 | -0.77316 | -1.532 | 0.21971 | 0.062764 | 5.0643 | 4.3781 | 5.2459 | 4.3462 | 4.8726 | 1.9341 | 15.7227 | 17.1169 | 17.1169
652 | 0.58032 | -1.6412 | 0.71915 | 0.050381 | 2.5138 | 5.9913 | 6.1155 | 4.307 | 3.9471 | 1.8141 | 14.6262 | 14.3905 | 14.6262
653 | -0.51972 | -0.80592 | 0.30163 | 0.21014 | 3.4033 | 4.6452 | 5.3015 | 4.6953 | 4.111 | 2.3977 | 15.1416 | 15.2136 | 15.2136
654 | 0.84324 | 1.6764 | 0.80045 | 0.95317 | 4.2844 | 6.327 | 6.5572 | 6.6542 | 3.2815 | 2.0344 | 19.2999 | 16.1575 | 19.2999
655 | -1.5439 | -0.35334 | 0.061306 | 0.36192 | 2.9494 | 3.7239 | 5.7399 | 4.99 | 4.6071 | 1.3556 | 13.0188 | 14.652 | 14.652
656 | 0.01315 | 0.0624 | 0.50525 | 0.52488 | 4.514 | 5.2711 | 5.352 | 5.3047 | 4.3802 | 2.6106 | 17.7004 | 16.8567 | 17.7004
657 | 2.4489 | 0.9351 | 0.99284 | 0.82513 | 3.9632 | 8.0302 | 6.12 | 6.0413 | 4.3721 | 2.3221 | 20.3568 | 16.7775 | 20.3568
658 | 1.2635 | 1.4802 | 0.8968 | 0.93058 | 4.0548 | 6.8453 | 6.0061 | 6.4988 | 3.2345 | 1.1487 | 18.5477 | 14.4441 | 18.5477
659 | -0.24223 | -0.32643 | 0.4043 | 0.37205 | 3.9319 | 4.9619 | 4.9078 | 5.0092 | 5.1246 | 1.6462 | 15.5493 | 15.6105 | 15.6105
660 | -1.3602 | -1.0828 | 0.086891 | 0.13946 | 3.81 | 3.8568 | 5.7466 | 4.5437 | 5.007 | 1.2937 | 13.5042 | 15.8573 | 15.8573
661 | 0.52251 | 0.56861 | 0.69934 | 0.71519 | 4.6041 | 5.917 | 7.4829 | 5.7258 | 4.2028 | 2.7089 | 18.9559 | 18.9988 | 18.9988
662 | -0.28907 | 0.16639 | 0.38626 | 0.56608 | 3.8376 | 4.9069 | 4.3623 | 5.3886 | 3.5524 | 2.6265 | 16.7596 | 14.3787 | 16.7596
663 | -0.44951 | -0.46679 | 0.32653 | 0.32033 | 4.8559 | 4.7232 | 6.5688 | 4.911 | 3.8003 | 2.3179 | 16.808 | 17.5429 | 17.5429
664 | 0.93021 | 0.012838 | 0.82387 | 0.50512 | 4.1444 | 6.4366 | 4.233 | 5.2654 | 5.338 | 2.0907 | 17.9371 | 15.8061 | 17.9371
665 | 1.0439 | 0.25422 | 0.85173 | 0.60034 | 4.1748 | 6.5784 | 7.2561 | 5.4607 | 3.8609 | 2.0023 | 18.2161 | 17.2941 | 18.2161
666 | 0.28044 | 0.70594 | 0.61043 | 0.75989 | 3.5277 | 5.6071 | 5.5478 | 5.8438 | 5.0123 | 1.4222 | 16.4009 | 15.51 | 16.4009
667 | -0.67489 | -1.782 | 0.24987 | 0.037372 | 4.5572 | 4.4789 | 6.053 | 4.2613 | 3.2695 | 1.6598 | 14.9573 | 15.5396 | 15.5396
668 | -0.14797 | 0.58177 | 0.44118 | 0.71964 | 3.7345 | 5.0744 | 6.8941 | 5.7371 | 5.2189 | 1.3221 | 15.8681 | 17.1696 | 17.1696
669 | 0.41925 | 0.59442 | 0.66248 | 0.72388 | 4.2727 | 5.7845 | 6.7279 | 5.7479 | 5.662 | 2.3986 | 18.2038 | 19.0612 | 19.0612
670 | 0.9089 | 0.91389 | 0.8183 | 0.81961 | 4.3609 | 6.4098 | 5.5155 | 6.023 | 3.6093 | 2.1618 | 18.9556 | 15.6476 | 18.9556
671 | -0.21728 | 1.0172 | 0.41399 | 0.84548 | 4.4649 | 4.9915 | 5.6691 | 6.1118 | 5.548 | 2.3298 | 17.8979 | 18.0117 | 18.0117
672 | -0.75171 | -1.0489 | 0.22611 | 0.14711 | 2.7478 | 4.3998 | 6.8921 | 4.561 | 4.341 | 1.747 | 13.4556 | 15.7279 | 15.7279
673 | 0.3099 | -1.9604 | 0.62168 | 0.024977 | 4.1692 | 5.6447 | 5.7242 | 4.2109 | 3.5424 | 2.4235 | 16.4483 | 15.8593 | 16.4483
674 | 1.1878 | -0.4506 | 0.88254 | 0.32614 | 4.2345 | 6.7544 | 5.6937 | 4.922 | 3.8497 | 1.4578 | 17.3687 | 15.2357 | 17.3687
675 | 0.33833 | 1.413 | 0.63244 | 0.92118 | 4.3037 | 5.681 | 6.3394 | 6.4442 | 4.919 | 2.0051 | 18.434 | 17.5671 | 18.434
676 | -0.52964 | -0.084008 | 0.29818 | 0.46653 | 3.8033 | 4.6344 | 4.8415 | 5.1898 | 4.8039 | 2.6725 | 16.3 | 16.1212 | 16.3
677 | -1.2366 | -1.132 | 0.10811 | 0.12881 | 3.3494 | 3.9544 | 5.3856 | 4.5191 | 4.5552 | 1.7005 | 13.5235 | 14.9908 | 14.9908
678 | -0.0048552 | -0.4316 | 0.49806 | 0.33302 | 4.6135 | 5.2489 | 6.4862 | 4.9351 | 4.7852 | 1.5461 | 16.3437 | 17.4311 | 17.4311
679 | 1.3291 | 1.0191 | 0.9081 | 0.84592 | 3.1097 | 6.9229 | 3.8257 | 6.1133 | 4.1428 | 1.862 | 18.0079 | 12.9401 | 18.0079
680 | -0.23857 | -0.027824 | 0.40572 | 0.4889 | 3.7139 | 4.9663 | 5.8564 | 5.2334 | 4.3646 | 1.9188 | 15.8324 | 15.8537 | 15.8537
681 | 1.6644 | 0.4963 | 0.95199 | 0.69016 | 4.1257 | 7.3008 | 6.3455 | 5.6641 | 3.2513 | 2.5133 | 19.6039 | 16.2358 | 19.6039
682 | 0.5062 | -0.99004 | 0.69364 | 0.16108 | 4.978 | 5.8961 | 5.9557 | 4.5919 | 3.9703 | 2.4096 | 17.8756 | 17.3136 | 17.8756
683 | 0.73675 | 0.6437 | 0.76936 | 0.74012 | 3.0563 | 6.1916 | 4.7622 | 5.7902 | 4.78 | 2.3163 | 17.3544 | 14.9148 | 17.3544
684 | -0.050317 | -0.018447 | 0.47994 | 0.49264 | 3.7492 | 5.193 | 7.059 | 5.2408 | 4.3601 | 2.4838 | 16.6667 | 17.6521 | 17.6521
685 | -0.3265 | -0.88538 | 0.37202 | 0.18798 | 3.6238 | 4.8634 | 6.7537 | 4.6494 | 5.664 | 1.7711 | 14.9077 | 17.8126 | 17.8126
686 | -2.1605 | -0.4608 | 0.015368 | 0.32247 | 4.7498 | 3.3812 | 4.8566 | 4.9151 | 3.9502 | 1.8499 | 14.8959 | 15.4065 | 15.4065
687 | 0.44876 | 0.30699 | 0.6732 | 0.62057 | 3.6265 | 5.8224 | 4.6693 | 5.5045 | 4.0515 | 2.8327 | 17.786 | 15.18 | 17.786
688 | 0.072074 | 0.66964 | 0.52873 | 0.74846 | 3.2191 | 5.3443 | 3.9081 | 5.8125 | 5.0404 | 2.0242 | 16.4001 | 14.1917 | 16.4001
689 | 1.0817 | 1.1445 | 0.86031 | 0.8738 | 3.9371 | 6.625 | 4.8762 | 6.2203 | 3.3472 | 1.8874 | 18.6697 | 14.0479 | 18.6697
690 | 0.69211 | -0.10216 | 0.75556 | 0.45932 | 4.1989 | 6.1345 | 6.8132 | 5.1758 | 5.1197 | 2.3793 | 17.8886 | 18.5111 | 18.5111
691 | 2.5397 | 1.8209 | 0.99445 | 0.96569 | 4.1722 | 8.0989 | 4.8335 | 6.764 | 4.3881 | 1.6999 | 20.7349 | 15.0936 | 20.7349
692 | 0.93377 | 0.66975 | 0.82479 | 0.74849 | 5.3663 | 6.4411 | 6.3222 | 5.8126 | 4.2898 | 1.7655 | 19.3855 | 17.7438 | 19.3855
693 | 1.0167 | 0.49036 | 0.84534 | 0.68806 | 3.9698 | 6.5446 | 4.1844 | 5.659 | 5.375 | 2.4618 | 18.6352 | 15.991 | 18.6352
694 | 0.21865 | 0.7729 | 0.58654 | 0.78021 | 5.5003 | 5.5287 | 6.3795 | 5.9015 | 3.4731 | 2.4456 | 19.3761 | 17.7985 | 19.3761
695 | 0.72592 | 0.37633 | 0.76606 | 0.64666 | 3.1974 | 6.1777 | 5.1607 | 5.5625 | 3.5615 | 2.7866 | 17.7243 | 14.7062 | 17.7243
696 | 0.92388 | 0.59647 | 0.82223 | 0.72457 | 4.0606 | 6.4287 | 6.1109 | 5.7497 | 4.0181 | 2.4846 | 18.7236 | 16.6742 | 18.7236
697 | 0.71241 | 0.26928 | 0.7619 | 0.60614 | 4.5279 | 6.1605 | 4.4522 | 5.4731 | 4.5724 | 1.6839 | 17.8454 | 15.2364 | 17.8454
698 | 0.97957 | -0.89437 | 0.83635 | 0.18556 | 3.8433 | 6.4984 | 7.0741 | 4.6444 | 4.4068 | 1.3085 | 16.2945 | 16.6326 | 16.6326
699 | 0.16337 | 1.3535 | 0.56488 | 0.91205 | 4.0913 | 5.4588 | 4.7706 | 6.3953 | 3.7676 | 2.1563 | 18.1016 | 14.7858 | 18.1016
700 | -1.4344 | -0.10653 | 0.075723 | 0.45758 | 2.6283 | 3.8013 | 6.9394 | 5.1725 | 3.6005 | 2.4467 | 14.0488 | 15.6149 | 15.6149
701 | -0.95369 | -0.9045 | 0.17012 | 0.18286 | 4.9523 | 4.2026 | 6.7144 | 4.6387 | 5.7901 | 1.6277 | 15.4212 | 19.0844 | 19.0844
702 | 0.7131 | 0.76084 | 0.76211 | 0.77662 | 4.2237 | 6.1614 | 5.3002 | 5.8911 | 4.4793 | 1.996 | 18.2722 | 15.9992 | 18.2722
703 | 1.815 | 2.5314 | 0.96524 | 0.99432 | 3.4758 | 7.4588 | 5.5114 | 7.2345 | 5.7365 | 2.0072 | 20.1763 | 16.7309 | 20.1763
704 | 1.159 | 1.5933 | 0.87677 | 0.94445 | 4.695 | 6.7195 | 5.8433 | 6.5891 | 5.2687 | 2.1744 | 20.178 | 17.9814 | 20.178
705 | -1.267 | -0.57928 | 0.10259 | 0.2812 | 4.0314 | 3.9299 | 4.112 | 4.8359 | 4.2562 | 2.1398 | 14.937 | 14.5394 | 14.937
706 | -1.9068 | 0.43679 | 0.028275 | 0.66887 | 3.6569 | 3.5036 | 7.5895 | 5.6135 | 3.1787 | 2.3829 | 15.1569 | 16.808 | 16.808
707 | -0.020128 | 0.84163 | 0.49197 | 0.8 | 4.5237 | 5.2301 | 7.2329 | 5.9608 | 3.8812 | 1.7396 | 17.4542 | 17.3775 | 17.4542
708 | -1.2921 | -1.9704 | 0.098158 | 0.024397 | 4.4194 | 3.9098 | 6.8029 | 4.2083 | 4.0464 | 1.5942 | 14.1316 | 16.8629 | 16.8629
709 | -0.54498 | -0.88235 | 0.29288 | 0.18879 | 4.8529 | 4.6176 | 6.9149 | 4.6511 | 4.0897 | 2.3744 | 16.4961 | 18.232 | 18.232
710 | -0.97046 | -0.45152 | 0.16591 | 0.32581 | 3.0945 | 4.1869 | 5.9258 | 4.9214 | 5.092 | 1.3948 | 13.5976 | 15.5071 | 15.5071
711 | 0.73643 | 2.3452 | 0.76927 | 0.99049 | 5.4176 | 6.1911 | 7.7233 | 7.1234 | 6.4838 | 2.4659 | 21.1981 | 22.0906 | 22.0906
712 | -0.36862 | -1.1288 | 0.3562 | 0.12948 | 5.5344 | 4.8149 | 6.8438 | 4.5207 | 4.7134 | 2.3125 | 17.1824 | 19.4041 | 19.4041
713 | 0.70255 | 0.18929 | 0.75883 | 0.57507 | 4.6449 | 6.1479 | 6.34 | 5.4073 | 4.0922 | 2.0566 | 18.2567 | 17.1337 | 18.2567
714 | -0.033921 | 0.91254 | 0.48647 | 0.81926 | 3.4501 | 5.2131 | 4.1309 | 6.0219 | 3.2017 | 2.0601 | 16.7452 | 12.8428 | 16.7452
715 | 0.78905 | 0.84598 | 0.78496 | 0.80122 | 3.3448 | 6.2582 | 5.0565 | 5.9645 | 4.1821 | 1.2886 | 16.8561 | 13.8719 | 16.8561
716 | -0.93289 | -0.33842 | 0.17544 | 0.36752 | 4.3233 | 4.2221 | 3.9521 | 5.0006 | 4.779 | 1.6857 | 15.2317 | 14.7401 | 15.2317
717 | -1.202 | -1.4615 | 0.11468 | 0.071946 | 4.1773 | 3.983 | 5.1446 | 4.3733 | 4.1942 | 1.7553 | 14.2889 | 15.2714 | 15.2714
718 | 1.598 | 1.2364 | 0.94498 | 0.89185 | 3.0786 | 7.2287 | 4.9529 | 6.2978 | 4.6281 | 2.2363 | 18.8413 | 14.8959 | 18.8413
719 | 0.70511 | -0.69319 | 0.75963 | 0.2441 | 4.268 | 6.1511 | 4.3348 | 4.7634 | 4.5331 | 1.85 | 17.0325 | 14.9859 | 17.0325
720 | -1.1636 | -1.003 | 0.1223 | 0.15794 | 3.5853 | 4.0153 | 6.1302 | 4.585 | 3.3165 | 1.4237 | 13.6093 | 14.4557 | 14.4557
721 | -2.1046 | -2.0363 | 0.017662 | 0.020859 | 4.9342 | 3.406 | 5.1103 | 4.1918 | 3.6348 | 1.9776 | 14.5095 | 15.6568 | 15.6568
722 | 1.5245 | 2.1457 | 0.9363 | 0.98405 | 4.0692 | 7.1472 | 5.5361 | 6.9945 | 3.8138 | 2.3374 | 20.5483 | 15.7566 | 20.5483
723 | 0.013065 | -0.50936 | 0.50521 | 0.30525 | 3.3724 | 5.271 | 4.3843 | 4.8822 | 3.2592 | 1.6629 | 15.1885 | 12.6788 | 15.1885
724 | 2.3757 | 1.8558 | 0.99124 | 0.96826 | 4.6054 | 7.9723 | 5.9755 | 6.7899 | 3.1885 | 1.8546 | 21.2222 | 15.624 | 21.2222
725 | -0.26921 | -0.88399 | 0.39388 | 0.18835 | 3.8661 | 4.9302 | 7.1463 | 4.6502 | 4.2793 | 1.7041 | 15.1506 | 16.9958 | 16.9958
726 | -3.5682 | -2.9139 | 0.00017975 | 0.0017845 | 3.7218 | 3.0542 | 5.5514 | 4.0542 | 3.8217 | 2.4016 | 13.2317 | 15.4964 | 15.4964
727 | 0.0010184 | 1.2096 | 0.50041 | 0.88678 | 4.4413 | 5.2561 | 6.4527 | 6.2752 | 3.7679 | 2.4481 | 18.4208 | 17.11 | 18.4208
728 | -0.46226 | -0.66252 | 0.32195 | 0.25382 | 2.6065 | 4.7089 | 7.1964 | 4.7826 | 3.3457 | 1.8485 | 13.9465 | 14.9972 | 14.9972
729 | 1.0587 | 1.5275 | 0.85513 | 0.93669 | 3.6305 | 6.5967 | 6.3564 | 6.5369 | 4.7095 | 2.0359 | 18.8 | 16.7323 | 18.8
730 | 0.030013 | -0.21355 | 0.51197 | 0.41545 | 3.5128 | 5.292 | 5.5251 | 5.0917 | 4.198 | 2.113 | 16.0095 | 15.3489 | 16.0095
731 | 0.57394 | 2.0745 | 0.717 | 0.98098 | 3.4327 | 5.9831 | 6.4772 | 6.9461 | 5.3572 | 1.4829 | 17.8448 | 16.75 | 17.8448
732 | -0.1703 | 1.245 | 0.43239 | 0.89344 | 2.9557 | 5.0475 | 3.5 | 6.305 | 4.6156 | 1.3209 | 15.6292 | 12.3923 | 15.6292
733 | -0.75108 | -1.0849 | 0.2263 | 0.13898 | 4.7263 | 4.4004 | 5.5597 | 4.5426 | 3.3336 | 1.9109 | 15.5801 | 15.5304 | 15.5801
734 | -1.2005 | -1.6634 | 0.11498 | 0.048119 | 3.5555 | 3.9842 | 6.2188 | 4.2995 | 4.0871 | 2.4933 | 14.3325 | 16.3547 | 16.3547
735 | -0.066048 | 1.6622 | 0.47367 | 0.95176 | 3.4896 | 5.1737 | 5.6469 | 6.6431 | 5.1356 | 1.9566 | 17.263 | 16.2286 | 17.263
736 | 0.17078 | 0.069784 | 0.5678 | 0.52782 | 3.7719 | 5.4681 | 6.8042 | 5.3106 | 4.5293 | 2.1944 | 16.7451 | 17.2998 | 17.2998
737 | 1.1991 | 0.59828 | 0.88476 | 0.72517 | 4.8929 | 6.7681 | 5.775 | 5.7512 | 4.8088 | 1.6478 | 19.0601 | 17.1246 | 19.0601
738 | 0.72164 | 0.96569 | 0.76474 | 0.8329 | 2.9138 | 6.1723 | 7.065 | 6.0676 | 4.3914 | 1.7929 | 16.9465 | 16.1631 | 16.9465
739 | 0.057617 | 0.38375 | 0.52297 | 0.64942 | 4.9769 | 5.3263 | 6.5205 | 5.5688 | 3.4387 | 1.4674 | 17.3395 | 16.4036 | 17.3395
740 | -0.57781 | 0.87141 | 0.2817 | 0.80823 | 4.0559 | 4.582 | 4.2354 | 5.9864 | 4.0147 | 2.5843 | 17.2086 | 14.8902 | 17.2086
741 | -1.2941 | -0.77258 | 0.097813 | 0.21989 | 3.614 | 3.9082 | 4.2212 | 4.715 | 4.82 | 1.5024 | 13.7395 | 14.1575 | 14.1575
742 | 2.3857 | 1.8396 | 0.99148 | 0.96709 | 3.1337 | 7.9804 | 4.3295 | 6.778 | 5.7965 | 2.4432 | 20.3352 | 15.7028 | 20.3352
743 | -0.41261 | -0.4258 | 0.33995 | 0.33513 | 4.4826 | 4.7647 | 6.0756 | 4.9392 | 4.0956 | 1.7028 | 15.8893 | 16.3566 | 16.3566
744 | -1.0379 | 0.029218 | 0.14966 | 0.51165 | 4.1642 | 4.1252 | 7.2666 | 5.2783 | 3.8926 | 1.8937 | 15.4614 | 17.2172 | 17.2172
745 | -0.028633 | 0.054212 | 0.48858 | 0.52162 | 3.5361 | 5.2196 | 7.1097 | 5.2982 | 5.0348 | 2.5203 | 16.5743 | 18.201 | 18.201
746 | 0.48642 | 2.6643 | 0.68667 | 0.99614 | 3.8902 | 5.8707 | 5.4629 | 7.3081 | 4.2804 | 2.379 | 19.448 | 16.0125 | 19.448
747 | 0.77563 | -0.13255 | 0.78102 | 0.44727 | 3.8632 | 6.2411 | 5.7188 | 5.1526 | 3.8639 | 2.2245 | 17.4814 | 15.6704 | 17.4814
748 | 1.1899 | 0.060496 | 0.88297 | 0.52412 | 5.3336 | 6.757 | 6.2546 | 5.3032 | 4.5413 | 2.0842 | 19.478 | 18.2137 | 19.478
749 | -1.1885 | -1.7161 | 0.11732 | 0.043075 | 3.759 | 3.9943 | 5.4265 | 4.2821 | 3.4875 | 1.9836 | 14.019 | 14.6567 | 14.6567
750 | -0.020118 | 0.083884 | 0.49197 | 0.53343 | 4.3052 | 5.2301 | 6.453 | 5.3219 | 3.52 | 1.5974 | 16.4545 | 15.8755 | 16.4545
751 | -0.83146 | -0.46561 | 0.20286 | 0.32075 | 3.2622 | 4.32 | 5.3352 | 4.9118 | 4.9909 | 1.9917 | 14.4857 | 15.58 | 15.58
752 | -0.87557 | -1.613 | 0.19063 | 0.053375 | 4.3053 | 4.2769 | 5.7966 | 4.3168 | 3.8686 | 1.862 | 14.7611 | 15.8326 | 15.8326
753 | 0.52749 | -0.35905 | 0.70107 | 0.35978 | 3.0429 | 5.9234 | 5.0499 | 4.986 | 4.0884 | 2.2215 | 16.1737 | 14.4027 | 16.1737
754 | -1.5577 | -0.044204 | 0.059655 | 0.48237 | 3.7011 | 3.7145 | 4.4308 | 5.2206 | 4.0766 | 2.3079 | 14.9441 | 14.5164 | 14.9441
755 | 0.21364 | -0.72374 | 0.58459 | 0.23461 | 4.1497 | 5.5223 | 5.0566 | 4.7446 | 4.5433 | 1.2932 | 15.7097 | 15.0427 | 15.7097
756 | 0.21655 | 0.87304 | 0.58572 | 0.80868 | 3.5017 | 5.526 | 5.9472 | 5.9879 | 3.6711 | 1.7304 | 16.746 | 14.8504 | 16.746
757 | 0.097972 | 1.12 | 0.53902 | 0.86864 | 2.8105 | 5.3767 | 6.0636 | 6.1994 | 3.229 | 2.5585 | 16.9451 | 14.6615 | 16.9451
758 | -0.13963 | -1.0906 | 0.44447 | 0.13773 | 2.807 | 5.0844 | 4.9735 | 4.5397 | 5.4158 | 2.3991 | 14.8302 | 15.5954 | 15.5954
759 | -0.17421 | 0.04043 | 0.43085 | 0.51612 | 5.5655 | 5.0428 | 6.6379 | 5.2872 | 4.6703 | 1.6488 | 17.5444 | 18.5225 | 18.5225
760 | 0.66215 | 0.95828 | 0.74606 | 0.83104 | 3.5801 | 6.0962 | 5.3444 | 6.0612 | 4.8132 | 1.6783 | 17.4158 | 15.416 | 17.4158
761 | 1.8971 | 0.13987 | 0.97109 | 0.55562 | 4.8003 | 7.5415 | 5.1112 | 5.367 | 3.1539 | 1.9595 | 19.6683 | 15.0248 | 19.6683
762 | -0.727 | -0.95443 | 0.23361 | 0.16993 | 3.4492 | 4.425 | 4.8987 | 4.6111 | 4.7626 | 2.4259 | 14.9112 | 15.5364 | 15.5364
763 | -1.0258 | 0.27711 | 0.1525 | 0.60915 | 4.2801 | 4.1361 | 5.4991 | 5.4796 | 4.0527 | 2.5797 | 16.4755 | 16.4116 | 16.4755
764 | 2.142 | -0.060871 | 0.9839 | 0.47573 | 3.1282 | 7.7732 | 3.6522 | 5.2077 | 3.6845 | 2.7907 | 18.8998 | 13.2556 | 18.8998
765 | 0.97023 | 0.83703 | 0.83403 | 0.79871 | 3.1825 | 6.4867 | 7.1145 | 5.9568 | 4.6706 | 1.8352 | 17.4614 | 16.8029 | 17.4614
766 | -0.31022 | -1.1416 | 0.3782 | 0.12681 | 3.856 | 4.8823 | 4.5154 | 4.5144 | 5.0316 | 1.4118 | 14.6645 | 14.8148 | 14.8148
767 | 0.17603 | 0.050077 | 0.56987 | 0.51997 | 4.4656 | 5.4748 | 4.2377 | 5.2949 | 3.642 | 2.5933 | 17.8285 | 14.9386 | 17.8285
768 | 1.102 | 0.77833 | 0.86478 | 0.78181 | 3.9936 | 6.65 | 7.8184 | 5.9062 | 3.5247 | 2.184 | 18.7338 | 17.5208 | 18.7338
769 | 0.057257 | -1.3617 | 0.52283 | 0.086644 | 2.6999 | 5.3259 | 6.3453 | 4.4141 | 5.1814 | 1.4315 | 13.8713 | 15.6581 | 15.6581
770 | -0.31413 | -1.6767 | 0.37671 | 0.046805 | 3.4286 | 4.8777 | 2.9537 | 4.295 | 5.1902 | 1.751 | 14.3523 | 13.3236 | 14.3523
771 | 0.10681 | -0.25418 | 0.54253 | 0.39968 | 3.0344 | 5.3877 | 7.4644 | 5.0617 | 3.8074 | 2.3721 | 15.8559 | 16.6783 | 16.6783
772 | 0.72817 | 2.2608 | 0.76675 | 0.98811 | 4.1551 | 6.1806 | 4.7652 | 7.0701 | 4.8766 | 2.0327 | 19.4385 | 15.8296 | 19.4385
773 | 0.042929 | -1.4388 | 0.51712 | 0.075105 | 4.2307 | 5.308 | 6.6795 | 4.3823 | 5.7658 | 1.6235 | 15.5446 | 18.2996 | 18.2996
774 | 2.2291 | 2.385 | 0.9871 | 0.99146 | 2.4674 | 7.85 | 4.4384 | 7.148 | 4.3971 | 1.4311 | 18.8965 | 12.734 | 18.8965
775 | -0.10087 | -0.34876 | 0.45983 | 0.36364 | 3.3016 | 5.1313 | 5.8246 | 4.9933 | 3.9377 | 1.3863 | 14.8125 | 14.4502 | 14.8125
776 | -1.0917 | -1.6947 | 0.13748 | 0.045063 | 2.6021 | 4.0773 | 5.2426 | 4.289 | 4.093 | 2.1164 | 13.0849 | 14.0541 | 14.0541
777 | 1.2528 | 0.34312 | 0.89486 | 0.63425 | 3.6004 | 6.8325 | 6.9756 | 5.5347 | 4.4319 | 2.4102 | 18.3777 | 17.418 | 18.3777
778 | -1.2726 | -1.0238 | 0.10158 | 0.15297 | 3.1314 | 3.9253 | 6.5864 | 4.5741 | 4.2387 | 2.1628 | 13.7935 | 16.1192 | 16.1192
779 | -1.4907 | -0.68834 | 0.068017 | 0.24562 | 3.8088 | 3.7608 | 6.0785 | 4.7664 | 4.0675 | 2.3532 | 14.6893 | 16.308 | 16.308
780 | -1.3863 | -0.52571 | 0.082832 | 0.29955 | 4.2894 | 3.837 | 5.7225 | 4.8712 | 4.0664 | 2.1549 | 15.1526 | 16.2333 | 16.2333
781 | -0.16935 | 1.1638 | 0.43276 | 0.87775 | 5.2893 | 5.0487 | 5.7159 | 6.2366 | 4.4119 | 2.2422 | 18.8168 | 17.6594 | 18.8168
782 | -1.1132 | -0.89199 | 0.13281 | 0.1862 | 4.3382 | 4.0585 | 7.6518 | 4.6457 | 4.496 | 2.7345 | 15.777 | 19.2206 | 19.2206
783 | 0.63516 | 0.889 | 0.73734 | 0.813 | 3.6795 | 6.0616 | 7.0614 | 6.0016 | 5.2124 | 2.0539 | 17.7966 | 18.0072 | 18.0072
784 | -0.99832 | -1.2727 | 0.15906 | 0.10156 | 3.6787 | 4.1612 | 5.3485 | 4.4529 | 5.3733 | 2.583 | 14.8758 | 16.9835 | 16.9835
785 | -0.39189 | 0.11759 | 0.34757 | 0.5468 | 4.1533 | 4.7883 | 4.5594 | 5.349 | 5.0382 | 1.4815 | 15.7721 | 15.2324 | 15.7721
786 | -1.2546 | 0.53279 | 0.10481 | 0.70291 | 4.7286 | 3.9398 | 4.0651 | 5.6952 | 3.1014 | 1.856 | 16.2196 | 13.7511 | 16.2196
787 | -0.26034 | 0.2456 | 0.3973 | 0.597 | 2.6161 | 4.9406 | 5.2768 | 5.4535 | 4.3997 | 1.4013 | 14.4115 | 13.6939 | 14.4115
788 | 1.3353 | 0.067256 | 0.90911 | 0.52681 | 3.2499 | 6.9302 | 5.5212 | 5.3086 | 4.5585 | 1.9013 | 17.3899 | 15.2309 | 17.3899
789 | -1.5823 | -0.45001 | 0.056787 | 0.32635 | 2.7467 | 3.6979 | 6.6094 | 4.9225 | 3.9384 | 1.4935 | 12.8605 | 14.788 | 14.788
790 | -1.0677 | -0.49753 | 0.14284 | 0.30941 | 2.8946 | 4.0986 | 3.8794 | 4.8901 | 3.6037 | 2.6791 | 14.5623 | 13.0567 | 14.5623
791 | 0.82782 | 0.089902 | 0.79611 | 0.53582 | 5.3211 | 6.3074 | 6.556 | 5.3267 | 5.3754 | 2.4485 | 19.4037 | 19.701 | 19.701
792 | -0.65565 | 0.29367 | 0.25602 | 0.61549 | 4.2725 | 4.4991 | 7.0856 | 5.4934 | 4.4761 | 2.8088 | 17.0738 | 18.643 | 18.643
793 | -0.83612 | 0.13183 | 0.20154 | 0.55244 | 2.9617 | 4.3154 | 6.6844 | 5.3605 | 4.409 | 1.7912 | 14.4288 | 15.8463 | 15.8463
794 | -1.0177 | -1.7126 | 0.15442 | 0.043395 | 4.1602 | 4.1435 | 5.5061 | 4.2832 | 5.4513 | 2.4844 | 15.0713 | 17.602 | 17.602
795 | 0.4104 | 0.21483 | 0.65924 | 0.58505 | 3.7239 | 5.7732 | 4.6949 | 5.4282 | 3.4692 | 1.3403 | 16.2657 | 13.2284 | 16.2657
796 | 1.0994 | 0.32287 | 0.8642 | 0.6266 | 4.5638 | 6.6467 | 4.8669 | 5.5177 | 4.0897 | 1.1973 | 17.9256 | 14.7177 | 17.9256
797 | -0.60209 | -1.2761 | 0.27356 | 0.10096 | 3.4269 | 4.5559 | 6.4461 | 4.4514 | 4.4641 | 1.3221 | 13.7563 | 15.6593 | 15.6593
798 | 0.28683 | -0.31737 | 0.61288 | 0.37548 | 4.5145 | 5.6153 | 7.1123 | 5.0157 | 4.2896 | 2.6608 | 17.8064 | 18.5772 | 18.5772
799 | 0.25655 | 0.15004 | 0.60124 | 0.55963 | 5.4431 | 5.5768 | 7.9441 | 5.3753 | 4.5084 | 2.2889 | 18.684 | 20.1845 | 20.1845
800 | 0.00040451 | -0.67762 | 0.50016 | 0.24901 | 3.2342 | 5.2554 | 4.4745 | 4.7731 | 4.8485 | 1.6582 | 14.9209 | 14.2154 | 14.9209
801 | 0.061992 | 1.1062 | 0.52472 | 0.86567 | 3.5938 | 5.3318 | 4.0429 | 6.1877 | 4.4209 | 2.7004 | 17.8136 | 14.758 | 17.8136
802 | 1.1578 | 0.81503 | 0.87653 | 0.79247 | 4.1824 | 6.7181 | 5.0376 | 5.9378 | 3.715 | 1.7552 | 18.5935 | 14.6901 | 18.5935
803 | 0.93384 | 1.8226 | 0.82481 | 0.96582 | 4.989 | 6.4412 | 5.9016 | 6.7653 | 3.7622 | 1.799 | 19.9944 | 16.4517 | 19.9944
804 | -1.1699 | -0.92763 | 0.12103 | 0.1768 | 4.44 | 4.0099 | 5.0188 | 4.6258 | 3.741 | 1.9143 | 14.99 | 15.114 | 15.114
805 | 0.60016 | 0.30493 | 0.7258 | 0.61979 | 3.0295 | 6.0167 | 5.7926 | 5.5028 | 3.5751 | 1.1859 | 15.7349 | 13.5831 | 15.7349
806 | -0.65919 | -0.36076 | 0.25489 | 0.35914 | 4.3814 | 4.4954 | 4.6757 | 4.9847 | 4.3913 | 1.5163 | 15.3777 | 14.9647 | 15.3777
807 | 1.0734 | 0.69761 | 0.85846 | 0.75729 | 3.5645 | 6.6148 | 4.297 | 5.8366 | 5.0553 | 2.6395 | 18.6554 | 15.5563 | 18.6554
808 | 0.67097 | 1.3 | 0.74888 | 0.9032 | 3.9316 | 6.1075 | 4.3398 | 6.3509 | 5.3313 | 1.5113 | 17.9013 | 15.114 | 17.9013
809 | -1.8604 | -0.86967 | 0.031415 | 0.19224 | 5.1838 | 3.5287 | 7.232 | 4.6583 | 3.4074 | 1.8382 | 15.2091 | 17.6615 | 17.6615
810 | -1.0785 | -1.447 | 0.14041 | 0.073946 | 3.738 | 4.089 | 5.9093 | 4.379 | 4.3744 | 1.6646 | 13.8706 | 15.6864 | 15.6864
811 | 0.5317 | 0.68071 | 0.70253 | 0.75197 | 5.5254 | 5.9288 | 4.7814 | 5.8221 | 4.5757 | 1.7984 | 19.0747 | 16.6808 | 19.0747
812 | -0.55081 | 0.025869 | 0.29088 | 0.51032 | 3.8862 | 4.6112 | 4.5267 | 5.2757 | 4.2018 | 1.6796 | 15.4526 | 14.2943 | 15.4526
813 | 0.10403 | 0.091233 | 0.54143 | 0.53635 | 4.8797 | 5.3843 | 5.4163 | 5.3278 | 4.033 | 2.2048 | 17.7966 | 16.5338 | 17.7966
814 | -0.13798 | -0.22143 | 0.44513 | 0.41238 | 2.8269 | 5.0864 | 7.2585 | 5.0858 | 3.5563 | 2.1596 | 15.1587 | 15.8013 | 15.8013
815 | -1.135 | -0.51747 | 0.12819 | 0.30241 | 2.9988 | 4.0397 | 5.6491 | 4.8767 | 3.7476 | 2.2169 | 14.132 | 14.6123 | 14.6123
816 | -0.61534 | -1.4908 | 0.26917 | 0.068005 | 4.7549 | 4.5418 | 6.061 | 4.3618 | 3.1498 | 2.05 | 15.7085 | 16.0157 | 16.0157
817 | -0.2883 | -0.64791 | 0.38656 | 0.25852 | 4.4801 | 4.9078 | 6.9858 | 4.7918 | 4.1765 | 2.1637 | 16.3434 | 17.8062 | 17.8062
818 | 0.83124 | 0.99835 | 0.79708 | 0.84095 | 4.2082 | 6.3117 | 5.0795 | 6.0956 | 3.3181 | 2.6024 | 19.218 | 15.2082 | 19.218
819 | -0.33132 | 0.37318 | 0.3702 | 0.64549 | 3.3097 | 4.8578 | 5.1859 | 5.5599 | 4.1011 | 1.6904 | 15.4178 | 14.2871 | 15.4178
820 | 0.89497 | -0.66117 | 0.8146 | 0.25425 | 4.432 | 6.3923 | 4.93 | 4.7834 | 4.4304 | 2.4548 | 18.0626 | 16.2472 | 18.0626
821 | 0.38049 | 0.72132 | 0.64821 | 0.76464 | 3.6238 | 5.7349 | 5.5866 | 5.8571 | 6.3621 | 2.086 | 17.3018 | 17.6585 | 17.6585
822 | 0.67827 | -0.34703 | 0.7512 | 0.36428 | 2.9963 | 6.1168 | 5.4896 | 4.9945 | 4.6914 | 2.3915 | 16.4991 | 15.5688 | 16.4991
823 | 0.92893 | -0.36954 | 0.82354 | 0.35586 | 4.3807 | 6.435 | 4.2114 | 4.9785 | 3.6099 | 2.5224 | 18.3167 | 14.7245 | 18.3167
824 | 0.38021 | 0.4019 | 0.6481 | 0.65612 | 4.9516 | 5.7345 | 5.9414 | 5.5841 | 3.6989 | 2.1434 | 18.4136 | 16.7353 | 18.4136
825 | -0.94863 | 0.92684 | 0.1714 | 0.823 | 3.9484 | 4.2073 | 6.8903 | 6.0342 | 3.485 | 1.9914 | 16.1813 | 16.3151 | 16.3151
826 | -1.0914 | -0.86296 | 0.13755 | 0.19408 | 3.6288 | 4.0776 | 6.5461 | 4.6622 | 4.4467 | 2.3323 | 14.7009 | 16.9539 | 16.9539
827 | -0.57063 | -0.25231 | 0.28412 | 0.4004 | 4.3309 | 4.5897 | 6.8915 | 5.063 | 4.4326 | 1.9397 | 15.9233 | 17.5946 | 17.5946
828 | -0.39373 | -0.26291 | 0.34689 | 0.39631 | 4.4303 | 4.7862 | 7.4034 | 5.0553 | 3.4879 | 1.5091 | 15.7809 | 16.8307 | 16.8307
829 | -0.29736 | -0.27896 | 0.38309 | 0.39014 | 4.2073 | 4.8972 | 6.3004 | 5.0435 | 5.0118 | 2.4852 | 16.6332 | 18.0046 | 18.0046
830 | 0.35133 | -0.54111 | 0.63733 | 0.29422 | 3.971 | 5.6976 | 5.2741 | 4.861 | 4.5089 | 2.0726 | 16.6022 | 15.8265 | 16.6022
831 | -1.4642 | -0.15194 | 0.071576 | 0.43962 | 2.1957 | 3.7798 | 4.869 | 5.1379 | 3.5124 | 1.1945 | 12.3078 | 11.7716 | 12.3078
832 | 0.13413 | 1.0021 | 0.55335 | 0.84185 | 4.0371 | 5.422 | 4.5425 | 6.0988 | 4.5624 | 1.9796 | 17.5375 | 15.1216 | 17.5375
833 | 0.7851 | -0.23296 | 0.7838 | 0.4079 | 2.4597 | 6.2532 | 5.4201 | 5.0773 | 3.5832 | 1.4928 | 15.283 | 12.9558 | 15.283
834 | -0.20263 | -0.84686 | 0.41971 | 0.19854 | 3.2204 | 5.0089 | 6.337 | 4.6714 | 3.5686 | 1.8809 | 14.7816 | 15.0069 | 15.0069
835 | 0.11899 | 0.086334 | 0.54736 | 0.5344 | 4.7424 | 5.403 | 6.3307 | 5.3238 | 3.4815 | 1.555 | 17.0242 | 16.1095 | 17.0242
836 | 0.60593 | -1.046 | 0.72772 | 0.14779 | 2.6372 | 6.0241 | 6.2623 | 4.5625 | 4.2001 | 2.2581 | 15.4819 | 15.3576 | 15.4819
837 | -0.15058 | -0.39773 | 0.44015 | 0.34541 | 3.641 | 5.0712 | 4.8053 | 4.9587 | 3.9466 | 1.8336 | 15.5045 | 14.2265 | 15.5045
838 | -0.76348 | -0.085394 | 0.22259 | 0.46597 | 3.393 | 4.3878 | 4.8626 | 5.1887 | 3.8786 | 2.1716 | 15.1412 | 14.3058 | 15.1412
839 | 0.14529 | 2.11 | 0.55776 | 0.98257 | 3.1341 | 5.436 | 6.4311 | 6.9704 | 6.0656 | 1.1879 | 16.7285 | 16.8187 | 16.8187
840 | -1.7824 | -1.83 | 0.037346 | 0.033627 | 3.4096 | 3.5729 | 5.144 | 4.247 | 3.5798 | 1.9971 | 13.2266 | 14.1305 | 14.1305
841 | 0.2066 | 0.95614 | 0.58184 | 0.8305 | 2.8604 | 5.5134 | 7.2391 | 6.0594 | 4.6349 | 1.7098 | 16.143 | 16.4441 | 16.4441
842 | 1.3412 | 1.6464 | 0.91006 | 0.95016 | 5.0651 | 6.937 | 5.5242 | 6.6308 | 3.5872 | 2.352 | 20.9849 | 16.5285 | 20.9849
843 | -0.56915 | -0.57675 | 0.28463 | 0.28206 | 3.5637 | 4.5913 | 5.4629 | 4.8376 | 3.9283 | 1.6299 | 14.6225 | 14.5848 | 14.6225
844 | -0.74523 | -1.888 | 0.22806 | 0.029513 | 4.0525 | 4.4064 | 6.5464 | 4.2304 | 4.8346 | 2.4172 | 15.1064 | 17.8507 | 17.8507
845 | -0.32528 | 0.395 | 0.37248 | 0.65358 | 5.0395 | 4.8648 | 7.4733 | 5.5782 | 3.7822 | 2.1465 | 17.629 | 18.4415 | 18.4415
846 | -1.2273 | -0.82864 | 0.10985 | 0.20365 | 4.9335 | 3.9621 | 4.6169 | 4.682 | 4.6954 | 2.2688 | 15.8464 | 16.5146 | 16.5146
847 | -0.85454 | 0.12574 | 0.1964 | 0.55003 | 4.561 | 4.2974 | 4.7784 | 5.3556 | 5.5973 | 2.7661 | 16.9801 | 17.7029 | 17.7029
848 | 0.43669 | 0.90241 | 0.66883 | 0.81658 | 3.9644 | 5.8069 | 5.0237 | 6.0131 | 4.5478 | 1.7343 | 17.5188 | 15.2702 | 17.5188
849 | 0.49333 | -0.19096 | 0.68911 | 0.42428 | 4.2719 | 5.8796 | 4.6615 | 5.1085 | 4.3491 | 2.0624 | 17.3224 | 15.3449 | 17.3224
850 | -0.56613 | 0.96365 | 0.28565 | 0.83239 | 4.7815 | 4.5946 | 4.8053 | 6.0658 | 4.043 | 2.1327 | 17.5746 | 15.7625 | 17.5746
851 | 0.070937 | 0.36575 | 0.52828 | 0.64273 | 2.6001 | 5.3429 | 6.2209 | 5.5536 | 3.9088 | 1.9729 | 15.4695 | 14.7027 | 15.4695
852 | 0.36061 | -1.1986 | 0.6408 | 0.11534 | 4.6986 | 5.7095 | 6.1791 | 4.487 | 4.3775 | 1.323 | 16.2181 | 16.5783 | 16.5783
853 | 0.6512 | 1.3632 | 0.74254 | 0.91359 | 4.4822 | 6.0821 | 3.293 | 6.4033 | 5.8182 | 2.116 | 19.0837 | 15.7093 | 19.0837
854 | -1.3635 | -0.85477 | 0.086359 | 0.19634 | 4.5343 | 3.8542 | 7.578 | 4.6669 | 3.9243 | 1.9666 | 15.022 | 18.0031 | 18.0031
855 | 0.29248 | 0.54764 | 0.61504 | 0.70803 | 2.7003 | 5.6225 | 3.5833 | 5.7079 | 3.1098 | 2.123 | 16.1537 | 11.5164 | 16.1537
856 | 0.68267 | 0.52841 | 0.75259 | 0.70139 | 3.6218 | 6.1225 | 6.8754 | 5.6915 | 4.5234 | 2.4666 | 17.9023 | 17.4872 | 17.9023
857 | 1.3164 | 0.13411 | 0.90598 | 0.55334 | 3.8337 | 6.9079 | 5.7359 | 5.3623 | 4.2611 | 1.731 | 17.835 | 15.5617 | 17.835
858 | 1.2985 | 0.62413 | 0.90294 | 0.73373 | 3.3728 | 6.8868 | 6.5432 | 5.7734 | 4.4224 | 2.0285 | 18.0615 | 16.3668 | 18.0615
859 | -0.64437 | 0.69511 | 0.25967 | 0.75651 | 4.4496 | 4.511 | 6.2923 | 5.8345 | 3.1074 | 1.9749 | 16.77 | 15.8243 | 16.77
860 | 0.56153 | 1.7169 | 0.71278 | 0.95701 | 3.1977 | 5.9671 | 5.7315 | 6.6854 | 3.3298 | 2.2495 | 18.0997 | 14.5085 | 18.0997
861 | 0.40344 | 0.17686 | 0.65669 | 0.57019 | 3.6339 | 5.7643 | 4.5762 | 5.3971 | 4.7239 | 2.0704 | 16.8657 | 15.0044 | 16.8657
862 | 0.54415 | -1.8722 | 0.70683 | 0.030592 | 3.9331 | 5.9448 | 6.2813 | 4.2348 | 3.9071 | 2.0098 | 16.1225 | 16.1312 | 16.1312
863 | 0.49804 | -1.4949 | 0.69077 | 0.067464 | 3.6687 | 5.8856 | 6.4732 | 4.3602 | 4.8304 | 2.064 | 15.9786 | 17.0362 | 17.0362
864 | -1.5428 | -0.50133 | 0.061436 | 0.30807 | 4.2473 | 3.7246 | 5.3646 | 4.8876 | 3.8375 | 1.5201 | 14.3796 | 14.9695 | 14.9695
865 | 0.74034 | 0.48509 | 0.77045 | 0.68619 | 5.5613 | 6.1961 | 5.469 | 5.6545 | 5.3375 | 2.5491 | 19.9611 | 18.9169 | 19.9611
866 | 0.59967 | 0.0081733 | 0.72564 | 0.50326 | 3.2885 | 6.0161 | 5.5781 | 5.2617 | 4.3893 | 2.0261 | 16.5924 | 15.282 | 16.5924
867 | -1.2546 | -0.86152 | 0.1048 | 0.19448 | 3.3806 | 3.9398 | 6.4985 | 4.663 | 4.8846 | 2.2209 | 14.2043 | 16.9846 | 16.9846
868 | 2.1374 | 1.7899 | 0.98372 | 0.96326 | 4.2507 | 7.7691 | 5.7423 | 6.7408 | 4.2813 | 2.3269 | 21.0875 | 16.6012 | 21.0875
869 | -0.47622 | -0.13044 | 0.31696 | 0.44811 | 3.764 | 4.6933 | 6.7426 | 5.1542 | 3.6935 | 2.6357 | 16.2472 | 16.8357 | 16.8357
870 | -0.49462 | -1.2612 | 0.31043 | 0.10362 | 2.5591 | 4.6729 | 4.5618 | 4.4581 | 5.1657 | 2.3541 | 14.0442 | 14.6407 | 14.6407
871 | 0.83202 | 0.12144 | 0.7973 | 0.54833 | 5.0458 | 6.3127 | 5.715 | 5.3521 | 3.5829 | 1.5593 | 18.27 | 15.903 | 18.27
872 | -0.19799 | -0.20229 | 0.42153 | 0.41985 | 2.5347 | 5.0144 | 5.8462 | 5.1001 | 4.3845 | 2.1999 | 14.8491 | 14.9652 | 14.9652
873 | 0.53031 | 2.0102 | 0.70205 | 0.97779 | 4.6035 | 5.9271 | 5.2851 | 6.9013 | 3.9469 | 1.3182 | 18.75 | 15.1537 | 18.75
874 | -0.21839 | 0.19699 | 0.41356 | 0.57808 | 4.4053 | 4.9902 | 5.25 | 5.4136 | 3.9573 | 1.9747 | 16.7838 | 15.5874 | 16.7838
875 | 0.42375 | 0.98029 | 0.66413 | 0.83653 | 3.0915 | 5.7903 | 4.0771 | 6.0801 | 3.9002 | 2.7054 | 17.6674 | 13.7742 | 17.6674
876 | -1.1463 | -1.8641 | 0.12583 | 0.031154 | 3.1053 | 4.0299 | 5.896 | 4.2371 | 3.7619 | 1.985 | 13.3573 | 14.7482 | 14.7482
877 | -1.0687 | -0.58687 | 0.14261 | 0.27864 | 3.4793 | 4.0977 | 7.1698 | 4.831 | 4.0188 | 1.498 | 13.9059 | 16.1659 | 16.1659
878 | 0.26123 | 0.51713 | 0.60304 | 0.69747 | 4.7472 | 5.5827 | 5.1188 | 5.6818 | 3.9179 | 1.6536 | 17.6654 | 15.4375 | 17.6654
879 | 0.091563 | 0.91792 | 0.53648 | 0.82067 | 2.5836 | 5.3687 | 5.7496 | 6.0265 | 3.7948 | 2.4721 | 16.4508 | 14.6001 | 16.4508
880 | 0.37187 | -0.062602 | 0.64501 | 0.47504 | 3.8483 | 5.7239 | 7.5007 | 5.2063 | 3.5781 | 1.9052 | 16.6838 | 16.8324 | 16.8324
881 | -0.61797 | 0.36848 | 0.2683 | 0.64374 | 5.2157 | 4.5389 | 5.5063 | 5.5559 | 5.1375 | 2.1515 | 17.462 | 18.011 | 18.011
882 | 1.3213 | 0.65726 | 0.90679 | 0.74449 | 4.8681 | 6.9137 | 4.083 | 5.8019 | 4.9081 | 1.8306 | 19.4142 | 15.6898 | 19.4142
883 | -0.49746 | -0.22956 | 0.30943 | 0.40922 | 3.5678 | 4.6698 | 7.5137 | 5.0798 | 4.3494 | 1.8967 | 15.2141 | 17.3277 | 17.3277
884 | -0.1757 | 0.16216 | 0.43027 | 0.56441 | 2.9692 | 5.0411 | 6.5666 | 5.3851 | 3.3148 | 2.7037 | 16.0991 | 15.5543 | 16.0991
885 | -1.092 | 0.31894 | 0.13743 | 0.62511 | 3.2029 | 4.0771 | 5.4357 | 5.5144 | 5.3707 | 1.8783 | 14.6728 | 15.8875 | 15.8875
886 | 0.21738 | -0.63549 | 0.58604 | 0.26256 | 3.1987 | 5.5271 | 6.6957 | 4.7997 | 4.0758 | 2.3896 | 15.915 | 16.3597 | 16.3597
887 | -1.4135 | -0.48244 | 0.078759 | 0.31475 | 4.2972 | 3.8167 | 5.5187 | 4.9003 | 3.7224 | 2.0085 | 15.0227 | 15.5467 | 15.5467
888 | -0.0015388 | 0.33993 | 0.49939 | 0.63305 | 4.0642 | 5.253 | 4.5015 | 5.532 | 4.8958 | 2.2845 | 17.1336 | 15.746 | 17.1336
889 | 1.1402 | 0.66973 | 0.8729 | 0.74849 | 4.928 | 6.6967 | 4.279 | 5.8126 | 4.3539 | 1.6229 | 19.0601 | 15.1838 | 19.0601
890 | 0.19711 | 0.96634 | 0.57813 | 0.83306 | 4.9129 | 5.5014 | 5.0304 | 6.0681 | 4.2749 | 1.9546 | 18.437 | 16.1728 | 18.437
891 | 0.4709 | 1.0868 | 0.68114 | 0.86143 | 4.7254 | 5.8508 | 4.3788 | 6.1712 | 4.1024 | 2.6135 | 19.3609 | 15.8201 | 19.3609
892 | 1.1977 | 0.057498 | 0.88449 | 0.52293 | 3.3062 | 6.7664 | 7.6074 | 5.3008 | 4.8854 | 1.5866 | 16.96 | 17.3856 | 17.3856
893 | 1.2035 | 1.0705 | 0.88561 | 0.85781 | 3.059 | 6.7734 | 3.4747 | 6.1573 | 5.4469 | 1.7818 | 17.7715 | 13.7624 | 17.7715
894 | 0.6629 | -0.42761 | 0.7463 | 0.33447 | 3.7737 | 6.0971 | 4.9915 | 4.9379 | 4.2863 | 1.8389 | 16.6477 | 14.8904 | 16.6477
895 | -0.7562 | 0.48728 | 0.22476 | 0.68697 | 4.9314 | 4.3952 | 5.713 | 5.6564 | 3.992 | 2.2128 | 17.1959 | 16.8492 | 17.1959
896 | 0.16283 | 0.62445 | 0.56467 | 0.73383 | 5.4789 | 5.4581 | 5.5943 | 5.7737 | 3.4348 | 2.1343 | 18.845 | 16.6423 | 18.845
897 | -0.39482 | -1.2044 | 0.34649 | 0.11423 | 4.9529 | 4.7849 | 5.1407 | 4.4843 | 4.7757 | 2.2251 | 16.4473 | 17.0944 | 17.0944
898 | 0.1956 | -0.48927 | 0.57754 | 0.31233 | 3.7291 | 5.4995 | 6.401 | 4.8957 | 3.4746 | 1.9969 | 16.1212 | 15.6017 | 16.1212
899 | -0.56646 | -1.4109 | 0.28554 | 0.079141 | 2.982 | 4.5943 | 4.3281 | 4.3936 | 3.741 | 1.7514 | 13.7212 | 12.8025 | 13.7212
900 | 1.2556 | -0.81048 | 0.89537 | 0.20883 | 4.9197 | 6.8359 | 6.9317 | 4.6926 | 4.0512 | 1.6404 | 18.0886 | 17.5431 | 18.0886
901 | 0.61703 | 0.5073 | 0.73139 | 0.69403 | 4.9171 | 6.0384 | 6.33 | 5.6734 | 3.8828 | 2.3028 | 18.9317 | 17.4327 | 18.9317
902 | 1.5261 | 1.0666 | 0.9365 | 0.85693 | 5.2217 | 7.149 | 5.5672 | 6.154 | 6.0375 | 2.1687 | 20.6934 | 18.9951 | 20.6934
903 | -0.91725 | -0.94149 | 0.17951 | 0.17323 | 5.0547 | 4.2369 | 5.5725 | 4.6182 | 3.5226 | 2.4719 | 16.3817 | 16.6217 | 16.6217
904 | -1.3949 | -1.9593 | 0.081529 | 0.025037 | 3.7156 | 3.8306 | 4.8608 | 4.2111 | 5.1611 | 2.1879 | 13.9452 | 15.9254 | 15.9254
905 | -0.10315 | 0.81537 | 0.45892 | 0.79257 | 2.6377 | 5.1286 | 5.7947 | 5.9381 | 4.7589 | 2.3089 | 16.0133 | 15.5001 | 16.0133
906 | 0.28182 | -0.44314 | 0.61096 | 0.32883 | 3.8363 | 5.6089 | 6.408 | 4.9272 | 4.3901 | 1.6397 | 16.012 | 16.2741 | 16.2741
907 | 1.7919 | 2.5779 | 0.96343 | 0.99503 | 4.7792 | 7.4351 | 4.3524 | 7.2608 | 6.1989 | 1.2226 | 20.6977 | 16.5532 | 20.6977
908 | 0.616 | 1.8571 | 0.73105 | 0.96835 | 3.3185 | 6.037 | 4.8414 | 6.7909 | 3.9822 | 1.5079 | 17.6543 | 13.6499 | 17.6543
909 | -1.0549 | -1.2596 | 0.14573 | 0.10391 | 3.2718 | 4.1099 | 3.9687 | 4.4588 | 4.3007 | 1.729 | 13.5696 | 13.2702 | 13.5696
910 | 0.16673 | -0.42296 | 0.56621 | 0.33616 | 4.6151 | 5.463 | 6.0019 | 4.9411 | 3.7962 | 2.3475 | 17.3668 | 16.7607 | 17.3668
911 | -2.0048 | -1.0772 | 0.022491 | 0.1407 | 2.8801 | 3.4533 | 5.571 | 4.5465 | 5.4639 | 2.2173 | 13.0972 | 16.1323 | 16.1323
912 | 0.69344 | 0.72478 | 0.75598 | 0.76571 | 4.3435 | 6.1362 | 5.3465 | 5.86 | 4.1275 | 1.5681 | 17.9079 | 15.3856 | 17.9079
913 | -0.21385 | 0.11301 | 0.41533 | 0.54499 | 4.8774 | 4.9956 | 5.3495 | 5.3453 | 4.0261 | 1.8693 | 17.0876 | 16.1223 | 17.0876
914 | 0.5453 | -0.30801 | 0.70723 | 0.37904 | 4.1068 | 5.9463 | 5.7296 | 5.0225 | 3.77 | 1.4796 | 16.5552 | 15.0859 | 16.5552
915 | -0.53181 | -1.0334 | 0.29743 | 0.1507 | 5.1796 | 4.632 | 5.4525 | 4.569 | 4.4268 | 2.2964 | 16.677 | 17.3552 | 17.3552
916 | 0.81126 | 0.51882 | 0.79139 | 0.69806 | 4.4535 | 6.2864 | 4.4234 | 5.6833 | 3.9464 | 1.614 | 18.0373 | 14.4373 | 18.0373
917 | -1.9812 | -1.8235 | 0.023783 | 0.034112 | 3.106 | 3.4651 | 3.6735 | 4.2489 | 3.1263 | 1.8049 | 12.6248 | 11.7107 | 12.6248
918 | 0.72624 | -0.019506 | 0.76615 | 0.49222 | 4.622 | 6.1781 | 5.7775 | 5.2399 | 3.5184 | 1.5961 | 17.6361 | 15.514 | 17.6361
919 | -0.23398 | 0.10736 | 0.4075 | 0.54275 | 2.8166 | 4.9717 | 6.3752 | 5.3407 | 3.7379 | 1.7517 | 14.8808 | 14.6814 | 14.8808
920 | -0.72175 | 1.3266 | 0.23522 | 0.90768 | 4.8972 | 4.4304 | 6.4591 | 6.373 | 4.447 | 1.8451 | 17.5457 | 17.6484 | 17.6484
921 | -0.14812 | 1.0622 | 0.44113 | 0.85593 | 5.2279 | 5.0742 | 4.4228 | 6.1502 | 4.3746 | 2.3672 | 18.8195 | 16.3925 | 18.8195
922 | -0.19618 | 0.36971 | 0.42223 | 0.6442 | 3.7914 | 5.0166 | 7.2319 | 5.557 | 3.085 | 2.0343 | 16.3992 | 16.1425 | 16.3992
923 | 2.3017 | 2.5038 | 0.98932 | 0.99386 | 5.286 | 7.9116 | 5.9356 | 7.2186 | 4.1453 | 2.2328 | 22.649 | 17.5997 | 22.649
924 | -1.4943 | -1.6848 | 0.067549 | 0.046016 | 3.6155 | 3.7583 | 5.6846 | 4.2923 | 5.1097 | 2.1815 | 13.8476 | 16.5913 | 16.5913
925 | 0.43867 | -0.20119 | 0.66955 | 0.42028 | 3.933 | 5.8095 | 4.8609 | 5.1009 | 4.1462 | 2.4566 | 17.2999 | 15.3967 | 17.2999
926 | -0.54502 | -1.1612 | 0.29287 | 0.12277 | 4.0214 | 4.6175 | 6.6211 | 4.5049 | 5.4275 | 2.2818 | 15.4257 | 18.3518 | 18.3518
927 | -2.0871 | -1.7119 | 0.018439 | 0.043454 | 3.4493 | 3.4141 | 6.8379 | 4.2834 | 4.7301 | 2.4183 | 13.5651 | 17.4356 | 17.4356
928 | 1.929 | 1.7208 | 0.97314 | 0.95735 | 4.6599 | 7.573 | 5.6263 | 6.6883 | 4.148 | 2.1197 | 21.0409 | 16.5538 | 21.0409
929 | 0.82269 | 0.12942 | 0.79466 | 0.55149 | 4.8201 | 6.3009 | 5.9083 | 5.3585 | 4.6102 | 1.8011 | 18.2806 | 17.1398 | 18.2806
930 | 1.2509 | 1.2104 | 0.89452 | 0.88693 | 4.587 | 6.8302 | 5.7287 | 6.2759 | 3.8447 | 1.6165 | 19.3096 | 15.7768 | 19.3096
931 | 1.1892 | 1.0624 | 0.88283 | 0.85597 | 3.6305 | 6.7561 | 4.3371 | 6.1504 | 3.7329 | 2.5675 | 19.1045 | 14.268 | 19.1045
932 | 1.5401 | -0.18527 | 0.93824 | 0.42651 | 4.8872 | 7.1647 | 6.1419 | 5.1128 | 4.5834 | 2.0479 | 19.2126 | 17.6604 | 19.2126
933 | -0.25816 | -0.29527 | 0.39814 | 0.3839 | 3.7926 | 4.9432 | 3.799 | 5.0317 | 5.059 | 1.8931 | 15.6605 | 14.5437 | 15.6605
934 | 0.53363 | 0.54489 | 0.7032 | 0.70709 | 4.7473 | 5.9313 | 5.8431 | 5.7055 | 3.3155 | 1.735 | 18.1192 | 15.6409 | 18.1192
935 | 0.66144 | 0.15317 | 0.74584 | 0.56087 | 4.9056 | 6.0953 | 6.385 | 5.3778 | 3.9001 | 2.1034 | 18.4821 | 17.2941 | 18.4821
936 | -1.8208 | -1.6654 | 0.034317 | 0.047913 | 3.0959 | 3.5508 | 3.3212 | 4.2988 | 3.7924 | 2.5116 | 13.4571 | 12.7211 | 13.4571
937 | 1.5632 | 0.19221 | 0.94099 | 0.57621 | 4.2987 | 7.1903 | 6.3016 | 5.4096 | 4.2491 | 1.8453 | 18.7439 | 16.6946 | 18.7439
938 | -2.7884 | -2.4526 | 0.0026487 | 0.0070915 | 4.8326 | 3.1744 | 6.1952 | 4.1095 | 3.8095 | 2.2071 | 14.3236 | 17.0444 | 17.0444
939 | 0.12023 | -1.1402 | 0.54785 | 0.12709 | 5.3507 | 5.4046 | 2.4557 | 4.5151 | 3.8184 | 1.3913 | 16.6616 | 13.0161 | 16.6616
940 | -0.93062 | -1.9335 | 0.17603 | 0.026587 | 4.1105 | 4.2243 | 6.0653 | 4.218 | 3.6601 | 2.0668 | 14.6196 | 15.9028 | 15.9028
941 | 1.041 | 1.41 | 0.85106 | 0.92073 | 4.1425 | 6.5748 | 3.8127 | 6.4417 | 5.3668 | 2.2677 | 19.4267 | 15.5897 | 19.4267
942 | 0.45838 | 0.086666 | 0.67666 | 0.53453 | 3.762 | 5.8347 | 7.3122 | 5.3241 | 5.1518 | 2.1141 | 17.0349 | 18.3401 | 18.3401
943 | -0.44547 | 0.15993 | 0.32799 | 0.56353 | 5.1236 | 4.7277 | 6.1771 | 5.3833 | 5.788 | 1.6234 | 16.858 | 18.7122 | 18.7122
944 | 1.9506 | 0.95617 | 0.97445 | 0.83051 | 3.2769 | 7.5941 | 4.912 | 6.0594 | 3.2571 | 1.6812 | 18.6116 | 13.1272 | 18.6116
945 | -0.81422 | -1.1089 | 0.20776 | 0.13373 | 3.8807 | 4.337 | 5.242 | 4.5305 | 4.9782 | 2.839 | 15.5872 | 16.9398 | 16.9398
946 | -1.4576 | -0.91965 | 0.072473 | 0.17888 | 5.8482 | 3.7845 | 5.7663 | 4.6302 | 4.7312 | 2.1603 | 16.4232 | 18.506 | 18.506
947 | -0.30561 | 0.50288 | 0.37995 | 0.69247 | 4.6403 | 4.8876 | 5.4775 | 5.6697 | 3.462 | 1.9766 | 17.1742 | 15.5563 | 17.1742
948 | 0.69412 | 1.6867 | 0.7562 | 0.95417 | 4.5415 | 6.1371 | 5.4519 | 6.6621 | 5.897 | 2.0283 | 19.3691 | 17.9188 | 19.3691
949 | -0.59747 | 0.34922 | 0.2751 | 0.63654 | 3.6781 | 4.5608 | 5.7683 | 5.5398 | 4.6248 | 2.3856 | 16.1643 | 16.4568 | 16.4568
950 | 0.22357 | 0.50668 | 0.58845 | 0.69381 | 3.7503 | 5.5349 | 5.0783 | 5.6729 | 3.8474 | 1.703 | 16.6611 | 14.3789 | 16.6611
951 | 0.43666 | -0.6794 | 0.66882 | 0.24844 | 4.2861 | 5.8069 | 4.8224 | 4.772 | 4.5384 | 1.2564 | 16.1214 | 14.9033 | 16.1214
952 | -1.718 | -0.40364 | 0.0429 | 0.34324 | 4.3454 | 3.6113 | 6.3512 | 4.9546 | 3.7483 | 2.6452 | 15.5564 | 17.0902 | 17.0902
953 | 0.20784 | -0.58774 | 0.58232 | 0.27836 | 4.2453 | 5.515 | 5.9214 | 4.8304 | 4.2141 | 2.3189 | 16.9096 | 16.6998 | 16.9096
954 | -0.29642 | 0.61606 | 0.38345 | 0.73107 | 3.9591 | 4.8983 | 6.2395 | 5.7665 | 3.1567 | 1.7514 | 16.3753 | 15.1066 | 16.3753
955 | -1.5861 | -0.70385 | 0.056354 | 0.24076 | 5.189 | 3.6953 | 6.7697 | 4.7568 | 4.914 | 1.8453 | 15.4864 | 18.718 | 18.718
956 | 1.3111 | 1.338 | 0.90509 | 0.90956 | 3.1755 | 6.9017 | 5.0727 | 6.3825 | 4.844 | 1.7936 | 18.2533 | 14.8857 | 18.2533
957 | 0.14598 | -0.89583 | 0.55803 | 0.18517 | 4.1554 | 5.4369 | 6.6247 | 4.6435 | 3.2464 | 2.0921 | 16.328 | 16.1187 | 16.328
958 | -0.88201 | -0.50077 | 0.18889 | 0.30827 | 4.5761 | 4.2707 | 6.0172 | 4.8879 | 4.3286 | 2.3833 | 16.1181 | 17.3052 | 17.3052
959 | 0.31674 | 1.5237 | 0.62428 | 0.93621 | 3.3795 | 5.6534 | 5.7643 | 6.5338 | 3.619 | 2.2782 | 17.8449 | 15.0409 | 17.8449
960 | -1.2774 | -0.81805 | 0.10073 | 0.20666 | 4.3075 | 3.9215 | 4.9309 | 4.6881 | 4.256 | 1.949 | 14.8662 | 15.4434 | 15.4434
961 | 1.7359 | 0.77888 | 0.95871 | 0.78197 | 3.4892 | 7.3768 | 6.6019 | 5.9067 | 4.0673 | 2.0628 | 18.8354 | 16.2212 | 18.8354
962 | 1.0073 | 0.58966 | 0.84311 | 0.72229 | 3.5091 | 6.533 | 7.8407 | 5.7439 | 3.91 | 1.3644 | 17.1503 | 16.6242 | 17.1503
963 | 0.91038 | 0.26281 | 0.81869 | 0.60365 | 4.8261 | 6.4117 | 3.9386 | 5.4678 | 3.9212 | 1.1848 | 17.8904 | 13.8707 | 17.8904
964 | 0.82125 | 0.98503 | 0.79425 | 0.83769 | 5.1235 | 6.2991 | 3.8078 | 6.0842 | 3.8453 | 2.1132 | 19.6199 | 14.8899 | 19.6199
965 | 2.1405 | 1.8714 | 0.98384 | 0.96935 | 4.6164 | 7.7719 | 3.7763 | 6.8014 | 3.471 | 2.1313 | 21.321 | 13.9949 | 21.321
966 | -0.33193 | -0.68837 | 0.36997 | 0.24561 | 3.3733 | 4.8571 | 4.3514 | 4.7664 | 5.0447 | 2.4254 | 15.4222 | 15.1948 | 15.4222
967 | -0.77949 | -0.83263 | 0.21785 | 0.20253 | 3.0381 | 4.3717 | 5.4112 | 4.6796 | 3.8969 | 2.0107 | 14.1002 | 14.357 | 14.357
968 | 0.32982 | -0.11987 | 0.62923 | 0.45229 | 4.7878 | 5.6701 | 5.9772 | 5.1623 | 4.5422 | 2.1423 | 17.7625 | 17.4494 | 17.7625
969 | 0.69037 | 1.3438 | 0.75502 | 0.9105 | 4.0551 | 6.1323 | 4.736 | 6.3873 | 4.5512 | 1.4194 | 17.994 | 14.7617 | 17.994
970 | -0.026273 | 0.4409 | 0.48952 | 0.67036 | 3.7263 | 5.2225 | 5.9933 | 5.617 | 3.2611 | 1.2374 | 15.8032 | 14.218 | 15.8032
971 | -0.74116 | -0.79912 | 0.2293 | 0.21211 | 3.66 | 4.4105 | 2.7859 | 4.6993 | 4.5085 | 2.1786 | 14.9484 | 13.133 | 14.9484
972 | -0.3052 | 0.95982 | 0.38011 | 0.83143 | 5.1422 | 4.8881 | 5.9408 | 6.0625 | 3.7764 | 2.2549 | 18.3477 | 17.1143 | 18.3477
973 | -0.28332 | -1.0043 | 0.38847 | 0.15762 | 4.0953 | 4.9136 | 4.1451 | 4.5843 | 4.5577 | 1.5741 | 15.1673 | 14.3721 | 15.1673
974 | -0.69631 | -1.847 | 0.24312 | 0.032373 | 5.0671 | 4.4566 | 5.2838 | 4.242 | 3.1222 | 1.6722 | 15.438 | 15.1453 | 15.438
975 | 1.5957 | 0.56573 | 0.94472 | 0.71421 | 3.6106 | 7.2262 | 4.278 | 5.7234 | 6.0447 | 2.0141 | 18.5742 | 15.9474 | 18.5742
976 | 1.1138 | 0.76873 | 0.86732 | 0.77897 | 4.4046 | 6.6644 | 6.2754 | 5.8979 | 3.2161 | 1.8415 | 18.8084 | 15.7376 | 18.8084
977 | -0.71028 | 0.71451 | 0.23877 | 0.76255 | 4.3874 | 4.4422 | 6.1949 | 5.8512 | 4.3668 | 2.3868 | 17.0675 | 17.3359 | 17.3359
978 | 0.59596 | -0.11198 | 0.7244 | 0.45542 | 3.558 | 6.0113 | 5.7286 | 5.1683 | 3.7862 | 1.649 | 16.3866 | 14.7218 | 16.3866
979 | 0.5146 | -0.027274 | 0.69659 | 0.48912 | 3.7605 | 5.9069 | 5.1656 | 5.2338 | 6.3838 | 2.1871 | 17.0884 | 17.4971 | 17.4971
980 | -0.93792 | -0.46269 | 0.17414 | 0.32179 | 3.6928 | 4.2174 | 5.5036 | 4.9138 | 3.6159 | 1.6853 | 14.5093 | 14.4977 | 14.5093
981 | 0.20795 | 0.37025 | 0.58236 | 0.6444 | 3.9979 | 5.5151 | 7.0171 | 5.5574 | 6.3876 | 1.9129 | 16.9833 | 19.3155 | 19.3155
982 | 1.0385 | -0.54684 | 0.85049 | 0.29224 | 3.5108 | 6.5717 | 4.5176 | 4.8572 | 3.7247 | 1.6049 | 16.5445 | 13.358 | 16.5445
983 | -0.057678 | -0.092373 | 0.477 | 0.4632 | 4.3226 | 5.184 | 5.1782 | 5.1834 | 3.8419 | 2.3845 | 17.0744 | 15.7272 | 17.0744
984 | -0.92763 | -0.077494 | 0.1768 | 0.46912 | 4.0415 | 4.2271 | 6.8594 | 5.1948 | 3.2789 | 1.8104 | 15.2737 | 15.9901 | 15.9901
985 | 1.219 | 1.0344 | 0.88858 | 0.84952 | 3.4241 | 6.7921 | 5.9188 | 6.1264 | 3.2057 | 1.5304 | 17.873 | 14.079 | 17.873
986 | -0.75768 | -0.69153 | 0.22432 | 0.24462 | 4.682 | 4.3937 | 7.1427 | 4.7644 | 4.6195 | 1.4319 | 15.272 | 17.876 | 17.876
987 | 0.25046 | 0.73818 | 0.59888 | 0.7698 | 2.7637 | 5.569 | 5.2529 | 5.8716 | 4.9302 | 1.6946 | 15.8989 | 14.6414 | 15.8989
988 | -0.3283 | -0.4941 | 0.37134 | 0.31062 | 2.6281 | 4.8613 | 6.3655 | 4.8924 | 3.6282 | 2.1005 | 14.4823 | 14.7223 | 14.7223
989 | 1.1707 | -0.64373 | 0.87915 | 0.25988 | 3.8213 | 6.7338 | 4.1256 | 4.7944 | 5.3006 | 1.7728 | 17.1223 | 15.0203 | 17.1223
990 | 1.4476 | 1.5823 | 0.92613 | 0.94321 | 4.398 | 7.0602 | 6.3178 | 6.5805 | 3.6164 | 1.5375 | 19.5762 | 15.8696 | 19.5762
991 | 0.21978 | 0.24567 | 0.58698 | 0.59703 | 3.1824 | 5.5301 | 5.3024 | 5.4536 | 4.7101 | 1.8054 | 15.9715 | 15.0003 | 15.9715
992 | -0.68957 | 0.058371 | 0.24523 | 0.52327 | 3.618 | 4.4636 | 6.14 | 5.3015 | 5.2866 | 2.3612 | 15.7443 | 17.4058 | 17.4058
993 | -1.5491 | -2.2087 | 0.060675 | 0.013599 | 4.5791 | 3.7203 | 5.0437 | 4.1533 | 3.7436 | 1.7265 | 14.1792 | 15.0928 | 15.0928
994 | -1.0891 | 0.20765 | 0.13806 | 0.58225 | 4.293 | 4.0796 | 6.4849 | 5.4223 | 4.664 | 1.1947 | 14.9896 | 16.6366 | 16.6366
995 | 0.88988 | -0.62536 | 0.81324 | 0.26587 | 4.5328 | 6.3859 | 6.6792 | 4.8061 | 4.4969 | 2.5828 | 18.3076 | 18.2917 | 18.3076
996 | -0.44069 | -0.88295 | 0.32972 | 0.18863 | 4.8726 | 4.7331 | 6.0039 | 4.6508 | 4.1703 | 1.6835 | 15.94 | 16.7303 | 16.7303
997 | 0.18694 | 0.11187 | 0.57414 | 0.54454 | 3.8092 | 5.4885 | 6.0301 | 5.3444 | 5.591 | 1.5841 | 16.2263 | 17.0145 | 17.0145
998 | 1.8192 | 1.5427 | 0.96556 | 0.93854 | 2.9455 | 7.4631 | 5.2842 | 6.549 | 3.9081 | 2.6339 | 19.5915 | 14.7717 | 19.5915
999 | -1.781 | -0.69807 | 0.037453 | 0.24257 | 3.5406 | 3.5737 | 6.6723 | 4.7604 | 3.4469 | 1.8409 | 13.7155 | 15.5007 | 15.5007
1000 | -0.92521 | 0.47915 | 0.17743 | 0.68408 | 3.1888 | 4.2294 | 5.1906 | 5.6495 | 5.0698 | 1.7267 | 14.7943 | 15.1759 | 15.1759
1001 | 0.54448 | -0.55646 | 0.70694 | 0.28895 | 3.2389 | 5.9452 | 3.9496 | 4.8509 | 3.3527 | 2.4003 | 16.4353 | 12.9415 | 16.4353
1002 | -1.4935 | -0.70863 | 0.067651 | 0.23928 | 4.1724 | 3.7589 | 3.5217 | 4.7538 | 3.3399 | 1.6959 | 14.381 | 12.7298 | 14.381
1003 | -0.34343 | -0.1348 | 0.36564 | 0.44638 | 4.3692 | 4.8438 | 3.6911 | 5.1509 | 3.7969 | 2.017 | 16.3809 | 13.8742 | 16.3809
1004 | 0.49533 | 0.53215 | 0.68982 | 0.70269 | 5.3689 | 5.8822 | 6.4368 | 5.6947 | 3.156 | 1.9426 | 18.8883 | 16.9043 | 18.8883
1005 | 1.1291 | 2.1924 | 0.87057 | 0.98582 | 3.0138 | 6.6831 | 7.6956 | 7.0256 | 4.8246 | 2.3504 | 19.0729 | 17.8845 | 19.0729
1006 | -0.33896 | 0.26614 | 0.36732 | 0.60494 | 3.2286 | 4.849 | 6.7838 | 5.4705 | 3.5323 | 2.5602 | 16.1083 | 16.1049 | 16.1083
1007 | 0.086703 | -0.51689 | 0.53455 | 0.30262 | 5.1239 | 5.3626 | 6.6841 | 4.8771 | 4.8268 | 1.9852 | 17.3488 | 18.62 | 18.62
1008 | -0.2165 | 0.32896 | 0.4143 | 0.62891 | 4.8115 | 4.9924 | 5.4517 | 5.5228 | 4.7056 | 1.6245 | 16.9513 | 16.5934 | 16.9513
1009 | -0.23136 | 1.2543 | 0.40852 | 0.89514 | 4.3689 | 4.9748 | 4.8454 | 6.3128 | 5.0235 | 2.0916 | 17.7481 | 16.3294 | 17.7481
1010 | 0.70787 | 0.62213 | 0.76049 | 0.73307 | 3.6154 | 6.1547 | 6.9894 | 5.7717 | 4.4971 | 2.1425 | 17.6843 | 17.2444 | 17.6843
1011 | 1.3414 | 0.39187 | 0.9101 | 0.65242 | 5.6399 | 6.9373 | 3.7383 | 5.5756 | 3.6681 | 1.4571 | 19.6098 | 14.5032 | 19.6098
1012 | -0.12868 | -0.72617 | 0.4488 | 0.23387 | 3.7429 | 5.0976 | 4.2793 | 4.7431 | 3.3901 | 1.7868 | 15.3704 | 13.1989 | 15.3704
1013 | 1.2326 | 0.42692 | 0.89113 | 0.66528 | 3.1944 | 6.8083 | 4.6981 | 5.6052 | 5.2024 | 2.0458 | 17.6537 | 15.1407 | 17.6537
1014 | 2.1769 | 1.8019 | 0.98526 | 0.96422 | 3.3999 | 7.8044 | 6.3672 | 6.7498 | 3.5904 | 1.9221 | 19.8762 | 15.2796 | 19.8762
1015 | 1.9763 | 1.6893 | 0.97594 | 0.95441 | 5.2491 | 7.619 | 5.2692 | 6.6641 | 6.0787 | 1.9731 | 21.5053 | 18.5701 | 21.5053
1016 | 0.48727 | 0.44556 | 0.68697 | 0.67204 | 2.9671 | 5.8718 | 6.9262 | 5.621 | 4.321 | 2.1083 | 16.5682 | 16.3225 | 16.5682
1017 | -0.85084 | 1.7357 | 0.19743 | 0.95869 | 4.6509 | 4.301 | 6.0051 | 6.6997 | 4.1257 | 2.512 | 18.1635 | 17.2936 | 18.1635
1018 | -0.11526 | -0.84481 | 0.45412 | 0.19911 | 3.2915 | 5.1139 | 4.1542 | 4.6726 | 4.6638 | 2.6682 | 15.7461 | 14.7776 | 15.7461
1019 | -2.1253 | -1.4259 | 0.016779 | 0.076955 | 3.6075 | 3.3967 | 4.4204 | 4.3875 | 3.3786 | 1.7715 | 13.1631 | 13.1779 | 13.1779
1020 | 0.97021 | 0.54091 | 0.83403 | 0.70571 | 4.8248 | 6.4867 | 4.4249 | 5.7021 | 4.0327 | 1.6806 | 18.6943 | 14.963 | 18.6943
1021 | -0.49286 | -0.79839 | 0.31106 | 0.21232 | 5.1775 | 4.6749 | 7.6724 | 4.6997 | 4.0191 | 2.3049 | 16.8569 | 19.1739 | 19.1739
1022 | -0.26222 | 0.098315 | 0.39657 | 0.53916 | 5.1703 | 4.9384 | 7.4555 | 5.3335 | 4.316 | 2.5137 | 17.9558 | 19.4555 | 19.4555
1023 | 0.31101 | 1.3296 | 0.6221 | 0.90817 | 5.0731 | 5.6461 | 6.3612 | 6.3755 | 4.1441 | 2.7823 | 19.8769 | 18.3606 | 19.8769
1024 | 0.23956 | -0.43886 | 0.59467 | 0.33038 | 2.5193 | 5.5552 | 5.0231 | 4.9301 | 4.2107 | 1.5419 | 14.5465 | 13.295 | 14.5465
1025 | 0.53599 | -0.48051 | 0.70402 | 0.31543 | 3.6368 | 5.9344 | 7.1299 | 4.9016 | 3.5947 | 2.4682 | 16.941 | 16.8296 | 16.941
1026 | 1.1155 | 1.2564 | 0.86768 | 0.89552 | 4.9233 | 6.6665 | 5.6183 | 6.3146 | 4.7859 | 2.337 | 20.2413 | 17.6645 | 20.2413
1027 | -0.54541 | -0.61315 | 0.29274 | 0.26989 | 4.2542 | 4.6171 | 3.9328 | 4.814 | 4.9656 | 2.0592 | 15.7445 | 15.2119 | 15.7445
1028 | 0.85824 | 0.14754 | 0.80462 | 0.55865 | 4.2109 | 6.3459 | 5.945 | 5.3732 | 3.4089 | 2.0275 | 17.9576 | 15.5923 | 17.9576
1029 | 0.42708 | -0.41737 | 0.66534 | 0.3382 | 3.1763 | 5.7946 | 5.8003 | 4.945 | 3.5052 | 2.0527 | 15.9686 | 14.5345 | 15.9686
1030 | -0.46936 | -1.0977 | 0.31941 | 0.13617 | 3.2372 | 4.701 | 4.7451 | 4.5362 | 4.6724 | 2.7135 | 15.1879 | 15.3682 | 15.3682
1031 | 0.54297 | 1.0381 | 0.70642 | 0.8504 | 4.6802 | 5.9433 | 4.9639 | 6.1297 | 4.0626 | 1.3071 | 18.0603 | 15.0138 | 18.0603
1032 | 1.7436 | -0.97097 | 0.95939 | 0.16578 | 4.6097 | 7.3849 | 6.7854 | 4.6021 | 3.8616 | 1.1269 | 17.7236 | 16.3836 | 17.7236
1033 | 0.30223 | 0.76689 | 0.61876 | 0.77843 | 4.0156 | 5.6349 | 5.0278 | 5.8963 | 4.4655 | 1.5626 | 17.1094 | 15.0714 | 17.1094
1034 | -0.77004 | -0.15358 | 0.22064 | 0.43897 | 2.5427 | 4.3812 | 5.5689 | 5.1367 | 5.3213 | 1.9383 | 13.999 | 15.3712 | 15.3712
1035 | -0.96167 | -1.4475 | 0.16811 | 0.073873 | 4.6694 | 4.1951 | 5.5301 | 4.3788 | 4.8197 | 1.6247 | 14.868 | 16.6438 | 16.6438
1036 | -1.2331 | -0.25591 | 0.10877 | 0.39901 | 3.4533 | 3.9573 | 4.5931 | 5.0604 | 3.9936 | 1.891 | 14.362 | 13.9309 | 14.362
1037 | -0.52878 | -0.074765 | 0.29848 | 0.4702 | 3.8436 | 4.6353 | 3.2024 | 5.1969 | 3.5841 | 2.8004 | 16.4763 | 13.4306 | 16.4763
1038 | 0.21166 | 1.091 | 0.58381 | 0.86237 | 4.1561 | 5.5198 | 6.5204 | 6.1748 | 3.5242 | 1.9602 | 17.811 | 16.161 | 17.811
1039 | -0.024603 | 0.48729 | 0.49019 | 0.68697 | 2.4943 | 5.2246 | 5.0637 | 5.6564 | 4.8526 | 1.9197 | 15.295 | 14.3304 | 15.295
1040 | 0.14458 | 0.58112 | 0.55748 | 0.71942 | 4.2865 | 5.4351 | 5.8241 | 5.7365 | 3.5663 | 1.4928 | 16.951 | 15.1697 | 16.951
1041 | -0.50593 | -1.0757 | 0.30645 | 0.14104 | 4.2165 | 4.6604 | 5.1072 | 4.5473 | 4.3192 | 2.6586 | 16.0828 | 16.3015 | 16.3015
1042 | -1.007 | -1.3685 | 0.15697 | 0.085583 | 3.687 | 4.1532 | 4.8224 | 4.4112 | 5.0489 | 2.4119 | 14.6634 | 15.9702 | 15.9702
1043 | 0.34894 | -0.80434 | 0.63643 | 0.2106 | 5.5228 | 5.6945 | 6.3869 | 4.6962 | 3.9662 | 1.4524 | 17.3659 | 17.3283 | 17.3659
1044 | -1.8473 | -1.3578 | 0.032353 | 0.087265 | 4.2625 | 3.5359 | 3.6152 | 4.4157 | 3.8243 | 2.7296 | 14.9437 | 14.4315 | 14.9437
1045 | 0.55408 | 0.82355 | 0.71024 | 0.7949 | 3.5228 | 5.9576 | 6.5363 | 5.9452 | 5.8673 | 2.092 | 17.5176 | 18.0184 | 18.0184
1046 | -1.0034 | -0.72754 | 0.15783 | 0.23345 | 3.9579 | 4.1565 | 3.9112 | 4.7422 | 5.0034 | 2.3582 | 15.2149 | 15.2307 | 15.2307
1047 | 0.45333 | 0.18863 | 0.67484 | 0.57481 | 3.3969 | 5.8282 | 6.0762 | 5.4067 | 5.3432 | 1.2438 | 15.8756 | 16.06 | 16.06
1048 | 0.63219 | -0.82639 | 0.73637 | 0.20429 | 4.6066 | 6.0578 | 7.5342 | 4.6833 | 3.991 | 1.8872 | 17.2349 | 18.019 | 18.019
1049 | -0.44011 | 0.080237 | 0.32993 | 0.53198 | 4.6982 | 4.7337 | 3.4608 | 5.319 | 4.068 | 2.1969 | 16.9478 | 14.4239 | 16.9478
1050 | 0.92952 | -0.60039 | 0.82369 | 0.27412 | 4.2476 | 6.4358 | 5.8199 | 4.8222 | 4.2715 | 2.0904 | 17.596 | 16.4295 | 17.596
1051 | 2.0392 | 1.3069 | 0.97928 | 0.90437 | 3.72 | 7.6788 | 5.3303 | 6.3567 | 5.7227 | 1.3862 | 19.1416 | 16.1591 | 19.1416
1052 | -1.7472 | -1.8761 | 0.040298 | 0.030322 | 3.187 | 3.5936 | 6.752 | 4.2337 | 5.4845 | 2.3247 | 13.339 | 17.7482 | 17.7482
1053 | 1.574 | -0.21512 | 0.94226 | 0.41484 | 3.2248 | 7.2023 | 5.3446 | 5.0905 | 3.246 | 1.5132 | 17.0308 | 13.3286 | 17.0308
1054 | 0.45078 | -1.4924 | 0.67393 | 0.067795 | 3.1722 | 5.825 | 4.8044 | 4.3612 | 5.137 | 2.5063 | 15.8647 | 15.6199 | 15.8647
1055 | 1.0301 | -0.086149 | 0.84852 | 0.46567 | 3.9233 | 6.5613 | 5.7503 | 5.1881 | 4.0762 | 1.9369 | 17.6096 | 15.6867 | 17.6096
1056 | -2.0423 | -1.0856 | 0.020563 | 0.13884 | 3.7439 | 3.4351 | 6.5792 | 4.5423 | 4.6181 | 2.1113 | 13.8326 | 17.0525 | 17.0525
1057 | 0.90812 | 1.2708 | 0.81809 | 0.8981 | 4.8314 | 6.4089 | 4.8309 | 6.3266 | 4.7034 | 1.5292 | 19.096 | 15.8949 | 19.096
1058 | -0.75175 | 0.71491 | 0.2261 | 0.76267 | 5.0809 | 4.3997 | 4.963 | 5.8515 | 3.7624 | 2.6775 | 18.0096 | 16.4838 | 18.0096
1059 | -0.22396 | -0.83612 | 0.4114 | 0.20154 | 5.1268 | 4.9836 | 3.6794 | 4.6776 | 5.2273 | 1.476 | 16.264 | 15.5095 | 16.264
1060 | -0.22289 | -1.6545 | 0.41181 | 0.049017 | 4.2322 | 4.9848 | 6.1201 | 4.3025 | 3.5592 | 2.3765 | 15.896 | 16.288 | 16.288
1061 | -1.9033 | -0.46291 | 0.028498 | 0.32172 | 4.8634 | 3.5054 | 6.0792 | 4.9136 | 3.8601 | 2.0091 | 15.2915 | 16.8118 | 16.8118
1062 | -0.35184 | -0.50116 | 0.36248 | 0.30813 | 3.62 | 4.8341 | 7.4664 | 4.8877 | 3.2392 | 1.8169 | 15.1587 | 16.1425 | 16.1425
1063 | 0.67079 | 0.50803 | 0.74882 | 0.69428 | 4.3354 | 6.1072 | 6.5225 | 5.6741 | 5.2189 | 1.959 | 18.0758 | 18.0358 | 18.0758
1064 | -0.9789 | -2.4136 | 0.16382 | 0.0078984 | 3.1548 | 4.1791 | 6.3915 | 4.1157 | 3.9782 | 2.2218 | 13.6714 | 15.7463 | 15.7463
1065 | -0.48778 | -0.4184 | 0.31285 | 0.33783 | 3.9698 | 4.6805 | 5.2198 | 4.9443 | 5.4691 | 2.1601 | 15.7546 | 16.8188 | 16.8188
1066 | 0.56062 | -0.98273 | 0.71247 | 0.16287 | 4.838 | 5.966 | 4.0567 | 4.5958 | 4.435 | 2.097 | 17.4968 | 15.4268 | 17.4968
1067 | 0.52824 | -0.06419 | 0.70133 | 0.47441 | 4.6791 | 5.9244 | 5.4865 | 5.2051 | 5.1637 | 2.6938 | 18.5025 | 18.0232 | 18.5025
1068 | 0.57034 | 1.0485 | 0.71578 | 0.85279 | 4.4182 | 5.9785 | 3.9546 | 6.1385 | 5.0422 | 1.6567 | 18.1918 | 15.0716 | 18.1918
1069 | 0.58753 | 0.13182 | 0.72158 | 0.55244 | 3.0619 | 6.0005 | 7.2607 | 5.3605 | 4.1633 | 1.8462 | 16.2691 | 16.332 | 16.332
1070 | 0.4929 | 1.4047 | 0.68896 | 0.91995 | 3.4542 | 5.879 | 5.4963 | 6.4374 | 4.1349 | 2.1402 | 17.9109 | 15.2257 | 17.9109
1071 | -0.69222 | -0.42371 | 0.2444 | 0.33589 | 4.1311 | 4.4609 | 4.7485 | 4.9406 | 3.4459 | 1.9273 | 15.4599 | 14.2528 | 15.4599
1072 | 0.98864 | 0.74637 | 0.83858 | 0.77228 | 5.0181 | 6.5097 | 6.5253 | 5.8786 | 3.5242 | 2.042 | 19.4485 | 17.1096 | 19.4485
1073 | -1.0158 | -0.6612 | 0.15487 | 0.25424 | 5.3942 | 4.1452 | 4.7426 | 4.7834 | 3.6848 | 2.6137 | 16.9366 | 16.4353 | 16.9366
1074 | 1.6846 | 1.2507 | 0.95397 | 0.89448 | 4.1774 | 7.3224 | 4.8687 | 6.3098 | 4.6731 | 1.8828 | 19.6924 | 15.6019 | 19.6924
1075 | -0.025497 | 3.2629 | 0.48983 | 0.99945 | 3.4641 | 5.2235 | 6.3689 | 7.581 | 4.6494 | 1.7724 | 18.0409 | 16.2547 | 18.0409
1076 | -0.71495 | 0.28205 | 0.23732 | 0.61105 | 4.9094 | 4.4374 | 5.6395 | 5.4837 | 5.862 | 1.6752 | 16.5057 | 18.086 | 18.086
1077 | 0.83772 | 0.25638 | 0.79891 | 0.60117 | 5.4538 | 6.32 | 6.6002 | 5.4624 | 3.6869 | 1.6199 | 18.8561 | 17.3608 | 18.8561
1078 | -1.1653 | -0.54586 | 0.12194 | 0.29258 | 3.9023 | 4.0138 | 6.3202 | 4.8579 | 3.7031 | 1.6605 | 14.4344 | 15.5861 | 15.5861
1079 | 0.54552 | 0.67881 | 0.7073 | 0.75137 | 3.4795 | 5.9466 | 4.9754 | 5.8204 | 3.3466 | 2.0447 | 17.2912 | 13.8462 | 17.2912
1080 | -0.22896 | -0.38481 | 0.40945 | 0.35019 | 4.0383 | 4.9776 | 6.2114 | 4.9678 | 3.036 | 2.1513 | 16.135 | 15.4371 | 16.135
1081 | 0.034997 | 0.53062 | 0.51396 | 0.70216 | 3.012 | 5.2982 | 3.0275 | 5.6933 | 3.6196 | 1.4809 | 15.4845 | 11.14 | 15.4845
1082 | 1.456 | 0.48157 | 0.9273 | 0.68494 | 4.2731 | 7.0698 | 5.9056 | 5.6515 | 3.485 | 2.728 | 19.7224 | 16.3916 | 19.7224
1083 | 0.57499 | 0.0093876 | 0.71735 | 0.50375 | 4.0181 | 5.9844 | 4.4382 | 5.2626 | 5.5905 | 2.3322 | 17.5974 | 16.379 | 17.5974
1084 | -0.64624 | -1.0316 | 0.25906 | 0.15114 | 3.4408 | 4.509 | 5.4502 | 4.57 | 5.5564 | 1.8968 | 14.4165 | 16.3441 | 16.3441
1085 | 0.22297 | 0.010176 | 0.58822 | 0.50406 | 4.5078 | 5.5341 | 6.4314 | 5.2633 | 3.9726 | 2.1394 | 17.4447 | 17.0513 | 17.4447
1086 | -0.67048 | -0.38801 | 0.25128 | 0.349 | 3.9321 | 4.4835 | 3.6632 | 4.9655 | 3.9583 | 1.72 | 15.1011 | 13.2735 | 15.1011
1087 | -0.79121 | -1.3411 | 0.21441 | 0.089942 | 3.1099 | 4.36 | 4.7357 | 4.4228 | 4.9731 | 2.0096 | 13.9022 | 14.8282 | 14.8282
1088 | 0.11041 | -0.92719 | 0.54396 | 0.17691 | 4.9396 | 5.3923 | 6.6293 | 4.6261 | 3.7865 | 1.9556 | 16.9135 | 17.311 | 17.311
1089 | 1.5928 | 1.2375 | 0.9444 | 0.89204 | 3.5168 | 7.223 | 7.2955 | 6.2987 | 4.9682 | 1.5181 | 18.5566 | 17.2987 | 18.5566
1090 | 0.97699 | 2.2864 | 0.83571 | 0.98888 | 4.6225 | 6.4952 | 7.3252 | 7.0865 | 4.5551 | 1.7271 | 19.9312 | 18.2298 | 19.9312
1091 | -0.41011 | -0.1227 | 0.34086 | 0.45117 | 2.7902 | 4.7676 | 6.7579 | 5.1601 | 4.8381 | 1.4966 | 14.2146 | 15.8829 | 15.8829
1092 | 0.12434 | -0.51245 | 0.54948 | 0.30417 | 4.4125 | 5.4097 | 4.616 | 4.8801 | 4.1738 | 2.1283 | 16.8306 | 15.3306 | 16.8306
1093 | 0.22793 | -0.049306 | 0.59015 | 0.48034 | 3.7099 | 5.5404 | 3.296 | 5.2167 | 5.3752 | 1.776 | 16.243 | 14.1572 | 16.243
1094 | 1.6738 | 0.36908 | 0.95292 | 0.64397 | 3.7633 | 7.3109 | 4.9409 | 5.5564 | 3.8085 | 1.9617 | 18.5923 | 14.4744 | 18.5923
1095 | 0.69455 | 1.0581 | 0.75633 | 0.85499 | 5.2265 | 6.1376 | 6.0884 | 6.1467 | 5.8714 | 2.1968 | 19.7076 | 19.383 | 19.7076
1096 | 0.78436 | 0.30762 | 0.78358 | 0.62081 | 3.7392 | 6.2522 | 5.1329 | 5.505 | 4.2772 | 1.8342 | 17.3306 | 14.9834 | 17.3306
1097 | 1.0649 | 0.52945 | 0.85654 | 0.70175 | 4.5259 | 6.6043 | 6.1826 | 5.6923 | 5.4963 | 2.394 | 19.2165 | 18.5987 | 19.2165
1098 | 0.06126 | 0.78691 | 0.52442 | 0.78433 | 4.1801 | 5.3308 | 4.2936 | 5.9136 | 4.7826 | 2.082 | 17.5065 | 15.3382 | 17.5065
1099 | -0.81917 | -1.9589 | 0.20634 | 0.02506 | 5.2895 | 4.3321 | 4.0653 | 4.2112 | 5.2832 | 2.005 | 15.8378 | 16.643 | 16.643
1100 | 1.6171 | -0.026285 | 0.94708 | 0.48952 | 3.6397 | 7.2496 | 5.765 | 5.2346 | 5.3723 | 2.3241 | 18.4481 | 17.1011 | 18.4481
1101 | 0.36502 | 0.80263 | 0.64245 | 0.7889 | 4.1596 | 5.7151 | 6.6245 | 5.9271 | 4.0258 | 1.9844 | 17.7862 | 16.7943 | 17.7862
1102 | -0.46126 | -1.302 | 0.32231 | 0.096458 | 4.1609 | 4.71 | 5.1911 | 4.4399 | 3.4648 | 2.4781 | 15.7889 | 15.2949 | 15.7889
1103 | 1.7997 | 2.0609 | 0.96404 | 0.98034 | 3.5478 | 7.4431 | 7.0342 | 6.9367 | 4.9979 | 1.4973 | 19.4249 | 17.0772 | 19.4249
1104 | -0.91884 | -0.072523 | 0.17909 | 0.47109 | 3.0169 | 4.2354 | 6.7871 | 5.1987 | 4.99 | 2.3958 | 14.8468 | 17.1898 | 17.1898
1105 | 0.47126 | 0.16387 | 0.68127 | 0.56508 | 3.3759 | 5.8513 | 6.6302 | 5.3865 | 3.9421 | 1.6724 | 16.2861 | 15.6205 | 16.2861
1106 | 2.1467 | 1.205 | 0.98409 | 0.88589 | 5.3659 | 7.7775 | 6.1241 | 6.2713 | 4.3972 | 1.4946 | 20.9094 | 17.3819 | 20.9094
1107 | 2.3275 | 1.184 | 0.99003 | 0.88179 | 3.3492 | 7.9331 | 3.5261 | 6.2536 | 5.2804 | 1.8121 | 19.348 | 13.9678 | 19.348
1108 | 0.56169 | 0.0090411 | 0.71284 | 0.50361 | 2.6295 | 5.9673 | 6.2659 | 5.2624 | 3.5966 | 2.7015 | 16.5607 | 15.1934 | 16.5607
1109 | 1.1841 | 1.196 | 0.88182 | 0.88415 | 4.1964 | 6.75 | 3.9502 | 6.2638 | 3.6686 | 2.7551 | 19.9652 | 14.5702 | 19.9652
1110 | -0.43659 | 0.038276 | 0.33121 | 0.51527 | 3.4715 | 4.7377 | 5.2244 | 5.2855 | 3.0957 | 1.6647 | 15.1594 | 13.4564 | 15.1594
1111 | 0.21583 | 0.83376 | 0.58544 | 0.79779 | 2.2578 | 5.5251 | 4.0174 | 5.954 | 4.5825 | 2.0901 | 15.827 | 12.9478 | 15.827
1112 | -0.95743 | 0.45979 | 0.16918 | 0.67717 | 3.0894 | 4.1991 | 6.6954 | 5.633 | 4.2331 | 1.9186 | 14.8401 | 15.9365 | 15.9365
1113 | 0.91641 | 0.75708 | 0.82027 | 0.7755 | 4.1791 | 6.4193 | 4.5965 | 5.8879 | 4.8907 | 1.663 | 18.1492 | 15.3293 | 18.1492
1114 | -3.1513 | -2.6971 | 0.0008127 | 0.0034978 | 2.8059 | 3.1041 | 4.7208 | 4.0763 | 5.4479 | 2.4554 | 12.4417 | 15.4299 | 15.4299
1115 | 0.54019 | -0.64883 | 0.70547 | 0.25823 | 2.4815 | 5.9397 | 7.3234 | 4.7912 | 4.7421 | 2.5286 | 15.7411 | 17.0757 | 17.0757
1116 | -0.97943 | -0.17665 | 0.16368 | 0.42989 | 2.8738 | 4.1786 | 5.0218 | 5.1193 | 4.4357 | 2.0794 | 14.2511 | 14.4108 | 14.4108
1117 | 0.032025 | -0.31954 | 0.51277 | 0.37466 | 3.2865 | 5.2945 | 5.0448 | 5.0142 | 3.9601 | 1.6768 | 15.272 | 13.9682 | 15.272
1118 | -0.13759 | 0.41166 | 0.44528 | 0.65971 | 3.3235 | 5.0869 | 5.7081 | 5.5923 | 4.9109 | 1.8251 | 15.8277 | 15.7676 | 15.8277
1119 | -0.5026 | 1.3849 | 0.30762 | 0.91695 | 2.7577 | 4.6641 | 4.6571 | 6.4211 | 4.0862 | 1.663 | 15.5059 | 13.164 | 15.5059
1120 | -0.61566 | -0.88801 | 0.26906 | 0.18727 | 3.854 | 4.5414 | 6.4908 | 4.6479 | 4.0188 | 2.6688 | 15.7121 | 17.0324 | 17.0324
1121 | 0.53746 | 1.2437 | 0.70452 | 0.8932 | 2.7938 | 5.9362 | 6.7605 | 6.3039 | 5.2763 | 2.4434 | 17.4774 | 17.274 | 17.4774
1122 | -0.5591 | -0.33601 | 0.28805 | 0.36843 | 5.2661 | 4.6022 | 3.9429 | 5.0024 | 3.1455 | 2.4894 | 17.3602 | 14.844 | 17.3602
1123 | -0.3184 | 1.5094 | 0.37509 | 0.9344 | 3.3528 | 4.8728 | 7.0862 | 6.5223 | 3.4889 | 2.7525 | 17.5004 | 16.6805 | 17.5004
1124 | -0.83475 | -0.56946 | 0.20193 | 0.28452 | 3.6701 | 4.3168 | 4.5685 | 4.8423 | 3.8677 | 1.9167 | 14.7459 | 14.0231 | 14.7459
1125 | -0.46914 | -0.4989 | 0.31949 | 0.30893 | 5.5428 | 4.7012 | 6.097 | 4.8892 | 3.6654 | 1.5387 | 16.6719 | 16.8439 | 16.8439
1126 | 0.058163 | 0.74684 | 0.52319 | 0.77242 | 4.5665 | 5.327 | 6.209 | 5.879 | 3.7661 | 1.5073 | 17.2799 | 16.049 | 17.2799
1127 | 1.3272 | -1.1423 | 0.90778 | 0.12666 | 5.0298 | 6.9207 | 6.4394 | 4.514 | 4.3248 | 2.3149 | 18.7794 | 18.1089 | 18.7794
1128 | 0.41723 | -1.053 | 0.66174 | 0.14617 | 3.4618 | 5.782 | 4.3687 | 4.5589 | 4.4931 | 1.9748 | 15.7774 | 14.2984 | 15.7774
1129 | -0.57407 | -1.252 | 0.28296 | 0.10529 | 5.1518 | 4.586 | 4.2688 | 4.4623 | 4.3683 | 2.1089 | 16.309 | 15.8978 | 16.309
1130 | 0.67544 | -0.62042 | 0.7503 | 0.26749 | 2.6488 | 6.1132 | 6.3308 | 4.8093 | 3.3375 | 2.2515 | 15.8229 | 14.5687 | 15.8229
1131 | 2.442 | 2.3727 | 0.9927 | 0.99117 | 3.9146 | 8.0248 | 6.4876 | 7.1405 | 5.0193 | 1.9921 | 21.072 | 17.4137 | 21.072
1132 | 0.11722 | -1.2127 | 0.54666 | 0.11263 | 2.7119 | 5.4008 | 3.8021 | 4.4804 | 4.5387 | 2.7204 | 15.3135 | 13.7731 | 15.3135
1133 | -0.56087 | 0.0039822 | 0.28744 | 0.50159 | 2.5874 | 4.6003 | 5.3778 | 5.2584 | 5.4577 | 2.0987 | 14.5448 | 15.5216 | 15.5216
1134 | 1.2089 | 1.5996 | 0.88666 | 0.94516 | 4.5168 | 6.7799 | 7.2266 | 6.5941 | 3.3785 | 1.9919 | 19.8828 | 17.1138 | 19.8828
1135 | 0.93962 | -1.3746 | 0.82629 | 0.084635 | 5.4792 | 6.4484 | 5.5635 | 4.4086 | 3.4596 | 1.7999 | 18.1362 | 16.3022 | 18.1362
1136 | 0.18538 | -0.7707 | 0.57354 | 0.22044 | 4.6595 | 5.4866 | 7.385 | 4.7161 | 5.021 | 1.9628 | 16.825 | 19.0283 | 19.0283
1137 | 0.08445 | 1.247 | 0.53365 | 0.8938 | 2.5016 | 5.3598 | 7.1143 | 6.3067 | 4.4167 | 2.0238 | 16.1918 | 16.0564 | 16.1918
1138 | 0.81459 | 0.94019 | 0.79235 | 0.82644 | 3.4577 | 6.2906 | 3.1376 | 6.0457 | 3.7803 | 2.5734 | 18.3674 | 12.9491 | 18.3674
1139 | 0.75206 | 1.5976 | 0.77399 | 0.94494 | 3.9026 | 6.2111 | 4.5522 | 6.5926 | 4.3063 | 1.7338 | 18.44 | 14.4949 | 18.44
1140 | 0.95521 | 0.68913 | 0.83026 | 0.75463 | 4.3466 | 6.468 | 6.0744 | 5.8293 | 4.0813 | 2.4545 | 19.0985 | 16.9569 | 19.0985
1141 | -0.61293 | 0.85755 | 0.26996 | 0.80443 | 4.5922 | 4.5443 | 4.1848 | 5.9745 | 4.2621 | 2.4437 | 17.5547 | 15.4828 | 17.5547
1142 | 0.090486 | 0.33485 | 0.53605 | 0.63113 | 3.1977 | 5.3673 | 4.1241 | 5.5277 | 3.9891 | 1.4869 | 15.5797 | 12.7978 | 15.5797
1143 | 0.61282 | -0.46918 | 0.73 | 0.31947 | 3.2101 | 6.033 | 4.979 | 4.9093 | 3.9367 | 1.9525 | 16.105 | 14.0784 | 16.105
1144 | 0.48498 | 0.33748 | 0.68616 | 0.63212 | 4.2984 | 5.8689 | 5.9105 | 5.5299 | 3.2898 | 1.6344 | 17.3316 | 15.1332 | 17.3316
1145 | -0.47025 | 0.80599 | 0.31909 | 0.78987 | 4.3993 | 4.7 | 4.9959 | 5.93 | 3.2746 | 2.5222 | 17.5515 | 15.192 | 17.5515
1146 | -0.94178 | -0.8939 | 0.17315 | 0.18569 | 3.5656 | 4.2137 | 5.5368 | 4.6446 | 3.8319 | 2.0152 | 14.4391 | 14.9495 | 14.9495
1147 | -0.064764 | 0.089074 | 0.47418 | 0.53549 | 4.1826 | 5.1753 | 5.9227 | 5.326 | 5.288 | 1.4506 | 16.1346 | 16.8439 | 16.8439
1148 | 0.39808 | -0.091305 | 0.65471 | 0.46363 | 3.1461 | 5.7574 | 5.6489 | 5.1842 | 4.0807 | 1.4932 | 15.5809 | 14.3688 | 15.5809
1149 | 0.35688 | -1.0029 | 0.63941 | 0.15796 | 3.7011 | 5.7047 | 5.2726 | 4.5851 | 3.3076 | 1.5092 | 15.5001 | 13.7905 | 15.5001
1150 | -0.90807 | -0.53606 | 0.18192 | 0.29596 | 4.193 | 4.2457 | 5.7712 | 4.8643 | 4.4121 | 1.9526 | 15.2556 | 16.3289 | 16.3289
1151 | 0.11977 | 0.22952 | 0.54767 | 0.59077 | 3.1269 | 5.404 | 7.0341 | 5.4403 | 3.9032 | 1.6913 | 15.6625 | 15.7556 | 15.7556
1152 | -1.011 | 0.0086369 | 0.15601 | 0.50345 | 3.853 | 4.1496 | 4.4088 | 5.262 | 4.698 | 2.4164 | 15.681 | 15.3762 | 15.681
1153 | -0.84122 | -0.48738 | 0.20011 | 0.313 | 3.2382 | 4.3104 | 5.2784 | 4.897 | 4.3432 | 1.5406 | 13.9861 | 14.4004 | 14.4004
1154 | 0.72743 | 0.47518 | 0.76652 | 0.68267 | 4.1384 | 6.1797 | 6.4604 | 5.6461 | 3.5059 | 1.8611 | 17.8252 | 15.9658 | 17.8252
1155 | -0.24969 | -1.0909 | 0.40141 | 0.13766 | 4.2138 | 4.9531 | 5.1766 | 4.5396 | 5.1974 | 2.5506 | 16.2571 | 17.1384 | 17.1384
1156 | 1.6003 | -0.27901 | 0.94523 | 0.39012 | 3.1236 | 7.2312 | 5.8914 | 5.0435 | 3.5382 | 1.6419 | 17.0402 | 14.1952 | 17.0402
1157 | 0.2373 | 1.0964 | 0.59379 | 0.86355 | 4.4161 | 5.5523 | 5.7575 | 6.1794 | 3.5107 | 1.9957 | 18.1434 | 15.68 | 18.1434
1158 | 1.8312 | 1.5459 | 0.96647 | 0.93893 | 3.3955 | 7.4754 | 5.8699 | 6.5515 | 3.4702 | 2.5722 | 19.9946 | 15.3078 | 19.9946
1159 | -0.26044 | 0.45919 | 0.39726 | 0.67695 | 5.0197 | 4.9405 | 6.2871 | 5.6325 | 4.802 | 1.6887 | 17.2814 | 17.7975 | 17.7975
1160 | -0.23728 | -0.57984 | 0.40622 | 0.28101 | 3.4192 | 4.9678 | 6.4292 | 4.8355 | 3.5691 | 1.7334 | 14.9559 | 15.1508 | 15.1508
1161 | 0.20538 | 0.73531 | 0.58136 | 0.76892 | 3.3118 | 5.5119 | 6.1317 | 5.8691 | 4.7151 | 2.1128 | 16.8056 | 16.2715 | 16.8056
1162 | -0.13962 | -0.038489 | 0.44448 | 0.48465 | 4.227 | 5.0844 | 7.0823 | 5.2251 | 5.5612 | 2.5472 | 17.0837 | 19.4177 | 19.4177
1163 | 0.14954 | 0.85741 | 0.55944 | 0.80439 | 3.569 | 5.4414 | 4.2211 | 5.9744 | 4.8702 | 1.6046 | 16.5894 | 14.265 | 16.5894
1164 | 1.0293 | 0.94107 | 0.84833 | 0.82666 | 5.0865 | 6.5603 | 5.6704 | 6.0464 | 3.3975 | 2.0467 | 19.7399 | 16.2011 | 19.7399
1165 | -0.017398 | -1.2524 | 0.49306 | 0.1052 | 2.9377 | 5.2334 | 5.0914 | 4.4621 | 4.189 | 2.011 | 14.6442 | 14.2291 | 14.6442
1166 | 0.52488 | 0.4142 | 0.70017 | 0.66063 | 4.6752 | 5.9201 | 7.1009 | 5.5944 | 4.6597 | 2.4226 | 18.6123 | 18.8583 | 18.8583
1167 | -0.21787 | 0.91132 | 0.41377 | 0.81894 | 4.0733 | 4.9908 | 5.2616 | 6.0208 | 3.4363 | 1.7528 | 16.8378 | 14.5241 | 16.8378
1168 | -2.527 | -1.1601 | 0.005752 | 0.123 | 5.1939 | 3.2456 | 5.8088 | 4.5054 | 5.0831 | 1.869 | 14.8138 | 17.9547 | 17.9547
1169 | 0.27668 | 0.26345 | 0.60899 | 0.6039 | 2.7514 | 5.6024 | 6.4601 | 5.4683 | 4.3727 | 2.3025 | 16.1246 | 15.8867 | 16.1246
1170 | -0.92113 | -0.80341 | 0.17849 | 0.21087 | 4.7792 | 4.2333 | 5.3268 | 4.6967 | 5.2699 | 1.7016 | 15.4107 | 17.0775 | 17.0775
1171 | 1.9535 | 0.9224 | 0.97462 | 0.82184 | 4.3926 | 7.597 | 4.1329 | 6.0304 | 4.3361 | 2.8169 | 20.8368 | 15.6785 | 20.8368
1172 | 1.636 | 0.94958 | 0.94908 | 0.82884 | 4.0065 | 7.2702 | 5.6901 | 6.0537 | 3.3827 | 2.4428 | 19.7732 | 15.5222 | 19.7732
1173 | 0.15013 | 0.52074 | 0.55967 | 0.69873 | 4.0795 | 5.4421 | 4.0118 | 5.6849 | 4.8304 | 1.9652 | 17.1717 | 14.8868 | 17.1717
1174 | 0.96991 | 2.398 | 0.83395 | 0.99176 | 4.4485 | 6.4863 | 6.3177 | 7.1558 | 4.2831 | 2.6679 | 20.7585 | 17.7171 | 20.7585
1175 | 0.948 | 1.9991 | 0.82844 | 0.9772 | 3.8549 | 6.4589 | 6.945 | 6.8935 | 4.2059 | 2.1644 | 19.3717 | 17.1702 | 19.3717
1176 | -1.9145 | -1.6681 | 0.02778 | 0.047652 | 4.1375 | 3.4995 | 6.7294 | 4.2979 | 5.7365 | 2.1387 | 14.0735 | 18.7421 | 18.7421
1177 | 0.070971 | -0.59889 | 0.52829 | 0.27462 | 2.9939 | 5.3429 | 6.0711 | 4.8232 | 5.2439 | 2.1028 | 15.2629 | 16.4118 | 16.4118
1178 | -0.65137 | -1.7106 | 0.2574 | 0.043577 | 3.4581 | 4.5036 | 7.5058 | 4.2838 | 4.0422 | 2.2103 | 14.4559 | 17.2165 | 17.2165
1179 | 0.87501 | 0.91792 | 0.80922 | 0.82067 | 4.3623 | 6.3671 | 5.8584 | 6.0265 | 3.8097 | 1.5328 | 18.2887 | 15.5633 | 18.2887
1180 | -1.0573 | -0.747 | 0.14518 | 0.22753 | 3.9936 | 4.1078 | 5.9202 | 4.7304 | 4.2584 | 2.5983 | 15.4301 | 16.7704 | 16.7704
1181 | 0.28955 | 1.1976 | 0.61392 | 0.88447 | 5.1329 | 5.6187 | 4.5808 | 6.2652 | 4.9439 | 2.139 | 19.1558 | 16.7965 | 19.1558
1182 | -0.37721 | -0.10219 | 0.35301 | 0.4593 | 3.0909 | 4.805 | 3.5826 | 5.1758 | 4.3058 | 1.8494 | 14.9211 | 12.8286 | 14.9211
1183 | 0.5011 | 0.7701 | 0.69185 | 0.77938 | 3.3293 | 5.8896 | 3.918 | 5.8991 | 3.8631 | 2.0307 | 17.1487 | 13.1411 | 17.1487
1184 | 0.93194 | -0.43421 | 0.82432 | 0.33207 | 3.2635 | 6.4388 | 5.5282 | 4.9333 | 3.4034 | 2.1314 | 16.7671 | 14.3265 | 16.7671
1185 | 0.4746 | -0.52773 | 0.68246 | 0.29884 | 4.035 | 5.8555 | 3.99 | 4.8699 | 4.1857 | 2.4889 | 17.2493 | 14.6996 | 17.2493
1186 | 0.0097775 | 0.69724 | 0.5039 | 0.75717 | 4.2888 | 5.267 | 4.9581 | 5.8363 | 4.2838 | 2.0572 | 17.4493 | 15.5879 | 17.4493
1187 | 0.95395 | -0.033317 | 0.82994 | 0.48671 | 4.3463 | 6.4664 | 4.6435 | 5.2291 | 3.9268 | 2.1439 | 18.1857 | 15.0606 | 18.1857
1188 | -1.5716 | -1.5168 | 0.058021 | 0.064664 | 4.0947 | 3.7051 | 4.8101 | 4.3519 | 3.1734 | 2.2767 | 14.4284 | 14.3549 | 14.4284
1189 | 0.049677 | 0.15754 | 0.51981 | 0.56259 | 4.6705 | 5.3164 | 6.1398 | 5.3814 | 3.9592 | 1.8137 | 17.182 | 16.5832 | 17.182
1190 | -0.48918 | -1.3973 | 0.31236 | 0.081155 | 5.0165 | 4.6789 | 6.3059 | 4.3992 | 4.5131 | 2.2604 | 16.355 | 18.0959 | 18.0959
1191 | -1.0323 | 0.53081 | 0.15096 | 0.70222 | 5.3019 | 4.1302 | 5.5315 | 5.6935 | 4.9107 | 2.3182 | 17.4439 | 18.0623 | 18.0623
1192 | -0.15704 | -0.66727 | 0.43761 | 0.2523 | 4.4567 | 5.0635 | 4.3511 | 4.7796 | 3.258 | 1.9929 | 16.2926 | 14.0587 | 16.2926
1193 | 2.6494 | 1.4803 | 0.99597 | 0.9306 | 3.9942 | 8.1775 | 5.6296 | 6.4989 | 3.7539 | 1.1685 | 19.8391 | 14.5463 | 19.8391
1194 | -1.5471 | -1.5987 | 0.06092 | 0.054946 | 5.3207 | 3.7217 | 6.9082 | 4.3219 | 3.7457 | 1.1511 | 14.5154 | 17.1257 | 17.1257
1195 | -0.89392 | -1.2909 | 0.18568 | 0.098369 | 4.1471 | 4.2592 | 5.7861 | 4.4448 | 4.6765 | 1.5284 | 14.3795 | 16.1381 | 16.1381
1196 | -1.4613 | -0.40579 | 0.071971 | 0.34245 | 3.2006 | 3.7818 | 4.4254 | 4.9531 | 4.0274 | 2.3333 | 14.2688 | 13.9867 | 14.2688
1197 | -0.54009 | -0.24586 | 0.29457 | 0.4029 | 3.9343 | 4.6229 | 5.753 | 5.0678 | 5.3086 | 1.7107 | 15.3358 | 16.7067 | 16.7067
1198 | 0.18927 | 1.1102 | 0.57506 | 0.86655 | 4.3782 | 5.4915 | 3.8936 | 6.1912 | 3.6705 | 1.9967 | 18.0576 | 13.939 | 18.0576
1199 | -0.47504 | 0.71124 | 0.31738 | 0.76153 | 3.5204 | 4.6946 | 5.0448 | 5.8484 | 5.5638 | 2.362 | 16.4254 | 16.4911 | 16.4911
1200 | -0.90289 | 0.22033 | 0.18329 | 0.58719 | 4.3863 | 4.2506 | 4.6453 | 5.4327 | 5.947 | 1.8737 | 15.9433 | 16.8523 | 16.8523
1201 | -0.096995 | -0.21528 | 0.46137 | 0.41478 | 5.2597 | 5.136 | 6.4273 | 5.0904 | 3.8922 | 2.0236 | 17.5097 | 17.6028 | 17.6028
1202 | -0.15432 | -0.37134 | 0.43868 | 0.35519 | 4.6673 | 5.0667 | 5.5622 | 4.9773 | 4.9932 | 2.074 | 16.7852 | 17.2967 | 17.2967
1203 | 1.0139 | 0.059983 | 0.84468 | 0.52392 | 5.3662 | 6.5411 | 3.5964 | 5.3028 | 5.1603 | 2.3219 | 19.532 | 16.4447 | 19.532
1204 | -0.25134 | -0.14899 | 0.40078 | 0.44078 | 4.1676 | 4.9512 | 4.8753 | 5.1401 | 5.1533 | 2.0609 | 16.3199 | 16.2572 | 16.3199
1205 | -0.19697 | 1.1016 | 0.42193 | 0.86469 | 5.5114 | 5.0157 | 6.0896 | 6.1838 | 4.5797 | 1.9486 | 18.6595 | 18.1293 | 18.6595
1206 | 0.93863 | 1.4103 | 0.82604 | 0.92077 | 4.1225 | 6.4472 | 5.1743 | 6.442 | 3.9644 | 1.159 | 18.1706 | 14.4202 | 18.1706
1207 | -0.35354 | -0.56155 | 0.36184 | 0.28721 | 3.328 | 4.8322 | 5.2216 | 4.8475 | 4.5476 | 2.801 | 15.8087 | 15.8982 | 15.8982
1208 | 0.63525 | -0.78736 | 0.73737 | 0.21554 | 4.9991 | 6.0617 | 7.1767 | 4.7062 | 4.8642 | 1.5692 | 17.3362 | 18.6092 | 18.6092
1209 | -0.15786 | 0.027178 | 0.43728 | 0.51084 | 4.9953 | 5.0625 | 4.3119 | 5.2767 | 3.5194 | 2.1794 | 17.5139 | 15.006 | 17.5139
1210 | 0.1524 | 0.36956 | 0.56056 | 0.64414 | 2.5264 | 5.445 | 6.4422 | 5.5568 | 5.3559 | 1.8489 | 15.3772 | 16.1735 | 16.1735
1211 | 0.83939 | 0.42261 | 0.79937 | 0.66371 | 4.1963 | 6.3221 | 5.0646 | 5.6015 | 5.5937 | 2.0387 | 18.1586 | 16.8933 | 18.1586
1212 | 2.0137 | 0.97894 | 0.97798 | 0.83619 | 4.2688 | 7.6547 | 6.712 | 6.0789 | 4.1702 | 1.8281 | 19.8306 | 16.9791 | 19.8306
1213 | -1.2106 | 0.24872 | 0.11302 | 0.59821 | 4.3502 | 3.9758 | 6.6768 | 5.4561 | 4.5152 | 1.9086 | 15.6907 | 17.4508 | 17.4508
1214 | -0.085674 | -1.2323 | 0.46586 | 0.10892 | 3.245 | 5.1498 | 5.673 | 4.4713 | 3.8063 | 2.3035 | 15.1696 | 15.0278 | 15.1696
1215 | -1.0968 | -0.74196 | 0.13637 | 0.22906 | 4.1189 | 4.0729 | 7.145 | 4.7335 | 4.9537 | 2.2802 | 15.2055 | 18.4979 | 18.4979
1216 | 0.5333 | 1.3595 | 0.70309 | 0.91301 | 3.7792 | 5.9309 | 4.3634 | 6.4003 | 5.8022 | 1.2776 | 17.388 | 15.2224 | 17.388
1217 | -1.7407 | -1.3283 | 0.040867 | 0.092036 | 4.311 | 3.5975 | 4.8626 | 4.4284 | 4.506 | 1.7764 | 14.1133 | 15.4561 | 15.4561
1218 | 2.4005 | 1.9711 | 0.99181 | 0.97565 | 4.9248 | 7.9922 | 5.8758 | 6.8737 | 4.6678 | 2.0955 | 21.8861 | 17.5639 | 21.8861
1219 | 0.55033 | 1.3709 | 0.70895 | 0.9148 | 3.7013 | 5.9528 | 5.9869 | 6.4096 | 3.7023 | 2.3661 | 18.4298 | 15.7565 | 18.4298
1220 | 1.1362 | -0.48579 | 0.87207 | 0.31356 | 2.7249 | 6.6918 | 6.9828 | 4.8981 | 4.209 | 1.6512 | 15.966 | 15.5679 | 15.966
1221 | -0.32579 | -0.90346 | 0.37229 | 0.18314 | 3.9045 | 4.8642 | 5.8265 | 4.6393 | 5.0989 | 1.6869 | 15.0949 | 16.5169 | 16.5169
1222 | 0.11195 | 1.265 | 0.54457 | 0.89706 | 3.5799 | 5.3942 | 4.2709 | 6.3217 | 3.9984 | 1.7834 | 17.0791 | 13.6325 | 17.0791
1223 | -0.006191 | -0.097973 | 0.49753 | 0.46098 | 4.4361 | 5.2472 | 4.8964 | 5.1791 | 6.0399 | 1.8199 | 16.6823 | 17.1923 | 17.1923
1224 | -0.36597 | 1.5895 | 0.35719 | 0.94403 | 2.5273 | 4.8179 | 5.5443 | 6.5862 | 5.7931 | 1.785 | 15.7164 | 15.6497 | 15.7164
1225 | -0.5988 | -0.73334 | 0.27465 | 0.23167 | 3.2235 | 4.5594 | 6.0943 | 4.7387 | 3.7089 | 1.3922 | 13.9138 | 14.4188 | 14.4188
1226 | 0.23929 | 1.6049 | 0.59456 | 0.94574 | 3.8789 | 5.5548 | 5.2146 | 6.5983 | 3.8339 | 1.2833 | 17.3153 | 14.2107 | 17.3153
1227 | 1.95 | 0.13719 | 0.97441 | 0.55456 | 4.3395 | 7.5935 | 5.5345 | 5.3648 | 4.6207 | 1.3888 | 18.6866 | 15.8834 | 18.6866
1228 | 0.52671 | 0.82988 | 0.7008 | 0.7967 | 4.9946 | 5.9224 | 5.6584 | 5.9506 | 3.2879 | 2.5943 | 19.462 | 16.5353 | 19.462
1229 | 1.1487 | -0.84704 | 0.87465 | 0.19849 | 4.3323 | 6.7069 | 5.6894 | 4.6713 | 4.5313 | 2.0294 | 17.7399 | 16.5823 | 17.7399
1230 | 0.95027 | 1.7402 | 0.82901 | 0.95909 | 4.4354 | 6.4618 | 5.738 | 6.7032 | 3.9099 | 2.3575 | 19.9578 | 16.4408 | 19.9578
1231 | -1.1635 | -1.0483 | 0.12231 | 0.14726 | 4.0154 | 4.0153 | 5.1333 | 4.5613 | 3.7395 | 2.0853 | 14.6773 | 14.9734 | 14.9734
1232 | 0.53321 | 1.0076 | 0.70306 | 0.84317 | 4.0981 | 5.9308 | 7.1383 | 6.1035 | 5.404 | 2.0859 | 18.2182 | 18.7262 | 18.7262
1233 | -0.9212 | -1.119 | 0.17847 | 0.13157 | 4.408 | 4.2332 | 4.8669 | 4.5255 | 3.9901 | 2.6034 | 15.7701 | 15.8684 | 15.8684
1234 | -0.028735 | 0.74384 | 0.48854 | 0.77151 | 3.9625 | 5.2195 | 6.5589 | 5.8765 | 3.6914 | 1.5108 | 16.5693 | 15.7237 | 16.5693
1235 | 0.45715 | 0.31399 | 0.67622 | 0.62324 | 3.4085 | 5.8331 | 7.1115 | 5.5103 | 3.5666 | 1.9761 | 16.728 | 16.0627 | 16.728
1236 | -0.47845 | -1.1443 | 0.31617 | 0.12625 | 4.1052 | 4.6908 | 7.3654 | 4.5131 | 4.2484 | 1.8274 | 15.1366 | 17.5465 | 17.5465
1237 | 1.4537 | 1.5768 | 0.92699 | 0.94258 | 3.3695 | 7.0673 | 4.7122 | 6.5761 | 4.0437 | 2.1902 | 19.2031 | 14.3156 | 19.2031
1238 | 0.029899 | -0.94279 | 0.51193 | 0.1729 | 4.429 | 5.2919 | 5.7935 | 4.6175 | 5.6033 | 2.5579 | 16.8963 | 18.3837 | 18.3837
1239 | -0.94393 | -0.45249 | 0.1726 | 0.32546 | 4.5631 | 4.2117 | 5.9222 | 4.9208 | 5.1196 | 2.0393 | 15.7348 | 17.6441 | 17.6441
1240 | 1.5973 | 0.657 | 0.9449 | 0.74441 | 4.612 | 7.2279 | 7.4803 | 5.8017 | 4.0235 | 2.5626 | 20.2042 | 18.6784 | 20.2042
1241 | -1.0971 | -1.6606 | 0.13629 | 0.048401 | 3.8984 | 4.0725 | 5.2893 | 4.3004 | 3.7859 | 2.7369 | 15.0083 | 15.7105 | 15.7105
1242 | -0.11455 | -0.022761 | 0.4544 | 0.49092 | 2.6906 | 5.1147 | 6.1168 | 5.2374 | 3.2931 | 1.8727 | 14.9154 | 13.9731 | 14.9154
1243 | -0.83171 | -0.40014 | 0.20278 | 0.34453 | 3.8455 | 4.3197 | 5.9801 | 4.957 | 4.1891 | 1.8776 | 14.9999 | 15.8923 | 15.8923
1244 | -0.41202 | -0.64535 | 0.34016 | 0.25935 | 4.8321 | 4.7654 | 5.7783 | 4.7934 | 4.0288 | 2.603 | 16.9939 | 17.2422 | 17.2422
1245 | 0.76095 | 1.3413 | 0.77666 | 0.91009 | 5.4595 | 6.2224 | 4.4297 | 6.3852 | 3.8487 | 2.3094 | 20.3766 | 16.0474 | 20.3766
1246 | -0.69531 | -0.53304 | 0.24343 | 0.297 | 3.692 | 4.4577 | 4.6757 | 4.8664 | 4.7562 | 2.3836 | 15.3996 | 15.5074 | 15.5074
1247 | -1.5116 | -0.90701 | 0.065315 | 0.1822 | 2.6867 | 3.7462 | 5.439 | 4.6373 | 3.5998 | 2.4947 | 13.5649 | 14.2203 | 14.2203
1248 | 0.79537 | 0.34753 | 0.7868 | 0.6359 | 3.3692 | 6.2662 | 3.229 | 5.5383 | 4.4997 | 1.2685 | 16.4422 | 12.3663 | 16.4422
1249 | -0.19278 | -1.1215 | 0.42357 | 0.13104 | 3.9056 | 5.0206 | 7.0652 | 4.5243 | 3.2884 | 2.4493 | 15.8998 | 16.7085 | 16.7085
1250 | -0.5095 | -0.66714 | 0.3052 | 0.25234 | 4.8105 | 4.6565 | 6.8546 | 4.7797 | 4.2699 | 2.0361 | 16.2828 | 17.9711 | 17.9711
1251 | 1.3144 | 1.4895 | 0.90565 | 0.93182 | 4.2413 | 6.9056 | 6.0862 | 6.5063 | 4.9755 | 2.2983 | 19.9515 | 17.6013 | 19.9515
1252 | 0.038624 | -0.018945 | 0.5154 | 0.49244 | 4.1538 | 5.3027 | 6.7362 | 5.2404 | 3.9522 | 1.5489 | 16.2458 | 16.3911 | 16.3911
1253 | -0.22081 | -0.20736 | 0.41262 | 0.41786 | 3.5108 | 4.9873 | 6.4681 | 5.0963 | 4.9451 | 2.3507 | 15.945 | 17.2746 | 17.2746
1254 | -1.2822 | -1.101 | 0.099883 | 0.13544 | 2.8799 | 3.9176 | 3.2675 | 4.5345 | 3.4814 | 1.8453 | 13.1774 | 11.4742 | 13.1774
1255 | 0.47799 | 0.60379 | 0.68367 | 0.72701 | 3.81 | 5.8599 | 6.2294 | 5.756 | 4.9118 | 1.9428 | 17.3686 | 16.8939 | 17.3686
1256 | -0.22752 | 1.0427 | 0.41001 | 0.85146 | 4.1007 | 4.9793 | 7.129 | 6.1336 | 3.9579 | 1.8385 | 17.0522 | 17.0262 | 17.0522
1257 | 0.20978 | -0.14003 | 0.58308 | 0.44432 | 2.7739 | 5.5174 | 5.6239 | 5.1469 | 3.2517 | 1.7553 | 15.1935 | 13.4047 | 15.1935
1258 | 0.96083 | 0.40022 | 0.83168 | 0.6555 | 5.2478 | 6.475 | 5.6929 | 5.5826 | 4.0459 | 2.7397 | 20.0452 | 17.7264 | 20.0452
1259 | 0.097473 | 1.184 | 0.53882 | 0.88179 | 3.1419 | 5.3761 | 6.9478 | 6.2537 | 4.8104 | 1.8987 | 16.6703 | 16.7988 | 16.7988
1260 | 0.78623 | -1.657 | 0.78413 | 0.048759 | 3.7962 | 6.2546 | 3.9253 | 4.3016 | 3.9573 | 1.4475 | 15.7999 | 13.1263 | 15.7999
1261 | -2.0529 | -1.3177 | 0.02004 | 0.093795 | 2.8908 | 3.4301 | 7.3525 | 4.433 | 3.8234 | 2.288 | 13.0418 | 16.3547 | 16.3547
1262 | -0.14511 | -0.45397 | 0.44231 | 0.32492 | 3.0236 | 5.0778 | 6.5402 | 4.9197 | 3.6315 | 2.1209 | 15.142 | 15.3162 | 15.3162
1263 | -0.2391 | -1.234 | 0.40551 | 0.10861 | 4.4943 | 4.9656 | 7.1808 | 4.4705 | 5.1499 | 2.2811 | 16.2115 | 19.1061 | 19.1061
1264 | 0.78315 | -0.041763 | 0.78323 | 0.48334 | 5.0398 | 6.2507 | 6.3261 | 5.2225 | 3.5034 | 1.7815 | 18.2945 | 16.6509 | 18.2945
1265 | 0.56463 | 1.1979 | 0.71384 | 0.88453 | 4.127 | 5.9711 | 6.9667 | 6.2654 | 3.6019 | 1.876 | 18.2395 | 16.5715 | 18.2395
1266 | 1.0526 | 2.2749 | 0.85373 | 0.98854 | 3.359 | 6.5891 | 7.1919 | 7.0792 | 3.427 | 1.5569 | 18.5842 | 15.5349 | 18.5842
1267 | 1.7206 | 0.84816 | 0.95734 | 0.80183 | 3.9341 | 7.3607 | 6.2972 | 5.9664 | 4.0361 | 1.9834 | 19.2446 | 16.2508 | 19.2446
1268 | 1.0743 | 0.57442 | 0.85865 | 0.71716 | 4.2629 | 6.6158 | 4.4322 | 5.7308 | 5.3949 | 1.9262 | 18.5357 | 16.0161 | 18.5357
1269 | -0.31246 | 0.5112 | 0.37735 | 0.69539 | 4.154 | 4.8797 | 4.7817 | 5.6768 | 4.1055 | 2.4569 | 17.1674 | 15.4981 | 17.1674
1270 | 1.0985 | 1.7502 | 0.86402 | 0.95996 | 3.531 | 6.6457 | 7.0826 | 6.7108 | 3.291 | 2.2281 | 19.1155 | 16.1326 | 19.1155
1271 | -0.41419 | -0.73628 | 0.33937 | 0.23078 | 3.5257 | 4.7629 | 6.6725 | 4.7369 | 4.466 | 1.7442 | 14.7698 | 16.4084 | 16.4084
1272 | -0.31693 | 0.20608 | 0.37565 | 0.58163 | 4.2157 | 4.8745 | 7.4835 | 5.421 | 5.6513 | 1.8685 | 16.3796 | 19.2189 | 19.2189
1273 | -0.59714 | -0.44669 | 0.27521 | 0.32755 | 3.4768 | 4.5612 | 5.7365 | 4.9247 | 4.6641 | 1.2837 | 14.2464 | 15.1611 | 15.1611
1274 | 1.611 | 1.0979 | 0.94641 | 0.86387 | 3.7389 | 7.243 | 7.1693 | 6.1806 | 4.2844 | 2.4373 | 19.5998 | 17.6299 | 19.5998
1275 | 0.035887 | 0.67106 | 0.51431 | 0.74891 | 2.9538 | 5.2993 | 6.9695 | 5.8138 | 3.6846 | 2.556 | 16.6228 | 16.1638 | 16.6228
1276 | -0.51923 | -0.33399 | 0.3018 | 0.36919 | 4.6497 | 4.6458 | 7.1605 | 5.0038 | 4.1484 | 2.0045 | 16.3037 | 17.9631 | 17.9631
1277 | -0.47404 | -0.20553 | 0.31774 | 0.41858 | 3.2288 | 4.6958 | 4.3879 | 5.0977 | 3.6146 | 2.1637 | 15.1859 | 13.395 | 15.1859
1278 | 0.46656 | -0.39023 | 0.67959 | 0.34818 | 3.3289 | 5.8452 | 6.8779 | 4.964 | 5.885 | 2.3194 | 16.4574 | 18.4112 | 18.4112
1279 | -0.91491 | -0.2984 | 0.18012 | 0.3827 | 4.7253 | 4.2392 | 6.9932 | 5.0294 | 4.0767 | 2.0705 | 16.0644 | 17.8658 | 17.8658
1280 | -0.23348 | 0.059006 | 0.40769 | 0.52353 | 4.9 | 4.9723 | 4.3944 | 5.302 | 6.0865 | 2.1471 | 17.3213 | 17.5279 | 17.5279
1281 | -0.25605 | -0.28444 | 0.39895 | 0.38804 | 3.8429 | 4.9456 | 5.5348 | 5.0395 | 4.524 | 2.3256 | 16.1537 | 16.2273 | 16.2273
1282 | -0.23694 | 0.026685 | 0.40635 | 0.51064 | 4.4307 | 4.9682 | 6.5961 | 5.2763 | 3.3041 | 1.5412 | 16.2165 | 15.8721 | 16.2165
1283 | 1.285 | 0.83214 | 0.9006 | 0.79734 | 4.0389 | 6.8708 | 6.9825 | 5.9526 | 3.7165 | 1.593 | 18.4553 | 16.3309 | 18.4553
1284 | 0.80493 | -0.038845 | 0.78957 | 0.48451 | 2.8952 | 6.2784 | 5.4884 | 5.2248 | 3.8841 | 1.4481 | 15.8466 | 13.7159 | 15.8466
1285 | 1.9278 | 1.4077 | 0.97306 | 0.9204 | 5.2849 | 7.5718 | 6.1686 | 6.4399 | 3.4272 | 2.5491 | 21.8457 | 17.4298 | 21.8457
1286 | -1.757 | -1.9103 | 0.039461 | 0.028048 | 5.5043 | 3.5878 | 6.7062 | 4.2242 | 4.374 | 1.6878 | 15.0042 | 18.2723 | 18.2723
1287 | 0.96574 | 0.292 | 0.83291 | 0.61486 | 4.3157 | 6.4811 | 5.6443 | 5.492 | 4.3777 | 1.7943 | 18.0831 | 16.132 | 18.0831
1288 | 1.1258 | 1.0289 | 0.86988 | 0.84824 | 4.5112 | 6.6791 | 5.3664 | 6.1218 | 4.9392 | 2.3391 | 19.6511 | 17.1557 | 19.6511
1289 | 0.95374 | -0.6983 | 0.82989 | 0.2425 | 4.2462 | 6.4661 | 5.0853 | 4.7602 | 4.8059 | 1.914 | 17.3866 | 16.0514 | 17.3866
1290 | 1.738 | 1.6221 | 0.95889 | 0.94761 | 3.696 | 7.379 | 5.1166 | 6.6118 | 3.3869 | 2.2801 | 19.9669 | 14.4796 | 19.9669
1291 | -1.746 | -0.49708 | 0.040402 | 0.30956 | 3.4447 | 3.5943 | 5.9202 | 4.8904 | 4.2059 | 2.5136 | 14.443 | 16.0844 | 16.0844
1292 | 0.22607 | 1.3881 | 0.58943 | 0.91744 | 3.7731 | 5.5381 | 5.3913 | 6.4237 | 5.6298 | 1.5005 | 17.2354 | 16.2947 | 17.2354
1293 | 0.9005 | 0.21303 | 0.81607 | 0.58435 | 5.1865 | 6.3993 | 7.1102 | 5.4267 | 4.8589 | 1.6765 | 18.689 | 18.8322 | 18.8322
1294 | -1.5817 | -1.1925 | 0.056855 | 0.11653 | 4.8379 | 3.6983 | 4.6275 | 4.4899 | 4.916 | 2.811 | 15.8371 | 17.1924 | 17.1924
1295 | 0.4194 | -0.3201 | 0.66254 | 0.37445 | 2.978 | 5.7847 | 5.1547 | 5.0138 | 5.383 | 1.8295 | 15.606 | 15.3451 | 15.606
1296 | -0.93358 | -0.67303 | 0.17526 | 0.25046 | 2.8033 | 4.2215 | 4.154 | 4.776 | 3.2698 | 2.4065 | 14.2072 | 12.6336 | 14.2072
1297 | -0.021288 | 0.47875 | 0.49151 | 0.68394 | 4.0621 | 5.2286 | 6.2765 | 5.6492 | 3.8797 | 1.8929 | 16.8328 | 16.1112 | 16.8328
1298 | -0.44557 | -1.357 | 0.32795 | 0.087395 | 2.3505 | 4.7276 | 4.8621 | 4.4161 | 3.9146 | 2.0221 | 13.5162 | 13.1492 | 13.5162
1299 | -1.3129 | -1.198 | 0.094616 | 0.11546 | 4.828 | 3.8934 | 7.1018 | 4.4873 | 3.1151 | 2.2017 | 15.4105 | 17.2466 | 17.2466
1300 | 1.0402 | 2.769 | 0.85088 | 0.99719 | 4.0369 | 6.5738 | 6.2353 | 7.3627 | 3.9768 | 2.0131 | 19.9864 | 16.262 | 19.9864
1301 | -0.0088408 | -0.21553 | 0.49647 | 0.41468 | 4.077 | 5.244 | 7.5691 | 5.0902 | 4.6003 | 1.7892 | 16.2004 | 18.0357 | 18.0357
1302 | -1.0028 | -1.2966 | 0.15799 | 0.097377 | 2.8662 | 4.1571 | 5.6537 | 4.4422 | 3.6511 | 2.0573 | 13.5229 | 14.2284 | 14.2284
1303 | -1.1104 | -0.96765 | 0.13342 | 0.16661 | 3.7632 | 4.061 | 3.6982 | 4.6039 | 4.65 | 2.0663 | 14.4944 | 14.1776 | 14.4944
1304 | 1.2415 | -0.23537 | 0.89279 | 0.40696 | 4.0736 | 6.819 | 5.2021 | 5.0755 | 4.8464 | 2.5539 | 18.522 | 16.6759 | 18.522
1305 | 0.22932 | 0.89641 | 0.59069 | 0.81498 | 3.1725 | 5.5422 | 5.4701 | 6.008 | 5.9836 | 2.2333 | 16.956 | 16.8595 | 16.956
1306 | 0.12891 | -1.1399 | 0.55129 | 0.12716 | 3.5177 | 5.4155 | 7.4115 | 4.5152 | 3.4672 | 2.0054 | 15.4538 | 16.4018 | 16.4018
1307 | -0.28195 | 0.010704 | 0.38899 | 0.50427 | 4.1751 | 4.9152 | 6.1475 | 5.2637 | 3.1939 | 1.2255 | 15.5795 | 14.742 | 15.5795
1308 | -1.2726 | -0.3589 | 0.10158 | 0.35983 | 3.4851 | 3.9253 | 5.4749 | 4.9861 | 3.9058 | 1.4478 | 13.8443 | 14.3136 | 14.3136
1309 | -0.88182 | -0.39263 | 0.18894 | 0.3473 | 3.3264 | 4.2709 | 4.9977 | 4.9623 | 5.8569 | 1.8115 | 14.3711 | 15.9925 | 15.9925
1310 | 1.3796 | -0.13994 | 0.91614 | 0.44435 | 3.9261 | 6.9819 | 6.5335 | 5.147 | 4.6432 | 2.1279 | 18.183 | 17.2308 | 18.183
1311 | 0.46432 | 1.49 | 0.67879 | 0.93188 | 3.6164 | 5.8424 | 6.8504 | 6.5067 | 4.169 | 1.4568 | 17.4223 | 16.0925 | 17.4223
1312 | -0.1305 | 0.040038 | 0.44809 | 0.51597 | 3.8632 | 5.0954 | 5.3931 | 5.2869 | 4.4582 | 1.7848 | 16.0303 | 15.4993 | 16.0303
1313 | -0.83273 | -2.112 | 0.2025 | 0.017345 | 2.6549 | 4.3187 | 6.8428 | 4.1741 | 3.783 | 2.0051 | 13.1529 | 15.2858 | 15.2858
1314 | 1.4826 | 1.2682 | 0.9309 | 0.89763 | 4.0804 | 7.1 | 4.7026 | 6.3244 | 3.5567 | 2.2613 | 19.7661 | 14.601 | 19.7661
1315 | -0.77067 | -1.1399 | 0.22045 | 0.12717 | 4.6509 | 4.3806 | 5.8845 | 4.5153 | 5.0724 | 1.7604 | 15.3071 | 17.3682 | 17.3682
1316 | 0.13455 | 0.39557 | 0.55352 | 0.65379 | 4.3261 | 5.4225 | 5.5615 | 5.5787 | 4.512 | 2.2701 | 17.5975 | 16.6697 | 17.5975
1317 | 0.30964 | -0.42881 | 0.62158 | 0.33403 | 3.941 | 5.6444 | 6.6839 | 4.9371 | 3.4725 | 1.795 | 16.3174 | 15.8924 | 16.3174
1318 | -1.238 | -0.95562 | 0.10786 | 0.16963 | 3.9113 | 3.9533 | 7.4376 | 4.6105 | 4.5123 | 1.9494 | 14.4245 | 17.8106 | 17.8106
1319 | 1.3641 | -0.29042 | 0.91374 | 0.38575 | 4.1533 | 6.9639 | 4.4644 | 5.0352 | 4.1639 | 1.2886 | 17.441 | 14.0702 | 17.441
1320 | -1.3363 | -1.142 | 0.090727 | 0.12673 | 3.5436 | 3.8752 | 6.7286 | 4.5142 | 3.0617 | 2.1983 | 14.1313 | 15.5322 | 15.5322
1321 | 0.70373 | 2.2452 | 0.7592 | 0.98762 | 5.0963 | 6.1494 | 6.0505 | 7.0601 | 3.5426 | 1.5008 | 19.8066 | 16.1902 | 19.8066
1322 | -0.79556 | -0.49336 | 0.21314 | 0.31088 | 4.7537 | 4.3556 | 4.9765 | 4.8929 | 3.054 | 2.0266 | 16.0288 | 14.8107 | 16.0288
1323 | -1.4661 | -1.3852 | 0.071314 | 0.082993 | 4.3366 | 3.7784 | 4.2827 | 4.4042 | 4.6961 | 1.8965 | 14.4157 | 15.2119 | 15.2119
1324 | 1.5343 | 0.67172 | 0.93752 | 0.74912 | 4.587 | 7.1582 | 5.1716 | 5.8143 | 3.6735 | 1.6461 | 19.2056 | 15.0782 | 19.2056
1325 | 0.15203 | 0.54839 | 0.56042 | 0.70829 | 4.6963 | 5.4445 | 5.7378 | 5.7085 | 3.7165 | 2.6321 | 18.4814 | 16.7826 | 18.4814
1326 | 1.363 | 1.938 | 0.91356 | 0.97369 | 4.6172 | 6.9626 | 4.9081 | 6.8499 | 3.3977 | 1.8571 | 20.2866 | 14.7799 | 20.2866
1327 | -0.69059 | -0.61887 | 0.24491 | 0.268 | 3.3185 | 4.4626 | 3.9278 | 4.8103 | 3.9013 | 2.3209 | 14.9123 | 13.4686 | 14.9123
1328 | 0.44522 | 0.58289 | 0.67192 | 0.72002 | 3.566 | 5.8179 | 5.0332 | 5.738 | 4.1274 | 2.1551 | 17.2771 | 14.8818 | 17.2771
1329 | 0.3205 | 0.58053 | 0.62571 | 0.71922 | 3.9994 | 5.6582 | 3.9372 | 5.736 | 4.2099 | 2.6462 | 18.0398 | 14.7927 | 18.0398
1330 | -0.26912 | -1.8772 | 0.39392 | 0.030247 | 4.1785 | 4.9303 | 6.6949 | 4.2334 | 5.8046 | 2.2123 | 15.5545 | 18.8904 | 18.8904
1331 | -2.417 | -2.2388 | 0.0078255 | 0.012585 | 4.7088 | 3.2816 | 3.0376 | 4.1473 | 5.2871 | 1.9164 | 14.054 | 14.9499 | 14.9499
1332 | -2.0846 | -1.5105 | 0.018554 | 0.065463 | 3.1731 | 3.4152 | 5.0645 | 4.3543 | 5.6373 | 2.2186 | 13.1613 | 16.0936 | 16.0936
1333 | -1.3433 | 0.057689 | 0.089585 | 0.523 | 3.1972 | 3.8697 | 5.2789 | 5.3009 | 4.5938 | 2.5981 | 14.966 | 15.6681 | 15.6681
1334 | 0.20114 | 1.3672 | 0.57971 | 0.91421 | 3.6632 | 5.5065 | 6.6162 | 6.4066 | 4.7926 | 2.0499 | 17.6262 | 17.1219 | 17.6262
1335 | -0.56008 | 0.37149 | 0.28771 | 0.64486 | 3.8413 | 4.6012 | 4.66 | 5.5585 | 4.6605 | 2.0496 | 16.0506 | 15.2115 | 16.0506
1336 | 0.11447 | -1.2202 | 0.54557 | 0.1112 | 4.5949 | 5.3973 | 6.4822 | 4.4769 | 4.1592 | 2.4666 | 16.9357 | 17.7029 | 17.7029
1337 | 1.1781 | 2.3393 | 0.88062 | 0.99034 | 4.524 | 6.7427 | 5.2888 | 7.1198 | 5.1974 | 2.2244 | 20.6109 | 17.2346 | 20.6109
1338 | -0.80668 | -0.6222 | 0.20993 | 0.2669 | 4.5972 | 4.3445 | 4.5645 | 4.8082 | 3.2206 | 2.683 | 16.4329 | 15.0653 | 16.4329
1339 | -0.24457 | -0.42286 | 0.4034 | 0.3362 | 5.341 | 4.9592 | 6.1455 | 4.9412 | 3.5924 | 1.5064 | 16.7477 | 16.5854 | 16.7477
1340 | -2.1003 | -1.4372 | 0.017851 | 0.075336 | 3.674 | 3.408 | 4.6853 | 4.383 | 6.6 | 2.2121 | 13.677 | 17.1713 | 17.1713
1341 | 1.1061 | -0.28043 | 0.86566 | 0.38957 | 5.4736 | 6.6549 | 7.2096 | 5.0425 | 3.5839 | 2.5043 | 19.6753 | 18.7715 | 19.6753
1342 | 0.7849 | 2.1975 | 0.78375 | 0.98601 | 2.6912 | 6.2529 | 4.8892 | 7.0289 | 3.3919 | 1.8236 | 17.7966 | 12.7959 | 17.7966
1343 | 1.8802 | 1.3365 | 0.96996 | 0.90931 | 4.7113 | 7.5247 | 6.2582 | 6.3812 | 4.7883 | 2.2612 | 20.8783 | 18.019 | 20.8783
1344 | -1.3204 | -0.27315 | 0.093354 | 0.39237 | 4.4176 | 3.8875 | 7.1564 | 5.0478 | 4.2608 | 2.1424 | 15.4953 | 17.9772 | 17.9772
1345 | 0.31899 | -1.3264 | 0.62513 | 0.09235 | 5.3193 | 5.6563 | 7.2489 | 4.4292 | 4.2771 | 1.5419 | 16.9467 | 18.3872 | 18.3872
1346 | -0.18421 | 0.19624 | 0.42692 | 0.57779 | 3.1068 | 5.0309 | 4.2075 | 5.4129 | 5.1575 | 1.9073 | 15.4579 | 14.379 | 15.4579
1347 | 0.86594 | 0.69723 | 0.80674 | 0.75717 | 4.6323 | 6.3557 | 4.6598 | 5.8363 | 3.4164 | 1.5396 | 18.3638 | 14.2481 | 18.3638
1348 | -0.30809 | -1.182 | 0.37901 | 0.11861 | 4.9678 | 4.8847 | 6.0777 | 4.4949 | 4.2716 | 2.3593 | 16.7068 | 17.6764 | 17.6764
1349 | 0.050364 | -0.31794 | 0.52008 | 0.37527 | 3.9765 | 5.3173 | 6.3118 | 5.0153 | 4.4632 | 2.1065 | 16.4156 | 16.858 | 16.858
1350 | -0.23472 | -2.3619 | 0.40721 | 0.0090909 | 3.3455 | 4.9708 | 5.9123 | 4.1244 | 4.2803 | 2.4087 | 14.8494 | 15.9467 | 15.9467
1351 | -1.6894 | -0.41822 | 0.045573 | 0.33789 | 3.4332 | 3.6289 | 7.6395 | 4.9444 | 3.7774 | 1.7283 | 13.7347 | 16.5783 | 16.5783
1352 | 0.59951 | 0.76067 | 0.72558 | 0.77657 | 4.0634 | 6.0159 | 7.0739 | 5.891 | 3.6864 | 1.2658 | 17.236 | 16.0894 | 17.236
1353 | 0.062515 | -0.75506 | 0.52492 | 0.22511 | 3.2614 | 5.3324 | 6.5161 | 4.7255 | 3.8308 | 2.7087 | 16.0281 | 16.317 | 16.317
1354 | -0.88934 | -1.4793 | 0.18691 | 0.069523 | 3.8229 | 4.2636 | 5.5208 | 4.3663 | 3.0953 | 1.4303 | 13.8831 | 13.8692 | 13.8831
1355 | -0.919 | -1.7635 | 0.17905 | 0.038911 | 4.3532 | 4.2353 | 5.1158 | 4.267 | 3.5387 | 1.5051 | 14.3606 | 14.5128 | 14.5128
1356 | 1.4391 | 0.25801 | 0.92494 | 0.6018 | 4.444 | 7.0506 | 4.701 | 5.4638 | 5.9471 | 2.3752 | 19.3336 | 17.4674 | 19.3336
1357 | -1.456 | -1.814 | 0.0727 | 0.034838 | 3.5402 | 3.7857 | 6.1215 | 4.2517 | 3.6425 | 2.2613 | 13.8388 | 15.5655 | 15.5655
1358 | -0.32396 | 0.11701 | 0.37299 | 0.54658 | 3.6314 | 4.8663 | 4.389 | 5.3485 | 4.6688 | 2.3381 | 16.1843 | 15.0272 | 16.1843
1359 | 1.1993 | 0.66131 | 0.88479 | 0.74579 | 5.3717 | 6.7683 | 7.1347 | 5.8054 | 3.5088 | 1.9439 | 19.8893 | 17.9592 | 19.8893
1360 | 1.6654 | 0.32321 | 0.95208 | 0.62673 | 5.0941 | 7.3019 | 7.081 | 5.518 | 3.5587 | 1.8003 | 19.7143 | 17.5342 | 19.7143
1361 | -0.41562 | -0.87061 | 0.33884 | 0.19198 | 2.341 | 4.7613 | 7.1696 | 4.6578 | 3.67 | 1.5271 | 13.2873 | 14.7078 | 14.7078
1362 | 0.98275 | 0.68855 | 0.83714 | 0.75445 | 3.2907 | 6.5024 | 5.62 | 5.8288 | 3.7664 | 1.687 | 17.3089 | 14.3641 | 17.3089
1363 | -2.5571 | -1.6439 | 0.005278 | 0.0501 | 5.0131 | 3.2364 | 4.8591 | 4.3061 | 4.3382 | 1.8498 | 14.4054 | 16.0601 | 16.0601
1364 | -0.12019 | -1.2853 | 0.45217 | 0.09934 | 4.2873 | 5.1079 | 5.6331 | 4.4473 | 4.4532 | 1.8795 | 15.7219 | 16.2532 | 16.2532
1365 | -0.82571 | -1.3414 | 0.20448 | 0.089896 | 2.9913 | 4.3257 | 5.7552 | 4.4227 | 4.0103 | 1.9503 | 13.69 | 14.7071 | 14.7071
1366 | 0.23839 | -0.38385 | 0.59421 | 0.35054 | 3.6591 | 5.5537 | 6.944 | 4.9684 | 5.7068 | 2.0343 | 16.2155 | 18.3442 | 18.3442
1367 | -1.9327 | -2.4355 | 0.026634 | 0.0074358 | 5.1303 | 3.4899 | 3.9563 | 4.1122 | 3.8042 | 1.9274 | 14.6598 | 14.8182 | 14.8182
1368 | -0.2976 | -0.68191 | 0.383 | 0.24765 | 4.9107 | 4.897 | 6.002 | 4.7704 | 3.5852 | 1.8854 | 16.4636 | 16.3833 | 16.4636
1369 | 0.88071 | 0.58652 | 0.81076 | 0.72124 | 2.4853 | 6.3743 | 3.4579 | 5.7412 | 4.3573 | 1.6405 | 16.2412 | 11.941 | 16.2412
1370 | -0.75018 | -0.93508 | 0.22657 | 0.17487 | 3.278 | 4.4013 | 3.6988 | 4.6217 | 5.1749 | 2.1401 | 14.4412 | 14.2918 | 14.4412
1371 | 0.2384 | 0.59209 | 0.59421 | 0.72311 | 5.0913 | 5.5537 | 3.2919 | 5.7459 | 4.2179 | 1.5199 | 17.9109 | 14.121 | 17.9109
1372 | -0.25355 | -0.74153 | 0.39992 | 0.22918 | 4.9576 | 4.9486 | 3.7495 | 4.7337 | 3.8574 | 1.6898 | 16.3297 | 14.2543 | 16.3297
1373 | 0.45347 | 1.5327 | 0.6749 | 0.93733 | 4.2102 | 5.8284 | 5.1209 | 6.541 | 3.6949 | 1.2985 | 17.8781 | 14.3245 | 17.8781
1374 | -2.5721 | -1.3731 | 0.0050535 | 0.084855 | 4.3445 | 3.2319 | 6.4928 | 4.4092 | 4.0622 | 2.0527 | 14.0384 | 16.9523 | 16.9523
1375 | 0.60522 | 0.58091 | 0.72748 | 0.71935 | 2.9156 | 6.0232 | 3.747 | 5.7364 | 3.7451 | 1.3366 | 16.0117 | 11.7442 | 16.0117
1376 | -0.6723 | -1.9751 | 0.25069 | 0.02413 | 3.3023 | 4.4816 | 5.8057 | 4.2071 | 4.6452 | 2.2442 | 14.2352 | 15.9975 | 15.9975
1377 | 1.6763 | 2.2147 | 0.95317 | 0.98661 | 4.0326 | 7.3136 | 6.3971 | 7.0403 | 3.6956 | 2.5023 | 20.8887 | 16.6276 | 20.8887
1378 | 0.88682 | 1.7456 | 0.81241 | 0.95956 | 3.7024 | 6.382 | 5.5677 | 6.7073 | 4.5861 | 1.8909 | 18.6827 | 15.7472 | 18.6827
1379 | -0.6914 | 0.1633 | 0.24466 | 0.56486 | 4.621 | 4.4617 | 3.6492 | 5.3861 | 4.0868 | 2.6241 | 17.0929 | 14.9811 | 17.0929
1380 | 0.60163 | -0.62792 | 0.72629 | 0.26503 | 4.3338 | 6.0186 | 3.6341 | 4.8045 | 3.5214 | 1.1783 | 16.3352 | 12.6676 | 16.3352
1381 | 0.38428 | 0.20163 | 0.64961 | 0.5799 | 5.0058 | 5.7397 | 5.7078 | 5.4174 | 6.1157 | 1.1862 | 17.3491 | 18.0155 | 18.0155
1382 | -0.13385 | 0.16784 | 0.44676 | 0.56665 | 3.9194 | 5.0914 | 5.3505 | 5.3897 | 4.3073 | 2.2552 | 16.6557 | 15.8324 | 16.6557
1383 | -0.029687 | -0.66766 | 0.48816 | 0.25218 | 4.2634 | 5.2183 | 6.0551 | 4.7793 | 4.5051 | 2.2478 | 16.5088 | 17.0714 | 17.0714
1384 | 0.55922 | 0.84786 | 0.712 | 0.80174 | 2.9103 | 5.9642 | 6.3822 | 5.9662 | 3.5085 | 1.5834 | 16.4239 | 14.3843 | 16.4239
1385 | 0.67743 | 0.64935 | 0.75093 | 0.74194 | 3.4667 | 6.1157 | 4.8304 | 5.7951 | 3.9823 | 2.2625 | 17.6401 | 14.5419 | 17.6401
1386 | 1.8578 | 0.099189 | 0.9684 | 0.53951 | 3.1183 | 7.5022 | 7.529 | 5.3342 | 4.3215 | 2.1986 | 18.1533 | 17.1674 | 18.1533
1387 | -0.02105 | 1.1346 | 0.4916 | 0.87173 | 4.9844 | 5.2289 | 6.0108 | 6.2119 | 3.7487 | 1.7169 | 18.1421 | 16.4609 | 18.1421
1388 | 0.57041 | 0.093655 | 0.7158 | 0.53731 | 4.9639 | 5.9785 | 6.4532 | 5.3297 | 5.3043 | 2.4876 | 18.7597 | 19.209 | 19.209
1389 | 0.71291 | 0.094581 | 0.76205 | 0.53768 | 3.3507 | 6.1611 | 7.1324 | 5.3305 | 3.6219 | 2.0011 | 16.8434 | 16.1062 | 16.8434
1390 | 0.010297 | 0.076626 | 0.50411 | 0.53054 | 3.7429 | 5.2676 | 6.7622 | 5.3161 | 4.0327 | 2.0096 | 16.3361 | 16.5474 | 16.5474
1391 | 0.7781 | 1.2451 | 0.78174 | 0.89345 | 5.3923 | 6.2443 | 4.8893 | 6.305 | 5.1839 | 2.2419 | 20.1835 | 17.7075 | 20.1835
1392 | -1.1659 | -2.4773 | 0.12183 | 0.0066193 | 4.9196 | 4.0133 | 4.4876 | 4.1057 | 4.2468 | 1.1712 | 14.2098 | 14.8252 | 14.8252
1393 | 0.50331 | 0.4015 | 0.69263 | 0.65597 | 4.324 | 5.8924 | 5.0514 | 5.5837 | 4.9637 | 1.5397 | 17.3398 | 15.8788 | 17.3398
1394 | -0.76101 | -0.11772 | 0.22332 | 0.45315 | 3.6189 | 4.3903 | 4.815 | 5.1639 | 3.5556 | 1.9438 | 15.1169 | 13.9332 | 15.1169
1395 | 0.39823 | 0.61899 | 0.65477 | 0.73204 | 3.5442 | 5.7576 | 6.6201 | 5.769 | 3.3229 | 2.0792 | 17.15 | 15.5664 | 17.15
1396 | -1.0285 | -0.41086 | 0.15185 | 0.34059 | 3.5025 | 4.1337 | 5.9762 | 4.9495 | 3.7258 | 2.3541 | 14.9398 | 15.5587 | 15.5587
1397 | -0.35476 | -0.3405 | 0.36139 | 0.36674 | 4.4304 | 4.8308 | 4.3433 | 4.9992 | 3.5828 | 2.0332 | 16.2935 | 14.3897 | 16.2935
1398 | 0.39436 | 2.4652 | 0.65334 | 0.99315 | 4.2308 | 5.7527 | 3.7412 | 7.1961 | 3.3203 | 1.9623 | 19.1418 | 13.2546 | 19.1418
1399 | 1.2935 | -0.38623 | 0.90209 | 0.34966 | 4.5522 | 6.881 | 6.4517 | 4.9668 | 4.1845 | 2.4302 | 18.8301 | 17.6186 | 18.8301
1400 | 0.44892 | -0.90897 | 0.67326 | 0.18168 | 3.9069 | 5.8226 | 4.1038 | 4.6362 | 3.928 | 2.6983 | 17.064 | 14.6371 | 17.064
1401 | -0.40188 | 0.346 | 0.34389 | 0.63533 | 5.2032 | 4.7769 | 5.8553 | 5.5371 | 4.4957 | 2.0259 | 17.5431 | 17.5801 | 17.5801
1402 | 1.376 | 1.1213 | 0.91559 | 0.86892 | 4.4322 | 6.9777 | 6.6875 | 6.2006 | 5.5958 | 2.1953 | 19.8057 | 18.9108 | 19.8057
1403 | -0.85344 | -1.6986 | 0.19671 | 0.044701 | 3.4721 | 4.2984 | 6.5422 | 4.2878 | 5.1898 | 1.7719 | 13.8302 | 16.976 | 16.976
1404 | -1.2896 | -1.5659 | 0.098596 | 0.058689 | 4.7041 | 3.9118 | 3.3268 | 4.3337 | 4.6052 | 1.7336 | 14.6831 | 14.3698 | 14.6831
1405 | -0.29989 | -1.7292 | 0.38213 | 0.041888 | 4.1866 | 4.8943 | 6.7928 | 4.2778 | 3.3275 | 1.8373 | 15.1961 | 16.1442 | 16.1442
1406 | -0.72496 | -0.090072 | 0.23424 | 0.46411 | 4.3634 | 4.4271 | 6.4995 | 5.1851 | 4.6235 | 1.6661 | 15.6417 | 17.1525 | 17.1525
1407 | -1.5578 | 0.17887 | 0.059639 | 0.57098 | 2.486 | 3.7144 | 5.0603 | 5.3987 | 3.9695 | 2.2583 | 13.8575 | 13.7741 | 13.8575
1408 | -1.2774 | -1.3259 | 0.10073 | 0.092437 | 5.0561 | 3.9215 | 5.0539 | 4.4294 | 4.8313 | 1.9837 | 15.3907 | 16.9251 | 16.9251
1409 | -0.57634 | 0.18711 | 0.28219 | 0.57421 | 4.0884 | 4.5836 | 5.6465 | 5.4055 | 5.2439 | 1.7842 | 15.8617 | 16.7631 | 16.7631
1410 | -0.4747 | 0.63338 | 0.3175 | 0.73676 | 4.1046 | 4.695 | 6.1393 | 5.7814 | 3.4795 | 2.1318 | 16.7128 | 15.8551 | 16.7128
1411 | 0.60251 | -0.26882 | 0.72658 | 0.39403 | 5.0695 | 6.0197 | 5.0008 | 5.0509 | 5.9049 | 1.6615 | 17.8016 | 17.6366 | 17.8016
1412 | 0.40596 | 0.96305 | 0.65761 | 0.83224 | 4.5839 | 5.7675 | 5.2824 | 6.0653 | 4.3087 | 2.4963 | 18.9131 | 16.6714 | 18.9131
1413 | 0.38246 | 1.3203 | 0.64894 | 0.90663 | 3.4971 | 5.7374 | 5.6341 | 6.3678 | 3.101 | 1.7111 | 17.3133 | 13.9433 | 17.3133
1414 | 1.2105 | 1.3389 | 0.88696 | 0.90969 | 4.0572 | 6.7819 | 4.1854 | 6.3832 | 5.486 | 2.6751 | 19.8974 | 16.4037 | 19.8974
1415 | -1.3159 | -0.39614 | 0.094098 | 0.346 | 4.2036 | 3.891 | 5.759 | 4.9598 | 3.5042 | 2.083 | 15.1375 | 15.5499 | 15.5499
1416 | 0.51856 | 0.36563 | 0.69797 | 0.64268 | 4.0795 | 5.912 | 6.0792 | 5.5535 | 3.7603 | 1.9582 | 17.5033 | 15.8772 | 17.5033
1417 | 0.91793 | -0.9114 | 0.82067 | 0.18104 | 3.0191 | 6.4212 | 6.4534 | 4.6348 | 4.5443 | 2.325 | 16.4001 | 16.3418 | 16.4001
1418 | -1.855 | -0.41303 | 0.031802 | 0.33979 | 4.7381 | 3.5317 | 7.1505 | 4.948 | 3.5757 | 2.2399 | 15.4576 | 17.7042 | 17.7042
1419 | 0.05441 | -0.32801 | 0.5217 | 0.37145 | 4.0789 | 5.3223 | 6.2985 | 5.0081 | 3.6799 | 2.795 | 17.2043 | 16.8522 | 17.2043
1420 | 0.51419 | 1.3816 | 0.69644 | 0.91645 | 4.3406 | 5.9064 | 5.7169 | 6.4184 | 4.6533 | 1.84 | 18.5054 | 16.5508 | 18.5054
1421 | -0.56502 | 0.0043021 | 0.28603 | 0.50172 | 4.4471 | 4.5958 | 6.5767 | 5.2586 | 3.533 | 2.1023 | 16.4038 | 16.659 | 16.659
1422 | 0.61436 | -0.22218 | 0.73051 | 0.41209 | 3.9935 | 6.0349 | 6.2605 | 5.0853 | 4.6015 | 2.1696 | 17.2834 | 17.0251 | 17.2834
1423 | 0.40461 | 1.9574 | 0.65712 | 0.97485 | 3.8962 | 5.7658 | 6.6036 | 6.8639 | 4.0909 | 2.3913 | 18.917 | 16.9819 | 18.917
1424 | 0.016951 | -0.46533 | 0.50676 | 0.32085 | 3.3805 | 5.2758 | 5.387 | 4.912 | 4.1697 | 1.8489 | 15.4173 | 14.7861 | 15.4173
1425 | -1.5395 | -0.6001 | 0.061837 | 0.27422 | 3.1702 | 3.7268 | 4.7811 | 4.8224 | 4.2873 | 1.583 | 13.3023 | 13.8216 | 13.8216
1426 | 0.2841 | 0.21379 | 0.61183 | 0.58465 | 3.5627 | 5.6118 | 5.3931 | 5.4273 | 3.8354 | 2.5378 | 17.1397 | 15.3291 | 17.1397
1427 | 0.3562 | -1.289 | 0.63916 | 0.098706 | 2.8739 | 5.7038 | 5.5584 | 4.4456 | 3.3418 | 1.9183 | 14.9417 | 13.6924 | 14.9417
1428 | -0.23362 | -1.4718 | 0.40764 | 0.070531 | 3.3572 | 4.9721 | 7.335 | 4.3692 | 3.4275 | 1.4912 | 14.1897 | 15.6109 | 15.6109
1429 | -2.6161 | -1.3181 | 0.0044464 | 0.093731 | 4.5614 | 3.2191 | 5.3293 | 4.4328 | 4.9647 | 1.6309 | 13.8442 | 16.4863 | 16.4863
1430 | -0.44315 | 0.059766 | 0.32883 | 0.52383 | 3.1031 | 4.7303 | 7.0384 | 5.3026 | 4.3635 | 2.4739 | 15.6099 | 16.9788 | 16.9788
1431 | 0.41641 | -0.22663 | 0.66145 | 0.41035 | 3.5082 | 5.7809 | 7.7127 | 5.082 | 4.1674 | 2.6587 | 17.0297 | 18.047 | 18.047
1432 | 0.51207 | 1.4298 | 0.6957 | 0.92361 | 5.4175 | 5.9036 | 4.8322 | 6.4579 | 4.4123 | 2.1917 | 19.9708 | 16.8537 | 19.9708
1433 | -0.085313 | -1.0466 | 0.46601 | 0.14763 | 5.0342 | 5.1502 | 5.2402 | 4.5622 | 4.3352 | 2.1616 | 16.9082 | 16.7713 | 16.9082
1434 | 2.0833 | 2.2354 | 0.98139 | 0.98731 | 4.5597 | 7.7198 | 6.2895 | 7.0538 | 4.5533 | 2.0657 | 21.399 | 17.4682 | 21.399
1435 | -1.5776 | -0.80362 | 0.05733 | 0.21081 | 4.3743 | 3.7011 | 4.8927 | 4.6966 | 3.6221 | 2.7252 | 15.4972 | 15.6143 | 15.6143
1436 | 0.89319 | 0.45637 | 0.81412 | 0.67594 | 4.6466 | 6.3901 | 7.7067 | 5.6301 | 3.5799 | 2.0215 | 18.6883 | 17.9547 | 18.6883
1437 | 1.0551 | 0.55141 | 0.85431 | 0.70932 | 3.6155 | 6.5922 | 5.7241 | 5.7111 | 4.1149 | 1.6638 | 17.5825 | 15.1181 | 17.5825
1438 | -0.74087 | -0.69715 | 0.22938 | 0.24286 | 4.3729 | 4.4108 | 7.3711 | 4.7609 | 6.153 | 1.8876 | 15.4323 | 19.7845 | 19.7845
1439 | 0.75907 | 3.166 | 0.7761 | 0.99923 | 2.6966 | 6.22 | 5.4579 | 7.5432 | 4.5795 | 1.3512 | 17.8111 | 14.0853 | 17.8111
1440 | -0.36153 | 0.51446 | 0.35885 | 0.69654 | 3.9975 | 4.823 | 5.936 | 5.6796 | 3.5074 | 1.8227 | 16.3227 | 15.2636 | 16.3227
1441 | 0.36546 | 0.79205 | 0.64262 | 0.78583 | 4.5631 | 5.7157 | 4.6032 | 5.918 | 4.3228 | 2.6211 | 18.8178 | 16.1101 | 18.8178
1442 | 2.9448 | 2.1772 | 0.99838 | 0.98527 | 2.3849 | 8.3653 | 6.6563 | 7.0155 | 4.8801 | 1.7763 | 19.5421 | 15.6976 | 19.5421
1443 | -0.12026 | 2.689 | 0.45214 | 0.99642 | 2.673 | 5.1078 | 5.0417 | 7.3212 | 5.0844 | 1.9642 | 17.0663 | 14.7634 | 17.0663
1444 | -0.34018 | -0.47775 | 0.36686 | 0.31641 | 2.3586 | 4.8476 | 5.5219 | 4.9035 | 3.459 | 2.0379 | 14.1476 | 13.3774 | 14.1476
1445 | 1.1522 | 1.137 | 0.87539 | 0.87223 | 4.7787 | 6.7113 | 4.3597 | 6.2139 | 4.3747 | 2.6553 | 20.3593 | 16.1685 | 20.3593
1446 | 0.78019 | -0.83081 | 0.78236 | 0.20304 | 3.3712 | 6.2469 | 4.8916 | 4.6807 | 4.7125 | 1.5163 | 15.8151 | 14.4916 | 15.8151
1447 | 0.13567 | -0.27057 | 0.55396 | 0.39336 | 3.4277 | 5.424 | 7.5868 | 5.0497 | 3.4533 | 1.8058 | 15.7071 | 16.2736 | 16.2736
1448 | -1.1697 | -0.21628 | 0.12107 | 0.41439 | 4.1484 | 4.0101 | 4.7496 | 5.0897 | 4.671 | 2.801 | 16.0491 | 16.37 | 16.37
1449 | -0.86858 | 0.062635 | 0.19254 | 0.52497 | 3.5738 | 4.2837 | 3.838 | 5.3049 | 3.9145 | 1.7402 | 14.9026 | 13.0666 | 14.9026
1450 | 0.27238 | -0.26077 | 0.60733 | 0.39713 | 3.0774 | 5.5969 | 5.593 | 5.0568 | 3.1154 | 2.0068 | 15.7379 | 13.7926 | 15.7379
1451 | 1.1352 | 0.49348 | 0.87186 | 0.68916 | 5.2356 | 6.6906 | 5.3272 | 5.6617 | 5.6934 | 1.4562 | 19.0441 | 17.7124 | 19.0441
1452 | 0.019227 | 0.054498 | 0.50767 | 0.52173 | 4.3912 | 5.2786 | 3.6378 | 5.2984 | 3.4365 | 1.7599 | 16.7281 | 13.2254 | 16.7281
1453 | 0.62785 | 0.26403 | 0.73495 | 0.60412 | 4.3699 | 6.0522 | 7.042 | 5.4688 | 4.2568 | 2.6313 | 18.5222 | 18.2999 | 18.5222
1454 | 0.41635 | 0.64367 | 0.66142 | 0.7401 | 3.4628 | 5.7808 | 5.2595 | 5.7902 | 4.3627 | 2.0484 | 17.0822 | 15.1333 | 17.0822
1455 | 1.4915 | 0.24398 | 0.93209 | 0.59638 | 4.4426 | 7.1102 | 6.918 | 5.4522 | 3.8007 | 1.6027 | 18.6077 | 16.7641 | 18.6077
1456 | -1.0538 | 0.98061 | 0.14599 | 0.83661 | 3.8749 | 4.1109 | 5.1708 | 6.0804 | 3.9166 | 2.211 | 16.2772 | 15.1733 | 16.2772
1457 | -0.10743 | -0.53385 | 0.45723 | 0.29672 | 3.3547 | 5.1234 | 7.128 | 4.8658 | 4.0869 | 2.6734 | 16.0173 | 17.243 | 17.243
1458 | -0.1363 | 0.64151 | 0.44579 | 0.7394 | 3.1169 | 5.0884 | 4.468 | 5.7884 | 3.1994 | 1.9167 | 15.9105 | 12.701 | 15.9105
1459 | 0.0029437 | 1.2942 | 0.50117 | 0.9022 | 2.8478 | 5.2585 | 3.7183 | 6.3461 | 4.702 | 2.2823 | 16.7347 | 13.5503 | 16.7347
1460 | 0.77665 | 0.46075 | 0.78132 | 0.67751 | 5.286 | 6.2424 | 6.1398 | 5.6339 | 3.7656 | 2.6454 | 19.8076 | 17.8368 | 19.8076
1461 | 0.62343 | 1.5868 | 0.7335 | 0.94372 | 4.2212 | 6.0466 | 7.5165 | 6.584 | 4.7112 | 1.6438 | 18.4955 | 18.0926 | 18.4955
1462 | -1.5682 | -0.27705 | 0.058413 | 0.39087 | 5.0611 | 3.7073 | 3.752 | 5.0449 | 3.8506 | 2.2635 | 16.0769 | 14.9272 | 16.0769
1463 | -0.27909 | 1.5609 | 0.39009 | 0.94073 | 5.384 | 4.9186 | 7.3937 | 6.5635 | 4.0174 | 2.6712 | 19.5372 | 19.4663 | 19.5372
1464 | -0.67004 | 0.23382 | 0.25141 | 0.59244 | 4.862 | 4.484 | 5.233 | 5.4438 | 4.0342 | 2.2676 | 17.0574 | 16.3967 | 17.0574
1465 | -0.71313 | -0.55451 | 0.23788 | 0.28962 | 3.4942 | 4.4392 | 5.9077 | 4.8521 | 4.0507 | 2.0713 | 14.8568 | 15.5238 | 15.5238
1466 | -0.13163 | -0.2039 | 0.44764 | 0.41921 | 3.9418 | 5.0941 | 4.4857 | 5.0989 | 5.2094 | 1.9204 | 16.0551 | 15.5574 | 16.0551
1467 | -0.032717 | -0.89287 | 0.48695 | 0.18596 | 3.648 | 5.2146 | 6.935 | 4.6452 | 5.3059 | 2.3252 | 15.8329 | 18.2141 | 18.2141
1468 | 0.41006 | -0.1278 | 0.65912 | 0.44915 | 3.4723 | 5.7728 | 5.5371 | 5.1562 | 5.1118 | 2.0552 | 16.4565 | 16.1764 | 16.4565
1469 | -1.4161 | -0.010285 | 0.078374 | 0.4959 | 4.0725 | 3.8148 | 6.0908 | 5.2472 | 5.0073 | 2.0434 | 15.1778 | 17.214 | 17.214
1470 | 1.8541 | 0.85013 | 0.96814 | 0.80237 | 3.6483 | 7.4985 | 6.7512 | 5.9681 | 4.8503 | 1.5245 | 18.6394 | 16.7742 | 18.6394
1471 | 0.74068 | -0.50543 | 0.77056 | 0.30663 | 3.8469 | 6.1966 | 6.5147 | 4.8848 | 3.3139 | 1.9415 | 16.8697 | 15.617 | 16.8697
1472 | -0.5553 | -1.6906 | 0.28935 | 0.045456 | 3.3035 | 4.6064 | 7.0296 | 4.2904 | 4.8155 | 1.8914 | 14.0916 | 17.0399 | 17.0399
1473 | 0.27755 | 0.9707 | 0.60932 | 0.83415 | 2.8681 | 5.6035 | 6.0174 | 6.0719 | 4.8715 | 1.8343 | 16.3777 | 15.5912 | 16.3777
1474 | 1.3112 | 2.2846 | 0.90511 | 0.98883 | 4.422 | 6.9019 | 6.9215 | 7.0854 | 4.7334 | 1.6889 | 20.0981 | 17.7658 | 20.0981
1475 | 0.21096 | -2.2936 | 0.58354 | 0.010906 | 3.8636 | 5.5189 | 5.0182 | 4.1367 | 4.624 | 1.6804 | 15.1997 | 15.1863 | 15.1997
1476 | -1.8449 | -2.2828 | 0.03253 | 0.011221 | 3.6848 | 3.5373 | 5.4092 | 4.1388 | 3.8597 | 1.8953 | 13.2562 | 14.849 | 14.849
1477 | 1.6951 | 0.23973 | 0.95497 | 0.59473 | 3.3029 | 7.3337 | 6.7353 | 5.4487 | 4.4484 | 1.7137 | 17.7989 | 16.2002 | 17.7989
1478 | 0.25916 | 0.58738 | 0.60225 | 0.72153 | 3.1325 | 5.5801 | 6.2172 | 5.7419 | 5.1414 | 1.5847 | 16.0392 | 16.0758 | 16.0758
1479 | -0.39002 | 1.1052 | 0.34826 | 0.86547 | 3.9361 | 4.7904 | 5.7909 | 6.1869 | 3.4906 | 2.6068 | 17.5202 | 15.8244 | 17.5202
1480 | 1.5351 | 1.9403 | 0.93762 | 0.97383 | 4.4995 | 7.159 | 5.3202 | 6.8515 | 4.5211 | 1.406 | 19.9161 | 15.7468 | 19.9161
1481 | 1.9891 | 1.4579 | 0.97665 | 0.92757 | 2.6353 | 7.6312 | 4.4161 | 6.4808 | 5.2062 | 2.7567 | 19.504 | 15.0143 | 19.504
1482 | 1.9219 | 1.1301 | 0.97269 | 0.87078 | 5.5768 | 7.5661 | 6.2039 | 6.208 | 3.9992 | 2.3783 | 21.7292 | 18.1582 | 21.7292
1483 | -2.7067 | -2.2113 | 0.0033983 | 0.013508 | 3.7139 | 3.1946 | 5.8815 | 4.1528 | 4.6613 | 1.7503 | 12.8116 | 16.007 | 16.007
1484 | -1.5116 | -0.69317 | 0.065312 | 0.2441 | 3.9913 | 3.7461 | 7.722 | 4.7634 | 6.2785 | 1.7406 | 14.2414 | 19.7323 | 19.7323
1485 | -0.71472 | -1.4778 | 0.23739 | 0.069726 | 3.6659 | 4.4376 | 6.414 | 4.3669 | 4.5979 | 1.703 | 14.1735 | 16.3809 | 16.3809
1486 | -0.99724 | -0.096377 | 0.15932 | 0.46161 | 4.5563 | 4.1622 | 7.0492 | 5.1803 | 4.1589 | 1.9441 | 15.8429 | 17.7086 | 17.7086
1487 | -0.18974 | -0.95678 | 0.42476 | 0.16934 | 4.1768 | 5.0243 | 6.6299 | 4.6098 | 3.5054 | 1.3953 | 15.2062 | 15.7074 | 15.7074
1488 | -0.3156 | -0.86034 | 0.37615 | 0.1948 | 3.3779 | 4.876 | 5.9234 | 4.6637 | 4.1446 | 2.796 | 15.7136 | 16.2419 | 16.2419
1489 | 0.39337 | 2.5202 | 0.65298 | 0.99413 | 3.6605 | 5.7514 | 5.9003 | 7.228 | 4.1186 | 1.4485 | 18.0885 | 15.1279 | 18.0885
1490 | -0.024999 | -0.46119 | 0.49003 | 0.32233 | 5.1671 | 5.2241 | 4.0542 | 4.9148 | 3.2283 | 2.1473 | 17.4534 | 14.597 | 17.4534
1491 | 0.60524 | -0.13176 | 0.72749 | 0.44759 | 3.7358 | 6.0232 | 6.0029 | 5.1532 | 4.6234 | 2.2929 | 17.2052 | 16.655 | 17.2052
1492 | -1.7849 | -0.69959 | 0.037141 | 0.24209 | 4.269 | 3.5714 | 7.3234 | 4.7594 | 3.7765 | 1.7514 | 14.3513 | 17.1204 | 17.1204
1493 | -0.23294 | -0.61973 | 0.40791 | 0.26772 | 4.613 | 4.9729 | 6.0233 | 4.8097 | 4.7142 | 1.8343 | 16.23 | 17.1848 | 17.1848
1494 | 0.90714 | -0.21742 | 0.81783 | 0.41394 | 4.8739 | 6.4076 | 5.23 | 5.0888 | 4.8947 | 2.5143 | 18.8846 | 17.5128 | 18.8846
1495 | -0.3141 | 0.89746 | 0.37672 | 0.81526 | 2.8215 | 4.8778 | 7.2201 | 6.0089 | 4.1462 | 2.0872 | 15.7953 | 16.275 | 16.275
1496 | 1.1629 | 0.98603 | 0.87756 | 0.83794 | 3.8697 | 6.7242 | 5.2562 | 6.085 | 3.9455 | 2.5985 | 19.2774 | 15.6699 | 19.2774
1497 | -0.48216 | 0.76915 | 0.31485 | 0.7791 | 3.9776 | 4.6867 | 6.7155 | 5.8983 | 5.6373 | 2.4655 | 17.0281 | 18.7958 | 18.7958
1498 | 0.14897 | -1.1919 | 0.55921 | 0.11665 | 4.5448 | 5.4407 | 7.6973 | 4.4902 | 3.6224 | 1.9331 | 16.4088 | 17.7976 | 17.7976
1499 | 0.21703 | -0.40366 | 0.58591 | 0.34323 | 5.2479 | 5.5266 | 7.4655 | 4.9546 | 4.3205 | 2.6174 | 18.3465 | 19.6514 | 19.6514
1500 | 1.1677 | 1.0492 | 0.87854 | 0.85295 | 3.2023 | 6.7301 | 4.0769 | 6.1391 | 5.8359 | 1.479 | 17.5505 | 14.594 | 17.5505
1501 | -1.2905 | -0.61794 | 0.098445 | 0.26831 | 4.2269 | 3.9111 | 6.8939 | 4.8109 | 3.8894 | 2.5664 | 15.5152 | 17.5766 | 17.5766
1502 | -0.85833 | -2.2225 | 0.19535 | 0.013125 | 2.7835 | 4.2937 | 3.8116 | 4.1505 | 4.1146 | 2.388 | 13.6157 | 13.0976 | 13.6157
1503 | -1.6775 | -2.2933 | 0.046725 | 0.010916 | 4.9893 | 3.6363 | 6.2896 | 4.1368 | 4.3956 | 1.9895 | 14.7519 | 17.6639 | 17.6639
1504 | 1.6456 | 0.40305 | 0.95008 | 0.65654 | 3.8571 | 7.2805 | 6.7448 | 5.585 | 3.8411 | 2.0156 | 18.7383 | 16.4587 | 18.7383
1505 | -1.3458 | 0.11663 | 0.089182 | 0.54642 | 4.2225 | 3.8678 | 7.1582 | 5.3482 | 4.7178 | 1.7772 | 15.2157 | 17.8756 | 17.8756
1506 | 0.65576 | 1.0685 | 0.74401 | 0.85736 | 3.6269 | 6.088 | 5.7173 | 6.1556 | 4.0632 | 2.6264 | 18.4969 | 16.0338 | 18.4969
1507 | 0.94088 | 1.2993 | 0.82662 | 0.90308 | 3.1993 | 6.45 | 5.7833 | 6.3503 | 4.4667 | 2.5393 | 18.5389 | 15.9886 | 18.5389
1508 | 1.8285 | 0.56575 | 0.96626 | 0.71422 | 2.8111 | 7.4725 | 6.2946 | 5.7234 | 3.5528 | 2.285 | 18.292 | 14.9436 | 18.292
1509 | 1.3004 | 1.8402 | 0.90326 | 0.96713 | 3.0448 | 6.889 | 7.6559 | 6.7784 | 4.7608 | 2.4473 | 19.1595 | 17.9089 | 19.1595
1510 | -0.33438 | -0.95628 | 0.36905 | 0.16946 | 3.7792 | 4.8543 | 5.2649 | 4.6101 | 5.1148 | 1.8584 | 15.102 | 16.0173 | 16.0173
1511 | 0.47468 | -0.096103 | 0.68249 | 0.46172 | 3.9947 | 5.8556 | 6.623 | 5.1805 | 3.3537 | 1.1268 | 16.1576 | 15.0982 | 16.1576
1512 | 0.4583 | -0.37154 | 0.67663 | 0.35512 | 3.2631 | 5.8346 | 6.5859 | 4.9771 | 3.5383 | 2.4819 | 16.5567 | 15.8692 | 16.5567
1513 | 0.056759 | 0.47489 | 0.52263 | 0.68257 | 4.8446 | 5.3252 | 7.598 | 5.6459 | 4.0964 | 2.0865 | 17.9021 | 18.6254 | 18.6254
1514 | -1.9059 | -1.2317 | 0.02833 | 0.10903 | 4.7962 | 3.504 | 6.2777 | 4.4716 | 5.5947 | 2.2523 | 15.0241 | 18.9209 | 18.9209
1515 | -0.42238 | 0.9465 | 0.33637 | 0.82805 | 3.6704 | 4.7537 | 4.0708 | 6.0511 | 4.8948 | 2.2315 | 16.7067 | 14.8675 | 16.7067
1516 | 0.49036 | 0.24622 | 0.68806 | 0.59724 | 4.284 | 5.8758 | 6.3359 | 5.4541 | 4.6607 | 1.7724 | 17.3862 | 17.053 | 17.3862
1517 | -0.6435 | -0.19039 | 0.25995 | 0.4245 | 3.0923 | 4.5119 | 5.3482 | 5.109 | 3.2996 | 1.7985 | 14.5117 | 13.5386 | 14.5117
1518 | -0.81412 | -1.2506 | 0.20779 | 0.10554 | 4.2247 | 4.3371 | 5.4427 | 4.4629 | 5.3351 | 2.4932 | 15.5179 | 17.4957 | 17.4957
1519 | -0.18766 | -0.45656 | 0.42557 | 0.32399 | 5.1933 | 5.0268 | 6.9315 | 4.918 | 4.9563 | 2.3106 | 17.4486 | 19.3917 | 19.3917
1520 | 1.0576 | 0.19139 | 0.85489 | 0.57589 | 5.2435 | 6.5953 | 6.0106 | 5.409 | 3.9781 | 1.5602 | 18.808 | 16.7924 | 18.808
1521 | 1.091 | -0.029811 | 0.86236 | 0.48811 | 2.8626 | 6.6364 | 5.4362 | 5.2319 | 3.8323 | 1.8185 | 16.5494 | 13.9497 | 16.5494
1522 | -0.87974 | -1.4631 | 0.1895 | 0.071724 | 5.281 | 4.2729 | 5.6897 | 4.3727 | 4.1285 | 2.065 | 15.9915 | 17.1641 | 17.1641
1523 | -0.6851 | 0.16855 | 0.24664 | 0.56693 | 4.4058 | 4.4683 | 6.0505 | 5.3903 | 4.2072 | 2.7067 | 16.9711 | 17.3702 | 17.3702
1524 | 0.18828 | 0.76513 | 0.57467 | 0.7779 | 4.4766 | 5.4902 | 6.4597 | 5.8948 | 3.2594 | 1.9634 | 17.8251 | 16.1592 | 17.8251
1525 | 0.55628 | 0.5537 | 0.71099 | 0.71011 | 3.5581 | 5.9604 | 4.7487 | 5.7131 | 5.0368 | 2.6529 | 17.8845 | 15.9965 | 17.8845
1526 | 2.1835 | 0.65265 | 0.9855 | 0.74301 | 2.4107 | 7.8102 | 5.4298 | 5.7979 | 4.3641 | 2.0087 | 18.0275 | 14.2133 | 18.0275
1527 | 0.35787 | 0.21657 | 0.63978 | 0.58573 | 4.4162 | 5.706 | 6.6608 | 5.4296 | 5.6632 | 2.2272 | 17.779 | 18.9675 | 18.9675
1528 | -0.85872 | -0.1971 | 0.19525 | 0.42187 | 3.2616 | 4.2933 | 5.3982 | 5.1039 | 4.2557 | 1.8647 | 14.5236 | 14.7802 | 14.7802
1529 | 0.41634 | 1.6681 | 0.66142 | 0.95235 | 4.4572 | 5.7808 | 7.3847 | 6.6477 | 4.4269 | 1.8351 | 18.7208 | 18.1039 | 18.7208
1530 | 0.90104 | 1.0306 | 0.81622 | 0.84863 | 4.2293 | 6.3999 | 5.3458 | 6.1232 | 3.6793 | 1.6027 | 18.3551 | 14.8571 | 18.3551
1531 | -0.074237 | 0.29974 | 0.47041 | 0.61781 | 4.0029 | 5.1637 | 3.3613 | 5.4984 | 5.3403 | 1.5189 | 16.184 | 14.2234 | 16.184
1532 | 1.2096 | 1.9773 | 0.88678 | 0.97599 | 4.0822 | 6.7807 | 6.3609 | 6.878 | 3.5366 | 2.563 | 20.3039 | 16.5426 | 20.3039
1533 | -0.82244 | -0.56699 | 0.20541 | 0.28536 | 4.1984 | 4.3289 | 4.7464 | 4.8439 | 4.1427 | 2.1607 | 15.532 | 15.2482 | 15.532
1534 | -0.021486 | 0.91748 | 0.49143 | 0.82056 | 4.5971 | 5.2284 | 5.5905 | 6.0261 | 4.3609 | 1.5188 | 17.3704 | 16.0673 | 17.3704
1535 | -0.038588 | 0.53606 | 0.48461 | 0.70404 | 2.9397 | 5.2074 | 4.1662 | 5.698 | 4.6104 | 2.0437 | 15.8888 | 13.7601 | 15.8888
1536 | 1.1514 | 0.90598 | 0.87522 | 0.81753 | 3.8794 | 6.7103 | 5.4409 | 6.0162 | 4.151 | 2.3915 | 18.9974 | 15.8628 | 18.9974
1537 | 0.043406 | -0.048762 | 0.51731 | 0.48055 | 3.2758 | 5.3086 | 6.52 | 5.2171 | 5.33 | 1.7163 | 15.5178 | 16.8421 | 16.8421
1538 | 0.36489 | -0.35012 | 0.6424 | 0.36312 | 3.9169 | 5.7149 | 4.0132 | 4.9923 | 4.4088 | 2.2658 | 16.89 | 14.6047 | 16.89
1539 | -0.82779 | -1.9494 | 0.20389 | 0.025625 | 4.5304 | 4.3236 | 4.677 | 4.2138 | 5.685 | 2.0437 | 15.1115 | 16.9361 | 16.9361
1540 | 0.35055 | -1.4825 | 0.63704 | 0.069107 | 4.8875 | 5.6966 | 7.2363 | 4.3651 | 3.675 | 1.9525 | 16.9016 | 17.7513 | 17.7513
1541 | -0.12034 | 0.34933 | 0.45211 | 0.63658 | 5.4857 | 5.1077 | 5.0776 | 5.5399 | 4.1627 | 1.5555 | 17.6888 | 16.2816 | 17.6888
1542 | -0.18394 | 0.16684 | 0.42703 | 0.56625 | 3.6578 | 5.0312 | 3.3431 | 5.3889 | 3.9727 | 2.2852 | 16.3632 | 13.2589 | 16.3632
1543 | 0.82447 | 2.1553 | 0.79516 | 0.98443 | 3.8657 | 6.3032 | 4.1869 | 7.0009 | 4.8222 | 1.2375 | 18.4073 | 14.1122 | 18.4073
1544 | -0.07534 | 0.44791 | 0.46997 | 0.67289 | 3.2011 | 5.1624 | 7.3747 | 5.623 | 4.7958 | 2.1143 | 16.1008 | 17.4859 | 17.4859
1545 | 0.13788 | 0.64191 | 0.55483 | 0.73953 | 4.9536 | 5.4267 | 6.4874 | 5.7887 | 5.1437 | 1.3302 | 17.4992 | 17.9149 | 17.9149
1546 | -0.68596 | 1.028 | 0.24637 | 0.84802 | 3.6919 | 4.4674 | 4.0749 | 6.121 | 3.7248 | 1.5791 | 15.8593 | 13.0707 | 15.8593
1547 | 0.70962 | 0.11203 | 0.76103 | 0.5446 | 3.4646 | 6.1569 | 6.4019 | 5.3445 | 4.1062 | 2.2292 | 17.1953 | 16.2019 | 17.1953
1548 | 0.24048 | -0.27825 | 0.59502 | 0.39041 | 4.2133 | 5.5564 | 6.5945 | 5.0441 | 4.3946 | 2.1937 | 17.0075 | 17.3962 | 17.3962
1549 | -0.35724 | 0.25758 | 0.36046 | 0.60164 | 3.3995 | 4.8279 | 4.3328 | 5.4634 | 4.695 | 1.9562 | 15.6471 | 14.3836 | 15.6471
1550 | 1.3498 | -0.85458 | 0.91147 | 0.19639 | 3.616 | 6.9472 | 5.2681 | 4.667 | 4.4337 | 2.5954 | 17.8256 | 15.9132 | 17.8256
1551 | -1.5075 | -0.97636 | 0.065843 | 0.16444 | 4.7442 | 3.749 | 5.4792 | 4.5992 | 5.1521 | 1.8921 | 14.9847 | 17.2676 | 17.2676
1552 | -0.88132 | 0.021763 | 0.18907 | 0.50868 | 3.0205 | 4.2714 | 6.5509 | 5.2724 | 5.4465 | 1.44 | 14.0043 | 16.4579 | 16.4579
1553 | -0.72918 | 0.071761 | 0.23295 | 0.5286 | 4.3666 | 4.4228 | 5.3234 | 5.3122 | 3.684 | 2.4225 | 16.524 | 15.7965 | 16.524
1554 | -1.0918 | -1.0826 | 0.13746 | 0.13949 | 3.928 | 4.0772 | 6.8047 | 4.5438 | 3.8583 | 1.2233 | 13.7723 | 15.8142 | 15.8142
1555 | -0.0061544 | 0.99291 | 0.49754 | 0.83962 | 3.8745 | 5.2473 | 5.6751 | 6.0909 | 3.5018 | 2.1448 | 17.3575 | 15.1962 | 17.3575
1556 | -3.0224 | -1.2571 | 0.0012539 | 0.10435 | 4.0524 | 3.1258 | 5.7992 | 4.4599 | 4.297 | 1.5337 | 13.1718 | 15.6824 | 15.6824
1557 | -2.201 | -0.8875 | 0.013869 | 0.1874 | 2.4338 | 3.3639 | 3.9998 | 4.6482 | 3.6046 | 1.4242 | 11.8702 | 11.4624 | 11.8702
1558 | 0.15153 | -0.4462 | 0.56022 | 0.32773 | 4.4599 | 5.4439 | 5.49 | 4.9251 | 5.1984 | 2.7589 | 17.5878 | 17.9072 | 17.9072
1559 | 1.2969 | 2.0387 | 0.90267 | 0.97926 | 4.0723 | 6.885 | 5.1422 | 6.9213 | 4.1665 | 2.2741 | 20.1527 | 15.6551 | 20.1527
1560 | -2.2902 | -2.7309 | 0.011004 | 0.0031583 | 3.2332 | 3.3279 | 3.2857 | 4.0724 | 5.1721 | 1.8969 | 12.5304 | 13.5879 | 13.5879
1561 | 0.18747 | -0.51912 | 0.57435 | 0.30184 | 4.8277 | 5.4892 | 5.5136 | 4.8756 | 4.209 | 1.772 | 16.9645 | 16.3222 | 16.9645
1562 | -1.8206 | -0.94283 | 0.034335 | 0.17288 | 4.1669 | 3.5509 | 7.3132 | 4.6175 | 5.1026 | 2.4722 | 14.8075 | 19.0549 | 19.0549
1563 | -1.0301 | 0.2435 | 0.15149 | 0.59619 | 4.3137 | 4.1323 | 6.0146 | 5.4518 | 5.3861 | 2.0159 | 15.9136 | 17.7303 | 17.7303
1564 | -0.48482 | -2.0424 | 0.3139 | 0.020555 | 2.8114 | 4.6838 | 6.2176 | 4.1903 | 3.0228 | 1.7197 | 13.4052 | 13.7716 | 13.7716
1565 | 1.3102 | 1.6683 | 0.90494 | 0.95237 | 4.8721 | 6.9006 | 5.3787 | 6.6479 | 4.2116 | 2.5256 | 20.9462 | 16.988 | 20.9462
1566 | 0.1374 | 0.35039 | 0.55464 | 0.63698 | 4.8828 | 5.4261 | 5.4026 | 5.5407 | 3.9361 | 1.9851 | 17.8347 | 16.2066 | 17.8347
1567 | 0.20339 | 0.53975 | 0.58058 | 0.70531 | 3.5082 | 5.5093 | 5.3368 | 5.7011 | 3.3876 | 2.0726 | 16.7913 | 14.3052 | 16.7913
1568 | 1.4127 | 1.2462 | 0.92113 | 0.89366 | 3.2911 | 7.0202 | 4.7708 | 6.306 | 4.9759 | 1.8546 | 18.472 | 14.8925 | 18.472
1569 | -0.89724 | 0.095511 | 0.1848 | 0.53805 | 4.3887 | 4.2561 | 4.2478 | 5.3312 | 3.7505 | 2.1935 | 16.1695 | 14.5805 | 16.1695
1570 | 1.3875 | 0.39457 | 0.91736 | 0.65342 | 4.5864 | 6.9911 | 5.0367 | 5.5779 | 4.6555 | 2.6195 | 19.7749 | 16.8981 | 19.7749
1571 | -0.99242 | 0.078643 | 0.1605 | 0.53134 | 4.3531 | 4.1666 | 6.456 | 5.3177 | 4.1318 | 2.479 | 16.3165 | 17.42 | 17.42
1572 | -0.067639 | 1.194 | 0.47304 | 0.88376 | 3.8134 | 5.1718 | 4.9685 | 6.2621 | 4.7058 | 1.9131 | 17.1605 | 15.4009 | 17.1605
1573 | -0.020782 | 0.59872 | 0.49171 | 0.72532 | 3.5112 | 5.2293 | 6.1115 | 5.7516 | 4.0814 | 2.0053 | 16.4974 | 15.7094 | 16.4974
1574 | 0.31893 | 1.2676 | 0.62511 | 0.89754 | 4.0598 | 5.6562 | 4.5818 | 6.3239 | 3.6778 | 1.7795 | 17.8194 | 14.0988 | 17.8194
1575 | -0.15545 | 1.3566 | 0.43823 | 0.91255 | 3.9866 | 5.0654 | 5.6302 | 6.3979 | 4.2461 | 2.1905 | 17.6403 | 16.0535 | 17.6403
1576 | -1.1386 | 0.044156 | 0.12744 | 0.51761 | 4.2648 | 4.0366 | 4.9153 | 5.2902 | 3.3538 | 2.4038 | 15.9954 | 14.9377 | 15.9954
1577 | 1.8633 | 0.70048 | 0.96879 | 0.75819 | 4.1712 | 7.5077 | 7.1171 | 5.8391 | 4.5764 | 2.4464 | 19.9645 | 18.3112 | 19.9645
1578 | 0.019474 | -0.17335 | 0.50777 | 0.43119 | 5.5033 | 5.279 | 5.3048 | 5.1218 | 5.0286 | 2.7049 | 18.6089 | 18.5417 | 18.6089
1579 | -1.0393 | -0.17881 | 0.14934 | 0.42904 | 4.2268 | 4.124 | 5.7379 | 5.1176 | 4.4223 | 2.3812 | 15.8496 | 16.7681 | 16.7681
1580 | -0.22381 | -0.29507 | 0.41145 | 0.38397 | 3.1273 | 4.9837 | 7.4486 | 5.0318 | 4.0773 | 2.223 | 15.3659 | 16.8762 | 16.8762
1581 | -1.3086 | 1.0353 | 0.09534 | 0.84974 | 4.2193 | 3.8968 | 4.2766 | 6.1272 | 3.747 | 1.9377 | 16.1811 | 14.1806 | 16.1811
1582 | -0.044328 | 0.12913 | 0.48232 | 0.55137 | 3.4117 | 5.2003 | 3.1775 | 5.3583 | 4.4073 | 1.7183 | 15.6887 | 12.7149 | 15.6887
1583 | -0.80206 | -0.12583 | 0.21126 | 0.44993 | 4.2849 | 4.3491 | 3.8856 | 5.1577 | 5.4407 | 2.181 | 15.9728 | 15.7922 | 15.9728
1584 | 1.1062 | 1.2825 | 0.86568 | 0.90016 | 4.263 | 6.6551 | 5.1515 | 6.3363 | 4.5536 | 1.7393 | 18.9937 | 15.7073 | 18.9937
1585 | 0.41258 | 0.20289 | 0.66004 | 0.58039 | 4.7524 | 5.776 | 6.6588 | 5.4184 | 3.2774 | 2.352 | 18.2987 | 17.0406 | 18.2987
1586 | 1.6825 | 0.92451 | 0.95376 | 0.82239 | 3.9942 | 7.3202 | 6.6656 | 6.0322 | 4.2605 | 1.7955 | 19.1421 | 16.716 | 19.1421
1587 | -0.88598 | -0.47572 | 0.18781 | 0.31714 | 3.7514 | 4.2669 | 4.7816 | 4.9049 | 4.5601 | 2.4571 | 15.3803 | 15.5502 | 15.5502
1588 | -0.50707 | 0.45261 | 0.30605 | 0.67459 | 3.6722 | 4.6592 | 5.8923 | 5.627 | 4.3854 | 1.7328 | 15.6911 | 15.6827 | 15.6911
1589 | -0.95455 | 0.00083786 | 0.1699 | 0.50033 | 4.2936 | 4.2018 | 5.4825 | 5.2559 | 4.0487 | 2.1833 | 15.9345 | 16.0081 | 16.0081
1590 | -0.14112 | -0.041234 | 0.44389 | 0.48355 | 3.5747 | 5.0826 | 6.8584 | 5.223 | 3.5926 | 1.871 | 15.7513 | 15.8967 | 15.8967
1591 | 0.45893 | 0.5328 | 0.67686 | 0.70291 | 4.0495 | 5.8354 | 4.1649 | 5.6952 | 3.9045 | 2.577 | 18.1571 | 14.6958 | 18.1571
1592 | -0.80845 | -0.31655 | 0.20941 | 0.37579 | 4.3066 | 4.3428 | 5.5677 | 5.0163 | 4.316 | 1.4247 | 15.0905 | 15.6151 | 15.6151
1593 | -0.29085 | -2.2822 | 0.38558 | 0.011239 | 4.0746 | 4.9048 | 5.3585 | 4.1389 | 5.1176 | 2.0162 | 15.1345 | 16.5668 | 16.5668
1594 | 0.39727 | 0.1546 | 0.65442 | 0.56143 | 3.8645 | 5.7564 | 5.2483 | 5.379 | 3.8336 | 2.3431 | 17.343 | 15.2895 | 17.343
1595 | -0.65661 | -0.86865 | 0.25572 | 0.19252 | 4.9013 | 4.4981 | 6.3975 | 4.6589 | 4.0787 | 1.9459 | 16.0042 | 17.3233 | 17.3233
1596 | 0.77554 | -1.562 | 0.78099 | 0.059142 | 4.1241 | 6.241 | 3.1322 | 4.3351 | 3.1832 | 2.2694 | 16.9697 | 12.709 | 16.9697
1597 | 1.5248 | 1.0598 | 0.93634 | 0.85539 | 3.7928 | 7.1475 | 6.9398 | 6.1482 | 5.5242 | 2.0189 | 19.1074 | 18.2757 | 19.1074
1598 | -0.18286 | 1.3358 | 0.42745 | 0.90919 | 5.3866 | 5.0325 | 5.7649 | 6.3806 | 4.195 | 1.8709 | 18.6706 | 17.2175 | 18.6706
1599 | -1.4575 | -0.62437 | 0.072495 | 0.26619 | 4.1786 | 3.7846 | 5.6449 | 4.8068 | 3.9383 | 2.0459 | 14.8158 | 15.8076 | 15.8076
1600 | 0.31581 | 1.1171 | 0.62393 | 0.86803 | 4.5122 | 5.6522 | 6.5032 | 6.197 | 3.8423 | 1.956 | 18.3175 | 16.8137 | 18.3175
1601 | -0.54557 | -0.93832 | 0.29268 | 0.17404 | 3.4412 | 4.617 | 5.0077 | 4.6199 | 4.1829 | 1.2971 | 13.9752 | 13.9289 | 13.9752
1602 | -0.62931 | -1.3597 | 0.26457 | 0.08697 | 4.128 | 4.5269 | 6.919 | 4.4149 | 4.9181 | 2.311 | 15.3808 | 18.2761 | 18.2761
1603 | 0.053661 | 1.3607 | 0.5214 | 0.91319 | 3.5788 | 5.3214 | 4.0688 | 6.4012 | 4.5253 | 1.9792 | 17.2806 | 14.1521 | 17.2806
1604 | -0.59915 | 0.4775 | 0.27453 | 0.6835 | 3.9111 | 4.559 | 7.3948 | 5.6481 | 4.9982 | 2.2915 | 16.4098 | 18.5958 | 18.5958
1605 | 1.4481 | 0.96582 | 0.9262 | 0.83293 | 4.6253 | 7.0608 | 7.5302 | 6.0677 | 5.5802 | 2.1462 | 19.9 | 19.8819 | 19.9
1606 | -2.1177 | -2.1117 | 0.0171 | 0.017357 | 4.1188 | 3.4001 | 7.3262 | 4.1741 | 4.9435 | 2.7288 | 14.4219 | 19.1173 | 19.1173
1607 | 0.97804 | 0.65766 | 0.83597 | 0.74462 | 4.2092 | 6.4965 | 6.4079 | 5.8022 | 4.4461 | 2.6232 | 19.1311 | 17.6864 | 19.1311
1608 | 0.97898 | -0.60472 | 0.83621 | 0.27268 | 3.8714 | 6.4977 | 6.3216 | 4.8194 | 4.9332 | 2.4519 | 17.6404 | 17.5782 | 17.6404
1609 | -0.79643 | -0.22059 | 0.21289 | 0.41271 | 2.6052 | 4.3547 | 6.5262 | 5.0865 | 3.7427 | 1.8592 | 13.9056 | 14.7333 | 14.7333
1610 | 0.68227 | 0.34896 | 0.75246 | 0.63644 | 4.1815 | 6.1219 | 6.2692 | 5.5395 | 4.1575 | 1.3638 | 17.2067 | 15.9721 | 17.2067
1611 | -0.46406 | -0.58485 | 0.3213 | 0.27932 | 4.3039 | 4.7069 | 6.1285 | 4.8323 | 4.4184 | 2.1901 | 16.0331 | 17.0409 | 17.0409
1612 | 0.027381 | -0.43022 | 0.51092 | 0.33352 | 5.386 | 5.2888 | 6.1556 | 4.9361 | 4.3765 | 1.2606 | 16.8715 | 17.1787 | 17.1787
1613 | -2.7606 | -1.6904 | 0.0028852 | 0.045472 | 4.5873 | 3.1811 | 4.543 | 4.2904 | 3.799 | 1.4563 | 13.5152 | 14.3857 | 14.3857
1614 | 0.84006 | 0.733 | 0.79956 | 0.76822 | 4.8028 | 6.3229 | 5.7318 | 5.8671 | 3.5525 | 1.8154 | 18.8082 | 15.9025 | 18.8082
1615 | 1.2388 | 1.089 | 0.89229 | 0.86192 | 4.4971 | 6.8158 | 4.9795 | 6.1731 | 5.2896 | 1.6551 | 19.1411 | 16.4214 | 19.1411
1616 | 0.72859 | 0.22117 | 0.76687 | 0.58752 | 3.9551 | 6.1811 | 5.9944 | 5.4334 | 4.0784 | 2.4076 | 17.9772 | 16.4354 | 17.9772
1617 | 0.62033 | 0.087103 | 0.73248 | 0.53471 | 4.528 | 6.0426 | 3.8563 | 5.3245 | 5.0892 | 1.9691 | 17.8641 | 15.4425 | 17.8641
1618 | -0.54026 | 0.75611 | 0.29451 | 0.77521 | 3.3806 | 4.6227 | 5.3503 | 5.887 | 4.154 | 1.2734 | 15.1638 | 14.1583 | 15.1638
1619 | -0.317 | -1.7662 | 0.37562 | 0.038685 | 3.3531 | 4.8744 | 7.6744 | 4.2662 | 5.0023 | 2.0967 | 14.5905 | 18.1266 | 18.1266
1620 | -0.13249 | 1.0305 | 0.4473 | 0.84861 | 3.1673 | 5.093 | 5.1052 | 6.1231 | 4.1064 | 1.438 | 15.8214 | 13.8169 | 15.8214
1621 | 0.0038238 | 0.058598 | 0.50153 | 0.52336 | 5.3491 | 5.2596 | 5.9489 | 5.3017 | 5.6997 | 1.8844 | 17.7947 | 18.8821 | 18.8821
1622 | -0.28047 | 1.3166 | 0.38956 | 0.90601 | 2.2692 | 4.917 | 3.2777 | 6.3647 | 3.8372 | 2.5098 | 16.0607 | 11.8938 | 16.0607
1623 | 0.13247 | -0.1841 | 0.55269 | 0.42697 | 3.2082 | 5.4199 | 5.7065 | 5.1137 | 3.6985 | 2.4702 | 16.212 | 15.0835 | 16.212
1624 | 2.3913 | 1.2826 | 0.99161 | 0.90019 | 4.1961 | 7.9849 | 4.4951 | 6.3365 | 5.3349 | 2.235 | 20.7524 | 16.2611 | 20.7524
1625 | -0.0079047 | -1.3581 | 0.49685 | 0.087211 | 4.0016 | 5.2451 | 6.2909 | 4.4156 | 4.2595 | 2.4609 | 16.1232 | 17.0129 | 17.0129
1626 | 0.83346 | 0.048412 | 0.79771 | 0.51931 | 5.1444 | 6.3146 | 7.2723 | 5.2935 | 4.1485 | 1.9961 | 18.7486 | 18.5613 | 18.7486
1627 | 1.8803 | 1.2086 | 0.96996 | 0.88658 | 2.8663 | 7.5248 | 3.7817 | 6.2744 | 5.758 | 1.5795 | 18.2449 | 13.9855 | 18.2449
1628 | -1.3057 | -0.13287 | 0.095824 | 0.44715 | 3.5511 | 3.899 | 6.6805 | 5.1524 | 5.7212 | 1.2575 | 13.86 | 17.2102 | 17.2102
1629 | 0.89593 | -0.11379 | 0.81485 | 0.4547 | 3.4812 | 6.3935 | 4.7027 | 5.1669 | 3.6021 | 2.48 | 17.5216 | 14.266 | 17.5216
1630 | -1.8335 | -2.2245 | 0.033362 | 0.013057 | 2.8719 | 3.5436 | 5.0883 | 4.1501 | 3.4046 | 2.3521 | 12.9177 | 13.7168 | 13.7168
1631 | 0.16926 | 0.4732 | 0.5672 | 0.68197 | 3.5532 | 5.4662 | 6.3194 | 5.6444 | 5.5211 | 2.4128 | 17.0766 | 17.8064 | 17.8064
1632 | 0.031974 | 1.1081 | 0.51275 | 0.86608 | 3.9711 | 5.2944 | 7.0813 | 6.1893 | 3.7055 | 2.0746 | 17.5294 | 16.8325 | 17.5294
1633 | 2.2143 | 0.70613 | 0.9866 | 0.75995 | 2.8628 | 7.8372 | 5.36 | 5.844 | 3.5205 | 2.6281 | 19.172 | 14.3714 | 19.172
1634 | -1.9036 | -0.40662 | 0.028482 | 0.34214 | 3.6999 | 3.5053 | 4.8468 | 4.9525 | 4.34 | 2.5684 | 14.726 | 15.4551 | 15.4551
1635 | 0.41934 | 1.5916 | 0.66251 | 0.94427 | 3.9839 | 5.7847 | 5.1962 | 6.5878 | 3.9432 | 2.0399 | 18.3963 | 15.1632 | 18.3963
1636 | 0.90897 | 1.2521 | 0.81832 | 0.89473 | 4.9026 | 6.4099 | 7.3169 | 6.3109 | 4.0934 | 1.6601 | 19.2835 | 17.9729 | 19.2835
1637 | 0.97343 | 0.0087556 | 0.83483 | 0.50349 | 3.6517 | 6.4907 | 5.7534 | 5.2621 | 5.1619 | 1.7227 | 17.1273 | 16.2897 | 17.1273
1638 | 0.29934 | 1.5646 | 0.61766 | 0.94116 | 4.3252 | 5.6312 | 7.6282 | 6.5665 | 4.1662 | 1.8054 | 18.3282 | 17.925 | 18.3282
1639 | 1.2506 | -0.54791 | 0.89445 | 0.29188 | 4.1807 | 6.8299 | 5.5558 | 4.8565 | 3.3061 | 2.2522 | 18.1193 | 15.2949 | 18.1193
1640 | -0.046379 | -0.22126 | 0.4815 | 0.41244 | 2.4794 | 5.1978 | 7.5448 | 5.086 | 5.4853 | 2.0553 | 14.8184 | 17.5647 | 17.5647
1641 | 0.15877 | 0.76252 | 0.56307 | 0.77713 | 3.6696 | 5.453 | 6.0294 | 5.8926 | 3.9197 | 2.2957 | 17.3109 | 15.9145 | 17.3109
1642 | 0.12757 | 0.021871 | 0.55075 | 0.50872 | 3.703 | 5.4138 | 5.5337 | 5.2725 | 4.6505 | 1.8216 | 16.2109 | 15.7088 | 16.2109
1643 | 1.5099 | -0.12557 | 0.93447 | 0.45004 | 3.6856 | 7.1309 | 6.0128 | 5.1579 | 3.8492 | 2.1084 | 18.0828 | 15.656 | 18.0828
1644 | -0.41325 | -0.83633 | 0.33971 | 0.20149 | 3.7616 | 4.764 | 4.529 | 4.6775 | 4.9346 | 2.3103 | 15.5134 | 15.5355 | 15.5355
1645 | 0.31847 | -0.39285 | 0.62493 | 0.34722 | 3.553 | 5.6556 | 7.6094 | 4.9621 | 3.6143 | 1.7278 | 15.8986 | 16.5046 | 16.5046
1646 | -0.34611 | 0.53344 | 0.36463 | 0.70313 | 4.6946 | 4.8407 | 6.1729 | 5.6957 | 4.0119 | 2.0657 | 17.2967 | 16.945 | 17.2967
1647 | 1.4986 | 1.4331 | 0.93301 | 0.92409 | 4.6418 | 7.1181 | 5.9328 | 6.4606 | 5.3972 | 2.1197 | 20.3402 | 18.0914 | 20.3402
1648 | -0.21273 | -1.0736 | 0.41577 | 0.1415 | 3.2684 | 4.9969 | 6.1077 | 4.5483 | 5.1052 | 1.7997 | 14.6133 | 16.2809 | 16.2809
1649 | 0.108 | 0.6035 | 0.543 | 0.72691 | 3.7588 | 5.3892 | 4.3535 | 5.7557 | 4.7022 | 2.4537 | 17.3574 | 15.2682 | 17.3574
1650 | -0.93355 | 0.084084 | 0.17527 | 0.53351 | 4.1793 | 4.2215 | 6.1553 | 5.322 | 4.7474 | 2.3849 | 16.1077 | 17.4669 | 17.4669
1651 | -1.9917 | 0.034893 | 0.023201 | 0.51392 | 3.6801 | 3.4598 | 6.5422 | 5.2828 | 4.6855 | 1.6444 | 14.0671 | 16.5522 | 16.5522
1652 | -0.40247 | -0.81309 | 0.34367 | 0.20808 | 3.0245 | 4.7762 | 6.0182 | 4.691 | 5.2072 | 2.0304 | 14.5222 | 16.2802 | 16.2802
1653 | -0.61435 | -0.67336 | 0.26949 | 0.25036 | 2.8634 | 4.5428 | 5.2795 | 4.7758 | 3.8034 | 1.7454 | 13.9273 | 13.6917 | 13.9273
1654 | -0.34458 | -0.9064 | 0.3652 | 0.18236 | 4.7259 | 4.8425 | 5.3497 | 4.6376 | 3.6534 | 2.5061 | 16.712 | 16.235 | 16.712
1655 | -0.48108 | -0.43001 | 0.31523 | 0.33359 | 3.8579 | 4.6879 | 6.1318 | 4.9362 | 4.7173 | 2.3685 | 15.8506 | 17.0756 | 17.0756
1656 | -0.8218 | 0.86955 | 0.2056 | 0.80773 | 3.2148 | 4.3295 | 4.661 | 5.9848 | 4.3361 | 1.8596 | 15.3887 | 14.0715 | 15.3887
1657 | -0.65378 | -0.43809 | 0.25663 | 0.33066 | 4.8004 | 4.501 | 7.5773 | 4.9307 | 4.4148 | 2.0287 | 16.2608 | 18.8213 | 18.8213
1658 | -1.0476 | 0.35199 | 0.14741 | 0.63758 | 3.3855 | 4.1165 | 2.685 | 5.5421 | 3.7315 | 1.787 | 14.8311 | 11.589 | 14.8311
1659 | 0.18279 | 0.65367 | 0.57252 | 0.74334 | 4.2019 | 5.4833 | 6.6226 | 5.7988 | 4.5498 | 1.9916 | 17.4757 | 17.3659 | 17.4757
1660 | 0.59179 | -0.54626 | 0.723 | 0.29244 | 3.9277 | 6.006 | 5.8901 | 4.8576 | 5.5846 | 2.364 | 17.1553 | 17.7664 | 17.7664
1661 | -0.47047 | -0.22606 | 0.31901 | 0.41058 | 3.6592 | 4.6997 | 6.0637 | 5.0824 | 4.3275 | 2.3096 | 15.751 | 16.36 | 16.36
1662 | 0.054079 | -1.5733 | 0.52156 | 0.057824 | 3.3042 | 5.3219 | 4.7845 | 4.331 | 4.2538 | 2.3599 | 15.3169 | 14.7023 | 15.3169
1663 | -1.6726 | -0.91057 | 0.047206 | 0.18126 | 3.6176 | 3.6394 | 5.5702 | 4.6353 | 5.7718 | 1.8823 | 13.7746 | 16.842 | 16.842
1664 | -0.21865 | 0.24639 | 0.41346 | 0.59731 | 3.9994 | 4.9899 | 6.8539 | 5.4542 | 4.3621 | 2.7019 | 17.1453 | 17.9172 | 17.9172
1665 | 0.91752 | -0.42487 | 0.82056 | 0.33546 | 4.3258 | 6.4207 | 4.3088 | 4.9398 | 4.8811 | 1.2783 | 16.9645 | 14.794 | 16.9645
1666 | -0.61464 | -0.26455 | 0.2694 | 0.39568 | 4.8945 | 4.5425 | 7.5163 | 5.0541 | 4.1647 | 2.3093 | 16.8003 | 18.8847 | 18.8847
1667 | 1.8911 | 1.703 | 0.9707 | 0.95571 | 3.6949 | 7.5356 | 6.2447 | 6.6747 | 3.3545 | 1.7158 | 19.6209 | 15.0098 | 19.6209
1668 | -0.43471 | -0.80689 | 0.33189 | 0.20986 | 3.3714 | 4.7398 | 6.0692 | 4.6947 | 4.5635 | 2.1564 | 14.9622 | 16.1604 | 16.1604
1669 | -1.3693 | -1.3061 | 0.085447 | 0.095757 | 4.9223 | 3.8498 | 4.3037 | 4.4381 | 3.5072 | 1.7828 | 14.993 | 14.516 | 14.993
1670 | 1.0491 | 0.18794 | 0.85294 | 0.57454 | 4.1906 | 6.5848 | 5.3118 | 5.4062 | 3.6833 | 1.9162 | 18.0977 | 15.1019 | 18.0977
1671 | -0.27498 | -1.0592 | 0.39167 | 0.14476 | 3.7587 | 4.9234 | 6.5431 | 4.5557 | 4.9086 | 1.8201 | 15.0579 | 17.0305 | 17.0305
1672 | -0.12908 | -0.23234 | 0.44865 | 0.40814 | 4.0245 | 5.0971 | 7.1855 | 5.0778 | 4.7599 | 1.5166 | 15.7159 | 17.4864 | 17.4864
1673 | -0.19551 | 0.096601 | 0.4225 | 0.53848 | 4.2943 | 5.0174 | 5.2818 | 5.3321 | 4.0292 | 2.2214 | 16.8651 | 15.8266 | 16.8651
1674 | -2.3986 | -1.9642 | 0.0082281 | 0.024755 | 4.4436 | 3.2879 | 7.4272 | 4.2099 | 3.5125 | 2.215 | 14.1564 | 17.5983 | 17.5983
1675 | 0.17115 | -0.61025 | 0.56795 | 0.27085 | 2.9735 | 5.4686 | 6.1051 | 4.8158 | 4.2752 | 2.2615 | 15.5195 | 15.6154 | 15.6154
1676 | -0.009284 | -0.084939 | 0.4963 | 0.46615 | 4.5595 | 5.2434 | 4.5614 | 5.1891 | 3.1842 | 2.5713 | 17.5633 | 14.8763 | 17.5633
1677 | 0.62628 | -0.25068 | 0.73443 | 0.40103 | 4.7404 | 6.0502 | 3.3407 | 5.0642 | 4.7571 | 2.656 | 18.5108 | 15.4941 | 18.5108
1678 | 0.24288 | -0.21549 | 0.59595 | 0.41469 | 4.7416 | 5.5594 | 5.1808 | 5.0902 | 3.8143 | 1.7255 | 17.1167 | 15.4622 | 17.1167
1679 | -1.3461 | -0.67826 | 0.08914 | 0.2488 | 4.1259 | 3.8676 | 5.1125 | 4.7727 | 3.6988 | 1.0744 | 13.8406 | 14.0115 | 14.0115
1680 | -0.54715 | 0.93228 | 0.29214 | 0.82441 | 4.8929 | 4.6152 | 6.4912 | 6.0389 | 3.9466 | 1.9488 | 17.4957 | 17.2794 | 17.4957
1681 | 0.26308 | 0.75967 | 0.60376 | 0.77628 | 3.7927 | 5.5851 | 7.7537 | 5.8901 | 3.506 | 1.9751 | 17.243 | 17.0275 | 17.243
1682 | 1.5189 | 1.03 | 0.93561 | 0.84849 | 3.6145 | 7.141 | 5.0619 | 6.1227 | 3.2109 | 2.1797 | 19.0579 | 14.067 | 19.0579
1683 | -0.0036935 | 0.65179 | 0.49853 | 0.74273 | 4.1696 | 5.2503 | 6.5892 | 5.7972 | 3.8081 | 1.1708 | 16.3879 | 15.7377 | 16.3879
1684 | 0.057669 | -1.0694 | 0.52299 | 0.14244 | 3.6927 | 5.3264 | 4.5277 | 4.5505 | 5.4558 | 1.4092 | 14.9787 | 15.0854 | 15.0854
1685 | -1.1072 | -0.26967 | 0.13411 | 0.39371 | 4.7337 | 4.0638 | 3.2559 | 5.0503 | 3.9359 | 2.3756 | 16.2235 | 14.3012 | 16.2235
1686 | 0.21824 | 0.47823 | 0.58638 | 0.68376 | 2.7615 | 5.5282 | 4.7103 | 5.6487 | 5.3675 | 2.4156 | 16.354 | 15.255 | 16.354
1687 | -0.23375 | 1.5098 | 0.40759 | 0.93446 | 4.0131 | 4.972 | 6.3218 | 6.5227 | 4.5935 | 2.3506 | 17.8584 | 17.279 | 17.8584
1688 | -0.40516 | 0.19655 | 0.34268 | 0.57791 | 3.8974 | 4.7732 | 5.0578 | 5.4132 | 5.4811 | 1.607 | 15.6909 | 16.0434 | 16.0434
1689 | 1.2752 | -0.42736 | 0.89888 | 0.33456 | 4.7376 | 6.8592 | 4.1812 | 4.9381 | 3.2551 | 1.5462 | 18.081 | 13.72 | 18.081
1690 | 0.49183 | 0.89802 | 0.68858 | 0.81541 | 3.1785 | 5.8777 | 6.4312 | 6.0094 | 5.2195 | 2.2863 | 17.3518 | 17.1154 | 17.3518
1691 | 0.47038 | -0.49789 | 0.68096 | 0.30928 | 5.1327 | 5.8501 | 6.6143 | 4.8899 | 5.3767 | 2.5084 | 18.3811 | 19.632 | 19.632
1692 | -0.33049 | 0.26682 | 0.37051 | 0.6052 | 3.1509 | 4.8588 | 5.4856 | 5.4711 | 3.2652 | 1.8019 | 15.2826 | 13.7036 | 15.2826
1693 | 1.7338 | 0.9443 | 0.95853 | 0.82749 | 3.9309 | 7.3746 | 5.4593 | 6.0492 | 5.0127 | 2.0999 | 19.4546 | 16.5029 | 19.4546
1694 | -0.63915 | -1.4393 | 0.26136 | 0.075038 | 3.7534 | 4.5165 | 6.4357 | 4.3821 | 4.6829 | 2.2413 | 14.8933 | 17.1133 | 17.1133
1695 | -0.46208 | -0.67134 | 0.32201 | 0.251 | 4.3666 | 4.7091 | 7.5132 | 4.777 | 3.5776 | 1.9605 | 15.8132 | 17.4179 | 17.4179
1696 | -0.88502 | -0.1021 | 0.18807 | 0.45934 | 4.003 | 4.2678 | 6.6891 | 5.1759 | 3.8667 | 2.2086 | 15.6553 | 16.7674 | 16.7674
1697 | -0.63922 | -0.87683 | 0.26134 | 0.19029 | 3.3657 | 4.5164 | 4.1967 | 4.6543 | 4.6184 | 2.054 | 14.5904 | 14.2349 | 14.5904
1698 | 0.34156 | -0.88573 | 0.63366 | 0.18788 | 3.9042 | 5.6851 | 5.608 | 4.6492 | 3.7994 | 2.121 | 16.3595 | 15.4326 | 16.3595
1699 | 0.50341 | 0.61163 | 0.69266 | 0.72961 | 5.0391 | 5.8925 | 7.0966 | 5.7627 | 3.9877 | 1.8523 | 18.5466 | 17.9757 | 18.5466
1700 | -1.9428 | -0.40816 | 0.02602 | 0.34158 | 4.525 | 3.4847 | 6.3731 | 4.9514 | 3.312 | 2.5223 | 15.4834 | 16.7325 | 16.7325
1701 | -0.52915 | 0.87055 | 0.29835 | 0.808 | 4.1989 | 4.6349 | 7.7479 | 5.9857 | 5.2243 | 2.7127 | 17.5322 | 19.8838 | 19.8838
1702 | 1.916 | 1.5031 | 0.97232 | 0.93359 | 3.6499 | 7.5602 | 4.591 | 6.5172 | 4.9445 | 1.4274 | 19.1548 | 14.6128 | 19.1548
1703 | 2.2862 | -0.18982 | 0.98888 | 0.42473 | 4.4422 | 7.8986 | 4.354 | 5.1094 | 3.6231 | 2.3911 | 19.8413 | 14.8104 | 19.8413
1704 | -0.63664 | 1.2686 | 0.26218 | 0.8977 | 4.9046 | 4.5191 | 4.8788 | 6.3247 | 3.5787 | 2.278 | 18.0265 | 15.6401 | 18.0265
1705 | -0.48166 | -1.0712 | 0.31502 | 0.14204 | 4.4954 | 4.6873 | 6.543 | 4.5496 | 4.8702 | 2.3013 | 16.0335 | 18.2099 | 18.2099
1706 | 1.09 | 1.541 | 0.86214 | 0.93834 | 4.884 | 6.6352 | 5.414 | 6.5476 | 5.3351 | 2.5424 | 20.6093 | 18.1756 | 20.6093
1707 | 0.023275 | 1.2727 | 0.50928 | 0.89843 | 5.6092 | 5.2837 | 6.9116 | 6.3282 | 4.0928 | 2.1709 | 19.3919 | 18.7845 | 19.3919
1708 | -1.0102 | -1.0113 | 0.1562 | 0.15593 | 2.3719 | 4.1503 | 5.5805 | 4.5806 | 4.6464 | 1.2297 | 12.3325 | 13.8284 | 13.8284
1709 | 0.27927 | 0.11185 | 0.60998 | 0.54453 | 2.7442 | 5.6057 | 4.3075 | 5.3444 | 3.9518 | 1.8924 | 15.5866 | 12.8959 | 15.5866
1710 | 1.0744 | 0.39954 | 0.85868 | 0.65525 | 3.5666 | 6.616 | 4.485 | 5.5821 | 3.243 | 2.1465 | 17.9112 | 13.4411 | 17.9112
1711 | 1.2694 | 0.41659 | 0.89786 | 0.66151 | 3.5453 | 6.8523 | 5.978 | 5.5965 | 4.1975 | 1.9452 | 17.9393 | 15.666 | 17.9393
1712 | -1.7915 | -0.38559 | 0.036607 | 0.3499 | 3.3905 | 3.5676 | 5.4853 | 4.9672 | 6.2148 | 1.9362 | 13.8614 | 17.0268 | 17.0268
1713 | 2.6799 | 0.75236 | 0.99632 | 0.77408 | 3.0803 | 8.1985 | 6.8252 | 5.8838 | 3.9727 | 1.5244 | 18.687 | 15.4026 | 18.687
1714 | 1.1128 | 1.6883 | 0.86711 | 0.95433 | 5.4152 | 6.6632 | 5.44 | 6.6634 | 4.187 | 1.4593 | 20.2011 | 16.5015 | 20.2011
1715 | 1.6211 | 1.086 | 0.9475 | 0.86125 | 3.4759 | 7.2539 | 5.6184 | 6.1705 | 3.8943 | 2.2114 | 19.1117 | 15.2 | 19.1117
1716 | 0.25432 | -0.16767 | 0.60038 | 0.43342 | 3.0021 | 5.5739 | 6.0833 | 5.126 | 3.1645 | 2.276 | 15.9781 | 14.526 | 15.9781
1717 | -1.0232 | -1.3099 | 0.1531 | 0.095111 | 3.2233 | 4.1385 | 4.6399 | 4.4364 | 3.6519 | 2.1401 | 13.9382 | 13.6551 | 13.9382
1718 | -0.98784 | -0.43863 | 0.16162 | 0.33047 | 4.9353 | 4.1708 | 6.0027 | 4.9303 | 3.68 | 1.9923 | 16.0287 | 16.6103 | 16.6103
1719 | 0.95385 | 0.65056 | 0.82992 | 0.74234 | 3.291 | 6.4663 | 7.0595 | 5.7961 | 3.1051 | 1.8406 | 17.394 | 15.2962 | 17.394
1720 | -1.1484 | -0.069186 | 0.12541 | 0.47242 | 4.316 | 4.0282 | 4.0031 | 5.2012 | 3.7365 | 1.4641 | 15.0095 | 13.5196 | 15.0095
1721 | -0.46323 | -0.056396 | 0.3216 | 0.47751 | 3.6778 | 4.7078 | 4.0835 | 5.2112 | 4.0656 | 1.9936 | 15.5903 | 13.8204 | 15.5903
1722 | -0.050713 | 0.29693 | 0.47978 | 0.61674 | 3.8483 | 5.1925 | 6.4875 | 5.4961 | 3.4471 | 2.105 | 16.642 | 15.888 | 16.642
1723 | -1.5736 | -0.75154 | 0.057793 | 0.22616 | 5.3603 | 3.7037 | 7.3966 | 4.7277 | 3.5271 | 2.0892 | 15.8809 | 18.3732 | 18.3732
1724 | -1.5756 | -1.1253 | 0.057555 | 0.13023 | 4.6002 | 3.7024 | 6.1434 | 4.5224 | 4.6169 | 2.6955 | 15.5205 | 18.056 | 18.056
1725 | -0.06952 | 0.71283 | 0.47229 | 0.76203 | 5.1359 | 5.1695 | 6.7923 | 5.8497 | 3.82 | 1.4669 | 17.622 | 17.2151 | 17.622
1726 | -0.14343 | 0.69964 | 0.44297 | 0.75792 | 4.0564 | 5.0798 | 6.998 | 5.8384 | 4.2288 | 1.9217 | 16.8963 | 17.2049 | 17.2049
1727 | 0.87472 | 0.20816 | 0.80914 | 0.58245 | 3.0834 | 6.3668 | 5.3242 | 5.4227 | 3.5674 | 1.709 | 16.5819 | 13.684 | 16.5819
1728 | 1.5917 | 0.25736 | 0.94428 | 0.60155 | 4.6575 | 7.2218 | 5.5469 | 5.4633 | 5.5694 | 2.0707 | 19.4133 | 17.8445 | 19.4133
1729 | 0.73221 | -1.0657 | 0.76798 | 0.14329 | 3.951 | 6.1858 | 6.2647 | 4.5524 | 5.3989 | 1.677 | 16.3662 | 17.2916 | 17.2916
1730 | -0.0068547 | -0.62648 | 0.49727 | 0.2655 | 4.8129 | 5.2464 | 7.379 | 4.8054 | 4.1059 | 2.2669 | 17.1316 | 18.5646 | 18.5646
1731 | -0.55626 | 0.26326 | 0.28902 | 0.60383 | 4.1713 | 4.6053 | 6.979 | 5.4681 | 4.0354 | 1.7592 | 16.0039 | 16.9448 | 16.9448
1732 | -0.19759 | 0.84862 | 0.42168 | 0.80195 | 3.3313 | 5.0149 | 5.2531 | 5.9668 | 3.5044 | 1.7131 | 16.0261 | 13.8019 | 16.0261
1733 | -0.70085 | 0.3259 | 0.2417 | 0.62775 | 4.1697 | 4.4519 | 7.0704 | 5.5202 | 4.0688 | 1.708 | 15.8498 | 17.0168 | 17.0168
1734 | 1.665 | 1.6024 | 0.95205 | 0.94547 | 4.3937 | 7.3015 | 2.7847 | 6.5964 | 4.1898 | 2.4197 | 20.7113 | 13.788 | 20.7113
1735 | -2.029 | -2.0225 | 0.021228 | 0.021563 | 3.1317 | 3.4415 | 5.7877 | 4.1951 | 4.5023 | 1.867 | 12.6353 | 15.2887 | 15.2887
1736 | -0.65951 | 0.72574 | 0.25478 | 0.766 | 4.9243 | 4.495 | 4.8466 | 5.8609 | 3.5697 | 2.5784 | 17.8586 | 15.9191 | 17.8586
1737 | -0.90752 | -0.70038 | 0.18207 | 0.24185 | 3.869 | 4.2462 | 5.6596 | 4.7589 | 4.4935 | 1.6723 | 14.5465 | 15.6945 | 15.6945
1738 | 1.0785 | 0.74018 | 0.85959 | 0.77041 | 5.4389 | 6.621 | 6.1891 | 5.8733 | 3.9749 | 1.939 | 19.8722 | 17.5419 | 19.8722
1739 | -2.5669 | 0.84906 | 0.0051305 | 0.80208 | 4.7808 | 3.2334 | 7.3002 | 5.9672 | 3.4119 | 2.1647 | 16.1461 | 17.6576 | 17.6576
1740 | 1.2467 | 0.93089 | 0.89375 | 0.82405 | 4.6065 | 6.8252 | 6.6267 | 6.0377 | 3.4151 | 2.6621 | 20.1315 | 17.3103 | 20.1315
1741 | -0.05698 | 0.354 | 0.47728 | 0.63833 | 3.9533 | 5.1848 | 5.1746 | 5.5438 | 4.584 | 2.6879 | 17.3697 | 16.3997 | 17.3697
1742 | 0.4372 | 0.8081 | 0.66902 | 0.79048 | 2.9401 | 5.8076 | 6.3105 | 5.9319 | 3.3584 | 2.0034 | 16.6828 | 14.6124 | 16.6828
1743 | -1.758 | -0.63262 | 0.03937 | 0.26349 | 5.0417 | 3.5872 | 6.7028 | 4.8015 | 3.708 | 2.843 | 16.2733 | 18.2955 | 18.2955
1744 | -0.9404 | -1.8103 | 0.17351 | 0.035125 | 4.3132 | 4.215 | 6.7983 | 4.2528 | 5.1997 | 1.36 | 14.141 | 17.6712 | 17.6712
1745 | -0.26282 | 0.0034981 | 0.39634 | 0.5014 | 3.3146 | 4.9377 | 6.9789 | 5.258 | 5.452 | 1.6663 | 15.1766 | 17.4118 | 17.4118
1746 | -0.66902 | -0.1408 | 0.25174 | 0.44401 | 3.4527 | 4.4851 | 4.865 | 5.1463 | 4.7364 | 1.1673 | 14.2514 | 14.2213 | 14.2514
1747 | 0.54171 | 1.1758 | 0.70599 | 0.88017 | 5.1255 | 5.9417 | 6.5073 | 6.2468 | 4.281 | 1.4566 | 18.7706 | 17.3703 | 18.7706
1748 | 1.4848 | 0.96419 | 0.9312 | 0.83252 | 2.912 | 7.1025 | 7.0806 | 6.0663 | 4.032 | 2.0436 | 18.1244 | 16.0682 | 18.1244
1749 | 0.099265 | -1.0415 | 0.53954 | 0.14883 | 4.8398 | 5.3783 | 6.2612 | 4.5648 | 5.223 | 2.1121 | 16.895 | 18.4361 | 18.4361
1750 | -2.1906 | -0.62516 | 0.01424 | 0.26593 | 3.8591 | 3.3683 | 6.4851 | 4.8063 | 3.5099 | 2.3037 | 14.3374 | 16.1578 | 16.1578
1751 | -1.0948 | -1.0607 | 0.13681 | 0.1444 | 3.9628 | 4.0746 | 4.6513 | 4.5549 | 4.9008 | 1.8474 | 14.4397 | 15.3623 | 15.3623
1752 | -1.3406 | -1.2865 | 0.090022 | 0.099143 | 4.2042 | 3.8718 | 4.7535 | 4.4468 | 4.4651 | 2.2565 | 14.7793 | 15.6794 | 15.6794
1753 | 0.63545 | 0.087601 | 0.73743 | 0.5349 | 2.8781 | 6.062 | 3.9586 | 5.3249 | 5.3953 | 1.6172 | 15.8821 | 13.8492 | 15.8821
1754 | 0.31502 | -0.48522 | 0.62363 | 0.31376 | 5.3566 | 5.6512 | 6.511 | 4.8984 | 4.4128 | 1.8057 | 17.7119 | 18.086 | 18.086
1755 | 0.18446 | 0.63603 | 0.57317 | 0.73762 | 4.8601 | 5.4854 | 5.5253 | 5.7837 | 5.2572 | 2.0499 | 18.1791 | 17.6925 | 18.1791
1756 | 0.50551 | -1.1661 | 0.6934 | 0.12178 | 3.1557 | 5.8952 | 5.5695 | 4.5025 | 4.6549 | 2.0409 | 15.5943 | 15.4211 | 15.5943
1757 | 0.34868 | 1.3561 | 0.63633 | 0.91247 | 3.4779 | 5.6942 | 5.6865 | 6.3974 | 3.7534 | 2.1991 | 17.7686 | 15.1169 | 17.7686
1758 | -0.89776 | -0.58834 | 0.18466 | 0.27815 | 2.8705 | 4.2556 | 6.0752 | 4.83 | 4.8489 | 2.0378 | 13.9939 | 15.8325 | 15.8325
1759 | -0.47771 | -0.40205 | 0.31643 | 0.34382 | 3.7626 | 4.6917 | 5.9041 | 4.9557 | 4.6328 | 2.2242 | 15.6342 | 16.5238 | 16.5238
1760 | -1.4564 | -0.97521 | 0.072638 | 0.16473 | 3.7561 | 3.7853 | 6.5041 | 4.5999 | 4.0455 | 2.0553 | 14.1965 | 16.3609 | 16.3609
1761 | 0.77429 | 1.3863 | 0.78062 | 0.91717 | 4.6 | 6.2394 | 5.125 | 6.4223 | 4.793 | 2.0524 | 19.3141 | 16.5704 | 19.3141
1762 | -0.041459 | 0.49026 | 0.48346 | 0.68802 | 3.4427 | 5.2038 | 5.4199 | 5.6589 | 5.177 | 1.6359 | 15.9413 | 15.6755 | 15.9413
1763 | 0.68544 | -0.18602 | 0.75347 | 0.42622 | 4.4889 | 6.126 | 6.731 | 5.1122 | 4.5651 | 1.6508 | 17.378 | 17.4359 | 17.4359
1764 | -0.30937 | -0.36462 | 0.37852 | 0.3577 | 3.2895 | 4.8833 | 4.0201 | 4.982 | 4.1606 | 1.572 | 14.7267 | 13.0423 | 14.7267
1765 | -0.61327 | -0.34107 | 0.26985 | 0.36653 | 3.9205 | 4.544 | 3.7956 | 4.9987 | 3.4476 | 2.063 | 15.5261 | 13.2266 | 15.5261
1766 | 1.3099 | 1.542 | 0.90488 | 0.93847 | 4.5708 | 6.9003 | 4.1335 | 6.5485 | 5.0141 | 1.9026 | 19.9221 | 15.621 | 19.9221
1767 | 0.59484 | 1.2947 | 0.72402 | 0.90229 | 3.583 | 6.0099 | 5.4762 | 6.3465 | 3.5151 | 2.4856 | 18.4251 | 15.06 | 18.4251
1768 | -0.44425 | -0.34018 | 0.32843 | 0.36686 | 4.8217 | 4.7291 | 5.0834 | 4.9994 | 4.6496 | 1.7897 | 16.3399 | 16.3445 | 16.3445
1769 | -1.3177 | -1.3064 | 0.093802 | 0.095703 | 4.6208 | 3.8896 | 6.2719 | 4.4379 | 3.6679 | 1.7177 | 14.6661 | 16.2783 | 16.2783
1770 | -0.34717 | 0.20034 | 0.36423 | 0.57939 | 4.2667 | 4.8395 | 5.178 | 5.4163 | 4.6084 | 2.5317 | 17.0542 | 16.5848 | 17.0542
1771 | -0.45081 | 0.53387 | 0.32606 | 0.70328 | 4.2509 | 4.7217 | 6.186 | 5.6961 | 3.6033 | 1.8235 | 16.4922 | 15.8636 | 16.4922
1772 | 0.85104 | 1.178 | 0.80263 | 0.88061 | 3.4981 | 6.3368 | 4.1601 | 6.2486 | 4.5079 | 2.2591 | 18.3426 | 14.4252 | 18.3426
1773 | -0.050081 | -1.0647 | 0.48003 | 0.1435 | 3.5045 | 5.1933 | 4.695 | 4.5529 | 4.8407 | 2.1259 | 15.3766 | 15.1662 | 15.3766
1774 | 0.58845 | -0.11912 | 0.72189 | 0.45259 | 4.6976 | 6.0017 | 4.5794 | 5.1629 | 4.1912 | 2.4162 | 18.2784 | 15.8845 | 18.2784
1775 | 0.19542 | 0.38585 | 0.57747 | 0.6502 | 5.6697 | 5.4993 | 5.9427 | 5.5705 | 4.8364 | 2.3798 | 19.1193 | 18.8286 | 19.1193
1776 | 0.56354 | -0.15029 | 0.71347 | 0.44027 | 2.9905 | 5.9697 | 5.683 | 5.1392 | 3.9905 | 1.5137 | 15.6131 | 14.1776 | 15.6131
1777 | 0.76868 | -1.2031 | 0.77896 | 0.11447 | 2.7665 | 6.2323 | 7.1378 | 4.4849 | 3.9079 | 2.1527 | 15.6364 | 15.965 | 15.965
1778 | 0.44324 | -0.062326 | 0.6712 | 0.47515 | 3.4287 | 5.8153 | 7.816 | 5.2066 | 3.1971 | 1.6865 | 16.1371 | 16.1284 | 16.1371
1779 | 0.98344 | -0.30069 | 0.8373 | 0.38183 | 3.085 | 6.5032 | 6.2588 | 5.0278 | 4.9935 | 2.4425 | 17.0585 | 16.7797 | 17.0585
1780 | -0.8675 | -0.28013 | 0.19283 | 0.38969 | 2.8529 | 4.2848 | 5.1229 | 5.0427 | 4.6403 | 1.9126 | 14.0929 | 14.5287 | 14.5287
1781 | -0.10146 | -0.43177 | 0.45959 | 0.33295 | 2.8798 | 5.1306 | 5.784 | 4.935 | 3.4768 | 2.0247 | 14.9701 | 14.1652 | 14.9701
1782 | 0.073316 | -0.022294 | 0.52922 | 0.49111 | 3.6049 | 5.3459 | 6.2003 | 5.2377 | 4.4122 | 1.2923 | 15.4808 | 15.5096 | 15.5096
1783 | -1.5853 | -2.5263 | 0.056452 | 0.005764 | 4.4282 | 3.6959 | 5.294 | 4.0984 | 4.9697 | 1.5959 | 13.8185 | 16.2878 | 16.2878
1784 | -1.2361 | -1.0274 | 0.10822 | 0.15211 | 3.9046 | 3.9549 | 6.5552 | 4.5722 | 3.6135 | 1.7745 | 14.2062 | 15.8479 | 15.8479
1785 | 0.7488 | -0.71767 | 0.77301 | 0.23648 | 3.3564 | 6.2069 | 7.0162 | 4.7483 | 3.3239 | 2.1122 | 16.4238 | 15.8087 | 16.4238
1786 | 1.728 | 0.70262 | 0.958 | 0.75885 | 2.9965 | 7.3684 | 5.4094 | 5.8409 | 5.2201 | 1.7599 | 17.9658 | 15.3859 | 17.9658
1787 | 0.27548 | -0.041526 | 0.60853 | 0.48344 | 3.8868 | 5.6008 | 6.069 | 5.2227 | 3.9389 | 1.9456 | 16.6559 | 15.8402 | 16.6559
1788 | -0.44289 | 0.27652 | 0.32892 | 0.60893 | 3.5031 | 4.7306 | 6.3963 | 5.4791 | 3.6351 | 1.7738 | 15.4866 | 15.3082 | 15.4866
1789 | -0.56541 | 0.68492 | 0.2859 | 0.7533 | 4.4458 | 4.5954 | 7.5421 | 5.8257 | 4.4122 | 2.2263 | 17.0932 | 18.6264 | 18.6264
1790 | 0.14371 | -0.37445 | 0.55714 | 0.35403 | 4.5018 | 5.4341 | 5.1476 | 4.9751 | 4.3064 | 2.0226 | 16.9335 | 15.9784 | 16.9335
1791 | 0.89927 | 1.4053 | 0.81575 | 0.92004 | 4.0327 | 6.3977 | 6.8006 | 6.4379 | 4.1618 | 2.3155 | 19.1838 | 17.3106 | 19.1838
1792 | -1.1011 | -0.5174 | 0.13544 | 0.30244 | 3.4171 | 4.0691 | 6.4294 | 4.8768 | 3.3797 | 2.1743 | 14.5373 | 15.4005 | 15.4005
1793 | 0.91766 | -1.2374 | 0.8206 | 0.10798 | 5.4732 | 6.4209 | 5.227 | 4.469 | 5.0929 | 2.1807 | 18.5438 | 17.9739 | 18.5438
1794 | 0.62948 | -1.19 | 0.73548 | 0.11702 | 3.5847 | 6.0543 | 5.3874 | 4.4911 | 3.834 | 1.5586 | 15.6888 | 14.3647 | 15.6888
1795 | 1.6194 | 1.6908 | 0.94732 | 0.95456 | 5.3885 | 7.2521 | 6.1785 | 6.6653 | 3.4092 | 1.6358 | 20.9417 | 16.612 | 20.9417
1796 | 0.23075 | -0.24182 | 0.59124 | 0.40446 | 3.4036 | 5.544 | 5.2212 | 5.0708 | 4.7732 | 2.1869 | 16.2053 | 15.585 | 16.2053
1797 | 0.67421 | 0.90523 | 0.74991 | 0.81733 | 5.207 | 6.1116 | 7.0975 | 6.0156 | 4.0866 | 2.214 | 19.5482 | 18.6051 | 19.5482
1798 | 0.23952 | 0.21747 | 0.59465 | 0.58608 | 3.482 | 5.5551 | 6.1957 | 5.4304 | 5.8443 | 2.2104 | 16.6779 | 17.7324 | 17.7324
1799 | 0.94355 | -0.82666 | 0.8273 | 0.20422 | 3.7896 | 6.4534 | 6.0909 | 4.6831 | 4.4145 | 1.7527 | 16.6787 | 16.0476 | 16.6787
1800 | -0.15241 | -0.65175 | 0.43943 | 0.25728 | 4.9247 | 5.069 | 4.2298 | 4.7894 | 3.8027 | 2.6194 | 17.4025 | 15.5766 | 17.4025
1801 | 0.67931 | -0.43586 | 0.75153 | 0.33147 | 4.1383 | 6.1182 | 6.2186 | 4.9322 | 4.7093 | 1.6123 | 16.801 | 16.6785 | 16.801
1802 | -0.13704 | 0.90297 | 0.4455 | 0.81673 | 3.0587 | 5.0875 | 6.4178 | 6.0136 | 3.2914 | 2.0517 | 16.2115 | 14.8194 | 16.2115
1803 | -0.82245 | -1.0431 | 0.20541 | 0.14846 | 5.0699 | 4.3289 | 5.5969 | 4.564 | 4.1135 | 2.4907 | 16.4536 | 17.2711 | 17.2711
1804 | -1.1785 | -1.1525 | 0.1193 | 0.12455 | 3.5956 | 4.0027 | 5.3329 | 4.5091 | 3.3116 | 2.695 | 14.8023 | 14.9351 | 14.9351
1805 | 1.8619 | 0.76899 | 0.96869 | 0.77905 | 3.374 | 7.5063 | 7.685 | 5.8981 | 4.2463 | 2.2129 | 18.9913 | 17.5181 | 18.9913
1806 | -0.051996 | -0.0045831 | 0.47927 | 0.49817 | 3.4292 | 5.1909 | 6.985 | 5.2516 | 4.0642 | 1.5816 | 15.4533 | 16.06 | 16.06
1807 | 0.089261 | 1.0134 | 0.53556 | 0.84456 | 3.516 | 5.3658 | 6.761 | 6.1085 | 3.884 | 2.1515 | 17.1418 | 16.3126 | 17.1418
1808 | 1.1058 | 1.3508 | 0.8656 | 0.91161 | 3.9074 | 6.6546 | 4.6737 | 6.393 | 3.6094 | 1.8394 | 18.7944 | 14.03 | 18.7944
1809 | 1.0155 | 2.6021 | 0.84507 | 0.99537 | 3.2751 | 6.5431 | 5.8478 | 7.2742 | 5.8609 | 2.3473 | 19.4398 | 17.3311 | 19.4398
1810 | -1.5155 | -0.7484 | 0.064825 | 0.22711 | 3.435 | 3.7435 | 3.2951 | 4.7296 | 5.5799 | 1.9773 | 13.8853 | 14.2873 | 14.2873
1811 | -1.0341 | 0.72236 | 0.15054 | 0.76496 | 2.8289 | 4.1286 | 7.7637 | 5.8579 | 4.236 | 1.3847 | 14.2002 | 16.2133 | 16.2133
1812 | -0.47042 | 0.23116 | 0.31903 | 0.5914 | 4.0757 | 4.6998 | 4.3887 | 5.4416 | 5.6212 | 1.6015 | 15.8187 | 15.6871 | 15.8187
1813 | 1.3406 | 1.7367 | 0.90997 | 0.95878 | 4.0389 | 6.9363 | 3.6812 | 6.7005 | 4.1811 | 1.7159 | 19.3917 | 13.6172 | 19.3917
1814 | -0.2047 | -0.63142 | 0.4189 | 0.26388 | 4.8974 | 5.0064 | 6.2295 | 4.8023 | 5.4615 | 2.3746 | 17.0807 | 18.963 | 18.963
1815 | 0.86757 | -1.2783 | 0.80719 | 0.10057 | 2.9982 | 6.3577 | 6.3365 | 4.4504 | 3.6335 | 1.5284 | 15.3347 | 14.4966 | 15.3347
1816 | 0.36086 | -2.055 | 0.6409 | 0.01994 | 4.7314 | 5.7098 | 7.1058 | 4.1873 | 4.7127 | 1.6425 | 16.271 | 18.1924 | 18.1924
1817 | 1.5555 | 0.74486 | 0.94008 | 0.77182 | 5.1243 | 7.1818 | 4.9181 | 5.8773 | 3.192 | 2.428 | 20.6114 | 15.6624 | 20.6114
1818 | -0.54192 | 0.0085778 | 0.29394 | 0.50342 | 4.5557 | 4.6209 | 6.7366 | 5.262 | 5.8504 | 1.8231 | 16.2617 | 18.9658 | 18.9658
1819 | 1.1618 | -0.34165 | 0.87734 | 0.36631 | 3.6929 | 6.7229 | 5.6166 | 4.9983 | 3.719 | 2.2211 | 17.6352 | 15.2495 | 17.6352
1820 | -0.42386 | -1.0844 | 0.33584 | 0.13908 | 3.903 | 4.752 | 6.313 | 4.5428 | 3.2368 | 1.8479 | 15.0457 | 15.3007 | 15.3007
1821 | -1.4757 | -1.6297 | 0.070018 | 0.051577 | 2.7657 | 3.7715 | 4.3917 | 4.311 | 3.2535 | 1.9452 | 12.7934 | 12.356 | 12.7934
1822 | -0.70081 | -0.58 | 0.24171 | 0.28096 | 4.5672 | 4.452 | 5.6773 | 4.8354 | 5.4943 | 1.6656 | 15.5202 | 17.4044 | 17.4044
1823 | 2.0478 | -0.11949 | 0.97971 | 0.45244 | 3.5497 | 7.6869 | 6.1991 | 5.1626 | 6.1214 | 2.3218 | 18.721 | 18.192 | 18.721
1824 | -1.8482 | -0.76535 | 0.032288 | 0.22203 | 3.4208 | 3.5354 | 6.0585 | 4.7194 | 4.0792 | 1.9309 | 13.6065 | 15.4895 | 15.4895
1825 | -0.32028 | -0.566 | 0.37438 | 0.2857 | 3.7548 | 4.8706 | 5.7977 | 4.8446 | 3.8078 | 2.3527 | 15.8226 | 15.7129 | 15.8226
1826 | -1.2252 | -1.7369 | 0.11025 | 0.041204 | 3.5989 | 3.9638 | 3.657 | 4.2754 | 4.4807 | 2.5637 | 14.4018 | 14.3003 | 14.4018
1827 | -0.31254 | 1.0487 | 0.37732 | 0.85284 | 3.5935 | 4.8796 | 5.5786 | 6.1387 | 5.0452 | 2.3067 | 16.9184 | 16.5239 | 16.9184
1828 | 1.6069 | 2.7908 | 0.94596 | 0.99737 | 4.1781 | 7.2384 | 5.0095 | 7.3737 | 3.8272 | 2.0522 | 20.8424 | 15.067 | 20.8424
1829 | 1.0162 | 1.4425 | 0.84522 | 0.92542 | 4.6659 | 6.544 | 6.5779 | 6.4682 | 4.7804 | 1.8987 | 19.5767 | 17.9228 | 19.5767
1830 | 0.44024 | 1.076 | 0.67012 | 0.85904 | 3.3864 | 5.8115 | 3.7234 | 6.162 | 3.6231 | 2.2223 | 17.5822 | 12.9552 | 17.5822
1831 | -1.0411 | -1.2768 | 0.14891 | 0.10083 | 2.667 | 4.1223 | 5.6293 | 4.4511 | 3.9857 | 1.8942 | 13.1346 | 14.1762 | 14.1762
1832 | -0.63836 | 0.47717 | 0.26162 | 0.68338 | 4.3792 | 4.5173 | 5.3239 | 5.6478 | 3.5952 | 1.8814 | 16.4257 | 15.1797 | 16.4257
1833 | 1.2624 | 1.1073 | 0.89659 | 0.86591 | 3.8426 | 6.8439 | 6.0618 | 6.1886 | 4.3575 | 1.9241 | 18.7993 | 16.1861 | 18.7993
1834 | -0.34107 | -0.47614 | 0.36652 | 0.31699 | 3.8253 | 4.8465 | 4.1859 | 4.9046 | 3.7301 | 2.1308 | 15.7072 | 13.8721 | 15.7072
1835 | 0.27973 | 0.26206 | 0.61016 | 0.60336 | 4.1035 | 5.6062 | 4.4162 | 5.4672 | 3.2788 | 1.6208 | 16.7977 | 13.4193 | 16.7977
1836 | -1.5837 | -2.1275 | 0.056631 | 0.016689 | 4.5619 | 3.697 | 4.6608 | 4.1706 | 4.2577 | 1.7595 | 14.189 | 15.2399 | 15.2399
1837 | -0.37029 | 0.61762 | 0.35558 | 0.73159 | 3.8776 | 4.813 | 5.9519 | 5.7678 | 5.2127 | 1.4955 | 15.9539 | 16.5377 | 16.5377
1838 | 1.0501 | 1.8796 | 0.85317 | 0.96992 | 3.0361 | 6.5861 | 4.2461 | 6.8074 | 4.5868 | 1.4341 | 17.8636 | 13.3031 | 17.8636
1839 | -1.3174 | -0.16579 | 0.09385 | 0.43416 | 2.9438 | 3.8898 | 6.088 | 5.1274 | 4.5117 | 1.9944 | 13.9555 | 15.5379 | 15.5379
1840 | 1.6136 | 1.2803 | 0.94669 | 0.89977 | 5.2697 | 7.2457 | 5.9009 | 6.3345 | 4.6054 | 2.2227 | 21.0726 | 17.9986 | 21.0726
1841 | 1.0394 | 0.46903 | 0.8507 | 0.68048 | 3.8971 | 6.5728 | 7.1622 | 5.6409 | 5.1611 | 2.2455 | 18.3563 | 18.4659 | 18.4659
1842 | -0.30879 | -0.10797 | 0.37874 | 0.45701 | 2.85 | 4.8839 | 6.4233 | 5.1714 | 4.6355 | 1.906 | 14.8114 | 15.8148 | 15.8148
1843 | 0.49668 | 0.75823 | 0.69029 | 0.77584 | 2.7261 | 5.8839 | 6.5811 | 5.8889 | 3.3945 | 2.7019 | 17.2007 | 15.4036 | 17.2007
1844 | -1.3402 | -0.1845 | 0.090098 | 0.42681 | 3.4448 | 3.8722 | 5.4853 | 5.1134 | 3.9421 | 2.1998 | 14.6302 | 15.072 | 15.072
1845 | 1.0566 | -0.47161 | 0.85466 | 0.3186 | 3.3777 | 6.5941 | 6.7241 | 4.9077 | 3.6903 | 2.0955 | 16.975 | 15.8877 | 16.975
1846 | -0.25614 | -0.2639 | 0.39892 | 0.39593 | 3.3114 | 4.9455 | 6.0976 | 5.0545 | 4.3017 | 2.0182 | 15.3297 | 15.7289 | 15.7289
1847 | 0.1751 | 0.032233 | 0.5695 | 0.51286 | 3.5104 | 5.4736 | 7.2078 | 5.2807 | 3.8796 | 1.9892 | 16.2539 | 16.587 | 16.587
1848 | -0.75549 | -1.2036 | 0.22498 | 0.11438 | 3.9558 | 4.3959 | 5.4277 | 4.4847 | 5.9682 | 1.6318 | 14.4682 | 16.9835 | 16.9835
1849 | -0.46591 | 0.53501 | 0.32064 | 0.70368 | 5.1069 | 4.7048 | 6.7407 | 5.6971 | 4.9862 | 1.947 | 17.4558 | 18.7807 | 18.7807
1850 | -1.2452 | -1.0679 | 0.10652 | 0.14278 | 2.74 | 3.9474 | 7.2273 | 4.5512 | 3.7053 | 2.6058 | 13.8444 | 16.2784 | 16.2784
1851 | -0.04735 | 0.51353 | 0.48112 | 0.69621 | 4.9159 | 5.1966 | 6.1724 | 5.6788 | 4.5258 | 2.6456 | 18.4369 | 18.2597 | 18.4369
1852 | 0.93431 | -0.29892 | 0.82493 | 0.3825 | 4.52 | 6.4418 | 2.7124 | 5.029 | 5.2268 | 1.557 | 17.5478 | 14.0163 | 17.5478
1853 | -2.1908 | -2.4564 | 0.014231 | 0.0070165 | 4.4324 | 3.3682 | 5.5274 | 4.1089 | 3.9864 | 2.2087 | 14.1182 | 16.1549 | 16.1549
1854 | -1.2015 | -1.0896 | 0.11477 | 0.13795 | 5.063 | 3.9834 | 5.4824 | 4.5402 | 4.4844 | 1.9073 | 15.4939 | 16.9372 | 16.9372
1855 | 1.7742 | -0.22733 | 0.96199 | 0.41008 | 4.2026 | 7.4168 | 5.4106 | 5.0815 | 4.3566 | 2.2997 | 19.0005 | 16.2694 | 19.0005
1856 | 0.76512 | 1.1136 | 0.7779 | 0.86727 | 2.9991 | 6.2277 | 4.8725 | 6.194 | 5.2234 | 2.2683 | 17.6891 | 15.3633 | 17.6891
1857 | 0.49028 | 0.19384 | 0.68803 | 0.57685 | 4.8859 | 5.8757 | 4.2038 | 5.411 | 3.9115 | 2.6248 | 18.7974 | 15.6261 | 18.7974
1858 | 2.5482 | 2.0696 | 0.99459 | 0.98076 | 3.6776 | 8.1052 | 6.1383 | 6.9427 | 4.1831 | 2.3298 | 21.0553 | 16.3287 | 21.0553
1859 | -1.5895 | -0.66829 | 0.055972 | 0.25197 | 3.5866 | 3.6931 | 5.3177 | 4.7789 | 5.5047 | 2.1528 | 14.2114 | 16.5617 | 16.5617
1860 | -1.5361 | -0.24925 | 0.062254 | 0.40158 | 2.7716 | 3.7292 | 5.1841 | 5.0653 | 4.4781 | 2.0333 | 13.5994 | 14.4671 | 14.4671
1861 | 0.92095 | 2.7311 | 0.82146 | 0.99684 | 4.0021 | 6.425 | 6.0755 | 7.3433 | 4.9063 | 2.2938 | 20.0642 | 17.2777 | 20.0642
1862 | -0.98959 | -0.62607 | 0.16119 | 0.26564 | 4.1774 | 4.1692 | 7.5072 | 4.8057 | 5.1097 | 1.7866 | 14.9389 | 18.5809 | 18.5809
1863 | -1.2575 | -1.6194 | 0.10429 | 0.052677 | 4.6426 | 3.9375 | 6.1664 | 4.3146 | 3.7057 | 2.392 | 15.2867 | 16.9068 | 16.9068
1864 | -0.45985 | -0.2554 | 0.32281 | 0.39921 | 5.5486 | 4.7116 | 7.2864 | 5.0608 | 5.4167 | 2.1452 | 17.4661 | 20.3969 | 20.3969
1865 | -1.0103 | 0.9147 | 0.15618 | 0.81983 | 3.8551 | 4.1503 | 4.835 | 6.0237 | 3.7573 | 2.1036 | 16.1327 | 14.551 | 16.1327
1866 | -1.3037 | -1.6514 | 0.096175 | 0.049333 | 5.3127 | 3.9006 | 6.5121 | 4.3035 | 3.9034 | 2.6207 | 16.1376 | 18.3489 | 18.3489
1867 | 0.83265 | 0.98954 | 0.79748 | 0.8388 | 3.739 | 6.3135 | 4.3448 | 6.088 | 4.8532 | 2.512 | 18.6525 | 15.4489 | 18.6525
1868 | 0.34379 | -1.0305 | 0.6345 | 0.15138 | 4.0531 | 5.688 | 6.3135 | 4.5705 | 4.8682 | 1.7308 | 16.0424 | 16.9655 | 16.9655
1869 | -0.91765 | -1.247 | 0.1794 | 0.1062 | 3.3629 | 4.2366 | 5.652 | 4.4646 | 5.1358 | 1.9169 | 13.981 | 16.0676 | 16.0676
1870 | -0.70872 | 0.056765 | 0.23925 | 0.52263 | 4.1367 | 4.4438 | 6.8117 | 5.3002 | 5.2171 | 1.9623 | 15.843 | 18.1278 | 18.1278
1871 | -1.7659 | -0.20692 | 0.038705 | 0.41803 | 4.3792 | 3.5825 | 5.4057 | 5.0966 | 4.2548 | 2.3222 | 15.3805 | 16.3618 | 16.3618
1872 | -0.74851 | -0.5284 | 0.22708 | 0.29861 | 4.2444 | 4.403 | 6.7239 | 4.8694 | 3.1222 | 1.9772 | 15.494 | 16.0677 | 16.0677
1873 | -0.88452 | -0.81778 | 0.18821 | 0.20674 | 4.0089 | 4.2683 | 5.7343 | 4.6883 | 4.1149 | 1.2938 | 14.2592 | 15.1518 | 15.1518
1874 | -1.3392 | -0.13354 | 0.090258 | 0.44688 | 3.7607 | 3.8729 | 5.5624 | 5.1519 | 3.6883 | 1.7312 | 14.5166 | 14.7424 | 14.7424
1875 | 0.016968 | 0.26127 | 0.50677 | 0.60306 | 4.5194 | 5.2759 | 2.9585 | 5.4665 | 3.977 | 2.805 | 18.0668 | 14.2599 | 18.0668
1876 | 0.11008 | 0.44445 | 0.54383 | 0.67164 | 3.2365 | 5.3918 | 4.271 | 5.62 | 3.9484 | 1.3481 | 15.5965 | 12.8039 | 15.5965
1877 | -1.1873 | -1.0288 | 0.11755 | 0.15179 | 4.9347 | 3.9952 | 6.7963 | 4.5715 | 3.4213 | 1.9995 | 15.5009 | 17.1518 | 17.1518
1878 | 1.0745 | 0.91035 | 0.8587 | 0.81868 | 3.3116 | 6.6161 | 5.2648 | 6.02 | 3.8326 | 1.8951 | 17.8428 | 14.3041 | 17.8428
1879 | -1.9784 | -0.70428 | 0.023944 | 0.24063 | 2.7779 | 3.4665 | 5.2141 | 4.7565 | 3.3503 | 2.8333 | 13.8342 | 14.1755 | 14.1755
1880 | 1.1341 | 0.98113 | 0.87162 | 0.83673 | 4.2255 | 6.6892 | 6.1863 | 6.0808 | 3.7152 | 1.3849 | 18.3804 | 15.5119 | 18.3804
1881 | -0.28659 | 0.82037 | 0.38721 | 0.794 | 3.7059 | 4.9098 | 4.8269 | 5.9424 | 4.9826 | 1.3084 | 15.8666 | 14.8238 | 15.8666
1882 | -1.3182 | -1.135 | 0.093726 | 0.12819 | 3.8197 | 3.8893 | 3.7402 | 4.5176 | 4.6087 | 2.0643 | 14.2909 | 14.2329 | 14.2909
1883 | 0.33932 | 0.071504 | 0.63282 | 0.5285 | 3.4491 | 5.6822 | 3.1319 | 5.312 | 5.6514 | 2.2813 | 16.7246 | 14.5137 | 16.7246
1884 | 1.0759 | 1.1111 | 0.85901 | 0.86673 | 3.7765 | 6.6178 | 5.7263 | 6.1919 | 4.3223 | 2.0594 | 18.6456 | 15.8845 | 18.6456
1885 | 0.40986 | 0.016704 | 0.65904 | 0.50666 | 3.7664 | 5.7725 | 5.1879 | 5.2684 | 5.1496 | 2.4889 | 17.2962 | 16.5928 | 17.2962
1886 | -0.68109 | 0.21081 | 0.24791 | 0.58348 | 5.0639 | 4.4724 | 5.8019 | 5.4249 | 4.0528 | 1.4831 | 16.4443 | 16.4016 | 16.4443
1887 | 0.040982 | 0.15367 | 0.51634 | 0.56107 | 3.579 | 5.3056 | 5.6121 | 5.3782 | 5.5448 | 1.6461 | 15.9089 | 16.3819 | 16.3819
1888 | -1.6219 | 0.4515 | 0.052411 | 0.67418 | 4.4506 | 3.6718 | 5.5922 | 5.626 | 4.649 | 2.2797 | 16.0281 | 16.9715 | 16.9715
1889 | -1.4445 | -1.0924 | 0.074297 | 0.13732 | 2.7713 | 3.794 | 4.2387 | 4.5388 | 4.0929 | 1.8569 | 12.961 | 12.9598 | 12.961
1890 | -2.2254 | -2.2823 | 0.013027 | 0.011236 | 3.0959 | 3.3538 | 3.3553 | 4.1389 | 3.3958 | 1.91 | 12.4986 | 11.757 | 12.4986
1891 | 0.31885 | 0.2581 | 0.62508 | 0.60184 | 3.1713 | 5.6561 | 6.858 | 5.4639 | 3.6718 | 2.0159 | 16.3071 | 15.7169 | 16.3071
1892 | 0.98837 | -0.90933 | 0.83851 | 0.18159 | 2.2665 | 6.5094 | 5.0605 | 4.636 | 4.0599 | 1.8306 | 15.2424 | 13.2174 | 15.2424
1893 | -1.4128 | -0.99776 | 0.078857 | 0.1592 | 5.0105 | 3.8172 | 5.9499 | 4.5878 | 4.3616 | 1.392 | 14.8075 | 16.714 | 16.714
1894 | -0.38833 | 0.12707 | 0.34889 | 0.55056 | 3.7736 | 4.7923 | 3.5343 | 5.3567 | 3.8611 | 2.1837 | 16.1063 | 13.3527 | 16.1063
1895 | -0.31717 | 0.40829 | 0.37556 | 0.65847 | 2.5498 | 4.8742 | 5.9678 | 5.5895 | 5.2809 | 1.9539 | 14.9674 | 15.7524 | 15.7524
1896 | -1.7054 | -1.9729 | 0.044063 | 0.024251 | 3.6643 | 3.619 | 6.3137 | 4.2076 | 5.1587 | 2.3525 | 13.8434 | 17.4892 | 17.4892
1897 | -1.6639 | -0.15401 | 0.048064 | 0.4388 | 3.72 | 3.6449 | 4.4788 | 5.1363 | 4.0832 | 1.7402 | 14.2414 | 14.0221 | 14.2414
1898 | 0.35891 | 0.52032 | 0.64017 | 0.69858 | 3.4184 | 5.7073 | 5.9297 | 5.6846 | 5.2878 | 2.4957 | 17.3059 | 17.1316 | 17.3059
1899 | 0.46597 | 0.32267 | 0.67938 | 0.62653 | 3.1124 | 5.8445 | 4.4219 | 5.5176 | 4.8355 | 2.4013 | 16.8757 | 14.771 | 16.8757
1900 | 1.0109 | 0.079463 | 0.84397 | 0.53167 | 4.7517 | 6.5374 | 4.8194 | 5.3183 | 4.785 | 1.2417 | 17.8492 | 15.5979 | 17.8492
1901 | 1.9351 | 0.44249 | 0.97351 | 0.67093 | 3.7918 | 7.579 | 4.4501 | 5.6184 | 4.5509 | 2.1832 | 19.1724 | 14.9759 | 19.1724
1902 | 0.39259 | 1.1717 | 0.65269 | 0.87934 | 3.5375 | 5.7504 | 5.2082 | 6.2433 | 4.5098 | 1.4726 | 17.0038 | 14.7281 | 17.0038
1903 | -0.051602 | 0.24166 | 0.47942 | 0.59548 | 4.3559 | 5.1914 | 4.1642 | 5.4503 | 4.0888 | 2.5261 | 17.5237 | 15.135 | 17.5237
1904 | -1.5548 | -1.074 | 0.059991 | 0.14142 | 4.2033 | 3.7164 | 7.4621 | 4.5481 | 3.7298 | 1.4043 | 13.8722 | 16.7996 | 16.7996
1905 | -1.9534 | -2.5417 | 0.025384 | 0.0055158 | 4.874 | 3.4792 | 6.2592 | 4.0962 | 4.086 | 2.0012 | 14.4506 | 17.2204 | 17.2204
1906 | 0.59297 | 1.8026 | 0.7234 | 0.96427 | 4.5747 | 6.0075 | 7.1151 | 6.7503 | 6.0622 | 2.1854 | 19.5178 | 19.9372 | 19.9372
1907 | -0.29085 | 1.0803 | 0.38558 | 0.86 | 4.1078 | 4.9048 | 6.6725 | 6.1657 | 4.5053 | 1.5183 | 16.6966 | 16.8039 | 16.8039
1908 | -0.66212 | -0.23735 | 0.25395 | 0.40619 | 5.0873 | 4.4923 | 5.6807 | 5.0741 | 4.4246 | 2.2848 | 16.9385 | 17.4775 | 17.4775
1909 | 0.91398 | 0.28761 | 0.81964 | 0.61318 | 4.5231 | 6.4162 | 5.4626 | 5.4883 | 4.5385 | 1.8934 | 18.321 | 16.4176 | 18.321
1910 | -0.54374 | 0.45244 | 0.29331 | 0.67452 | 3.6364 | 4.6189 | 4.622 | 5.6268 | 4.4278 | 1.7551 | 15.6373 | 14.4413 | 15.6373
1911 | 1.8101 | 1.6271 | 0.96486 | 0.94814 | 3.9069 | 7.4537 | 6.9278 | 6.6157 | 4.3214 | 1.8295 | 19.8059 | 16.9856 | 19.8059
1912 | -0.51764 | -0.33941 | 0.30235 | 0.36715 | 2.8346 | 4.6475 | 4.2454 | 4.9999 | 3.9344 | 1.4161 | 13.8981 | 12.4305 | 13.8981
1913 | -1.369 | -0.084738 | 0.085501 | 0.46623 | 4.4132 | 3.8501 | 3.6707 | 5.1892 | 4.3915 | 2.0639 | 15.5165 | 14.5394 | 15.5165
1914 | -1.1385 | -0.18747 | 0.12745 | 0.42565 | 3.4621 | 4.0366 | 5.5875 | 5.1112 | 4.7356 | 1.6628 | 14.2727 | 15.4481 | 15.4481
1915 | 0.09738 | -0.31556 | 0.53879 | 0.37617 | 3.7496 | 5.3759 | 6.2827 | 5.017 | 3.8205 | 1.7735 | 15.9161 | 15.6262 | 15.9161
1916 | -0.01066 | -0.11313 | 0.49575 | 0.45496 | 5.7425 | 5.2417 | 7.1388 | 5.1674 | 3.7529 | 1.9964 | 18.148 | 18.6306 | 18.6306
1917 | -0.048129 | -0.63158 | 0.48081 | 0.26383 | 3.7981 | 5.1957 | 4.6752 | 4.8022 | 3.6626 | 2.231 | 16.027 | 14.367 | 16.027
1918 | -0.81348 | -0.72199 | 0.20797 | 0.23515 | 4.9272 | 4.3378 | 6.389 | 4.7456 | 4.4607 | 1.7105 | 15.7211 | 17.4873 | 17.4873
1919 | 0.53044 | 0.17073 | 0.7021 | 0.56778 | 3.5478 | 5.9272 | 7.7667 | 5.3921 | 3.1118 | 2.2133 | 17.0804 | 16.6396 | 17.0804
1920 | 1.4219 | 0.73982 | 0.92247 | 0.77029 | 2.7778 | 7.0308 | 5.7951 | 5.873 | 4.2641 | 1.5423 | 17.2238 | 14.3792 | 17.2238
1921 | 0.26837 | -0.13148 | 0.60579 | 0.4477 | 3.0817 | 5.5918 | 4.941 | 5.1534 | 3.7359 | 1.3441 | 15.1711 | 13.1027 | 15.1711
1922 | 0.7188 | 0.081285 | 0.76387 | 0.53239 | 4.4157 | 6.1686 | 3.8484 | 5.3198 | 4.3933 | 1.987 | 17.8911 | 14.6443 | 17.8911
1923 | 0.91353 | 0.0070955 | 0.81952 | 0.50283 | 4.8803 | 6.4157 | 4.9725 | 5.2608 | 4.6973 | 1.5689 | 18.1257 | 16.1191 | 18.1257
1924 | 1.6366 | 2.8146 | 0.94914 | 0.99756 | 5.3159 | 7.2708 | 4.8506 | 7.3855 | 3.3619 | 2.3445 | 22.3167 | 15.8729 | 22.3167
1925 | -0.47913 | 0.7739 | 0.31592 | 0.78051 | 4.5474 | 4.6901 | 5.6952 | 5.9024 | 4.4259 | 2.0356 | 17.1754 | 16.704 | 17.1754
1926 | -0.94109 | -0.84251 | 0.17333 | 0.19975 | 4.2752 | 4.2144 | 6.2203 | 4.6739 | 4.804 | 1.9887 | 15.1522 | 17.2882 | 17.2882
1927 | 0.18054 | 0.68964 | 0.57164 | 0.75479 | 5.3385 | 5.4805 | 3.8049 | 5.8298 | 3.6207 | 1.9049 | 18.5536 | 14.669 | 18.5536
1928 | 0.59127 | 1.6646 | 0.72283 | 0.952 | 5.3435 | 6.0053 | 3.3098 | 6.645 | 3.9615 | 2.7036 | 20.6974 | 15.3184 | 20.6974
1929 | 0.61039 | 1.0629 | 0.7292 | 0.8561 | 4.8443 | 6.0298 | 5.3985 | 6.1509 | 3.5396 | 2.0717 | 19.0966 | 15.854 | 19.0966
1930 | 1.3073 | -0.059959 | 0.90445 | 0.47609 | 4.6387 | 6.8972 | 5.5003 | 5.2084 | 3.8207 | 1.4699 | 18.2143 | 15.4296 | 18.2143
1931 | 1.9469 | 0.6607 | 0.97423 | 0.7456 | 3.6728 | 7.5905 | 5.1582 | 5.8049 | 4.2171 | 1.8657 | 18.9338 | 14.9137 | 18.9338
1932 | -1.0016 | -1.0421 | 0.15827 | 0.14867 | 2.5728 | 4.1582 | 5.3552 | 4.5645 | 4.3581 | 1.5507 | 12.8463 | 13.8368 | 13.8368
1933 | -1.9554 | -0.85939 | 0.025265 | 0.19506 | 3.5084 | 3.4781 | 4.4974 | 4.6642 | 4.5933 | 1.9656 | 13.6163 | 14.5648 | 14.5648
1934 | 0.061157 | -1.5322 | 0.52438 | 0.062734 | 3.4312 | 5.3307 | 4.4366 | 4.3461 | 3.6488 | 1.9045 | 15.0126 | 13.4212 | 15.0126
1935 | -0.46101 | 0.43534 | 0.3224 | 0.66834 | 3.1326 | 4.7103 | 4.0828 | 5.6123 | 3.4953 | 1.5629 | 15.0181 | 12.2736 | 15.0181
1936 | 0.80093 | 0.94654 | 0.78841 | 0.82806 | 5.3696 | 6.2733 | 6.0909 | 6.0511 | 5.1924 | 2.0171 | 19.7111 | 18.67 | 19.7111
1937 | 0.59817 | 0.71493 | 0.72514 | 0.76267 | 3.923 | 6.0142 | 6.3424 | 5.8515 | 3.5702 | 2.3009 | 18.0896 | 16.1365 | 18.0896
1938 | -1.0214 | -0.73578 | 0.15354 | 0.23093 | 4.1484 | 4.1402 | 6.7187 | 4.7372 | 4.1782 | 1.6781 | 14.7038 | 16.7234 | 16.7234
1939 | -1.3788 | -1.8807 | 0.083985 | 0.030005 | 3.6883 | 3.8427 | 6.313 | 4.2324 | 3.1386 | 1.5124 | 13.2758 | 14.6523 | 14.6523
1940 | 1.2035 | 0.0047842 | 0.88562 | 0.50191 | 4.0265 | 6.7734 | 3.5203 | 5.259 | 4.063 | 1.3992 | 17.4581 | 13.0091 | 17.4581
1941 | 0.12734 | -0.8279 | 0.55066 | 0.20386 | 5.6112 | 5.4135 | 5.053 | 4.6824 | 6.4022 | 2.0103 | 17.7173 | 19.0767 | 19.0767
1942 | 0.41732 | -0.47963 | 0.66178 | 0.31575 | 4.0474 | 5.7821 | 5.6403 | 4.9022 | 5.566 | 1.4278 | 16.1595 | 16.6815 | 16.6815
1943 | -0.060293 | 0.3681 | 0.47596 | 0.6436 | 4.0329 | 5.1808 | 7.6783 | 5.5556 | 3.8681 | 1.7673 | 16.5366 | 17.3466 | 17.3466
1944 | 1.3459 | 0.06005 | 0.91083 | 0.52394 | 4.8522 | 6.9426 | 7.7307 | 5.3028 | 3.6278 | 2.0845 | 19.1821 | 18.2952 | 19.1821
1945 | -0.89554 | -0.42194 | 0.18525 | 0.33653 | 5.0521 | 4.2577 | 7.0792 | 4.9418 | 3.6599 | 1.3118 | 15.5634 | 17.103 | 17.103
1946 | -2.1088 | -0.72583 | 0.017481 | 0.23397 | 2.7835 | 3.4041 | 7.5888 | 4.7433 | 4.2838 | 1.6963 | 12.6273 | 16.3525 | 16.3525
1947 | -1.0431 | -1.5811 | 0.14846 | 0.056932 | 4.6982 | 4.1205 | 3.5542 | 4.3282 | 3.489 | 1.4186 | 14.5655 | 13.16 | 14.5655
1948 | -0.52194 | -1.2834 | 0.30086 | 0.099685 | 3.6969 | 4.6428 | 5.248 | 4.4481 | 5.2801 | 2.2297 | 15.0175 | 16.4547 | 16.4547
1949 | 1.2471 | -0.23817 | 0.89383 | 0.40588 | 3.191 | 6.8258 | 6.6444 | 5.0734 | 4.6142 | 2.094 | 17.1842 | 16.5436 | 17.1842
1950 | 0.82645 | 0.78787 | 0.79573 | 0.78461 | 4.8455 | 6.3057 | 3.946 | 5.9144 | 3.7269 | 1.2403 | 18.3059 | 13.7587 | 18.3059
1951 | 1.5116 | 1.0595 | 0.93468 | 0.85531 | 5.6255 | 7.1327 | 6.7071 | 6.1479 | 4.1209 | 1.9204 | 20.8265 | 18.3739 | 20.8265
1952 | -0.25685 | -0.89161 | 0.39865 | 0.1863 | 4.6523 | 4.9447 | 6.0352 | 4.6459 | 3.7028 | 2.1149 | 16.3579 | 16.5053 | 16.5053
1953 | 0.17925 | 1.1998 | 0.57113 | 0.8849 | 3.8728 | 5.4788 | 6.7244 | 6.267 | 3.6548 | 1.4299 | 17.0486 | 15.6819 | 17.0486
1954 | 0.93134 | -0.00029659 | 0.82416 | 0.49988 | 3.7413 | 6.438 | 4.8904 | 5.255 | 3.526 | 1.7532 | 17.1876 | 13.911 | 17.1876
1955 | -0.74322 | -0.67377 | 0.22868 | 0.25023 | 5.1384 | 4.4084 | 5.5222 | 4.7755 | 3.632 | 1.6752 | 15.9976 | 15.9678 | 15.9976
1956 | 1.0071 | 0.33854 | 0.84305 | 0.63252 | 3.8072 | 6.5327 | 7.0673 | 5.5308 | 4.0689 | 2.0479 | 17.9186 | 16.9913 | 17.9186
1957 | -1.2314 | -0.062752 | 0.10908 | 0.47498 | 4.9723 | 3.9587 | 7.324 | 5.2062 | 4.4006 | 2.1657 | 16.3029 | 18.8626 | 18.8626
1958 | -1.35 | -0.7459 | 0.088514 | 0.22787 | 4.0883 | 3.8646 | 4.8721 | 4.7311 | 5.778 | 2.2926 | 14.9766 | 17.031 | 17.031
1959 | 0.48432 | 1.0804 | 0.68592 | 0.86002 | 4.1901 | 5.868 | 6.0254 | 6.1658 | 4.9117 | 1.47 | 17.6939 | 16.5971 | 17.6939
1960 | 1.596 | 1.593 | 0.94476 | 0.94442 | 4.8853 | 7.2265 | 3.9471 | 6.5889 | 4.2905 | 2.2394 | 20.9401 | 15.3623 | 20.9401
1961 | -1.0597 | 0.14137 | 0.14464 | 0.55621 | 4.1683 | 4.1056 | 5.7195 | 5.3682 | 3.9261 | 1.4441 | 15.0862 | 15.258 | 15.258
1962 | -1.2116 | -0.85262 | 0.11284 | 0.19693 | 3.5244 | 3.975 | 6.8722 | 4.6681 | 4.4466 | 1.9058 | 14.0733 | 16.749 | 16.749
1963 | 0.091956 | -0.76899 | 0.53663 | 0.22095 | 2.9906 | 5.3692 | 5.3187 | 4.7172 | 5.9253 | 1.4985 | 14.5755 | 15.733 | 15.733
1964 | 0.26822 | 0.45118 | 0.60573 | 0.67407 | 5.1497 | 5.5916 | 5.2287 | 5.6257 | 4.3086 | 1.7512 | 18.1183 | 16.4383 | 18.1183
1965 | -1.0739 | 1.0824 | 0.14144 | 0.86045 | 3.8025 | 4.093 | 6.3672 | 6.1674 | 5.1025 | 2.6088 | 16.6718 | 17.881 | 17.881
1966 | -0.40451 | -0.24019 | 0.34292 | 0.40509 | 4.4499 | 4.7739 | 4.8002 | 5.072 | 3.6495 | 2.0908 | 16.3866 | 14.9904 | 16.3866
1967 | 1.0083 | 1.4849 | 0.84335 | 0.93121 | 3.6405 | 6.5342 | 4.8466 | 6.5026 | 4.3204 | 1.4572 | 18.1346 | 14.2648 | 18.1346
1968 | -0.23144 | -0.626 | 0.40849 | 0.26566 | 3.1063 | 4.9747 | 7.2363 | 4.8057 | 3.2571 | 1.7257 | 14.6125 | 15.3254 | 15.3254
1969 | -0.29932 | -0.12016 | 0.38235 | 0.45218 | 4.2599 | 4.895 | 5.7257 | 5.1621 | 4.0901 | 2.4836 | 16.8005 | 16.5593 | 16.8005
1970 | 1.1581 | 1.5366 | 0.87658 | 0.93781 | 4.0418 | 6.7184 | 6.394 | 6.5442 | 3.5623 | 2.7718 | 20.0761 | 16.7699 | 20.0761
1971 | 0.36193 | 0.64465 | 0.6413 | 0.74042 | 4.0746 | 5.7111 | 6.6312 | 5.7911 | 5.2594 | 2.3241 | 17.9009 | 18.2893 | 18.2893
1972 | 0.75281 | 0.56478 | 0.77422 | 0.71389 | 4.3028 | 6.212 | 6.1077 | 5.7225 | 4.1842 | 1.8114 | 18.0488 | 16.4061 | 18.0488
1973 | -0.66948 | 0.29555 | 0.25159 | 0.61621 | 3.7662 | 4.4846 | 6.9912 | 5.4949 | 3.6073 | 1.987 | 15.7328 | 16.3518 | 16.3518
1974 | -0.063237 | 0.69422 | 0.47479 | 0.75623 | 4.0563 | 5.1772 | 6.6472 | 5.8337 | 3.9433 | 2.047 | 17.1142 | 16.6938 | 17.1142
1975 | -0.1412 | -0.54285 | 0.44386 | 0.29361 | 4.8199 | 5.0825 | 3.0932 | 4.8598 | 3.763 | 2.5399 | 17.3022 | 14.216 | 17.3022
1976 | 1.0788 | 1.9358 | 0.85966 | 0.97355 | 3.9821 | 6.6214 | 6.3281 | 6.8483 | 3.9997 | 1.4643 | 18.9161 | 15.7742 | 18.9161
1977 | 0.52577 | 1.4078 | 0.70048 | 0.92041 | 2.3041 | 5.9212 | 5.5055 | 6.4399 | 3.7283 | 2.0808 | 16.746 | 13.6186 | 16.746
1978 | -0.42944 | 0.087013 | 0.3338 | 0.53467 | 3.9424 | 4.7457 | 5.3053 | 5.3244 | 5.4821 | 2.5165 | 16.5289 | 17.2463 | 17.2463
1979 | 0.47566 | -0.95848 | 0.68284 | 0.16891 | 3.2879 | 5.8569 | 3.7813 | 4.6089 | 4.4854 | 1.4022 | 15.156 | 12.9569 | 15.156
1980 | 0.057159 | -0.63672 | 0.52279 | 0.26215 | 3.1373 | 5.3257 | 4.8074 | 4.7989 | 4.7551 | 2.3522 | 15.6141 | 15.0519 | 15.6141
1981 | 1.1253 | 0.090034 | 0.86977 | 0.53587 | 3.7229 | 6.6785 | 6.4263 | 5.3268 | 4.452 | 1.4783 | 17.2064 | 16.0795 | 17.2064
1982 | 1.2336 | 1.5133 | 0.89132 | 0.9349 | 4.0984 | 6.8095 | 5.4025 | 6.5255 | 5.1286 | 1.6693 | 19.1027 | 16.2988 | 19.1027
1983 | 0.53168 | 0.54936 | 0.70253 | 0.70862 | 2.813 | 5.9288 | 5.5175 | 5.7094 | 4.44 | 1.6792 | 16.1304 | 14.4498 | 16.1304
1984 | 0.32809 | -0.29243 | 0.62858 | 0.38498 | 2.308 | 5.6679 | 5.257 | 5.0337 | 3.8986 | 2.1823 | 15.1919 | 13.6458 | 15.1919
1985 | -0.42774 | -0.35594 | 0.33442 | 0.36094 | 4.4192 | 4.7476 | 7.5763 | 4.9882 | 3.4988 | 1.97 | 16.1249 | 17.4643 | 17.4643
1986 | -0.57091 | 0.17464 | 0.28403 | 0.56932 | 3.8732 | 4.5894 | 6.729 | 5.3953 | 4.2455 | 2.6766 | 16.5345 | 17.5243 | 17.5243
1987 | 1.0535 | 1.6393 | 0.85395 | 0.94943 | 3.1211 | 6.5903 | 3.6106 | 6.6253 | 3.9913 | 2.0725 | 18.4092 | 12.7955 | 18.4092
1988 | -0.32304 | -0.85362 | 0.37333 | 0.19666 | 4.1541 | 4.8674 | 5.0295 | 4.6675 | 4.8808 | 1.8722 | 15.5612 | 15.9366 | 15.9366
1989 | -0.26676 | 0.5024 | 0.39483 | 0.69231 | 4.5291 | 4.9331 | 3.1644 | 5.6693 | 3.6792 | 1.6828 | 16.8143 | 13.0556 | 16.8143
1990 | 1.223 | 1.2576 | 0.88934 | 0.89574 | 4.8551 | 6.7969 | 6.9085 | 6.3156 | 4.022 | 1.5139 | 19.4814 | 17.2995 | 19.4814
1991 | 0.097413 | -0.5946 | 0.5388 | 0.27606 | 3.6089 | 5.376 | 5.7006 | 4.8259 | 4.3148 | 1.7368 | 15.5477 | 15.3612 | 15.5477
1992 | 0.35704 | 1.5318 | 0.63947 | 0.93721 | 2.2686 | 5.7049 | 5.9686 | 6.5403 | 4.4239 | 2.1446 | 16.6584 | 14.8057 | 16.6584
1993 | -0.63848 | -1.9385 | 0.26158 | 0.026282 | 3.9934 | 4.5172 | 4.7052 | 4.2166 | 5.6335 | 1.9088 | 14.636 | 16.2409 | 16.2409
1994 | -0.78461 | -1.8142 | 0.21634 | 0.034826 | 3.2669 | 4.3666 | 6.0691 | 4.2516 | 3.7018 | 1.9828 | 13.8679 | 15.0207 | 15.0207
1995 | -0.28489 | -1.0398 | 0.38786 | 0.14921 | 2.978 | 4.9118 | 6.8567 | 4.5657 | 3.401 | 1.8748 | 14.3303 | 15.1105 | 15.1105
1996 | 1.0471 | 1.1766 | 0.85246 | 0.88033 | 2.7807 | 6.5823 | 6.1472 | 6.2474 | 4.4146 | 1.6538 | 17.2642 | 14.9962 | 17.2642
1997 | 0.97846 | -0.031234 | 0.83608 | 0.48754 | 4.3586 | 6.497 | 5.6549 | 5.2308 | 3.8619 | 2.6171 | 18.7035 | 16.4925 | 18.7035
1998 | -0.63335 | -1.0731 | 0.26325 | 0.14162 | 4.21 | 4.5226 | 7.2788 | 4.5486 | 4.0968 | 1.625 | 14.9062 | 17.2106 | 17.2106
1999 | 0.53092 | -0.059341 | 0.70226 | 0.47634 | 3.5243 | 5.9278 | 5.8673 | 5.2089 | 4.7535 | 2.1221 | 16.7831 | 16.2672 | 16.7831
2000 | 2.4154 | 0.78556 | 0.99214 | 0.78394 | 4.4691 | 8.0039 | 7.2317 | 5.9124 | 4.3329 | 1.7541 | 20.1395 | 17.7878 | 20.1395
2001 | -0.70364 | -0.4126 | 0.24083 | 0.33995 | 4.1883 | 4.449 | 6.3986 | 4.9483 | 4.4284 | 2.4508 | 16.0365 | 17.4661 | 17.4661
2002 | -1.5352 | -0.45695 | 0.062364 | 0.32385 | 5.3367 | 3.7298 | 5.116 | 4.9177 | 5.2648 | 1.1039 | 15.0881 | 16.8214 | 16.8214
2003 | -0.011664 | -0.87256 | 0.49535 | 0.19145 | 3.2985 | 5.2405 | 5.6759 | 4.6567 | 4.8119 | 1.8986 | 15.0942 | 15.6848 | 15.6848
2004 | 0.4308 | -0.22121 | 0.66669 | 0.41246 | 3.9131 | 5.7993 | 7.0122 | 5.086 | 4.5042 | 1.7905 | 16.589 | 17.22 | 17.22
2005 | 0.97949 | 0.0056002 | 0.83633 | 0.50223 | 4.4269 | 6.4983 | 6.1266 | 5.2597 | 3.7458 | 2.5797 | 18.7645 | 16.879 | 18.7645
2006 | -0.076464 | -0.2946 | 0.46952 | 0.38415 | 3.7539 | 5.161 | 5.5669 | 5.0322 | 3.1998 | 2.4576 | 16.4047 | 14.9782 | 16.4047
2007 | 0.2134 | -0.71205 | 0.58449 | 0.23822 | 4.1154 | 5.522 | 5.7624 | 4.7517 | 3.4312 | 2.4955 | 16.8847 | 15.8045 | 16.8847
2008 | 0.5549 | -1.7789 | 0.71052 | 0.037631 | 3.1092 | 5.9586 | 5.4342 | 4.2623 | 6.1765 | 1.8911 | 15.2212 | 16.6109 | 16.6109
2009 | 0.29133 | 1.3324 | 0.6146 | 0.90863 | 4.434 | 5.621 | 4.8983 | 6.3778 | 3.1346 | 1.6597 | 18.0926 | 14.1267 | 18.0926
2010 | -1.5661 | -0.33852 | 0.058666 | 0.36748 | 3.7444 | 3.7088 | 6.2624 | 5.0006 | 3.8369 | 1.9613 | 14.4151 | 15.805 | 15.805
2011 | 0.27645 | 0.67964 | 0.6089 | 0.75163 | 4.0044 | 5.6021 | 6.3451 | 5.8212 | 3.8097 | 1.7197 | 17.1473 | 15.8789 | 17.1473
2012 | 0.17631 | -0.63119 | 0.56997 | 0.26396 | 3.4096 | 5.4751 | 6.8921 | 4.8024 | 4.6821 | 1.8648 | 15.552 | 16.8486 | 16.8486
2013 | 0.42257 | 0.31918 | 0.6637 | 0.62521 | 3.4902 | 5.7888 | 4.2669 | 5.5146 | 4.1231 | 2.0216 | 16.8153 | 13.9018 | 16.8153
2014 | 1.0478 | 0.92641 | 0.85264 | 0.82288 | 3.5032 | 6.5832 | 6.0436 | 6.0338 | 3.2667 | 2.1063 | 18.2265 | 14.9198 | 18.2265
2015 | -1.1442 | -0.3122 | 0.12627 | 0.37745 | 4.6833 | 4.0318 | 6.1509 | 5.0195 | 3.3158 | 2.6882 | 16.4227 | 16.8382 | 16.8382
2016 | 0.38879 | 0.64386 | 0.65129 | 0.74017 | 5.5304 | 5.7455 | 5.1756 | 5.7904 | 4.5596 | 1.9261 | 18.9925 | 17.1917 | 18.9925
2017 | 1.44 | 0.047846 | 0.92506 | 0.51908 | 3.585 | 7.0515 | 5.7882 | 5.2931 | 3.1168 | 1.151 | 17.0807 | 13.6411 | 17.0807
2018 | -1.2124 | -2.5269 | 0.11268 | 0.0057532 | 4.1785 | 3.9743 | 7.0151 | 4.0983 | 4.1246 | 2.0826 | 14.3338 | 17.4008 | 17.4008
2019 | -0.6564 | -0.87376 | 0.25578 | 0.19112 | 4.111 | 4.4983 | 6.1582 | 4.656 | 3.9625 | 1.8028 | 15.0681 | 16.0345 | 16.0345
2020 | 0.59873 | 0.21097 | 0.72532 | 0.58354 | 3.4059 | 6.0149 | 6.7596 | 5.425 | 3.7942 | 2.2069 | 17.0528 | 16.1667 | 17.0528
2021 | 0.46625 | 0.45518 | 0.67948 | 0.67551 | 3.0898 | 5.8448 | 6.2881 | 5.6291 | 4.3796 | 1.9285 | 16.4923 | 15.6861 | 16.4923
2022 | -0.23437 | 0.75336 | 0.40735 | 0.77438 | 5.0828 | 4.9712 | 7.2625 | 5.8847 | 4.4807 | 1.5744 | 17.513 | 18.4004 | 18.4004
2023 | 0.29235 | 0.50819 | 0.61499 | 0.69434 | 3.2795 | 5.6223 | 6.9853 | 5.6742 | 3.3645 | 2.2971 | 16.8731 | 15.9263 | 16.8731
2024 | 0.38509 | 0.59969 | 0.64992 | 0.72564 | 3.5325 | 5.7408 | 5.3514 | 5.7524 | 4.9366 | 1.9688 | 16.9945 | 15.7893 | 16.9945
2025 | 0.23087 | 1.1798 | 0.59129 | 0.88096 | 4.3643 | 5.5442 | 4.5878 | 6.2501 | 3.9485 | 1.4718 | 17.6304 | 14.3724 | 17.6304
2026 | 0.094812 | -1.093 | 0.53777 | 0.1372 | 5.2505 | 5.3727 | 4.3074 | 4.5385 | 3.8785 | 2.1212 | 17.283 | 15.5576 | 17.283
2027 | -1.046 | -1.4669 | 0.14778 | 0.071203 | 4.2396 | 4.1179 | 3.9689 | 4.3712 | 4.84 | 1.7682 | 14.4969 | 14.8167 | 14.8167
2028 | 0.51769 | 0.37222 | 0.69766 | 0.64514 | 5.0569 | 5.9109 | 3.7051 | 5.5591 | 3.8294 | 2.0448 | 18.5716 | 14.6362 | 18.5716
2029 | -1.5566 | -0.26447 | 0.059788 | 0.39571 | 4.749 | 3.7152 | 6.2368 | 5.0541 | 4.3384 | 1.9044 | 15.4227 | 17.2286 | 17.2286
2030 | 0.44841 | -0.0019687 | 0.67307 | 0.49921 | 4.1995 | 5.8219 | 5.3488 | 5.2537 | 4.259 | 2.1672 | 17.4423 | 15.9745 | 17.4423
2031 | -1.8403 | -0.0084143 | 0.032863 | 0.49664 | 3.7887 | 3.5398 | 6.2112 | 5.2486 | 4.5529 | 1.7684 | 14.3455 | 16.3212 | 16.3212
2032 | 0.65628 | -0.039329 | 0.74418 | 0.48431 | 5.2495 | 6.0887 | 5.2535 | 5.2244 | 4.0019 | 2.2442 | 18.8068 | 16.7492 | 18.8068
2033 | 0.38126 | -0.92393 | 0.64849 | 0.17776 | 3.4185 | 5.7359 | 5.7654 | 4.6279 | 4.5426 | 2.1916 | 15.9738 | 15.9181 | 15.9738
2034 | -0.99959 | -0.18238 | 0.15875 | 0.42764 | 4.6396 | 4.16 | 6.5943 | 5.115 | 4.9583 | 1.8575 | 15.7721 | 18.0496 | 18.0496
2035 | -0.16187 | -0.82582 | 0.4357 | 0.20445 | 4.3505 | 5.0576 | 5.1177 | 4.6836 | 4.1126 | 2.2407 | 16.3324 | 15.8215 | 16.3324
2036 | -0.66732 | -1.3856 | 0.25228 | 0.082936 | 2.5678 | 4.4868 | 4.02 | 4.404 | 4.6393 | 1.8028 | 13.2614 | 13.0299 | 13.2614
2037 | 0.44367 | 0.39511 | 0.67136 | 0.65362 | 3.5957 | 5.8159 | 3.7088 | 5.5783 | 4.4367 | 2.4171 | 17.407 | 14.1584 | 17.407
2038 | -0.17524 | 0.35031 | 0.43045 | 0.63695 | 5.1824 | 5.0416 | 7.572 | 5.5407 | 5.7037 | 1.8968 | 17.6615 | 20.3549 | 20.3549
2039 | 1.2506 | 1.3734 | 0.89446 | 0.91518 | 4.6059 | 6.8299 | 3.9904 | 6.4117 | 3.5046 | 1.6159 | 19.4633 | 13.7169 | 19.4633
2040 | -1.047 | 0.46708 | 0.14754 | 0.67978 | 4.7888 | 4.117 | 3.4414 | 5.6392 | 3.7286 | 2.2959 | 16.841 | 14.2548 | 16.841
2041 | -0.60196 | -1.2304 | 0.2736 | 0.10926 | 5.1031 | 4.556 | 5.9088 | 4.4722 | 4.39 | 1.8574 | 15.9886 | 17.2593 | 17.2593
2042 | 0.23715 | -1.0161 | 0.59373 | 0.15478 | 3.8672 | 5.5521 | 7.0628 | 4.5781 | 3.9798 | 2.4678 | 16.4652 | 17.3776 | 17.3776
2043 | -1.6869 | -1.0465 | 0.045813 | 0.14767 | 3.5011 | 3.6304 | 6.9986 | 4.5623 | 5.8284 | 1.4345 | 13.1283 | 17.7627 | 17.7627
2044 | 1.6682 | 0.45506 | 0.95236 | 0.67547 | 4.0212 | 7.3049 | 5.9096 | 5.629 | 3.939 | 1.6142 | 18.5693 | 15.484 | 18.5693
2045 | 1.1593 | 1.3623 | 0.87684 | 0.91345 | 5.6963 | 6.7199 | 5.4484 | 6.4026 | 5.0952 | 1.286 | 20.1048 | 17.5259 | 20.1048
2046 | -2.4621 | -2.2766 | 0.0069067 | 0.011405 | 5.2807 | 3.2663 | 6.5587 | 4.1399 | 4.1555 | 2.0819 | 14.7689 | 18.0768 | 18.0768
2047 | 0.75756 | 0.0348 | 0.77564 | 0.51388 | 3.6 | 6.2181 | 6.146 | 5.2827 | 5.455 | 1.4108 | 16.5116 | 16.6118 | 16.6118
2048 | -0.33692 | -1.9274 | 0.36809 | 0.026966 | 4.8522 | 4.8513 | 6.7797 | 4.2196 | 3.8401 | 2.1278 | 16.051 | 17.5998 | 17.5998
2049 | -0.40945 | 0.30985 | 0.34111 | 0.62166 | 3.1387 | 4.7683 | 6.1016 | 5.5069 | 4.3463 | 2.5446 | 15.9585 | 16.1313 | 16.1313
2050 | 1.3233 | 1.1047 | 0.90712 | 0.86534 | 3.567 | 6.916 | 5.6132 | 6.1864 | 4.1295 | 1.8536 | 18.523 | 15.1632 | 18.523
2051 | 0.80118 | 1.3793 | 0.78849 | 0.91609 | 5.0797 | 6.2736 | 5.1431 | 6.4165 | 4.6257 | 1.7605 | 19.5303 | 16.609 | 19.5303
2052 | -0.74401 | -0.94775 | 0.22844 | 0.17163 | 3.3618 | 4.4076 | 2.7348 | 4.6148 | 4.9157 | 2.1661 | 14.5503 | 13.1785 | 14.5503
2053 | -0.99406 | -1.0229 | 0.1601 | 0.15317 | 4.574 | 4.1651 | 5.3233 | 4.5745 | 3.7013 | 2.1974 | 15.511 | 15.796 | 15.796
2054 | 0.44583 | -0.87882 | 0.67214 | 0.18975 | 4.0306 | 5.8186 | 4.6043 | 4.6531 | 4.6497 | 2.5029 | 17.0053 | 15.7875 | 17.0053
2055 | 0.079846 | 0.43627 | 0.53182 | 0.66868 | 3.5358 | 5.354 | 5.2609 | 5.6131 | 3.8785 | 2.0022 | 16.5051 | 14.6774 | 16.5051
2056 | 0.21849 | 0.51432 | 0.58648 | 0.69648 | 4.6618 | 5.5285 | 5.6309 | 5.6794 | 4.6437 | 1.7619 | 17.6316 | 16.6984 | 17.6316
2057 | 1.6424 | 1.7203 | 0.94974 | 0.95731 | 2.4506 | 7.2771 | 5.525 | 6.6879 | 4.298 | 2.0385 | 18.4542 | 14.3122 | 18.4542
2058 | 0.77081 | 1.0455 | 0.77959 | 0.8521 | 4.2784 | 6.235 | 6.6372 | 6.136 | 5.1919 | 1.8646 | 18.514 | 17.9722 | 18.514
2059 | -0.08515 | 0.47152 | 0.46607 | 0.68136 | 3.9553 | 5.1504 | 5.1383 | 5.643 | 3.3726 | 1.9245 | 16.6732 | 14.3906 | 16.6732
2060 | 1.0367 | -0.67682 | 0.85007 | 0.24926 | 4.2418 | 6.5695 | 5.2218 | 4.7736 | 3.0653 | 1.7458 | 17.3307 | 14.2747 | 17.3307
2061 | -0.82731 | 0.37271 | 0.20403 | 0.64532 | 5.7724 | 4.3241 | 6.5989 | 5.5595 | 4.2117 | 1.7071 | 17.363 | 18.29 | 18.29
2062 | -0.79444 | -0.58954 | 0.21347 | 0.27775 | 4.3331 | 4.3567 | 5.0591 | 4.8292 | 3.5545 | 1.95 | 15.4691 | 14.8967 | 15.4691
2063 | -0.43671 | 0.77607 | 0.33116 | 0.78115 | 3.8797 | 4.7375 | 6.8281 | 5.9043 | 5.888 | 1.3589 | 15.8804 | 17.9547 | 17.9547
2064 | -0.1775 | -0.49441 | 0.42956 | 0.31051 | 3.4631 | 5.0389 | 4.2661 | 4.8922 | 4.6434 | 2.1955 | 15.5897 | 14.5681 | 15.5897
2065 | -1.0573 | 0.66514 | 0.14519 | 0.74702 | 5.2537 | 4.1078 | 3.5514 | 5.8087 | 5.1345 | 2.3137 | 17.4839 | 16.2534 | 17.4839
2066 | 0.080817 | 0.33931 | 0.53221 | 0.63281 | 3.6866 | 5.3552 | 7.2889 | 5.5315 | 3.157 | 2.0558 | 16.6291 | 16.1883 | 16.6291
2067 | -0.60593 | 0.17398 | 0.27228 | 0.56906 | 4.5469 | 4.5518 | 6.2183 | 5.3947 | 3.8716 | 1.8692 | 16.3626 | 16.506 | 16.506
2068 | 1.8499 | 0.45395 | 0.96783 | 0.67507 | 3.3457 | 7.4942 | 6.0223 | 5.6281 | 4.2254 | 2.1292 | 18.5972 | 15.7227 | 18.5972
2069 | 0.18586 | 1.765e-05 | 0.57372 | 0.50001 | 3.7516 | 5.4872 | 5.5861 | 5.2553 | 4.5991 | 2.1937 | 16.6877 | 16.1305 | 16.6877
2070 | 0.93846 | 0.20917 | 0.826 | 0.58284 | 3.0574 | 6.447 | 6.3104 | 5.4236 | 3.4952 | 2.0222 | 16.9501 | 14.8851 | 16.9501
2071 | -1.728 | -0.69411 | 0.041995 | 0.24381 | 4.4097 | 3.6052 | 5.8805 | 4.7628 | 4.8139 | 2.6847 | 15.4624 | 17.7887 | 17.7887
2072 | -0.066663 | 1.1079 | 0.47342 | 0.86604 | 2.6882 | 5.173 | 6.0952 | 6.1892 | 4.2177 | 2.2586 | 16.3089 | 15.2596 | 16.3089
2073 | -0.27279 | -0.59573 | 0.39251 | 0.27568 | 2.4294 | 4.926 | 5.4012 | 4.8252 | 4.8309 | 2.0317 | 14.2123 | 14.6932 | 14.6932
2074 | -0.84385 | -0.11557 | 0.19938 | 0.454 | 3.5648 | 4.3078 | 4.3257 | 5.1656 | 5.2123 | 2.2356 | 15.2738 | 15.3384 | 15.3384
2075 | -0.61093 | -0.47523 | 0.27062 | 0.31731 | 3.5942 | 4.5465 | 6.403 | 4.9052 | 4.6953 | 2.1527 | 15.1986 | 16.8452 | 16.8452
2076 | 0.36445 | 0.5818 | 0.64224 | 0.71965 | 4.6103 | 5.7144 | 6.2166 | 5.7371 | 4.9152 | 1.9782 | 18.04 | 17.7203 | 18.04
2077 | -2.6022 | -2.4671 | 0.004632 | 0.0068113 | 4.1924 | 3.2231 | 5.223 | 4.1073 | 4.4555 | 2.0072 | 13.53 | 15.8782 | 15.8782
2078 | 1.6874 | 1.4552 | 0.95424 | 0.92719 | 4.5486 | 7.3255 | 7.0201 | 6.4785 | 5.1809 | 2.2315 | 20.5841 | 18.9811 | 20.5841
2079 | 0.024211 | 1.0547 | 0.50966 | 0.85421 | 4.5054 | 5.2848 | 7.0696 | 6.1438 | 3.4301 | 2.0057 | 17.9397 | 17.0108 | 17.9397
2080 | 1.659 | -0.59353 | 0.95144 | 0.27641 | 2.3573 | 7.295 | 5.3108 | 4.8266 | 4.4398 | 1.2899 | 15.7688 | 13.3977 | 15.7688
2081 | -2.0402 | -0.67818 | 0.020664 | 0.24883 | 4.289 | 3.4361 | 6.6645 | 4.7727 | 3.9245 | 1.8349 | 14.3328 | 16.7129 | 16.7129
2082 | 0.89663 | -0.63031 | 0.81504 | 0.26424 | 4.9079 | 6.3944 | 6.5655 | 4.803 | 5.1763 | 1.6198 | 17.725 | 18.2695 | 18.2695
2083 | -1.6107 | -0.34474 | 0.053622 | 0.36515 | 3.5918 | 3.6791 | 4.6569 | 4.9961 | 3.4874 | 2.7995 | 15.0666 | 14.5356 | 15.0666
2084 | 2.0351 | 0.4071 | 0.97908 | 0.65803 | 4.1878 | 7.675 | 6.966 | 5.5885 | 3.6833 | 2.3606 | 19.8119 | 17.1977 | 19.8119
2085 | -0.80784 | 0.14356 | 0.20959 | 0.55708 | 3.9586 | 4.3434 | 7.053 | 5.37 | 4.127 | 1.685 | 15.357 | 16.8236 | 16.8236
2086 | -0.020623 | 0.56713 | 0.49177 | 0.71469 | 3.1363 | 5.2295 | 5.7122 | 5.7246 | 3.8408 | 1.939 | 16.0292 | 14.6282 | 16.0292
2087 | -1.1563 | -0.95907 | 0.12378 | 0.16876 | 4.5825 | 4.0214 | 5.3547 | 4.6086 | 3.2113 | 1.9279 | 15.1403 | 15.0764 | 15.1403
2088 | 1.5373 | 1.2912 | 0.93789 | 0.90169 | 3.104 | 7.1616 | 6.7015 | 6.3436 | 4.7168 | 2.076 | 18.6853 | 16.5983 | 18.6853
2089 | 0.73596 | -1.2226 | 0.76912 | 0.11075 | 5.1085 | 6.1906 | 6.9827 | 4.4758 | 4.0801 | 1.4889 | 17.2637 | 17.6602 | 17.6602
2090 | 0.51624 | 0.17993 | 0.69716 | 0.5714 | 4.3144 | 5.909 | 4.6716 | 5.3996 | 4.7854 | 2.0256 | 17.6486 | 15.7969 | 17.6486
2091 | -0.53323 | 0.12555 | 0.29694 | 0.54995 | 4.9829 | 4.6304 | 5.3182 | 5.3554 | 4.4164 | 2.4506 | 17.4193 | 17.1681 | 17.4193
2092 | 0.80332 | 0.33538 | 0.7891 | 0.63133 | 3.8604 | 6.2763 | 5.9484 | 5.5282 | 3.9122 | 1.6244 | 17.2893 | 15.3454 | 17.2893
2093 | -0.32102 | 1.7452 | 0.3741 | 0.95952 | 5.1893 | 4.8697 | 7.2038 | 6.707 | 4.175 | 1.7337 | 18.4996 | 18.3017 | 18.4996
2094 | 0.14287 | 0.77955 | 0.5568 | 0.78217 | 4.7163 | 5.433 | 7.1849 | 5.9072 | 3.4437 | 2.4708 | 18.5274 | 17.8157 | 18.5274
2095 | 0.16113 | -0.33676 | 0.564 | 0.36815 | 3.9687 | 5.456 | 6.0203 | 5.0018 | 3.6551 | 1.899 | 16.3255 | 15.5431 | 16.3255
2096 | -0.36763 | 0.092129 | 0.35657 | 0.5367 | 3.3603 | 4.816 | 5.3405 | 5.3285 | 4.6063 | 2.7167 | 16.2214 | 16.0237 | 16.2214
2097 | -0.0095364 | -0.92359 | 0.4962 | 0.17785 | 4.4481 | 5.2431 | 6.2258 | 4.6281 | 3.9976 | 1.9028 | 16.2221 | 16.5743 | 16.5743
2098 | 0.74319 | 0.55261 | 0.77132 | 0.70973 | 4.3594 | 6.1998 | 7.7298 | 5.7121 | 5.374 | 2.7243 | 18.9956 | 20.1875 | 20.1875
2099 | -0.50919 | 0.29256 | 0.30531 | 0.61507 | 4.5803 | 4.6568 | 7.3207 | 5.4925 | 4.6348 | 2.7336 | 17.4631 | 19.2694 | 19.2694
2100 | 0.48488 | -0.84671 | 0.68612 | 0.19858 | 2.9808 | 5.8687 | 5.1356 | 4.6715 | 3.4946 | 1.2812 | 14.8022 | 12.8921 | 14.8022
2101 | -0.78838 | -0.33678 | 0.21524 | 0.36814 | 5.1326 | 4.3628 | 4.5278 | 5.0018 | 3.2344 | 1.2354 | 15.7326 | 14.1302 | 15.7326
2102 | 0.0069578 | 0.45741 | 0.50278 | 0.67631 | 5.0639 | 5.2635 | 6.6596 | 5.631 | 4.5247 | 1.5381 | 17.4965 | 17.7863 | 17.7863
2103 | -1.5157 | -0.48386 | 0.064803 | 0.31424 | 4.6622 | 3.7433 | 4.4554 | 4.8994 | 3.8878 | 2.2059 | 15.5108 | 15.2113 | 15.5108
2104 | -0.8627 | -0.32523 | 0.19415 | 0.37251 | 2.557 | 4.2894 | 6.0114 | 5.0101 | 3.6816 | 1.3958 | 13.2523 | 13.6457 | 13.6457
2105 | 0.96354 | -0.076904 | 0.83236 | 0.46935 | 3.2763 | 6.4784 | 7.3856 | 5.1953 | 4.677 | 1.4064 | 16.3564 | 16.7453 | 16.7453
2106 | -0.62847 | 0.05831 | 0.26485 | 0.52325 | 3.6845 | 4.5278 | 6.2896 | 5.3014 | 5.3416 | 1.7176 | 15.2313 | 17.0333 | 17.0333
2107 | -1.2266 | 0.25628 | 0.10998 | 0.60113 | 2.6791 | 3.9626 | 5.1126 | 5.4624 | 3.97 | 1.6633 | 13.7674 | 13.425 | 13.7674
2108 | -0.42112 | -1.353 | 0.33683 | 0.08803 | 4.0965 | 4.7551 | 4.2762 | 4.4178 | 4.1022 | 2.0396 | 15.309 | 14.5145 | 15.309
2109 | 0.40445 | -0.081776 | 0.65706 | 0.46741 | 3.9234 | 5.7656 | 5.1858 | 5.1915 | 3.6868 | 1.7414 | 16.622 | 14.5374 | 16.622
2110 | 1.5377 | 0.77999 | 0.93794 | 0.7823 | 4.2184 | 7.162 | 6.1004 | 5.9076 | 4.1317 | 2.3489 | 19.6369 | 16.7993 | 19.6369
2111 | 0.33068 | 0.86428 | 0.62956 | 0.80628 | 5.1515 | 5.6712 | 6.8097 | 5.9803 | 4.2958 | 2.5412 | 19.3442 | 18.7982 | 19.3442
2112 | -0.2777 | -0.34621 | 0.39062 | 0.36459 | 3.528 | 4.9202 | 3.6016 | 4.9951 | 5.0772 | 1.3473 | 14.7906 | 13.5541 | 14.7906
2113 | -0.5614 | -0.95471 | 0.28726 | 0.16986 | 3.0849 | 4.5997 | 6.7819 | 4.611 | 5.118 | 1.9852 | 14.2809 | 16.97 | 16.97
2114 | -1.2236 | 0.74142 | 0.11055 | 0.77078 | 4.7031 | 3.9651 | 7.2049 | 5.8744 | 4.6594 | 1.8513 | 16.3938 | 18.4187 | 18.4187
2115 | 0.59435 | 0.31192 | 0.72386 | 0.62245 | 3.7422 | 6.0093 | 3.7332 | 5.5086 | 3.9215 | 1.7445 | 17.0045 | 13.1413 | 17.0045
2116 | 0.3818 | -0.50341 | 0.64869 | 0.30734 | 3.5067 | 5.7366 | 5.7407 | 4.8862 | 4.7189 | 2.7232 | 16.8527 | 16.6896 | 16.8527
2117 | 0.3403 | -0.21829 | 0.63319 | 0.4136 | 3.4088 | 5.6835 | 5.5232 | 5.0882 | 4.6188 | 1.596 | 15.7764 | 15.1467 | 15.7764
2118 | -0.42791 | -1.136 | 0.33436 | 0.12798 | 3.4257 | 4.7475 | 6.6419 | 4.5172 | 4.0944 | 1.4226 | 14.1129 | 15.5846 | 15.5846
2119 | -0.25041 | 1.131 | 0.40114 | 0.87097 | 4.9355 | 4.9523 | 6.767 | 6.2088 | 3.2837 | 2.136 | 18.2327 | 17.1222 | 18.2327
2120 | 0.23082 | -0.33936 | 0.59127 | 0.36717 | 4.5697 | 5.5441 | 5.0763 | 5 | 4.601 | 2.5171 | 17.6309 | 16.7641 | 17.6309
2121 | -1.0062 | -0.62822 | 0.15715 | 0.26493 | 3.0521 | 4.154 | 6.3579 | 4.8043 | 4.1322 | 2.133 | 14.1434 | 15.6752 | 15.6752
2122 | 0.52528 | 0.5875 | 0.70031 | 0.72156 | 3.3259 | 5.9206 | 4.4537 | 5.742 | 3.7432 | 1.4217 | 16.4102 | 12.9445 | 16.4102
2123 | -0.71693 | -0.30586 | 0.23671 | 0.37986 | 3.3741 | 4.4353 | 4.9966 | 5.024 | 4.4859 | 1.748 | 14.5814 | 14.6045 | 14.6045
2124 | 1.5314 | 2.2258 | 0.93716 | 0.98699 | 3.0587 | 7.1549 | 6.79 | 7.0475 | 3.9475 | 1.6404 | 18.9015 | 15.4366 | 18.9015
2125 | -0.68813 | -0.25903 | 0.24569 | 0.39781 | 4.0994 | 4.4651 | 4.6237 | 5.0581 | 5.0291 | 1.8818 | 15.5044 | 15.6341 | 15.6341
2126 | -1.8031 | -0.99644 | 0.035687 | 0.15952 | 3.6242 | 3.5609 | 4.6186 | 4.5885 | 3.6753 | 2.7331 | 14.5068 | 14.6512 | 14.6512
2127 | -0.61387 | 0.4148 | 0.26965 | 0.66085 | 3.6495 | 4.5433 | 7.3301 | 5.5949 | 4.6328 | 1.9446 | 15.7323 | 17.557 | 17.557
2128 | -0.58049 | -1.7088 | 0.28079 | 0.043741 | 4.5693 | 4.5791 | 6.3981 | 4.2844 | 3.9121 | 2.6805 | 16.1133 | 17.56 | 17.56
2129 | -1.2121 | -0.40858 | 0.11273 | 0.34142 | 3.4579 | 3.9746 | 5.1011 | 4.9511 | 4.6954 | 1.9871 | 14.3707 | 15.2416 | 15.2416
2130 | 1.2928 | 0.78065 | 0.90196 | 0.7825 | 4.9578 | 6.8801 | 7.3172 | 5.9082 | 4.6284 | 2.4414 | 20.1875 | 19.3449 | 20.1875
2131 | -0.87345 | 0.22448 | 0.19121 | 0.58881 | 2.6227 | 4.279 | 4.9912 | 5.4361 | 4.501 | 1.8516 | 14.1894 | 13.9665 | 14.1894
2132 | -0.15472 | 0.56657 | 0.43852 | 0.7145 | 3.8001 | 5.0662 | 7.6231 | 5.7241 | 4.2088 | 1.6502 | 16.2406 | 17.2822 | 17.2822
2133 | -0.24177 | 0.066732 | 0.40448 | 0.5266 | 2.8319 | 4.9625 | 5.8191 | 5.3082 | 4.3787 | 2.3693 | 15.4718 | 15.3989 | 15.4718
2134 | -0.011557 | -1.1623 | 0.49539 | 0.12256 | 3.7101 | 5.2406 | 5.6241 | 4.5044 | 3.8771 | 2.1346 | 15.5897 | 15.3459 | 15.5897
2135 | -1.4781 | -0.77344 | 0.069695 | 0.21963 | 4.9734 | 3.7698 | 3.5049 | 4.7145 | 4.6058 | 2.6689 | 16.1267 | 15.753 | 16.1267
2136 | 0.41578 | -0.16189 | 0.66122 | 0.4357 | 4.2906 | 5.7801 | 4.6056 | 5.1304 | 4.861 | 1.6566 | 16.8576 | 15.4137 | 16.8576
2137 | 0.91712 | 0.90282 | 0.82046 | 0.81669 | 2.8937 | 6.4202 | 5.776 | 6.0135 | 3.8717 | 2.0228 | 17.3502 | 14.5643 | 17.3502
2138 | -0.3683 | 0.067999 | 0.35632 | 0.52711 | 4.3937 | 4.8152 | 6.6844 | 5.3092 | 3.9529 | 1.4619 | 15.98 | 16.4928 | 16.4928
2139 | -1.7226 | -2.2278 | 0.042479 | 0.012945 | 3.0586 | 3.6085 | 6.8169 | 4.1495 | 4.7307 | 2.0958 | 12.9123 | 16.7021 | 16.7021
2140 | -0.51415 | -0.48024 | 0.30357 | 0.31553 | 2.7957 | 4.6514 | 4.722 | 4.9018 | 3.5841 | 2.0076 | 14.3564 | 13.1094 | 14.3564
2141 | 0.011981 | 1.202 | 0.50478 | 0.88531 | 3.7964 | 5.2697 | 4.7046 | 6.2688 | 3.2326 | 1.9556 | 17.2905 | 13.6892 | 17.2905
2142 | 1.3319 | -0.17956 | 0.90856 | 0.42875 | 5.1725 | 6.9262 | 3.9498 | 5.1171 | 3.6895 | 1.9319 | 19.1477 | 14.7437 | 19.1477
2143 | -1.0018 | 0.022457 | 0.15823 | 0.50896 | 3.6012 | 4.158 | 6.3146 | 5.273 | 3.2035 | 1.8537 | 14.8859 | 14.973 | 14.973
2144 | 0.02585 | -0.17907 | 0.51031 | 0.42894 | 4.5892 | 5.2869 | 4.496 | 5.1174 | 4.7479 | 1.6897 | 16.6832 | 15.5227 | 16.6832
2145 | 0.75079 | 0.96037 | 0.77361 | 0.83156 | 4.2106 | 6.2095 | 7.1696 | 6.063 | 4.3266 | 2.4719 | 18.955 | 18.1787 | 18.955
2146 | -0.17393 | 0.30649 | 0.43096 | 0.62039 | 5.136 | 5.0432 | 6.5501 | 5.5041 | 4.9836 | 2.1281 | 17.8114 | 18.7979 | 18.7979
2147 | -0.44689 | -0.52996 | 0.32748 | 0.29807 | 2.9323 | 4.7261 | 6.8228 | 4.8684 | 3.7398 | 2.012 | 14.5387 | 15.5069 | 15.5069
2148 | 0.55409 | -0.029616 | 0.71024 | 0.48819 | 4.3239 | 5.9576 | 6.6623 | 5.232 | 3.8396 | 1.6413 | 17.1548 | 16.4671 | 17.1548
2149 | 0.17819 | 0.17237 | 0.57071 | 0.56843 | 3.2552 | 5.4775 | 6.1163 | 5.3934 | 5.4242 | 1.9767 | 16.1028 | 16.7723 | 16.7723
2150 | -0.31611 | 1.3233 | 0.37596 | 0.90712 | 4.2995 | 4.8754 | 5.0655 | 6.3703 | 3.7842 | 2.2368 | 17.782 | 15.3861 | 17.782
2151 | -0.50176 | -1.2391 | 0.30792 | 0.10765 | 4.2391 | 4.665 | 4.4594 | 4.4682 | 5.4447 | 1.7617 | 15.134 | 15.9049 | 15.9049
2152 | 0.58096 | -0.26153 | 0.71937 | 0.39684 | 2.8962 | 5.9921 | 6.1806 | 5.0563 | 3.3137 | 1.8072 | 15.7518 | 14.1977 | 15.7518
2153 | 0.88108 | 0.89901 | 0.81086 | 0.81568 | 4.9211 | 6.3748 | 3.0962 | 6.0102 | 5.1242 | 2.606 | 19.9121 | 15.7475 | 19.9121
2154 | -2.0803 | -0.3333 | 0.018748 | 0.36945 | 3.0025 | 3.4172 | 3.6521 | 5.0043 | 3.9547 | 2.9163 | 14.3403 | 13.5256 | 14.3403
2155 | -0.083313 | -0.64657 | 0.4668 | 0.25895 | 3.0323 | 5.1527 | 5.8305 | 4.7926 | 4.2737 | 2.2596 | 15.2372 | 15.396 | 15.396
2156 | -0.50851 | -1.2781 | 0.30555 | 0.10061 | 4.901 | 4.6576 | 5.2149 | 4.4505 | 4.3498 | 1.9498 | 15.9589 | 16.4155 | 16.4155
2157 | -1.3677 | -1.4797 | 0.085703 | 0.069482 | 4.8177 | 3.8511 | 7.2758 | 4.3662 | 5.6124 | 1.639 | 14.6739 | 19.3448 | 19.3448
2158 | 0.8181 | 1.0016 | 0.79335 | 0.84173 | 3.7655 | 6.2951 | 4.5677 | 6.0984 | 4.0833 | 2.2339 | 18.3929 | 14.6505 | 18.3929
2159 | 0.77003 | -0.046423 | 0.77936 | 0.48149 | 2.4133 | 6.234 | 5.249 | 5.2189 | 4.8747 | 1.7025 | 15.5687 | 14.2395 | 15.5687
2160 | -2.5629 | -1.0595 | 0.00519 | 0.14469 | 3.6137 | 3.2346 | 6.3809 | 4.5555 | 4.3451 | 1.4249 | 12.8288 | 15.7646 | 15.7646
2161 | 0.93818 | 1.9115 | 0.82592 | 0.97203 | 2.6587 | 6.4466 | 2.9807 | 6.8308 | 4.5157 | 1.6168 | 17.5529 | 11.7719 | 17.5529
2162 | 2.0766 | 0.0060507 | 0.98108 | 0.50241 | 3.9395 | 7.7137 | 3.3194 | 5.26 | 3.7691 | 2.0175 | 18.9307 | 13.0456 | 18.9307
2163 | -0.56689 | 0.26464 | 0.2854 | 0.60436 | 3.6784 | 4.5938 | 5.9124 | 5.4693 | 5.1333 | 2.4216 | 16.1631 | 17.1457 | 17.1457
2164 | 1.0214 | 0.91957 | 0.84648 | 0.8211 | 4.4423 | 6.5505 | 5.9005 | 6.0279 | 3.5278 | 2.007 | 19.0277 | 15.8776 | 19.0277
2165 | 0.59415 | 0.83487 | 0.72379 | 0.7981 | 3.6189 | 6.009 | 5.1401 | 5.9549 | 4.6851 | 2.6989 | 18.2817 | 16.1429 | 18.2817
2166 | 1.0882 | 1.192 | 0.86174 | 0.88338 | 4.6141 | 6.633 | 7.7349 | 6.2604 | 4.2948 | 2.3722 | 19.8797 | 19.0159 | 19.8797
2167 | 0.86118 | -0.15361 | 0.80543 | 0.43896 | 4.4793 | 6.3496 | 7.1859 | 5.1366 | 3.6717 | 2.8647 | 18.8303 | 18.2017 | 18.8303
2168 | 0.19126 | -0.57951 | 0.57584 | 0.28112 | 4.4281 | 5.494 | 5.7893 | 4.8358 | 3.745 | 2.5017 | 17.2595 | 16.4641 | 17.2595
2169 | -1.1529 | -0.41041 | 0.12448 | 0.34075 | 5.015 | 4.0244 | 5.7575 | 4.9498 | 4.8816 | 1.7257 | 15.7149 | 17.3798 | 17.3798
2170 | 2.201 | 1.2731 | 0.98613 | 0.8985 | 3.2947 | 7.8256 | 7.0088 | 6.3285 | 4.2284 | 1.332 | 18.7807 | 15.8639 | 18.7807
2171 | 0.75474 | 1.0431 | 0.7748 | 0.85155 | 4.3855 | 6.2145 | 6.02 | 6.1339 | 3.6878 | 1.4797 | 18.2136 | 15.573 | 18.2136
2172 | 1.6704 | 0.84556 | 0.95258 | 0.8011 | 4.5042 | 7.3072 | 6.5903 | 5.9642 | 3.9032 | 1.4078 | 19.1834 | 16.4054 | 19.1834
2173 | -0.1422 | 0.9854 | 0.44346 | 0.83779 | 4.5345 | 5.0813 | 7.5104 | 6.0845 | 4.5682 | 1.2289 | 16.9292 | 17.842 | 17.842
2174 | -1.7131 | -0.8679 | 0.04335 | 0.19272 | 3.0067 | 3.6143 | 4.8217 | 4.6594 | 3.9074 | 2.3378 | 13.6182 | 14.0736 | 14.0736
2175 | 0.10621 | -1.338 | 0.54229 | 0.09045 | 4.5287 | 5.387 | 6.6894 | 4.4242 | 3.3795 | 2.1184 | 16.4584 | 16.716 | 16.716
2176 | 1.0658 | 0.85295 | 0.85674 | 0.80316 | 3.1589 | 6.6054 | 5.1329 | 5.9705 | 4.1633 | 1.974 | 17.7088 | 14.4291 | 17.7088
2177 | -1.79 | -0.2287 | 0.036727 | 0.40955 | 3.9734 | 3.5684 | 5.3457 | 5.0804 | 3.9441 | 2.183 | 14.8053 | 15.4462 | 15.4462
2178 | -0.0050088 | 0.20358 | 0.498 | 0.58066 | 4.291 | 5.2487 | 6.716 | 5.419 | 5.0969 | 2.0571 | 17.0157 | 18.1609 | 18.1609
2179 | -0.2649 | -0.27337 | 0.39554 | 0.39228 | 3.3436 | 4.9352 | 5.6664 | 5.0476 | 3.8402 | 2.2145 | 15.5409 | 15.0647 | 15.5409
2180 | -2.1815 | -1.0917 | 0.014571 | 0.13748 | 3.9382 | 3.3722 | 6.9245 | 4.5392 | 3.8253 | 1.7207 | 13.5703 | 16.4087 | 16.4087
2181 | 0.074223 | -0.81056 | 0.52958 | 0.20881 | 3.6556 | 5.347 | 3.896 | 4.6925 | 5.0726 | 2.6219 | 16.317 | 15.246 | 16.317
2182 | -1.7252 | -2.0252 | 0.042245 | 0.021422 | 4.7066 | 3.6069 | 5.1012 | 4.1945 | 3.6138 | 1.6854 | 14.1934 | 15.107 | 15.107
2183 | 0.22675 | 0.22809 | 0.58969 | 0.59021 | 4.2168 | 5.5389 | 5.5163 | 5.4391 | 3.6963 | 1.5014 | 16.6962 | 14.9308 | 16.6962
2184 | 1.3059 | 1.1969 | 0.90421 | 0.88433 | 4.3087 | 6.8956 | 6.6641 | 6.2646 | 5.4939 | 1.2868 | 18.7557 | 17.7535 | 18.7557
2185 | 0.99466 | 1.905 | 0.84005 | 0.97161 | 5.268 | 6.5172 | 6.2067 | 6.826 | 3.2957 | 2.5369 | 21.1482 | 17.3073 | 21.1482
2186 | -0.1528 | -0.69574 | 0.43928 | 0.2433 | 4.0037 | 5.0685 | 7.3957 | 4.7618 | 4.6893 | 1.8603 | 15.6944 | 17.949 | 17.949
2187 | 1.2192 | 0.75319 | 0.88862 | 0.77433 | 5.2573 | 6.7923 | 7.1032 | 5.8845 | 4.0073 | 1.579 | 19.5131 | 17.9468 | 19.5131
2188 | 0.088523 | 0.25219 | 0.53527 | 0.59955 | 4.3309 | 5.3649 | 5.3122 | 5.459 | 4.8959 | 2.0154 | 17.1701 | 16.5544 | 17.1701
2189 | -0.25628 | -0.20542 | 0.39887 | 0.41862 | 2.9835 | 4.9454 | 5.2907 | 5.0977 | 4.1393 | 1.7931 | 14.8197 | 14.2065 | 14.8197
2190 | 0.72745 | 0.84074 | 0.76653 | 0.79975 | 3.8907 | 6.1797 | 4.9678 | 5.96 | 4.3753 | 2.6578 | 18.6883 | 15.8916 | 18.6883
2191 | 1.3186 | 0.57901 | 0.90635 | 0.71871 | 5.0293 | 6.9106 | 4.0741 | 5.7347 | 3.4168 | 1.8009 | 19.4756 | 14.3211 | 19.4756
2192 | -0.12458 | -0.046465 | 0.45043 | 0.48147 | 4.7168 | 5.1026 | 4.3426 | 5.2189 | 4.5412 | 1.9424 | 16.9806 | 15.543 | 16.9806
2193 | -0.71421 | 0.42368 | 0.23755 | 0.6641 | 3.4031 | 4.4381 | 5.4476 | 5.6025 | 4.242 | 1.7628 | 15.2065 | 14.8555 | 15.2065
2194 | 0.43468 | -0.31057 | 0.6681 | 0.37806 | 4.3076 | 5.8043 | 4.7398 | 5.0206 | 3.8301 | 2.2273 | 17.3599 | 15.1048 | 17.3599
2195 | 0.39109 | 0.57882 | 0.65213 | 0.71865 | 4.9199 | 5.7485 | 6.2306 | 5.7346 | 3.7698 | 1.7267 | 18.1296 | 16.647 | 18.1296
2196 | 0.023218 | -0.098287 | 0.50926 | 0.46085 | 3.242 | 5.2836 | 6.9181 | 5.1788 | 4.0007 | 1.3766 | 15.081 | 15.5374 | 15.5374
2197 | 0.37155 | 0.40493 | 0.64489 | 0.65723 | 3.8957 | 5.7235 | 6.6346 | 5.5866 | 3.2232 | 1.7214 | 16.9272 | 15.4749 | 16.9272
2198 | 1.5009 | 0.68492 | 0.93332 | 0.7533 | 4.0531 | 7.1208 | 4.6601 | 5.8257 | 6.1122 | 2.0137 | 19.0133 | 16.8392 | 19.0133
2199 | -0.51985 | -0.0010557 | 0.30158 | 0.49958 | 4.046 | 4.6451 | 5.804 | 5.2544 | 4.6073 | 2.0023 | 15.9477 | 16.4596 | 16.4596
2200 | -0.64162 | -1.1345 | 0.26056 | 0.1283 | 4.7717 | 4.5139 | 7.6189 | 4.5179 | 4.6378 | 1.2885 | 15.0919 | 18.3169 | 18.3169
2201 | -1.7669 | -1.9955 | 0.038624 | 0.022995 | 2.7884 | 3.582 | 5.1362 | 4.2019 | 3.759 | 2.1132 | 12.6855 | 13.7969 | 13.7969
2202 | 0.08859 | -0.94638 | 0.5353 | 0.17198 | 5.2316 | 5.3649 | 6.716 | 4.6155 | 3.3969 | 1.7089 | 16.921 | 17.0534 | 17.0534
2203 | 0.6642 | 1.9887 | 0.74672 | 0.97663 | 3.479 | 6.0988 | 6.6616 | 6.8861 | 4.9442 | 2.1291 | 18.593 | 17.2139 | 18.593
2204 | -1.8393 | -2.3976 | 0.032936 | 0.0082515 | 2.808 | 3.5404 | 6.0004 | 4.1184 | 3.3929 | 2.8202 | 13.2869 | 15.0214 | 15.0214
2205 | 1.1557 | 0.54377 | 0.87609 | 0.7067 | 5.0468 | 6.7155 | 5.2216 | 5.7046 | 4.7803 | 1.294 | 18.7609 | 16.3427 | 18.7609
2206 | 0.56372 | -0.16768 | 0.71353 | 0.43342 | 4.8729 | 5.97 | 5.445 | 5.126 | 4.6778 | 2.403 | 18.3719 | 17.3988 | 18.3719
2207 | -1.7312 | -0.82883 | 0.041705 | 0.2036 | 3.8446 | 3.6032 | 5.3359 | 4.6819 | 3.1905 | 2.0019 | 14.1316 | 14.3729 | 14.3729
2208 | -0.22254 | -0.9393 | 0.41195 | 0.17379 | 3.278 | 4.9852 | 4.9614 | 4.6194 | 4.2937 | 1.7125 | 14.5951 | 14.2455 | 14.5951
2209 | -0.41158 | -0.29765 | 0.34032 | 0.38298 | 4.6301 | 4.7659 | 7.1056 | 5.03 | 5.237 | 1.8037 | 16.2297 | 18.7764 | 18.7764
2210 | -0.27979 | 0.68222 | 0.38982 | 0.75245 | 4.5527 | 4.9178 | 5.5091 | 5.8234 | 3.5706 | 1.7261 | 17.02 | 15.3585 | 17.02
2211 | -0.89686 | 0.54525 | 0.1849 | 0.70721 | 3.1553 | 4.2564 | 7.0994 | 5.7058 | 3.3384 | 2.6057 | 15.7232 | 16.1988 | 16.1988
2212 | 1.1578 | -0.3166 | 0.87652 | 0.37577 | 3.0182 | 6.718 | 5.6702 | 5.0163 | 3.3281 | 1.7925 | 16.5451 | 13.809 | 16.5451
2213 | -0.55425 | -1.0288 | 0.28971 | 0.15178 | 2.3359 | 4.6075 | 4.7398 | 4.5714 | 4.7212 | 2.3268 | 13.8417 | 14.1238 | 14.1238
2214 | -1.6991 | -0.51151 | 0.044649 | 0.3045 | 3.9142 | 3.6229 | 5.4378 | 4.8807 | 3.8114 | 2.1876 | 14.6054 | 15.3511 | 15.3511
2215 | 0.05082 | 0.11084 | 0.52027 | 0.54413 | 4.1297 | 5.3179 | 5.664 | 5.3435 | 4.4169 | 1.9692 | 16.7603 | 16.1798 | 16.7603
2216 | 0.41236 | 1.264 | 0.65996 | 0.89688 | 4.1701 | 5.7757 | 4.1463 | 6.3209 | 4.2982 | 2.3922 | 18.6588 | 15.0067 | 18.6588
2217 | -0.30608 | -0.93667 | 0.37977 | 0.17446 | 4.202 | 4.8871 | 4.2933 | 4.6208 | 5.2451 | 2.5331 | 16.243 | 16.2736 | 16.2736
2218 | 0.85898 | 0.49569 | 0.80482 | 0.68994 | 4.2136 | 6.3469 | 6.0832 | 5.6636 | 3.7579 | 2.0277 | 18.2517 | 16.0824 | 18.2517
2219 | -0.92324 | -1.0274 | 0.17794 | 0.15211 | 4.1516 | 4.2313 | 7.2287 | 4.5722 | 5.5885 | 1.5867 | 14.5417 | 18.5554 | 18.5554
2220 | 0.69993 | 0.14522 | 0.75802 | 0.55773 | 4.2498 | 6.1445 | 3.722 | 5.3714 | 4.2767 | 2.7543 | 18.5199 | 15.0028 | 18.5199
2221 | -0.57172 | -0.40825 | 0.28376 | 0.34154 | 4.198 | 4.5886 | 7.4376 | 4.9513 | 4.3903 | 1.8809 | 15.6188 | 17.9069 | 17.9069
2222 | -0.12252 | -1.1323 | 0.45125 | 0.12875 | 3.9908 | 5.1051 | 6.0977 | 4.519 | 3.4628 | 2.4149 | 16.0297 | 15.9662 | 16.0297
2223 | -0.089311 | -0.12125 | 0.46442 | 0.45175 | 3.8046 | 5.1454 | 4.9206 | 5.1612 | 5.4768 | 2.3158 | 16.4269 | 16.5177 | 16.5177
2224 | 0.57492 | 0.5458 | 0.71733 | 0.7074 | 5.195 | 5.9843 | 5.6943 | 5.7063 | 4.4155 | 2.0834 | 18.969 | 17.3882 | 18.969
2225 | -0.66361 | -0.33241 | 0.25347 | 0.36979 | 3.6954 | 4.4907 | 4.6704 | 5.0049 | 4.5335 | 2.1439 | 15.335 | 15.0432 | 15.335
2226 | -0.78965 | -0.99138 | 0.21487 | 0.16075 | 3.4256 | 4.3615 | 3.8501 | 4.5912 | 4.5418 | 1.9915 | 14.3698 | 13.809 | 14.3698
2227 | -0.26233 | 0.37277 | 0.39653 | 0.64534 | 4.6668 | 4.9383 | 5.671 | 5.5595 | 3.5907 | 2.3707 | 17.5353 | 16.2992 | 17.5353
2228 | -0.68708 | 0.64262 | 0.24602 | 0.73977 | 3.6969 | 4.4662 | 5.5619 | 5.7893 | 3.9049 | 2.3456 | 16.298 | 15.5093 | 16.298
2229 | 0.7551 | 0.3105 | 0.77491 | 0.62191 | 3.9531 | 6.215 | 4.5249 | 5.5074 | 3.6939 | 2.4406 | 18.1161 | 14.6125 | 18.1161
2230 | -0.49106 | 0.73578 | 0.31169 | 0.76907 | 2.6971 | 4.6769 | 4.766 | 5.8695 | 4.3024 | 2.3855 | 15.629 | 14.151 | 15.629
2231 | 0.14545 | -0.58422 | 0.55782 | 0.27953 | 3.3622 | 5.4362 | 6.0146 | 4.8327 | 3.9104 | 2.5992 | 16.2303 | 15.8863 | 16.2303
2232 | 0.71384 | 0.85523 | 0.76234 | 0.80379 | 4.8801 | 6.1623 | 5.706 | 5.9725 | 4.3561 | 2.0801 | 19.095 | 17.0224 | 19.095
2233 | -1.5297 | -2.0091 | 0.063048 | 0.022265 | 3.4055 | 3.7336 | 6.3872 | 4.1985 | 6.4375 | 2.1553 | 13.4928 | 18.3855 | 18.3855
2234 | 1.0702 | 1.1505 | 0.85774 | 0.87502 | 4.4135 | 6.6108 | 6.9929 | 6.2253 | 5.7273 | 1.6821 | 18.9317 | 18.8157 | 18.9317
2235 | -0.32426 | 0.093904 | 0.37287 | 0.53741 | 3.8256 | 4.866 | 4.557 | 5.3299 | 4.3608 | 1.4928 | 15.5143 | 14.2362 | 15.5143
2236 | 0.66803 | 0.70324 | 0.74794 | 0.75905 | 3.8752 | 6.1037 | 5.1 | 5.8415 | 4.6597 | 2.3771 | 18.1975 | 16.0121 | 18.1975
2237 | 0.64171 | 1.0567 | 0.73947 | 0.85469 | 3.5479 | 6.07 | 7.7444 | 6.1456 | 4.4063 | 1.9068 | 17.6703 | 17.6054 | 17.6703
2238 | -0.33177 | -0.2677 | 0.37003 | 0.39446 | 5.2779 | 4.8573 | 5.5904 | 5.0518 | 3.7084 | 2.3726 | 17.5595 | 16.9492 | 17.5595
2239 | 0.69038 | -0.16246 | 0.75502 | 0.43547 | 2.8402 | 6.1323 | 7.4373 | 5.13 | 5.1461 | 1.4568 | 15.5593 | 16.8804 | 16.8804
2240 | 1.1173 | 0.76021 | 0.86807 | 0.77643 | 2.9717 | 6.6687 | 6.8258 | 5.8906 | 4.0505 | 1.9601 | 17.4911 | 15.808 | 17.4911
2241 | -1.5122 | -0.32282 | 0.06524 | 0.37342 | 3.3465 | 3.7457 | 7.1949 | 5.0118 | 4.0922 | 1.8535 | 13.9575 | 16.4871 | 16.4871
2242 | 0.099113 | 0.9643 | 0.53948 | 0.83255 | 4.2253 | 5.3781 | 6.3273 | 6.0664 | 4.2531 | 1.247 | 16.9169 | 16.0527 | 16.9169
2243 | -4.0055 | -4.566 | 3.0949e-05 | 2.4858e-06 | 4.1198 | 3.0254 | 6.3021 | 4.002 | 4.9526 | 1.8726 | 13.0198 | 17.2471 | 17.2471
2244 | -1.024 | -2.1146 | 0.15291 | 0.017233 | 4.7479 | 4.1377 | 4.9572 | 4.1735 | 4.1227 | 2.3518 | 15.4109 | 16.1795 | 16.1795
2245 | 0.64119 | 0.72074 | 0.7393 | 0.76447 | 2.3062 | 6.0693 | 5.9845 | 5.8566 | 3.4835 | 2.4293 | 16.6613 | 14.2035 | 16.6613
2246 | 0.60837 | 0.88275 | 0.72853 | 0.81131 | 3.3004 | 6.0273 | 7.7347 | 5.9962 | 4.8286 | 1.6527 | 16.9766 | 17.5164 | 17.5164
2247 | -1.3233 | 0.25605 | 0.092865 | 0.60104 | 4.2453 | 3.8852 | 3.714 | 5.4622 | 4.0712 | 1.7638 | 15.3565 | 13.7943 | 15.3565
2248 | -0.35854 | -1.6928 | 0.35997 | 0.045245 | 3.6985 | 4.8264 | 7.549 | 4.2896 | 4.4268 | 2.5263 | 15.3408 | 18.2005 | 18.2005
2249 | 0.30487 | 0.27602 | 0.61977 | 0.60873 | 4.7348 | 5.6383 | 6.9387 | 5.4787 | 4.3125 | 2.6363 | 18.488 | 18.6222 | 18.6222
2250 | 2.4454 | 0.39555 | 0.99277 | 0.65378 | 2.1409 | 8.0275 | 5.8476 | 5.5787 | 4.1217 | 1.3845 | 17.1316 | 13.4948 | 17.1316
2251 | 0.52786 | 0.29103 | 0.7012 | 0.61448 | 2.9477 | 5.9239 | 6.4268 | 5.4912 | 5.8253 | 2.156 | 16.5188 | 17.3559 | 17.3559
2252 | -1.5159 | 0.75236 | 0.064772 | 0.77408 | 3.5304 | 3.7432 | 4.3516 | 5.8838 | 3.4039 | 2.3189 | 15.4763 | 13.6048 | 15.4763
2253 | 1.0998 | 0.90917 | 0.86429 | 0.81837 | 3.2488 | 6.6473 | 5.0893 | 6.019 | 4.4763 | 1.7776 | 17.6925 | 14.592 | 17.6925
2254 | 1.2803 | 2.4635 | 0.89979 | 0.99312 | 5.1684 | 6.8653 | 7.4396 | 7.1951 | 3.7617 | 1.1601 | 20.3889 | 17.5298 | 20.3889
2255 | -0.095887 | -0.18649 | 0.46181 | 0.42603 | 3.9237 | 5.1374 | 6.7266 | 5.1119 | 5.335 | 1.3847 | 15.5577 | 17.37 | 17.37
2256 | 1.9865 | 3.2696 | 0.97651 | 0.99946 | 3.4309 | 7.6288 | 5.8097 | 7.5836 | 4.5792 | 1.8699 | 20.5131 | 15.6896 | 20.5131
2257 | 1.094 | 1.0158 | 0.86303 | 0.84514 | 2.7446 | 6.6402 | 4.766 | 6.1105 | 3.6032 | 2.5479 | 18.0433 | 13.6617 | 18.0433
2258 | 0.41773 | 1.2916 | 0.66193 | 0.90175 | 3.7582 | 5.7826 | 7.2482 | 6.3439 | 4.5269 | 2.3434 | 18.2281 | 17.8766 | 18.2281
2259 | 0.80339 | 0.9787 | 0.78912 | 0.83614 | 4.52 | 6.2764 | 5.2947 | 6.0787 | 4.626 | 1.7303 | 18.6054 | 16.1711 | 18.6054
2260 | 0.74437 | 0.59525 | 0.77167 | 0.72416 | 3.7837 | 6.2013 | 5.0284 | 5.7486 | 5.3358 | 2.1118 | 17.8455 | 16.2597 | 17.8455
2261 | 0.053825 | -0.21937 | 0.52146 | 0.41318 | 4.8753 | 5.3216 | 6.1071 | 5.0874 | 5.4044 | 1.2963 | 16.5806 | 17.6832 | 17.6832
2262 | -3.1867 | -1.0354 | 0.00071952 | 0.15023 | 3.8874 | 3.0988 | 7.0819 | 4.568 | 4.4637 | 2.4162 | 13.9703 | 17.8491 | 17.8491
2263 | 1.1508 | 0.54439 | 0.87509 | 0.70691 | 5.4645 | 6.7095 | 4.1548 | 5.7051 | 3.913 | 2.0167 | 19.8958 | 15.549 | 19.8958
2264 | -0.0089889 | 0.18728 | 0.49641 | 0.57428 | 4.6371 | 5.2438 | 4.8846 | 5.4056 | 4.2531 | 2.4733 | 17.7598 | 16.2481 | 17.7598
2265 | 0.76849 | 0.30344 | 0.7789 | 0.61922 | 3.8657 | 6.232 | 6.8045 | 5.5015 | 4.5227 | 2.5259 | 18.1251 | 17.7187 | 18.1251
2266 | -1.2927 | -1.0941 | 0.098056 | 0.13695 | 4.5535 | 3.9093 | 4.4612 | 4.538 | 4.1738 | 1.715 | 14.7158 | 14.9036 | 14.9036
2267 | 2.1028 | 0.2589 | 0.98226 | 0.60215 | 3.7205 | 7.7377 | 6.6056 | 5.4645 | 4.7334 | 2.2182 | 19.1409 | 17.2777 | 19.1409
2268 | -1.4075 | 0.11508 | 0.079642 | 0.54581 | 4.7986 | 3.8212 | 2.9965 | 5.347 | 5.5011 | 1.9993 | 15.9661 | 15.2956 | 15.9661
2269 | 0.57475 | 2.2954 | 0.71727 | 0.98915 | 2.5501 | 5.9841 | 3.1106 | 7.0922 | 4.5047 | 2.0766 | 17.7031 | 12.242 | 17.7031
2270 | 0.03034 | 0.97705 | 0.5121 | 0.83573 | 3.9377 | 5.2924 | 7.3513 | 6.0773 | 3.6339 | 1.477 | 16.7845 | 16.3999 | 16.7845
2271 | -0.56894 | -1.6087 | 0.2847 | 0.053836 | 3.7949 | 4.5916 | 3.8282 | 4.3183 | 4.725 | 1.9749 | 14.6797 | 14.3229 | 14.6797
2272 | -0.093751 | 0.56186 | 0.46265 | 0.7129 | 3.5679 | 5.14 | 4.5198 | 5.72 | 5.0662 | 1.7399 | 16.1678 | 14.8938 | 16.1678
2273 | 0.010952 | 1.0601 | 0.50437 | 0.85545 | 3.6779 | 5.2684 | 7.427 | 6.1484 | 4.5082 | 1.9824 | 17.0772 | 17.5956 | 17.5956
2274 | -0.82618 | -0.4376 | 0.20435 | 0.33084 | 3.7387 | 4.3252 | 7.6242 | 4.931 | 4.4668 | 1.7613 | 14.7562 | 17.591 | 17.591
2275 | -0.6363 | -0.50318 | 0.26229 | 0.30742 | 3.1856 | 4.5195 | 6.538 | 4.8863 | 3.7835 | 1.8198 | 14.4113 | 15.327 | 15.327
2276 | 1.3643 | 0.50048 | 0.91377 | 0.69163 | 3.9866 | 6.9641 | 3.4198 | 5.6676 | 4.8996 | 1.5764 | 18.1949 | 13.8825 | 18.1949
2277 | 0.0040577 | 0.42712 | 0.50162 | 0.66536 | 3.486 | 5.2599 | 4.4776 | 5.6054 | 4.8953 | 1.3958 | 15.7471 | 14.2547 | 15.7471
2278 | -0.56918 | 1.2601 | 0.28462 | 0.89619 | 4.9013 | 4.5913 | 5.6019 | 6.3177 | 3.5822 | 1.9936 | 17.8039 | 16.079 | 17.8039
2279 | -0.048931 | 0.31033 | 0.48049 | 0.62184 | 4.3815 | 5.1947 | 3.6916 | 5.5073 | 4.7421 | 2.4293 | 17.5127 | 15.2444 | 17.5127
2280 | -0.41638 | -0.14582 | 0.33857 | 0.44203 | 3.1465 | 4.7605 | 4.4209 | 5.1425 | 4.2649 | 2.822 | 15.8715 | 14.6543 | 15.8715
2281 | 0.218 | 0.21883 | 0.58629 | 0.58661 | 4.5355 | 5.5278 | 5.6785 | 5.4315 | 3.64 | 1.9245 | 17.4193 | 15.7785 | 17.4193
2282 | 0.31132 | -1.237 | 0.62222 | 0.10804 | 4.3284 | 5.6465 | 5.533 | 4.4692 | 4.3893 | 2.2257 | 16.6697 | 16.4763 | 16.6697
2283 | 0.44842 | 0.87674 | 0.67308 | 0.80969 | 3.1582 | 5.822 | 6.912 | 5.991 | 3.6472 | 1.1775 | 16.1488 | 14.895 | 16.1488
2284 | -1.1085 | -2.914 | 0.13383 | 0.001784 | 5.0894 | 4.0626 | 7.0868 | 4.0542 | 4.5137 | 1.9375 | 15.1437 | 18.6275 | 18.6275
2285 | -0.11308 | -0.44029 | 0.45498 | 0.32987 | 3.2082 | 5.1165 | 6.4928 | 4.9291 | 5.6075 | 2.4188 | 15.6727 | 17.7273 | 17.7273
2286 | 0.83079 | 0.75939 | 0.79695 | 0.77619 | 5.4952 | 6.3112 | 3.9323 | 5.8899 | 3.5928 | 1.9287 | 19.6249 | 14.949 | 19.6249
2287 | -0.35567 | 0.86017 | 0.36105 | 0.80515 | 4.5562 | 4.8297 | 6.5217 | 5.9768 | 4.4254 | 2.3304 | 17.6931 | 17.8336 | 17.8336
2288 | -1.8281 | -2.0453 | 0.033768 | 0.02041 | 3.7982 | 3.5467 | 6.2557 | 4.1896 | 3.933 | 2.5901 | 14.1246 | 16.5771 | 16.5771
2289 | 1.2602 | -0.22004 | 0.8962 | 0.41292 | 3.9417 | 6.8413 | 6.7616 | 5.0869 | 4.8833 | 1.7306 | 17.6005 | 17.3172 | 17.6005
2290 | -0.92316 | -1.7029 | 0.17796 | 0.044294 | 4.1452 | 4.2313 | 4.5597 | 4.2863 | 4.4278 | 2.4505 | 15.1133 | 15.5832 | 15.5832
2291 | -0.54066 | 0.69888 | 0.29437 | 0.75769 | 5.1141 | 4.6223 | 4.7081 | 5.8377 | 4.8353 | 1.6289 | 17.203 | 16.2864 | 17.203
2292 | -1.8823 | -1.1324 | 0.029901 | 0.12873 | 5.1734 | 3.5167 | 7.1251 | 4.5189 | 5.1731 | 2.4638 | 15.6729 | 19.9354 | 19.9354
2293 | -0.7976 | 0.86082 | 0.21255 | 0.80533 | 3.3934 | 4.3536 | 7.3384 | 5.9773 | 4.7663 | 1.9472 | 15.6716 | 17.4454 | 17.4454
2294 | 1.6433 | 0.38576 | 0.94984 | 0.65016 | 4.6367 | 7.278 | 7.4391 | 5.5705 | 3.5897 | 1.743 | 19.2282 | 17.4085 | 19.2282
2295 | 1.0823 | 1.3707 | 0.86044 | 0.91477 | 4.6164 | 6.6257 | 4.125 | 6.4095 | 3.3024 | 2.0177 | 19.6693 | 14.0616 | 19.6693
2296 | 1.2768 | 0.44821 | 0.89916 | 0.673 | 4.7524 | 6.8611 | 6.1263 | 5.6232 | 5.8909 | 2.0381 | 19.2748 | 18.8078 | 19.2748
2297 | -0.21692 | 1.1769 | 0.41413 | 0.88038 | 4.157 | 4.9919 | 4.7203 | 6.2477 | 3.5077 | 2.4675 | 17.8641 | 14.8526 | 17.8641
2298 | 1.0517 | 1.8289 | 0.85353 | 0.96629 | 5.355 | 6.588 | 5.2985 | 6.77 | 3.7467 | 2.0603 | 20.7732 | 16.4604 | 20.7732
2299 | 1.9232 | 1.0797 | 0.97277 | 0.85985 | 3.4313 | 7.5673 | 6.1882 | 6.1651 | 4.0843 | 1.9254 | 19.0891 | 15.6291 | 19.0891
2300 | 0.66528 | 0.27196 | 0.74706 | 0.60717 | 4.2323 | 6.1002 | 5.8702 | 5.4754 | 5.3698 | 1.7918 | 17.5996 | 17.2641 | 17.5996
2301 | -0.11608 | 0.2008 | 0.45379 | 0.57957 | 3.7932 | 5.1129 | 5.7279 | 5.4167 | 4.4832 | 1.919 | 16.2417 | 15.9233 | 16.2417
2302 | 1.0708 | 0.74017 | 0.85787 | 0.7704 | 4.526 | 6.6116 | 5.5043 | 5.8733 | 4.2709 | 2.4105 | 19.4214 | 16.7117 | 19.4214
2303 | 0.74269 | -0.056589 | 0.77117 | 0.47744 | 2.9912 | 6.1991 | 6.3697 | 5.211 | 3.8952 | 2 | 16.4014 | 15.2561 | 16.4014
2304 | 0.31998 | 0.079864 | 0.62551 | 0.53183 | 3.9579 | 5.6575 | 6.0484 | 5.3187 | 3.6244 | 1.9578 | 16.8919 | 15.5885 | 16.8919
2305 | -0.78996 | 0.9237 | 0.21478 | 0.82218 | 3.6226 | 4.3612 | 5.8505 | 6.0315 | 3.8197 | 2.151 | 16.1662 | 15.4438 | 16.1662
2306 | 1.1061 | 0.336 | 0.86565 | 0.63156 | 3.9146 | 6.6549 | 6.4038 | 5.5287 | 4.1374 | 1.7586 | 17.8568 | 16.2145 | 17.8568
2307 | -0.4996 | 1.2184 | 0.30868 | 0.88846 | 5.5972 | 4.6674 | 4.7579 | 6.2827 | 4.006 | 2.2278 | 18.7751 | 16.5889 | 18.7751
2308 | 0.85725 | 1.0431 | 0.80435 | 0.85154 | 4.1631 | 6.3447 | 5.1448 | 6.1339 | 3.9246 | 2.1596 | 18.8012 | 15.3921 | 18.8012
2309 | -0.66023 | -0.09497 | 0.25455 | 0.46217 | 5.4414 | 4.4943 | 6.0975 | 5.1814 | 3.5234 | 1.908 | 17.025 | 16.9702 | 17.025
2310 | 0.23986 | 0.68651 | 0.59478 | 0.7538 | 4.1067 | 5.5556 | 5.1961 | 5.8271 | 4.7804 | 1.8949 | 17.3842 | 15.9781 | 17.3842
2311 | 1.0776 | 1.3943 | 0.8594 | 0.91839 | 3.8881 | 6.62 | 5.6891 | 6.4289 | 4.6371 | 1.3124 | 18.2494 | 15.5267 | 18.2494
2312 | -0.7383 | -1.0504 | 0.23017 | 0.14677 | 3.9504 | 4.4134 | 5.1545 | 4.5602 | 4.3568 | 2.4812 | 15.4052 | 15.9429 | 15.9429
2313 | -0.50568 | -1.016 | 0.30654 | 0.15482 | 5.2142 | 4.6607 | 4.5425 | 4.5782 | 5.5609 | 2.1383 | 16.5913 | 17.4559 | 17.4559
2314 | -0.91849 | -0.28187 | 0.17918 | 0.38902 | 4.8087 | 4.2358 | 6.4124 | 5.0414 | 5.9695 | 1.9274 | 16.0133 | 19.118 | 19.118
2315 | 0.010594 | -0.60658 | 0.50423 | 0.27206 | 3.2298 | 5.268 | 5.9429 | 4.8182 | 4.3097 | 1.9701 | 15.286 | 15.4525 | 15.4525
2316 | -0.68642 | -0.48274 | 0.24623 | 0.31464 | 4.1612 | 4.4669 | 7.2917 | 4.9001 | 3.2099 | 2.6029 | 16.1311 | 17.2657 | 17.2657
2317 | -0.42777 | -0.58512 | 0.33441 | 0.27923 | 4.1301 | 4.7476 | 5.493 | 4.8321 | 3.3565 | 1.7947 | 15.5046 | 14.7744 | 15.5046
2318 | 0.25263 | -0.3389 | 0.59972 | 0.36734 | 4.9537 | 5.5718 | 5.4036 | 5.0003 | 3.7175 | 1.3731 | 16.899 | 15.448 | 16.899
2319 | 0.54527 | 0.57574 | 0.70722 | 0.7176 | 4.8834 | 5.9463 | 7.3227 | 5.7319 | 4.6938 | 1.7316 | 18.2932 | 18.6316 | 18.6316
2320 | -0.38344 | -0.49718 | 0.3507 | 0.30953 | 3.3959 | 4.7979 | 6.4086 | 4.8904 | 4.4734 | 1.8667 | 14.9509 | 16.1446 | 16.1446
2321 | -1.124 | -1.3424 | 0.13051 | 0.089731 | 4.1929 | 4.0492 | 5.9432 | 4.4223 | 3.772 | 1.8644 | 14.5287 | 15.7725 | 15.7725
2322 | 1.0734 | 1.3975 | 0.85845 | 0.91888 | 3.9389 | 6.6147 | 3.906 | 6.4315 | 5.6883 | 2.6985 | 19.6837 | 16.2317 | 19.6837
2323 | -0.99323 | 0.20417 | 0.1603 | 0.58089 | 2.8316 | 4.1659 | 5.06 | 5.4194 | 3.7209 | 1.914 | 14.3309 | 13.5265 | 14.3309
2324 | 0.77605 | 0.4791 | 0.78114 | 0.68407 | 4.7413 | 6.2417 | 5.0547 | 5.6494 | 4.6507 | 2.1583 | 18.7907 | 16.6049 | 18.7907
2325 | 0.90257 | 0.41098 | 0.81662 | 0.65946 | 4.8538 | 6.4019 | 6.5679 | 5.5917 | 4.5203 | 1.6462 | 18.4936 | 17.5882 | 18.4936
2326 | -2.0635 | -0.93608 | 0.019532 | 0.17462 | 5.2497 | 3.4251 | 4.4508 | 4.6212 | 4.9069 | 2.2986 | 15.5945 | 16.906 | 16.906
2327 | 1.1004 | -0.79421 | 0.86441 | 0.21354 | 4.4789 | 6.6479 | 4.3405 | 4.7022 | 4.7563 | 2.2195 | 18.0485 | 15.7953 | 18.0485
2328 | 0.094862 | 0.22912 | 0.53779 | 0.59061 | 2.8336 | 5.3728 | 4.6315 | 5.4399 | 3.9962 | 1.8886 | 15.5349 | 13.3498 | 15.5349
2329 | -0.71774 | -1.7754 | 0.23646 | 0.037913 | 5.0442 | 4.4345 | 5.9621 | 4.2633 | 3.8165 | 1.3417 | 15.0837 | 16.1644 | 16.1644
2330 | -0.19695 | -0.094184 | 0.42193 | 0.46248 | 2.7652 | 5.0157 | 5.1215 | 5.182 | 4.9627 | 2.0332 | 14.9961 | 14.8826 | 14.9961
2331 | -0.85659 | -0.10917 | 0.19584 | 0.45654 | 3.8335 | 4.2954 | 3.8197 | 5.1705 | 3.775 | 1.6844 | 14.9838 | 13.1126 | 14.9838
2332 | 0.10437 | 0.95849 | 0.54156 | 0.83109 | 5.2244 | 5.3847 | 6.0171 | 6.0614 | 5.7441 | 2.2996 | 18.9701 | 19.2852 | 19.2852
2333 | 0.662 | 0.081536 | 0.74601 | 0.53249 | 4.55 | 6.096 | 5.6926 | 5.32 | 4.0616 | 2.0847 | 18.0507 | 16.389 | 18.0507
2334 | 0.24074 | -0.56274 | 0.59512 | 0.28681 | 4.901 | 5.5567 | 7.0783 | 4.8467 | 5.1167 | 1.9496 | 17.2539 | 19.0455 | 19.0455
2335 | -1.0655 | 0.12454 | 0.14333 | 0.54955 | 3.1666 | 4.1005 | 4.2716 | 5.3546 | 4.3843 | 1.9238 | 14.5455 | 13.7463 | 14.5455
2336 | -0.19168 | -1.302 | 0.424 | 0.096458 | 4.6608 | 5.022 | 5.334 | 4.4399 | 5.4709 | 1.8253 | 15.9479 | 17.291 | 17.291
2337 | -0.52475 | -0.92422 | 0.29988 | 0.17769 | 5.8158 | 4.6397 | 4.0723 | 4.6277 | 5.2703 | 2.3324 | 17.4156 | 17.4908 | 17.4908
2338 | 1.5458 | 0.30322 | 0.93892 | 0.61914 | 3.4435 | 7.171 | 3.2779 | 5.5013 | 4.8158 | 1.904 | 18.0199 | 13.4413 | 18.0199
2339 | -0.047539 | -0.2388 | 0.48104 | 0.40563 | 2.9335 | 5.1964 | 4.1819 | 5.073 | 3.4893 | 1.6427 | 14.8456 | 12.2475 | 14.8456
2340 | 1.4311 | -0.59655 | 0.92379 | 0.2754 | 3.0045 | 7.0413 | 7.4302 | 4.8247 | 4.1818 | 2.0767 | 16.9472 | 16.6933 | 16.9472
2341 | 1.6469 | 1.0991 | 0.95021 | 0.86414 | 5.1228 | 7.2819 | 5.4188 | 6.1817 | 4.4373 | 2.1296 | 20.716 | 17.1084 | 20.716
2342 | 0.048787 | 0.88307 | 0.51946 | 0.8114 | 5.5603 | 5.3153 | 5.5003 | 5.9965 | 6.0227 | 2.077 | 18.9491 | 19.1602 | 19.1602
2343 | -0.10242 | -0.42468 | 0.45921 | 0.33554 | 3.2754 | 5.1294 | 3.7491 | 4.9399 | 4.2741 | 2.2594 | 15.6042 | 13.5581 | 15.6042
2344 | 0.85571 | 1.4629 | 0.80392 | 0.92825 | 3.8629 | 6.3427 | 6.5438 | 6.4848 | 4.1263 | 2.4644 | 19.1548 | 16.9975 | 19.1548
2345 | 0.085313 | 1.4647 | 0.53399 | 0.92849 | 4.5684 | 5.3609 | 4.6404 | 6.4862 | 4.9401 | 2.2845 | 18.7 | 16.4334 | 18.7
2346 | -0.44134 | -1.1857 | 0.32948 | 0.11787 | 2.5819 | 4.7323 | 6.7109 | 4.4931 | 3.4674 | 1.9572 | 13.7646 | 14.7174 | 14.7174
2347 | 0.53292 | 1.0696 | 0.70296 | 0.85759 | 3.5686 | 5.9304 | 7.0935 | 6.1565 | 3.8208 | 1.5907 | 17.2462 | 16.0736 | 17.2462
2348 | 1.9537 | 1.7691 | 0.97463 | 0.96156 | 4.3538 | 7.5972 | 7.0664 | 6.7251 | 3.9769 | 2.2119 | 20.888 | 17.609 | 20.888
2349 | -1.8728 | -0.90758 | 0.030547 | 0.18205 | 4.6676 | 3.5219 | 6.8653 | 4.637 | 3.9703 | 2.4402 | 15.2665 | 17.9433 | 17.9433
2350 | -0.73958 | 0.068275 | 0.22978 | 0.52722 | 3.693 | 4.4121 | 3.6786 | 5.3094 | 3.2002 | 1.9075 | 15.322 | 12.4793 | 15.322
2351 | -1.6968 | -1.9255 | 0.04487 | 0.027085 | 4.2343 | 3.6243 | 6.5983 | 4.2201 | 4.9708 | 1.7638 | 13.8425 | 17.5672 | 17.5672
2352 | 0.6552 | -1.537 | 0.74383 | 0.06215 | 5.0192 | 6.0873 | 3.1856 | 4.3443 | 4.5785 | 1.2414 | 16.6922 | 14.0248 | 16.6922
2353 | -0.26575 | -0.50104 | 0.39522 | 0.30817 | 5.4073 | 4.9342 | 6.7959 | 4.8878 | 4.4995 | 1.6743 | 16.9037 | 18.377 | 18.377
2354 | 0.35124 | 0.24783 | 0.6373 | 0.59787 | 4.2537 | 5.6975 | 5.082 | 5.4554 | 4.0078 | 1.5032 | 16.9097 | 14.8466 | 16.9097
2355 | -2.626 | -3.2879 | 0.0043195 | 0.00050475 | 3.6983 | 3.2163 | 6.3016 | 4.0286 | 4.5932 | 1.7964 | 12.7396 | 16.3895 | 16.3895
2356 | 0.53177 | -0.81953 | 0.70256 | 0.20624 | 4.412 | 5.9289 | 5.694 | 4.6873 | 4.7904 | 1.958 | 16.9862 | 16.8544 | 16.9862
2357 | -0.60293 | -0.21304 | 0.27328 | 0.41565 | 3.7345 | 4.555 | 7.5805 | 5.0921 | 4.2163 | 1.8046 | 15.1861 | 17.3358 | 17.3358
2358 | 1.0546 | -0.2385 | 0.8542 | 0.40575 | 4.7579 | 6.5916 | 5.436 | 5.0732 | 3.2241 | 1.8622 | 18.2849 | 15.2802 | 18.2849
2359 | -0.94685 | 1.1735 | 0.17186 | 0.8797 | 2.5235 | 4.209 | 5.9581 | 6.2448 | 3.7213 | 2.4907 | 15.468 | 14.6936 | 15.468
2360 | -2.677 | -0.31221 | 0.003714 | 0.37744 | 3.5034 | 3.2024 | 5.0362 | 5.0194 | 5.3196 | 1.5848 | 13.3101 | 15.444 | 15.444
2361 | 0.85313 | 1.7907 | 0.80321 | 0.96333 | 3.5121 | 6.3395 | 6.9823 | 6.7414 | 4.5671 | 1.9338 | 18.5267 | 16.9953 | 18.5267
2362 | 0.34294 | -0.64713 | 0.63418 | 0.25877 | 3.7746 | 5.6869 | 4.8161 | 4.7923 | 3.8086 | 2.087 | 16.3407 | 14.4864 | 16.3407
2363 | -0.035572 | 1.2897 | 0.48581 | 0.90143 | 3.4746 | 5.2111 | 6.0203 | 6.3424 | 5.4516 | 1.9134 | 16.9415 | 16.8599 | 16.9415
2364 | 0.59849 | 0.36191 | 0.72524 | 0.64129 | 4.3798 | 6.0146 | 6.7008 | 5.5504 | 4.3691 | 2.6117 | 18.5565 | 18.0614 | 18.5565
2365 | -0.92565 | -0.84744 | 0.17731 | 0.19837 | 3.6746 | 4.229 | 3.5103 | 4.6711 | 3.9119 | 1.8561 | 14.4307 | 12.9529 | 14.4307
2366 | 1.4337 | 0.46224 | 0.92417 | 0.67805 | 4.2432 | 7.0443 | 6.6716 | 5.6351 | 3.7527 | 1.5044 | 18.4271 | 16.172 | 18.4271
2367 | -0.062297 | -0.063261 | 0.47516 | 0.47478 | 4.1966 | 5.1783 | 4.6101 | 5.2058 | 4.0843 | 1.213 | 15.7938 | 14.104 | 15.7938
2368 | -0.24427 | -1.852 | 0.40351 | 0.032015 | 3.6294 | 4.9595 | 5.8657 | 4.2406 | 5.67 | 1.7862 | 14.6157 | 16.9513 | 16.9513
2369 | 0.17843 | 1.2969 | 0.57081 | 0.90266 | 4.643 | 5.4778 | 2.6192 | 6.3483 | 4.4785 | 2.0716 | 18.5408 | 13.8124 | 18.5408
2370 | -0.47906 | 0.33867 | 0.31595 | 0.63257 | 3.1117 | 4.6902 | 6.0707 | 5.5309 | 4.2266 | 1.769 | 15.1018 | 15.178 | 15.178
2371 | -0.072173 | -1.0637 | 0.47123 | 0.14372 | 3.8171 | 5.1663 | 7.1794 | 4.5534 | 4.2972 | 2.1739 | 15.7106 | 17.4674 | 17.4674
2372 | 1.3158 | 0.4295 | 0.90588 | 0.66622 | 3.1138 | 6.9073 | 3.2725 | 5.6074 | 3.6575 | 1.6558 | 17.2843 | 11.6997 | 17.2843
2373 | -0.34604 | 0.14423 | 0.36466 | 0.55734 | 4.1089 | 4.8408 | 5.2095 | 5.3705 | 4.2495 | 2.2684 | 16.5886 | 15.8363 | 16.5886
2374 | 0.65735 | 0.66068 | 0.74452 | 0.74559 | 2.3003 | 6.09 | 6.0497 | 5.8048 | 4.898 | 2.2667 | 16.4619 | 15.5147 | 16.4619
2375 | 0.45082 | 2.1061 | 0.67394 | 0.9824 | 2.494 | 5.825 | 7.0554 | 6.9677 | 4.5835 | 1.4278 | 16.7146 | 15.5607 | 16.7146
2376 | -0.39856 | 0.50048 | 0.34511 | 0.69163 | 3.4485 | 4.7807 | 2.9892 | 5.6676 | 3.7147 | 1.6079 | 15.5047 | 11.7603 | 15.5047
2377 | 0.63267 | 1.2506 | 0.73653 | 0.89446 | 4.9147 | 6.0584 | 6.9093 | 6.3097 | 4.2527 | 1.8473 | 19.1301 | 17.924 | 19.1301
2378 | -2.7981 | -1.9106 | 0.0025704 | 0.02803 | 4.0974 | 3.1721 | 5.2746 | 4.2242 | 3.6685 | 2.6011 | 14.0948 | 15.6416 | 15.6416
2379 | -0.18472 | -1.2823 | 0.42672 | 0.099873 | 5.245 | 5.0303 | 5.1623 | 4.4486 | 4.5107 | 2.2841 | 17.008 | 17.2022 | 17.2022
2380 | -0.95784 | -0.41681 | 0.16907 | 0.33841 | 4.1452 | 4.1987 | 7.277 | 4.9454 | 4.692 | 2.4729 | 15.7622 | 18.5872 | 18.5872
2381 | 0.55033 | 0.83697 | 0.70895 | 0.7987 | 4.9974 | 5.9528 | 5.5488 | 5.9568 | 5.1367 | 2.1559 | 19.0628 | 17.8388 | 19.0628
2382 | 0.24053 | 0.57958 | 0.59504 | 0.7189 | 3.3308 | 5.5564 | 7.4183 | 5.7352 | 5.5673 | 1.5898 | 16.2123 | 17.9063 | 17.9063
2383 | 2.2205 | 1.0688 | 0.98681 | 0.85743 | 4.6609 | 7.8425 | 6.0885 | 6.1559 | 4.1292 | 2.0138 | 20.6732 | 16.8925 | 20.6732
2384 | -1.3858 | -0.58823 | 0.082904 | 0.27819 | 3.3439 | 3.8374 | 5.3559 | 4.8301 | 3.3559 | 1.4346 | 13.446 | 13.4903 | 13.4903
2385 | -0.81337 | 0.7047 | 0.208 | 0.7595 | 4.0465 | 4.3379 | 3.0441 | 5.8427 | 4.2464 | 2.5383 | 16.7654 | 13.8754 | 16.7654
2386 | -0.49861 | -0.19049 | 0.30903 | 0.42446 | 4.6604 | 4.6685 | 7.3706 | 5.1089 | 4.4057 | 2.2354 | 16.6732 | 18.6721 | 18.6721
2387 | -0.13855 | 0.52964 | 0.4449 | 0.70182 | 2.9536 | 5.0857 | 4.8129 | 5.6925 | 3.1876 | 1.7909 | 15.5227 | 12.745 | 15.5227
2388 | -1.0792 | -0.18293 | 0.14026 | 0.42743 | 3.3683 | 4.0884 | 5.3172 | 5.1146 | 4.153 | 1.8539 | 14.4251 | 14.6924 | 14.6924
2389 | 0.19123 | 1.4497 | 0.57583 | 0.92643 | 3.9696 | 5.494 | 4.2406 | 6.4741 | 3.7671 | 2.1421 | 18.0798 | 14.1195 | 18.0798
2390 | 0.82816 | 0.58771 | 0.79621 | 0.72163 | 4.3516 | 6.3078 | 7.202 | 5.7422 | 4.8141 | 1.6991 | 18.1008 | 18.0668 | 18.1008
2391 | 0.4946 | -0.20156 | 0.68956 | 0.42013 | 4.3352 | 5.8812 | 5.4998 | 5.1006 | 3.7493 | 2.6714 | 17.9885 | 16.2558 | 17.9885
2392 | 0.05956 | -0.60929 | 0.52375 | 0.27117 | 3.8127 | 5.3287 | 7.4365 | 4.8165 | 4.155 | 1.421 | 15.3789 | 16.8252 | 16.8252
2393 | 0.8436 | 0.34754 | 0.80055 | 0.63591 | 4.3982 | 6.3274 | 5.3976 | 5.5384 | 4.3091 | 1.7225 | 17.9865 | 15.8274 | 17.9865
2394 | 2.216 | 2.5261 | 0.98665 | 0.99423 | 5.0183 | 7.8386 | 6.6388 | 7.2315 | 5.8707 | 2.3946 | 22.483 | 19.9224 | 22.483
2395 | -0.5493 | -0.32515 | 0.2914 | 0.37253 | 3.3589 | 4.6129 | 7.3691 | 5.0101 | 4.4191 | 1.8615 | 14.8435 | 17.0087 | 17.0087
2396 | 0.33671 | 1.8761 | 0.63183 | 0.96968 | 3.1904 | 5.6789 | 6.8854 | 6.8049 | 4.6024 | 2.1725 | 17.8468 | 16.8507 | 17.8468
2397 | 0.56007 | 1.5097 | 0.71229 | 0.93444 | 4.6761 | 5.9653 | 4.7401 | 6.5226 | 4.2003 | 2.6893 | 19.8532 | 16.3057 | 19.8532
2398 | -0.12272 | -0.12162 | 0.45116 | 0.4516 | 3.3595 | 5.1048 | 4.8079 | 5.161 | 5.7548 | 2.0879 | 15.7131 | 16.01 | 16.01
2399 | -0.28733 | -1.507 | 0.38693 | 0.065908 | 3.7636 | 4.909 | 6.1803 | 4.3556 | 4.9322 | 2.7933 | 15.8215 | 17.6694 | 17.6694
2400 | 1.6936 | 1.4919 | 0.95483 | 0.93214 | 4.1819 | 7.332 | 3.7882 | 6.5083 | 3.3862 | 2.1031 | 20.1253 | 13.4594 | 20.1253
2401 | 0.41698 | 0.26335 | 0.66166 | 0.60386 | 3.5639 | 5.7816 | 6.8558 | 5.4682 | 4.9967 | 1.6191 | 16.4328 | 17.0353 | 17.0353
2402 | 1.8049 | 0.93523 | 0.96445 | 0.82516 | 4.6649 | 7.4484 | 6.7934 | 6.0414 | 3.7854 | 1.8237 | 19.9784 | 17.0675 | 19.9784
2403 | -0.15041 | 0.67478 | 0.44022 | 0.75009 | 3.4357 | 5.0714 | 3.4917 | 5.817 | 5.5975 | 1.8286 | 16.1527 | 14.3534 | 16.1527
2404 | 1.6283 | 1.8628 | 0.94827 | 0.96876 | 3.3111 | 7.2618 | 3.4767 | 6.7951 | 3.4979 | 1.2301 | 18.5981 | 11.5158 | 18.5981
2405 | 1.1851 | 0.69075 | 0.88202 | 0.75514 | 4.0295 | 6.7512 | 4.6159 | 5.8307 | 5.6575 | 2.8167 | 19.4281 | 17.1196 | 19.4281
2406 | 0.82984 | 0.61793 | 0.79669 | 0.73169 | 3.8302 | 6.31 | 6.0301 | 5.7681 | 3.8321 | 1.8756 | 17.7839 | 15.5679 | 17.7839
2407 | -1.087 | -1.815 | 0.13851 | 0.034765 | 4.6813 | 4.0814 | 4.591 | 4.2514 | 4.5516 | 1.7701 | 14.7842 | 15.594 | 15.594
2408 | -3.1222 | -1.4421 | 0.00089766 | 0.074641 | 3.4771 | 3.1087 | 5.3904 | 4.381 | 3.8447 | 2.551 | 13.5178 | 15.2631 | 15.2631
2409 | -0.15024 | -1.443 | 0.44029 | 0.074514 | 3.4915 | 5.0716 | 6.5886 | 4.3806 | 4.3043 | 2.2981 | 15.2418 | 16.6824 | 16.6824
2410 | -0.47517 | 0.17012 | 0.31733 | 0.56754 | 3.6252 | 4.6945 | 6.3773 | 5.3916 | 4.2283 | 1.5838 | 15.2952 | 15.8147 | 15.8147
2411 | 0.23872 | 0.36005 | 0.59434 | 0.6406 | 4.448 | 5.5541 | 6.8165 | 5.5489 | 3.7895 | 1.9926 | 17.5436 | 17.0467 | 17.5436
2412 | 1.1053 | 1.7107 | 0.86548 | 0.95644 | 3.2263 | 6.6539 | 4.8461 | 6.6806 | 4.1049 | 2.0228 | 18.5837 | 14.2002 | 18.5837
2413 | 0.16801 | 0.055051 | 0.56671 | 0.52195 | 4.2844 | 5.4647 | 7.5405 | 5.2988 | 4.3484 | 2.2972 | 17.345 | 18.4705 | 18.4705
2414 | 0.11824 | 0.56228 | 0.54706 | 0.71304 | 3.4929 | 5.4021 | 7.1991 | 5.7204 | 4.6915 | 1.9822 | 16.5976 | 17.3657 | 17.3657
2415 | 0.24062 | 0.64089 | 0.59507 | 0.7392 | 4.5617 | 5.5565 | 5.532 | 5.7878 | 5.2058 | 1.8921 | 17.7982 | 17.1916 | 17.7982
2416 | 0.54555 | 0.32791 | 0.70731 | 0.62851 | 3.1457 | 5.9466 | 6.8391 | 5.5219 | 6.0386 | 1.4617 | 16.076 | 17.485 | 17.485
2417 | -0.70627 | -0.85602 | 0.24001 | 0.19599 | 2.7928 | 4.4463 | 2.7705 | 4.6661 | 4.1032 | 1.774 | 13.6793 | 11.4406 | 13.6793
2418 | -0.10269 | -0.61053 | 0.4591 | 0.27076 | 4.5474 | 5.1291 | 3.1692 | 4.8157 | 4.3024 | 2.0583 | 16.5504 | 14.0772 | 16.5504
2419 | -0.89296 | -1.7546 | 0.18594 | 0.039666 | 2.3735 | 4.2602 | 6.4102 | 4.2698 | 4.5295 | 1.6854 | 12.5889 | 14.9986 | 14.9986
2420 | -0.16529 | -0.67517 | 0.43436 | 0.24978 | 3.0143 | 5.0535 | 5.1041 | 4.7746 | 4.6373 | 2.2956 | 15.138 | 15.0513 | 15.138
2421 | 1.7834 | 2.0232 | 0.96274 | 0.97847 | 5.1194 | 7.4263 | 6.5312 | 6.9105 | 4.1196 | 1.823 | 21.2791 | 17.5932 | 21.2791
2422 | 1.0977 | 1.0746 | 0.86383 | 0.85873 | 2.7745 | 6.6446 | 3.4062 | 6.1608 | 4.8896 | 1.9116 | 17.4916 | 12.9818 | 17.4916
2423 | -1.4734 | -0.72926 | 0.070327 | 0.23292 | 4.5954 | 3.7732 | 6.8607 | 4.7412 | 4.8757 | 1.4591 | 14.5688 | 17.7909 | 17.7909
2424 | -1.3215 | -1.5214 | 0.093173 | 0.064077 | 5.7768 | 3.8867 | 3.8211 | 4.3502 | 3.4806 | 1.3823 | 15.3959 | 14.4608 | 15.3959
2425 | 1.3617 | 1.0078 | 0.91335 | 0.84323 | 3.3628 | 6.961 | 7.4546 | 6.1037 | 5.2028 | 2.197 | 18.6245 | 18.2171 | 18.6245
2426 | -0.30897 | -0.72753 | 0.37867 | 0.23345 | 2.6542 | 4.8837 | 5.879 | 4.7423 | 5.9814 | 2.1007 | 14.3809 | 16.6153 | 16.6153
2427 | -0.30637 | -0.42156 | 0.37966 | 0.33667 | 3.6167 | 4.8867 | 5.7144 | 4.9421 | 3.3144 | 1.7257 | 15.1713 | 14.3713 | 15.1713
2428 | 0.52096 | -0.017011 | 0.6988 | 0.49321 | 5.0491 | 5.9151 | 6.8606 | 5.2419 | 4.4004 | 2.4402 | 18.6462 | 18.7503 | 18.7503
2429 | 0.43551 | -0.89615 | 0.66841 | 0.18509 | 4.6005 | 5.8054 | 6.8582 | 4.6434 | 3.7958 | 1.7146 | 16.7639 | 16.9691 | 16.9691
2430 | 0.71741 | -2.1758 | 0.76344 | 0.014784 | 2.71 | 6.1669 | 4.6699 | 4.1601 | 3.9568 | 2.1921 | 15.229 | 13.5287 | 15.229
2431 | -0.12525 | -1.0693 | 0.45016 | 0.14247 | 3.9503 | 5.1018 | 6.3593 | 4.5505 | 3.6872 | 2.0624 | 15.665 | 16.0591 | 16.0591
2432 | 0.67648 | 0.71092 | 0.75063 | 0.76143 | 5.1523 | 6.1145 | 6.2403 | 5.8481 | 3.5686 | 1.7559 | 18.8709 | 16.7172 | 18.8709
2433 | 0.27326 | -1.1049 | 0.60767 | 0.1346 | 4.6666 | 5.598 | 5.7487 | 4.5325 | 3.9596 | 1.6038 | 16.401 | 15.9787 | 16.401
2434 | -1.1498 | 0.3294 | 0.12512 | 0.62908 | 3.9514 | 4.027 | 3.361 | 5.5232 | 5.2791 | 2.1974 | 15.699 | 14.7889 | 15.699
2435 | 2.4319 | 0.72123 | 0.99249 | 0.76462 | 2.6088 | 8.017 | 7.1399 | 5.857 | 5.5136 | 1.5741 | 18.0569 | 16.8364 | 18.0569
2436 | -1.335 | 0.54154 | 0.090935 | 0.70593 | 3.5005 | 3.8761 | 7.0228 | 5.7027 | 4.4099 | 1.9214 | 15.0007 | 16.8545 | 16.8545
2437 | 1.8348 | 0.46605 | 0.96673 | 0.67941 | 3.6771 | 7.479 | 4.4114 | 5.6384 | 3.948 | 2.0602 | 18.8547 | 14.0968 | 18.8547
2438 | -0.63805 | 0.24895 | 0.26172 | 0.5983 | 3.8014 | 4.5176 | 5.5163 | 5.4563 | 4.4212 | 1.9949 | 15.7703 | 15.7339 | 15.7703
2439 | 0.25285 | -0.51299 | 0.59981 | 0.30398 | 5.2367 | 5.5721 | 5.6938 | 4.8797 | 4.9543 | 1.47 | 17.1585 | 17.3548 | 17.3548
2440 | -2.0808 | -2.4936 | 0.018724 | 0.0063222 | 4.3038 | 3.417 | 6.335 | 4.1032 | 4.0276 | 2.5141 | 14.3381 | 17.1806 | 17.1806
2441 | -1.4716 | -0.20567 | 0.070559 | 0.41853 | 4.6228 | 3.7744 | 6.4293 | 5.0976 | 3.4272 | 2.0515 | 15.5463 | 16.5308 | 16.5308
2442 | -0.78305 | 0.57151 | 0.2168 | 0.71617 | 3.8593 | 4.3681 | 6.7582 | 5.7283 | 3.2121 | 2.4465 | 16.4022 | 16.2761 | 16.4022
2443 | -0.15071 | -0.65558 | 0.4401 | 0.25605 | 3.7142 | 5.0711 | 6.2802 | 4.7869 | 4.7875 | 1.7007 | 15.273 | 16.4827 | 16.4827
2444 | -0.10064 | -0.32044 | 0.45992 | 0.37432 | 3.988 | 5.1316 | 5.3857 | 5.0135 | 3.8727 | 2.3566 | 16.4898 | 15.603 | 16.4898
2445 | -1.7249 | -0.79833 | 0.04227 | 0.21234 | 4.2319 | 3.6071 | 6.6733 | 4.6997 | 4.0116 | 1.7377 | 14.2764 | 16.6545 | 16.6545
2446 | -0.96031 | -1.0806 | 0.16845 | 0.13994 | 5.1078 | 4.1964 | 6.6946 | 4.5448 | 4.9929 | 1.3883 | 15.2373 | 18.1837 | 18.1837
2447 | 0.74737 | 0.62908 | 0.77258 | 0.73535 | 4.6929 | 6.2051 | 4.6052 | 5.7777 | 4.3476 | 1.6398 | 18.3155 | 15.2855 | 18.3155
2448 | 2.7802 | 2.9186 | 0.99728 | 0.99824 | 3.5202 | 8.2648 | 6.0645 | 7.4356 | 3.4601 | 1.4995 | 20.7201 | 14.5442 | 20.7201
2449 | -0.46251 | 0.62176 | 0.32186 | 0.73295 | 3.7998 | 4.7086 | 3.177 | 5.7714 | 3.7881 | 2.1968 | 16.4765 | 12.9617 | 16.4765
2450 | -0.6909 | -0.6061 | 0.24482 | 0.27223 | 3.6777 | 4.4622 | 7.4544 | 4.8185 | 4.9518 | 1.3976 | 14.356 | 17.4814 | 17.4814
2451 | 1.0208 | -1.05 | 0.84632 | 0.14687 | 4.0188 | 6.5497 | 5.0952 | 4.5604 | 4.5149 | 1.8972 | 17.0262 | 15.5262 | 17.0262
2452 | 1.1084 | 1.1286 | 0.86615 | 0.87046 | 3.5011 | 6.6578 | 5.9672 | 6.2067 | 4.2187 | 1.6997 | 18.0653 | 15.3868 | 18.0653
2453 | 2.2236 | 0.69216 | 0.98691 | 0.75558 | 3.083 | 7.8453 | 5.8982 | 5.8319 | 3.6933 | 1.6714 | 18.4316 | 14.3459 | 18.4316
2454 | 0.67047 | 0.57905 | 0.74872 | 0.71872 | 3.743 | 6.1068 | 6.6027 | 5.7348 | 4.2051 | 1.9202 | 17.5047 | 16.471 | 17.5047
2455 | 0.23243 | -2.1274 | 0.5919 | 0.016695 | 3.1658 | 5.5461 | 6.2973 | 4.1706 | 3.3347 | 1.9897 | 14.8723 | 14.7875 | 14.8723
2456 | 0.47954 | 0.81709 | 0.68422 | 0.79306 | 3.7449 | 5.8619 | 5.2655 | 5.9396 | 4.4916 | 2.522 | 18.0684 | 16.024 | 18.0684
2457 | 0.58816 | 0.70261 | 0.72179 | 0.75885 | 4.806 | 6.0013 | 4.0486 | 5.8409 | 6.2794 | 1.3128 | 17.961 | 16.4468 | 17.961
2458 | 1.2031 | 0.89216 | 0.88552 | 0.81385 | 3.2027 | 6.7728 | 5.3898 | 6.0043 | 4.4345 | 1.841 | 17.8209 | 14.868 | 17.8209
2459 | -1.3045 | -1.17 | 0.096027 | 0.121 | 3.0683 | 3.9 | 7.0189 | 4.5006 | 5.5479 | 2.1721 | 13.641 | 17.8072 | 17.8072
2460 | -1.2933 | -1.7018 | 0.097954 | 0.044396 | 3.315 | 3.9088 | 6.7485 | 4.2867 | 4.2278 | 1.8414 | 13.3519 | 16.1327 | 16.1327
2461 | 0.77781 | 0.69276 | 0.78166 | 0.75577 | 5.0625 | 6.2439 | 5.7917 | 5.8324 | 3.1484 | 2.0428 | 19.1816 | 16.0454 | 19.1816
2462 | -0.90262 | 0.79977 | 0.18336 | 0.78808 | 3.406 | 4.2509 | 3.3913 | 5.9247 | 6.1057 | 1.8442 | 15.4258 | 14.7472 | 15.4258
2463 | 1.1186 | 0.82603 | 0.86834 | 0.79561 | 5.2823 | 6.6703 | 4.443 | 5.9473 | 4.1092 | 2.1035 | 20.0034 | 15.938 | 20.0034
2464 | -0.45505 | 0.63512 | 0.32454 | 0.73733 | 4.1526 | 4.717 | 4.8999 | 5.7829 | 3.4335 | 2.3133 | 16.9657 | 14.7992 | 16.9657
2465 | -0.062382 | -0.07825 | 0.47513 | 0.46881 | 3.575 | 5.1782 | 6.4427 | 5.1942 | 4.8742 | 2.9577 | 16.9051 | 17.8496 | 17.8496
2466 | 0.6219 | 0.23529 | 0.733 | 0.59301 | 3.409 | 6.0446 | 6.8479 | 5.445 | 3.4589 | 1.5824 | 16.481 | 15.2982 | 16.481
2467 | -0.27461 | 0.61444 | 0.39181 | 0.73054 | 4.0499 | 4.9238 | 5.2936 | 5.7651 | 3.5296 | 1.6467 | 16.3855 | 14.5198 | 16.3855
2468 | 1.6234 | 0.44773 | 0.94775 | 0.67282 | 3.2858 | 7.2564 | 5.9844 | 5.6228 | 4.9688 | 1.7318 | 17.8969 | 15.9707 | 17.8969
2469 | -0.65368 | -1.2137 | 0.25666 | 0.11244 | 3.7165 | 4.5011 | 6.0469 | 4.48 | 3.9438 | 1.8608 | 14.5584 | 15.568 | 15.568
2470 | -0.42301 | -0.28278 | 0.33614 | 0.38867 | 3.2233 | 4.753 | 3.5539 | 5.0408 | 4.4621 | 2.3881 | 15.4051 | 13.6274 | 15.4051
2471 | 0.44826 | 0.0433 | 0.67302 | 0.51727 | 3.459 | 5.8217 | 6.2047 | 5.2895 | 4.3351 | 2.0677 | 16.638 | 16.0665 | 16.638
2472 | 0.82098 | 0.47333 | 0.79417 | 0.68201 | 2.9272 | 6.2987 | 7.273 | 5.6445 | 4.5753 | 2.5148 | 17.3852 | 17.2902 | 17.3852
2473 | -0.90172 | -0.9824 | 0.1836 | 0.16295 | 4.1207 | 4.2518 | 4.8262 | 4.596 | 3.5601 | 2.1129 | 15.0814 | 14.6199 | 15.0814
2474 | 0.17561 | 0.4199 | 0.5697 | 0.66272 | 3.6275 | 5.4742 | 5.0393 | 5.5993 | 4.4882 | 1.262 | 15.9631 | 14.4171 | 15.9631
2475 | -1.2114 | -0.33549 | 0.11287 | 0.36863 | 4.6284 | 3.9752 | 6.5625 | 5.0027 | 4.8435 | 2.1306 | 15.7369 | 18.165 | 18.165
2476 | -2.1464 | -2.8554 | 0.015919 | 0.0021489 | 5.0702 | 3.3874 | 5.2614 | 4.0595 | 4.28 | 1.6894 | 14.2065 | 16.301 | 16.301
2477 | -0.49236 | -0.54219 | 0.31123 | 0.29384 | 2.8731 | 4.6754 | 4.9026 | 4.8603 | 4.2335 | 2.1325 | 14.5413 | 14.1417 | 14.5413
2478 | -0.3968 | 0.71583 | 0.34576 | 0.76295 | 3.2521 | 4.7827 | 6.2215 | 5.8523 | 3.483 | 2.4833 | 16.3704 | 15.4398 | 16.3704
2479 | 1.3988 | 0.34287 | 0.91907 | 0.63415 | 4.9459 | 7.0042 | 5.0459 | 5.5344 | 3.948 | 1.7517 | 19.2362 | 15.6915 | 19.2362
2480 | -1.9943 | 0.50905 | 0.023059 | 0.69464 | 2.9328 | 3.4585 | 5.4028 | 5.6749 | 4.9177 | 2.34 | 14.4063 | 15.5933 | 15.5933
2481 | -0.023525 | -0.16943 | 0.49062 | 0.43273 | 3.6012 | 5.2259 | 7.7188 | 5.1247 | 5.4202 | 1.7216 | 15.6733 | 18.4618 | 18.4618
2482 | 1.2012 | 0.085759 | 0.88516 | 0.53417 | 2.3858 | 6.7706 | 5.5235 | 5.3234 | 5.0115 | 2.1824 | 16.6621 | 15.1032 | 16.6621
2483 | 0.69806 | 0.34899 | 0.75743 | 0.63645 | 3.7929 | 6.1421 | 3.7737 | 5.5396 | 5.0037 | 1.2328 | 16.7074 | 13.8032 | 16.7074
2484 | 2.0287 | 1.1858 | 0.97875 | 0.88216 | 3.2259 | 7.6689 | 4.6807 | 6.2552 | 4.0478 | 1.5895 | 18.7395 | 13.5439 | 18.7395
2485 | -0.78474 | -0.61143 | 0.2163 | 0.27046 | 4.5017 | 4.3664 | 4.9656 | 4.8151 | 5.0608 | 2.7249 | 16.4081 | 17.253 | 17.253
2486 | -1.9819 | -1.4306 | 0.023744 | 0.076266 | 3.8531 | 3.4647 | 5.961 | 4.3856 | 3.3246 | 2.3414 | 14.0447 | 15.48 | 15.48
2487 | -0.072796 | 0.60886 | 0.47098 | 0.72869 | 3.1598 | 5.1655 | 6.9789 | 5.7603 | 3.3493 | 1.7035 | 15.7891 | 15.1914 | 15.7891
2488 | -0.066597 | 0.54306 | 0.47345 | 0.70646 | 5.0778 | 5.1731 | 5.6376 | 5.704 | 3.6076 | 2.8313 | 18.7861 | 17.1543 | 18.7861
2489 | -0.37239 | -0.52341 | 0.3548 | 0.30034 | 5.5891 | 4.8105 | 7.4247 | 4.8728 | 4.0105 | 2.2061 | 17.4784 | 19.2303 | 19.2303
2490 | 0.78102 | 1.5133 | 0.7826 | 0.9349 | 3.7539 | 6.248 | 5.1544 | 6.5255 | 4.4557 | 1.8691 | 18.3964 | 15.2331 | 18.3964
2491 | -0.82595 | -1.2546 | 0.20442 | 0.1048 | 2.9791 | 4.3254 | 5.8516 | 4.4611 | 4.7544 | 1.73 | 13.4957 | 15.3152 | 15.3152
2492 | 0.01445 | 0.032316 | 0.50576 | 0.51289 | 3.2903 | 5.2727 | 6.0862 | 5.2808 | 3.5403 | 1.8943 | 15.7381 | 14.8111 | 15.7381
2493 | 1.4432 | 0.62051 | 0.92552 | 0.73254 | 4.384 | 7.0552 | 5.4621 | 5.7703 | 4.7379 | 1.2744 | 18.4839 | 15.8584 | 18.4839
2494 | 1.9612 | 0.55608 | 0.97507 | 0.71092 | 2.7029 | 7.6044 | 7.6717 | 5.7151 | 4.5766 | 1.3944 | 17.4167 | 16.3456 | 17.4167
2495 | -0.22285 | -0.58277 | 0.41183 | 0.28002 | 5.0323 | 4.9849 | 6.2931 | 4.8336 | 3.6628 | 1.9938 | 16.8446 | 16.9821 | 16.9821
2496 | 1.1173 | -0.33079 | 0.86806 | 0.3704 | 4.0537 | 6.6686 | 5.5255 | 5.0061 | 4.0044 | 1.8155 | 17.5439 | 15.399 | 17.5439
2497 | -0.8089 | -0.50782 | 0.20929 | 0.30579 | 3.8698 | 4.3423 | 5.4579 | 4.8832 | 5.2232 | 1.4629 | 14.5583 | 16.0138 | 16.0138
2498 | 0.56155 | -0.57159 | 0.71279 | 0.2838 | 4.1815 | 5.9672 | 7.1903 | 4.8409 | 4.969 | 1.8093 | 16.7988 | 18.1501 | 18.1501
2499 | 0.62017 | 0.013034 | 0.73243 | 0.5052 | 5.445 | 6.0424 | 6.6553 | 5.2655 | 4.49 | 2.265 | 19.0178 | 18.8552 | 19.0178
2500 | -0.34017 | 0.59032 | 0.36686 | 0.72251 | 3.7532 | 4.8476 | 4.166 | 5.7444 | 6.4 | 1.5918 | 15.937 | 15.911 | 15.937
2501 | -1.308 | -0.19554 | 0.095443 | 0.42248 | 4.8407 | 3.8973 | 5.7714 | 5.1051 | 3.578 | 2.4981 | 16.3412 | 16.6883 | 16.6883
2502 | -0.16493 | -0.68493 | 0.4345 | 0.2467 | 4.5658 | 5.054 | 6.7641 | 4.7685 | 3.8767 | 2.5489 | 16.9373 | 17.7555 | 17.7555
2503 | -0.44381 | -0.7183 | 0.32859 | 0.23629 | 5.5423 | 4.7295 | 5.0966 | 4.7479 | 4.1775 | 1.8004 | 16.8202 | 16.6168 | 16.8202
2504 | -0.8341 | 0.31247 | 0.20211 | 0.62266 | 3.1696 | 4.3174 | 3.9947 | 5.509 | 4.0024 | 1.7478 | 14.7438 | 12.9144 | 14.7438
2505 | 1.6621 | 0.98028 | 0.95175 | 0.83653 | 3.3836 | 7.2983 | 5.3446 | 6.0801 | 5.0995 | 2.4154 | 19.1774 | 16.2431 | 19.1774
2506 | -1.5395 | -0.94978 | 0.061843 | 0.17111 | 2.9128 | 3.7269 | 4.9775 | 4.6137 | 3.3484 | 2.3598 | 13.6132 | 13.5985 | 13.6132
2507 | -0.87982 | -2.3179 | 0.18948 | 0.010227 | 4.1689 | 4.2728 | 5.2511 | 4.1323 | 4.0806 | 2.4243 | 14.9982 | 15.9248 | 15.9248
2508 | -0.35368 | 0.2582 | 0.36179 | 0.60187 | 3.1273 | 4.832 | 6.7325 | 5.464 | 5.1557 | 2.2152 | 15.6384 | 17.2307 | 17.2307
2509 | -1.0841 | -1.505 | 0.13917 | 0.066167 | 3.9614 | 4.084 | 4.8502 | 4.3564 | 3.5024 | 2.702 | 15.1038 | 15.0159 | 15.1038
2510 | -0.064431 | 0.052938 | 0.47431 | 0.52111 | 2.2804 | 5.1757 | 5.8941 | 5.2972 | 4.573 | 2.098 | 14.8513 | 14.8455 | 14.8513
2511 | 0.94507 | -0.073332 | 0.82769 | 0.47077 | 5.0079 | 6.4553 | 5.5655 | 5.198 | 3.8926 | 2.3141 | 18.9753 | 16.78 | 18.9753
2512 | -0.37783 | -0.97811 | 0.35278 | 0.16401 | 4.9728 | 4.8043 | 3.8315 | 4.5983 | 5.7956 | 2.3466 | 16.722 | 16.9465 | 16.9465
2513 | -0.93513 | 1.2802 | 0.17486 | 0.89975 | 3.0511 | 4.22 | 6.2836 | 6.3344 | 4.3856 | 1.4969 | 15.1025 | 15.2172 | 15.2172
2514 | -0.040836 | -1.1302 | 0.48371 | 0.12919 | 4.2701 | 5.2046 | 4.3932 | 4.52 | 5.6421 | 1.957 | 15.9517 | 16.2624 | 16.2624
2515 | 1.4186 | 1.0971 | 0.922 | 0.8637 | 3.8581 | 7.027 | 5.3381 | 6.18 | 5.3445 | 1.6982 | 18.7633 | 16.2389 | 18.7633
2516 | 0.046794 | 0.35348 | 0.51866 | 0.63814 | 4.4223 | 5.3128 | 4.8732 | 5.5433 | 5.2236 | 1.9028 | 17.1812 | 16.4218 | 17.1812
2517 | -1.6515 | -0.20629 | 0.049321 | 0.41828 | 3.8698 | 3.6528 | 5.6198 | 5.0971 | 5.243 | 1.4914 | 14.1111 | 16.2241 | 16.2241
2518 | -1.2291 | -1.7611 | 0.10952 | 0.039115 | 2.9467 | 3.9606 | 5.4039 | 4.2678 | 4.0439 | 1.763 | 12.9382 | 14.1575 | 14.1575
2519 | 0.55648 | -0.23217 | 0.71106 | 0.4082 | 4.8104 | 5.9607 | 4.0927 | 5.0779 | 3.6988 | 1.5333 | 17.3822 | 14.1352 | 17.3822
2520 | -0.71573 | -0.096656 | 0.23708 | 0.4615 | 5.3452 | 4.4366 | 7.7452 | 5.1801 | 3.8173 | 2.3801 | 17.3419 | 19.2878 | 19.2878
2521 | -0.92136 | -1.9953 | 0.17843 | 0.023007 | 5.0645 | 4.233 | 6.4094 | 4.2019 | 4.2459 | 1.705 | 15.2045 | 17.4247 | 17.4247
2522 | 1.3381 | -0.52149 | 0.90957 | 0.30101 | 4.536 | 6.9335 | 6.8281 | 4.874 | 3.556 | 1.5648 | 17.9084 | 16.485 | 17.9084
2523 | 1.2255 | 0.51846 | 0.8898 | 0.69793 | 4.9135 | 6.7998 | 6.8711 | 5.683 | 4.7245 | 2.3236 | 19.7199 | 18.8327 | 19.7199
2524 | -0.68401 | -1.0287 | 0.24699 | 0.15182 | 4.4615 | 4.4694 | 4.76 | 4.5715 | 4.6183 | 1.6443 | 15.1468 | 15.4842 | 15.4842
2525 | -0.5506 | -0.18523 | 0.29095 | 0.42652 | 5.7156 | 4.6115 | 6.4843 | 5.1128 | 5.0288 | 1.3124 | 16.7523 | 18.5411 | 18.5411
2526 | -0.22592 | 0.47596 | 0.41063 | 0.68295 | 5.7327 | 4.9812 | 5.2606 | 5.6468 | 4.1116 | 2.3972 | 18.7579 | 17.5022 | 18.7579
2527 | 0.59942 | -0.4447 | 0.72555 | 0.32827 | 5.1004 | 6.0158 | 5.0664 | 4.9261 | 4.8348 | 1.5042 | 17.5465 | 16.5058 | 17.5465
2528 | 1.3095 | 0.52546 | 0.90481 | 0.70037 | 4.0342 | 6.8998 | 4.81 | 5.6889 | 5.1708 | 1.5688 | 18.1917 | 15.5837 | 18.1917
2529 | 1.748 | 1.8495 | 0.95976 | 0.96781 | 2.5047 | 7.3894 | 6.473 | 6.7853 | 4.2201 | 2.2861 | 18.9655 | 15.4838 | 18.9655
2530 | 0.77295 | 1.0923 | 0.78022 | 0.86265 | 3.9512 | 6.2377 | 6.3182 | 6.1759 | 4.021 | 1.3591 | 17.7239 | 15.6495 | 17.7239
2531 | 2.3647 | 2.8222 | 0.99098 | 0.99761 | 3.8286 | 7.9634 | 5.7813 | 7.3893 | 3.7061 | 1.7251 | 20.9065 | 15.0411 | 20.9065
2532 | 1.0498 | 0.36726 | 0.8531 | 0.64329 | 3.7737 | 6.5857 | 5.5852 | 5.5549 | 5.4109 | 2.7123 | 18.6265 | 17.482 | 18.6265
2533 | 0.46393 | 0.60806 | 0.67865 | 0.72843 | 4.744 | 5.8418 | 5.3243 | 5.7596 | 4.4224 | 2.4564 | 18.8019 | 16.9471 | 18.8019
2534 | -0.64339 | 0.56826 | 0.25998 | 0.71507 | 3.9324 | 4.512 | 7.0507 | 5.7255 | 4.0763 | 1.3639 | 15.5338 | 16.4233 | 16.4233
2535 | 1.6752 | 1.233 | 0.95305 | 0.89121 | 4.6509 | 7.3124 | 5.2497 | 6.2949 | 3.8308 | 1.8535 | 20.1117 | 15.5849 | 20.1117
2536 | -1.1727 | -0.54453 | 0.12045 | 0.29304 | 3.5345 | 4.0075 | 6.2519 | 4.8587 | 4.3415 | 2.1162 | 14.517 | 16.2442 | 16.2442
2537 | -0.62712 | -0.63197 | 0.26529 | 0.2637 | 4.1884 | 4.5292 | 5.5866 | 4.8019 | 5.5016 | 1.7332 | 15.2527 | 17.0098 | 17.0098
2538 | 1.9567 | 1.9619 | 0.97481 | 0.97511 | 2.5875 | 7.6 | 4.663 | 6.867 | 4.257 | 1.5952 | 18.6497 | 13.1026 | 18.6497
2539 | 1.495 | 0.13593 | 0.93255 | 0.55406 | 3.3257 | 7.1141 | 4.4764 | 5.3638 | 4.6129 | 1.9038 | 17.7074 | 14.3188 | 17.7074
2540 | -0.59969 | -3.3742 | 0.27436 | 0.00037018 | 4.6126 | 4.5585 | 4.8829 | 4.0245 | 3.3545 | 2.3923 | 15.5879 | 15.2423 | 15.5879
2541 | -2.4935 | -0.78688 | 0.0063245 | 0.21568 | 4.39 | 3.2561 | 6.0664 | 4.7065 | 4.1394 | 1.9187 | 14.2712 | 16.5145 | 16.5145
2542 | -0.83172 | -0.32111 | 0.20278 | 0.37406 | 4.6856 | 4.3197 | 7.0222 | 5.013 | 3.0655 | 1.3549 | 15.3733 | 16.1283 | 16.1283
2543 | 0.039478 | -0.72625 | 0.51575 | 0.23384 | 3.8696 | 5.3038 | 5.0284 | 4.743 | 3.8802 | 1.5984 | 15.5149 | 14.3767 | 15.5149
2544 | 0.41482 | -0.1184 | 0.66086 | 0.45288 | 3.0279 | 5.7789 | 5.8034 | 5.1634 | 5.2184 | 1.9965 | 15.9667 | 16.0463 | 16.0463
2545 | -0.94428 | -0.73617 | 0.17251 | 0.23082 | 3.7339 | 4.2114 | 6.4376 | 4.737 | 3.778 | 1.8939 | 14.5762 | 15.8434 | 15.8434
2546 | -0.43553 | 0.18877 | 0.33159 | 0.57486 | 3.8579 | 4.7389 | 4.0538 | 5.4068 | 3.2231 | 1.6576 | 15.6612 | 12.7924 | 15.6612
2547 | -1.2337 | -2.4136 | 0.10865 | 0.0078989 | 2.2777 | 3.9568 | 7.1155 | 4.1157 | 5.2416 | 1.616 | 11.9662 | 16.2508 | 16.2508
2548 | -0.26604 | 0.77947 | 0.39511 | 0.78215 | 3.714 | 4.9339 | 6.8616 | 5.9072 | 3.595 | 1.1771 | 15.7322 | 15.3477 | 15.7322
2549 | -1.9272 | -1.0596 | 0.02698 | 0.14466 | 3.7905 | 3.4928 | 6.817 | 4.5555 | 4.0447 | 2.0326 | 13.8714 | 16.6849 | 16.6849
2550 | -0.52341 | -1.548 | 0.30034 | 0.060815 | 4.0205 | 4.6412 | 5.8955 | 4.3403 | 3.3925 | 2.4898 | 15.4916 | 15.7982 | 15.7982
2551 | 0.19729 | -0.13305 | 0.5782 | 0.44708 | 3.796 | 5.5016 | 5.7406 | 5.1522 | 3.8997 | 1.3052 | 15.7551 | 14.7416 | 15.7551
2552 | -1.2348 | 0.4739 | 0.10844 | 0.68222 | 4.1029 | 3.9559 | 4.7505 | 5.645 | 6.1788 | 1.8622 | 15.566 | 16.8945 | 16.8945
2553 | 0.2309 | 2.4582 | 0.59131 | 0.99302 | 4.6915 | 5.5442 | 7.2687 | 7.1919 | 3.3908 | 1.8535 | 19.2812 | 17.2045 | 19.2812
2554 | 1.6114 | 1.1602 | 0.94645 | 0.87701 | 4.8224 | 7.2433 | 2.4488 | 6.2335 | 4.9952 | 2.5966 | 20.8958 | 14.863 | 20.8958
2555 | 2.0237 | 2.153 | 0.9785 | 0.98434 | 3.2658 | 7.6642 | 7.1725 | 6.9994 | 4.2886 | 2.6682 | 20.5976 | 17.3952 | 20.5976
2556 | 0.1244 | -0.25191 | 0.5495 | 0.40055 | 4.0301 | 5.4098 | 5.5586 | 5.0633 | 4.505 | 2.4564 | 16.9597 | 16.5501 | 16.9597
2557 | -0.7421 | -1.7823 | 0.22901 | 0.037354 | 2.9992 | 4.4096 | 6.5944 | 4.2613 | 5.9349 | 2.0294 | 13.6994 | 17.5579 | 17.5579
2558 | -0.20966 | 0.42157 | 0.41697 | 0.66333 | 5.4841 | 5.0005 | 6.6307 | 5.6007 | 3.7672 | 1.9626 | 18.048 | 17.8447 | 18.048
2559 | 1.5005 | 1.1155 | 0.93326 | 0.86768 | 5.0098 | 7.1203 | 4.9688 | 6.1956 | 5.5991 | 1.8586 | 20.1843 | 17.4363 | 20.1843
2560 | -0.010444 | 0.15421 | 0.49583 | 0.56128 | 4.5412 | 5.242 | 5.0502 | 5.3786 | 4.1289 | 2.5523 | 17.7141 | 16.2726 | 17.7141
2561 | -1.2242 | -0.078501 | 0.11044 | 0.46871 | 5.243 | 3.9646 | 5.2235 | 5.194 | 4.6041 | 1.9059 | 16.3075 | 16.9765 | 16.9765
2562 | -0.60867 | -0.355 | 0.27137 | 0.36129 | 3.8508 | 4.5489 | 5.0864 | 4.9888 | 4.331 | 2.1083 | 15.4967 | 15.3765 | 15.4967
2563 | 0.42029 | 0.1158 | 0.66286 | 0.54609 | 4.6703 | 5.7859 | 6.754 | 5.3475 | 4.8287 | 1.3747 | 17.1784 | 17.6277 | 17.6277
2564 | -0.69414 | -0.27309 | 0.2438 | 0.39239 | 2.717 | 4.4589 | 7.446 | 5.0478 | 4.3427 | 1.8951 | 14.1188 | 16.4008 | 16.4008
2565 | 1.4992 | 1.2768 | 0.93309 | 0.89917 | 4.1546 | 7.1188 | 5.0113 | 6.3316 | 4.4304 | 1.9299 | 19.5349 | 15.5262 | 19.5349
2566 | 0.13813 | 1.2278 | 0.55493 | 0.89023 | 4.6613 | 5.427 | 6.0594 | 6.2905 | 5.004 | 1.7528 | 18.1316 | 17.4775 | 18.1316
2567 | -0.16085 | 0.49533 | 0.43611 | 0.68982 | 4.8351 | 5.0589 | 5.8008 | 5.6633 | 4.057 | 1.4426 | 16.9998 | 16.1355 | 16.9998
2568 | -0.49665 | -1.4725 | 0.30972 | 0.070446 | 3.7239 | 4.6707 | 5.9613 | 4.369 | 3.9665 | 1.5469 | 14.3104 | 15.1986 | 15.1986
2569 | -1.074 | -1.2398 | 0.14142 | 0.10752 | 3.9784 | 4.093 | 5.0408 | 4.4679 | 4.7141 | 1.6626 | 14.2018 | 15.3959 | 15.3959
2570 | 0.48383 | 1.1162 | 0.68575 | 0.86783 | 3.7117 | 5.8674 | 6.3635 | 6.1962 | 4.9929 | 1.402 | 17.1773 | 16.4701 | 17.1773
2571 | -0.57168 | 0.20901 | 0.28377 | 0.58278 | 4.7668 | 4.5886 | 5.1499 | 5.4234 | 4.1545 | 2.335 | 17.1138 | 16.4061 | 17.1138
2572 | -1.0915 | -0.37254 | 0.13752 | 0.35475 | 4.4802 | 4.0775 | 6.6136 | 4.9764 | 4.431 | 1.8759 | 15.4099 | 17.4006 | 17.4006
2573 | -0.11576 | -0.37195 | 0.45392 | 0.35496 | 3.6429 | 5.1133 | 4.3677 | 4.9768 | 3.5057 | 2.2637 | 15.9966 | 13.7799 | 15.9966
2574 | 1.6293 | -0.1583 | 0.94837 | 0.43711 | 4.2 | 7.2628 | 5.9652 | 5.1331 | 3.985 | 2.3685 | 18.9644 | 16.5187 | 18.9644
2575 | 0.050656 | 0.59089 | 0.5202 | 0.7227 | 3.0964 | 5.3177 | 5.6793 | 5.7449 | 3.6499 | 2.2815 | 16.4404 | 14.7071 | 16.4404
2576 | 0.80326 | -0.061387 | 0.78909 | 0.47553 | 4.2913 | 6.2762 | 7.5562 | 5.2073 | 4.3653 | 1.4289 | 17.2037 | 17.6417 | 17.6417
2577 | 0.24419 | -0.73301 | 0.59646 | 0.23178 | 3.1725 | 5.5611 | 4.7345 | 4.7389 | 3.6745 | 2.1408 | 15.6133 | 13.7223 | 15.6133
2578 | 0.45594 | -0.46302 | 0.67578 | 0.32167 | 3.8445 | 5.8316 | 6.7755 | 4.9135 | 4.1633 | 2.0163 | 16.6059 | 16.7996 | 16.7996
2579 | 0.477 | 0.4473 | 0.68332 | 0.67267 | 3.1104 | 5.8586 | 6.1542 | 5.6225 | 5.075 | 1.4292 | 16.0207 | 15.7688 | 16.0207
2580 | 0.17097 | -0.42058 | 0.56788 | 0.33703 | 3.001 | 5.4684 | 7.7492 | 4.9428 | 4.9153 | 1.882 | 15.2941 | 17.5475 | 17.5475
2581 | 0.71839 | -0.72063 | 0.76374 | 0.23557 | 2.9879 | 6.1681 | 6.3551 | 4.7465 | 3.6075 | 2.09 | 15.9925 | 15.0405 | 15.9925
2582 | -0.63201 | -0.43911 | 0.26369 | 0.33029 | 3.4505 | 4.524 | 5.5189 | 4.93 | 4.6748 | 1.631 | 14.5355 | 15.2752 | 15.2752
2583 | -0.2222 | -1.075 | 0.41208 | 0.14118 | 5.035 | 4.9857 | 6.2619 | 4.5476 | 3.927 | 1.8871 | 16.4553 | 17.1109 | 17.1109
2584 | 1.3812 | -0.2415 | 0.91639 | 0.40458 | 4.5675 | 6.9838 | 4.7265 | 5.071 | 5.9335 | 2.2436 | 18.8659 | 17.4712 | 18.8659
2585 | 0.83922 | -0.78912 | 0.79933 | 0.21502 | 4.0869 | 6.3219 | 7.2876 | 4.7052 | 4.2252 | 2.0191 | 17.1331 | 17.6188 | 17.6188
2586 | -0.75046 | 0.12779 | 0.22649 | 0.55084 | 3.49 | 4.401 | 5.5759 | 5.3572 | 3.5494 | 2.622 | 15.8703 | 15.2373 | 15.8703
2587 | 1.6214 | 0.7447 | 0.94754 | 0.77177 | 3.7576 | 7.2543 | 6.5671 | 5.8772 | 4.3974 | 1.4163 | 18.3055 | 16.1385 | 18.3055
2588 | -0.85869 | -1.1717 | 0.19525 | 0.12065 | 4.5913 | 4.2933 | 7.1465 | 4.4998 | 3.6075 | 2.5587 | 15.9431 | 17.9041 | 17.9041
2589 | -1.137 | -0.13249 | 0.12776 | 0.4473 | 3.309 | 4.0379 | 4.2 | 5.1527 | 4.3602 | 2.2098 | 14.7093 | 14.079 | 14.7093
2590 | -0.94726 | -1.0585 | 0.17175 | 0.1449 | 3.9446 | 4.2086 | 3.9504 | 4.556 | 3.723 | 1.8312 | 14.5404 | 13.4492 | 14.5404
2591 | -0.44882 | -0.052967 | 0.32678 | 0.47888 | 3.8912 | 4.7239 | 5.0514 | 5.2138 | 4.9803 | 1.8163 | 15.6452 | 15.7391 | 15.7391
2592 | 0.25832 | -0.54225 | 0.60192 | 0.29382 | 5.2301 | 5.579 | 5.2376 | 4.8602 | 3.5869 | 1.7706 | 17.44 | 15.8252 | 17.44
2593 | -0.21698 | 1.2444 | 0.41411 | 0.89333 | 3.0528 | 4.9918 | 6.0121 | 6.3045 | 3.8842 | 2.4135 | 16.7627 | 15.3626 | 16.7627
2594 | 0.27098 | 0.079769 | 0.6068 | 0.53179 | 3.4666 | 5.5951 | 3.6753 | 5.3186 | 5.2572 | 1.8401 | 16.2204 | 14.2391 | 16.2204
2595 | 0.17004 | 0.1731 | 0.56751 | 0.56871 | 3.407 | 5.4672 | 7.1137 | 5.394 | 4.4431 | 2.6856 | 16.9538 | 17.6493 | 17.6493
2596 | 1.0088 | -0.12832 | 0.84347 | 0.44895 | 4.2664 | 6.5348 | 7.4147 | 5.1558 | 5.0744 | 1.3905 | 17.3476 | 18.1461 | 18.1461
2597 | -0.1978 | 0.13305 | 0.4216 | 0.55292 | 2.9577 | 5.0147 | 5.8677 | 5.3615 | 3.9245 | 2.2344 | 15.5682 | 14.9842 | 15.5682
2598 | 0.87762 | 0.62838 | 0.80992 | 0.73512 | 4.9032 | 6.3704 | 6.2297 | 5.7771 | 4.7586 | 1.6214 | 18.6721 | 17.5129 | 18.6721
2599 | 1.3225 | 2.5596 | 0.90699 | 0.99476 | 4.9653 | 6.9151 | 5.1181 | 7.2505 | 3.0634 | 1.9468 | 21.0777 | 15.0936 | 21.0777
2600 | -0.98503 | -1.5733 | 0.1623 | 0.057826 | 3.8496 | 4.1734 | 4.862 | 4.331 | 4.7636 | 1.5825 | 13.9365 | 15.0577 | 15.0577
2601 | 1.3316 | 1.2111 | 0.9085 | 0.88707 | 4.8046 | 6.9258 | 4.0237 | 6.2765 | 4.0598 | 1.9553 | 19.9622 | 14.8434 | 19.9622
2602 | 0.52387 | 0.20927 | 0.69981 | 0.58288 | 4.063 | 5.9188 | 6.9386 | 5.4236 | 4.416 | 1.3644 | 16.7698 | 16.7821 | 16.7821
2603 | -0.87037 | -0.86656 | 0.19205 | 0.19309 | 2.8547 | 4.282 | 5.4986 | 4.6601 | 5.7633 | 2.3619 | 14.1587 | 16.4785 | 16.4785
2604 | -0.58705 | -1.369 | 0.27858 | 0.085499 | 3.4321 | 4.572 | 5.8003 | 4.411 | 4.1767 | 2.104 | 14.5191 | 15.5131 | 15.5131
2605 | -1.292 | -0.39579 | 0.098176 | 0.34613 | 4.9919 | 3.9098 | 5.0035 | 4.9601 | 5.1182 | 1.7696 | 15.6314 | 16.8832 | 16.8832
2606 | 0.0097295 | 0.23037 | 0.50388 | 0.5911 | 4.9589 | 5.2669 | 6.6028 | 5.441 | 4.027 | 1.8378 | 17.5045 | 17.4264 | 17.5045
2607 | 0.82187 | 0.42568 | 0.79442 | 0.66483 | 4.5132 | 6.2999 | 6.595 | 5.6041 | 4.6703 | 1.518 | 17.9352 | 17.2966 | 17.9352
2608 | -1.8352 | -1.0817 | 0.033241 | 0.1397 | 3.4646 | 3.5427 | 7.4137 | 4.5442 | 3.6802 | 1.873 | 13.4245 | 16.4314 | 16.4314
2609 | 1.2706 | 1.1712 | 0.89807 | 0.87924 | 3.7254 | 6.8538 | 6.3569 | 6.2428 | 3.6397 | 1.8089 | 18.6309 | 15.531 | 18.6309
2610 | -1.5678 | -1.8917 | 0.058464 | 0.029265 | 3.0579 | 3.7076 | 7.437 | 4.2293 | 4.4816 | 2.2686 | 13.2634 | 17.245 | 17.245
2611 | -1.6511 | -0.30215 | 0.049359 | 0.38127 | 2.7279 | 3.653 | 6.704 | 5.0267 | 3.3689 | 2.395 | 13.8025 | 15.1957 | 15.1957
2612 | -0.050676 | -0.16325 | 0.47979 | 0.43516 | 3.4359 | 5.1925 | 3.0742 | 5.1294 | 4.1209 | 2.8683 | 16.6262 | 13.4994 | 16.6262
2613 | 1.3334 | 0.27722 | 0.9088 | 0.60919 | 4.2197 | 6.928 | 7.1861 | 5.4797 | 6.4741 | 1.3154 | 17.9428 | 19.1953 | 19.1953
2614 | 0.55937 | -0.45793 | 0.71205 | 0.3235 | 3.7056 | 5.9644 | 7.1055 | 4.917 | 3.3999 | 2.4913 | 17.0784 | 16.7023 | 17.0784
2615 | 1.4628 | -0.18981 | 0.92824 | 0.42473 | 3.103 | 7.0776 | 5.6737 | 5.1094 | 4.671 | 2.1011 | 17.3911 | 15.5488 | 17.3911
2616 | 0.49307 | 1.6114 | 0.68902 | 0.94646 | 5.3343 | 5.8792 | 5.8687 | 6.6034 | 4.1892 | 2.3287 | 20.1456 | 17.7208 | 20.1456
2617 | 1.3054 | 0.14135 | 0.90412 | 0.55621 | 4.8174 | 6.895 | 4.9725 | 5.3682 | 4.7444 | 1.5268 | 18.6074 | 16.0611 | 18.6074
2618 | -1.8799 | -0.42791 | 0.030062 | 0.33436 | 3.3239 | 3.518 | 6.4882 | 4.9377 | 3.4916 | 2.7255 | 14.5051 | 16.0292 | 16.0292
2619 | -0.9011 | -1.911 | 0.18377 | 0.028004 | 4.7792 | 4.2524 | 4.2361 | 4.224 | 4.3154 | 1.5274 | 14.783 | 14.8581 | 14.8581
2620 | 2.4099 | 0.78863 | 0.99202 | 0.78483 | 4.6728 | 7.9996 | 6.2258 | 5.9151 | 3.5171 | 2.2574 | 20.8449 | 16.673 | 20.8449
2621 | -1.5809 | -2.1656 | 0.056951 | 0.015171 | 4.7004 | 3.6988 | 5.0541 | 4.1623 | 4.1183 | 1.4251 | 13.9867 | 15.2979 | 15.2979
2622 | -0.1592 | -0.47017 | 0.43676 | 0.31912 | 3.3627 | 5.0609 | 4.9507 | 4.9087 | 5.1251 | 1.6753 | 15.0076 | 15.1138 | 15.1138
2623 | 0.32424 | 0.31385 | 0.62712 | 0.62318 | 3.3214 | 5.663 | 4.5654 | 5.5102 | 4.576 | 2.3657 | 16.8603 | 14.8285 | 16.8603
2624 | -0.27592 | -0.25201 | 0.3913 | 0.40052 | 4.791 | 4.9223 | 4.4561 | 5.0633 | 4.543 | 1.5554 | 16.3321 | 15.3456 | 16.3321
2625 | 0.99963 | 0.092221 | 0.84126 | 0.53674 | 2.9062 | 6.5234 | 5.4262 | 5.3286 | 3.8212 | 1.4759 | 16.2341 | 13.6295 | 16.2341
2626 | 1.2298 | 1.05 | 0.89061 | 0.85315 | 5.0933 | 6.805 | 3.9997 | 6.1398 | 5.3331 | 1.7021 | 19.7402 | 16.1283 | 19.7402
2627 | -0.75429 | -0.6491 | 0.22534 | 0.25814 | 4.9482 | 4.3972 | 3.207 | 4.791 | 4.3357 | 1.6349 | 15.7713 | 14.1258 | 15.7713
2628 | -0.048865 | -1.089 | 0.48051 | 0.13807 | 4.6928 | 5.1948 | 4.0062 | 4.5405 | 4.9724 | 2.2925 | 16.7206 | 15.9638 | 16.7206
2629 | 0.82079 | 0.041461 | 0.79412 | 0.51654 | 5.1173 | 6.2985 | 4.982 | 5.288 | 3.2682 | 1.8752 | 18.579 | 15.2427 | 18.579
2630 | 0.50252 | -0.7907 | 0.69235 | 0.21456 | 3.9959 | 5.8914 | 5.8565 | 4.7042 | 4.5236 | 2.0804 | 16.672 | 16.4564 | 16.672
2631 | -0.27412 | -0.87844 | 0.39199 | 0.18985 | 3.2062 | 4.9244 | 7.3925 | 4.6534 | 5.6916 | 1.6574 | 14.4413 | 17.9476 | 17.9476
2632 | -0.011031 | 1.0274 | 0.4956 | 0.84789 | 2.9065 | 5.2413 | 4.9875 | 6.1205 | 4.3892 | 2.4667 | 16.735 | 14.75 | 16.735
2633 | -0.60478 | -0.68462 | 0.27266 | 0.24679 | 2.51 | 4.553 | 5.6996 | 4.7687 | 3.3478 | 1.3964 | 13.2281 | 12.9538 | 13.2281
2634 | -1.0957 | -1.1141 | 0.1366 | 0.13262 | 4.5929 | 4.0738 | 3.6233 | 4.528 | 4.7289 | 2.3901 | 15.5848 | 15.3352 | 15.5848
2635 | -0.95547 | -0.13158 | 0.16967 | 0.44766 | 2.5261 | 4.2009 | 6.5742 | 5.1534 | 4.2872 | 2.292 | 14.1724 | 15.6796 | 15.6796
2636 | -0.75586 | -1.369 | 0.22487 | 0.085499 | 4.9345 | 4.3956 | 6.4794 | 4.411 | 5.2875 | 2.0515 | 15.7926 | 18.7529 | 18.7529
2637 | -1.0167 | 1.5791 | 0.15466 | 0.94285 | 4.9671 | 4.1444 | 4.8628 | 6.578 | 4.171 | 1.9432 | 17.6326 | 15.944 | 17.6326
2638 | -1.4868 | -1.0822 | 0.068528 | 0.13959 | 4.2549 | 3.7636 | 5.1559 | 4.544 | 4.9853 | 1.5451 | 14.1075 | 15.9411 | 15.9411
2639 | 0.40952 | -0.0073376 | 0.65892 | 0.49707 | 4.9872 | 5.7721 | 5.0355 | 5.2495 | 3.7557 | 1.7965 | 17.8053 | 15.5749 | 17.8053
2640 | 1.0703 | 1.7521 | 0.85776 | 0.96012 | 4.4831 | 6.6109 | 7.1955 | 6.7123 | 3.9217 | 2.1474 | 19.9537 | 17.7476 | 19.9537
2641 | 1.3143 | 2.1597 | 0.90563 | 0.9846 | 3.7931 | 6.9055 | 6.7414 | 7.0039 | 3.2616 | 2.3045 | 20.0069 | 16.1006 | 20.0069
2642 | -0.49215 | -0.33893 | 0.31131 | 0.36733 | 3.8577 | 4.6756 | 6.0826 | 5.0003 | 4.0123 | 1.7508 | 15.2845 | 15.7034 | 15.7034
2643 | 1.6766 | 0.19024 | 0.95319 | 0.57544 | 4.3233 | 7.3139 | 6.1107 | 5.408 | 4.7282 | 1.8013 | 18.8464 | 16.9634 | 18.8464
2644 | -0.098231 | -1.4679 | 0.46087 | 0.071062 | 3.2753 | 5.1345 | 6.09 | 4.3707 | 4.0571 | 2.0397 | 14.8204 | 15.4621 | 15.4621
2645 | 0.43078 | 1.5311 | 0.66669 | 0.93712 | 2.781 | 5.7993 | 6.8692 | 6.5397 | 3.4689 | 1.5981 | 16.7182 | 14.7172 | 16.7182
2646 | 0.036079 | -0.83507 | 0.51439 | 0.20184 | 4.4444 | 5.2995 | 6.3352 | 4.6782 | 4.4871 | 2.281 | 16.7032 | 17.5476 | 17.5476
2647 | -1.2158 | -1.4336 | 0.11204 | 0.075845 | 4.8761 | 3.9716 | 6.1809 | 4.3844 | 4.4035 | 2.6821 | 15.9141 | 18.1427 | 18.1427
2648 | -0.6939 | -0.48966 | 0.24387 | 0.31219 | 3.0966 | 4.4591 | 6.096 | 4.8954 | 4.8854 | 1.8312 | 14.2823 | 15.9092 | 15.9092
2649 | -0.92181 | -0.84978 | 0.17831 | 0.19772 | 3.9025 | 4.2326 | 6.1331 | 4.6697 | 5.1161 | 2.1051 | 14.9099 | 17.2568 | 17.2568
2650 | 1.674 | 1.1629 | 0.95293 | 0.87756 | 3.1529 | 7.3111 | 6.7694 | 6.2358 | 4.6272 | 2.0474 | 18.7471 | 16.5968 | 18.7471
2651 | 1.5469 | 1.3224 | 0.93906 | 0.90699 | 3.4844 | 7.1723 | 6.7464 | 6.3696 | 3.5775 | 1.3813 | 18.4076 | 15.1897 | 18.4076
2652 | -0.07019 | 0.52843 | 0.47202 | 0.7014 | 4.7674 | 5.1687 | 5.7808 | 5.6915 | 3.7245 | 1.8048 | 17.4323 | 16.0774 | 17.4323
2653 | 0.88138 | 1.1052 | 0.81095 | 0.86546 | 3.9981 | 6.3752 | 5.1338 | 6.1868 | 3.7793 | 2.3477 | 18.9078 | 15.2589 | 18.9078
2654 | 0.23693 | -0.60928 | 0.59364 | 0.27117 | 3.9326 | 5.5518 | 6.0501 | 4.8165 | 4.2031 | 1.9268 | 16.2277 | 16.1126 | 16.2277
2655 | -1.2551 | -0.92032 | 0.10473 | 0.1787 | 3.6007 | 3.9394 | 6.0147 | 4.6299 | 5.1576 | 1.935 | 14.105 | 16.7079 | 16.7079
2656 | -1.1372 | 0.45089 | 0.12773 | 0.67397 | 3.219 | 4.0378 | 4.4986 | 5.6255 | 3.8433 | 2.1279 | 15.0102 | 13.6888 | 15.0102
2657 | -0.37629 | 0.95027 | 0.35335 | 0.82901 | 5.6349 | 4.8061 | 6.3886 | 6.0543 | 4.1805 | 1.5933 | 18.0886 | 17.7973 | 18.0886
2658 | -0.53953 | 0.8905 | 0.29476 | 0.8134 | 4.4577 | 4.6235 | 5.8532 | 6.0029 | 4.0809 | 2.1404 | 17.2246 | 16.5323 | 17.2246
2659 | 1.0709 | 1.3744 | 0.8579 | 0.91535 | 3.0981 | 6.6117 | 5.2728 | 6.4125 | 4.8335 | 1.7778 | 17.9002 | 14.9823 | 17.9002
2660 | 1.7778 | 0.6874 | 0.96228 | 0.75409 | 2.601 | 7.4205 | 6.7417 | 5.8278 | 4.2598 | 1.7693 | 17.6187 | 15.3717 | 17.6187
2661 | -0.61574 | -1.4796 | 0.26903 | 0.069488 | 4.6151 | 4.5413 | 4.4124 | 4.3662 | 4.3758 | 2.1525 | 15.6751 | 15.5558 | 15.6751
2662 | -1.4467 | -1.0278 | 0.073986 | 0.15202 | 3.1698 | 3.7923 | 7.2362 | 4.572 | 4.2593 | 2.106 | 13.6401 | 16.7713 | 16.7713
2663 | -0.54047 | -0.53348 | 0.29444 | 0.29685 | 3.5181 | 4.6225 | 3.4541 | 4.8661 | 3.107 | 1.7908 | 14.7975 | 11.87 | 14.7975
2664 | -0.15611 | 0.75708 | 0.43797 | 0.7755 | 4.2587 | 5.0646 | 4.3023 | 5.8879 | 4.5871 | 2.4307 | 17.6419 | 15.5788 | 17.6419
2665 | 0.46383 | 0.80591 | 0.67862 | 0.78985 | 4.1034 | 5.8417 | 6.8424 | 5.93 | 4.2554 | 2.4775 | 18.3527 | 17.6788 | 18.3527
2666 | 1.0757 | 0.642 | 0.85897 | 0.73956 | 4.4118 | 6.6176 | 6.3064 | 5.7888 | 5.1024 | 2.7587 | 19.5769 | 18.5793 | 19.5769
2667 | 0.91656 | 0.081211 | 0.82031 | 0.53236 | 3.5561 | 6.4195 | 5.7497 | 5.3197 | 5.4592 | 2.0401 | 17.3355 | 16.8052 | 17.3355
2668 | -0.77225 | -0.81994 | 0.21998 | 0.20612 | 3.8528 | 4.379 | 5.9474 | 4.687 | 4.887 | 1.5232 | 14.442 | 16.2103 | 16.2103
2669 | 0.13471 | -1.5718 | 0.55358 | 0.057993 | 4.1102 | 5.4227 | 5.3228 | 4.3315 | 3.7973 | 1.485 | 15.3495 | 14.7153 | 15.3495
2670 | -0.10366 | -0.2136 | 0.45872 | 0.41543 | 4.7378 | 5.1279 | 4.3453 | 5.0916 | 3.4055 | 1.659 | 16.6164 | 14.1476 | 16.6164
2671 | -0.50248 | -2.1204 | 0.30766 | 0.016986 | 4.1385 | 4.6642 | 5.5361 | 4.1722 | 4.0508 | 2.202 | 15.1769 | 15.9274 | 15.9274
2672 | 0.14088 | 0.022981 | 0.55602 | 0.50917 | 2.8318 | 5.4305 | 4.3944 | 5.2734 | 4.9408 | 1.4141 | 14.9498 | 13.5811 | 14.9498
2673 | -0.24777 | 0.0036777 | 0.40216 | 0.50147 | 2.8064 | 4.9554 | 7.2289 | 5.2581 | 4.8031 | 2.0718 | 15.0918 | 16.9102 | 16.9102
2674 | -0.54665 | -1.5746 | 0.29231 | 0.057673 | 5.0645 | 4.6158 | 6.0046 | 4.3305 | 5.7204 | 1.9328 | 15.9436 | 18.7223 | 18.7223
2675 | -0.24041 | -1.358 | 0.40501 | 0.08723 | 4.5718 | 4.9641 | 7.3473 | 4.4156 | 4.6398 | 2.1021 | 16.0535 | 18.661 | 18.661
2676 | -0.94238 | -0.66633 | 0.173 | 0.2526 | 3.5348 | 4.2132 | 4.4916 | 4.7802 | 5.278 | 2.1905 | 14.7186 | 15.4947 | 15.4947
2677 | 0.39458 | 1.7542 | 0.65342 | 0.96031 | 3.7539 | 5.7529 | 3.9994 | 6.7139 | 3.5054 | 2.4153 | 18.636 | 13.6741 | 18.636
2678 | -0.018074 | -2.3848 | 0.49279 | 0.008545 | 3.9684 | 5.2326 | 7.0047 | 4.1205 | 4.2647 | 2.1096 | 15.4311 | 17.3474 | 17.3474
2679 | -0.95926 | 0.11967 | 0.16871 | 0.54763 | 3.65 | 4.1974 | 4.6193 | 5.3507 | 5.8504 | 1.5907 | 14.7886 | 15.7103 | 15.7103
2680 | -0.58279 | 0.98724 | 0.28002 | 0.83824 | 4.3932 | 4.5766 | 6.8403 | 6.0861 | 5.431 | 1.6046 | 16.6605 | 18.269 | 18.269
2681 | -2.3602 | -1.3942 | 0.0091333 | 0.081634 | 4.6792 | 3.3017 | 6.5662 | 4.4005 | 3.9619 | 1.9118 | 14.2931 | 17.1191 | 17.1191
2682 | 0.047438 | 0.89721 | 0.51892 | 0.8152 | 2.7045 | 5.3136 | 6.7896 | 6.0087 | 3.7082 | 1.8018 | 15.8287 | 15.0042 | 15.8287
2683 | 2.3587 | 1.5414 | 0.99083 | 0.93839 | 4.635 | 7.9586 | 3.5522 | 6.548 | 3.4218 | 2.4667 | 21.6084 | 14.0758 | 21.6084
2684 | 0.5845 | 0.46876 | 0.72056 | 0.68038 | 3.6637 | 5.9966 | 5.52 | 5.6407 | 4.7249 | 2.1561 | 17.457 | 16.0647 | 17.457
2685 | 0.72327 | 0.035872 | 0.76524 | 0.51431 | 2.7068 | 6.1744 | 4.7338 | 5.2836 | 4.1884 | 1.8109 | 15.9757 | 13.44 | 15.9757
2686 | -0.586 | 0.10125 | 0.27894 | 0.54033 | 4.9813 | 4.5732 | 6.5859 | 5.3358 | 3.9509 | 2.2622 | 17.1525 | 17.7804 | 17.7804
2687 | -0.058567 | 0.19766 | 0.47665 | 0.57834 | 2.8583 | 5.1829 | 6.5402 | 5.4141 | 4.8184 | 1.9835 | 15.4388 | 16.2004 | 16.2004
2688 | 0.13393 | -0.90969 | 0.55327 | 0.18149 | 2.591 | 5.4218 | 7.0098 | 4.6358 | 4.5962 | 2.2159 | 14.8645 | 16.413 | 16.413
2689 | 0.42061 | -1.06 | 0.66298 | 0.14457 | 3.112 | 5.7863 | 7.632 | 4.5553 | 3.6014 | 2.0604 | 15.5139 | 16.4057 | 16.4057
2690 | -0.38478 | -0.52286 | 0.3502 | 0.30054 | 3.8391 | 4.7964 | 4.4315 | 4.8731 | 3.5742 | 2.2701 | 15.7787 | 14.1149 | 15.7787
2691 | -1.8903 | -1.3839 | 0.029362 | 0.083187 | 3.6317 | 3.5124 | 6.1064 | 4.4047 | 5.1249 | 1.4014 | 12.9502 | 16.2644 | 16.2644
2692 | 0.37442 | -1.4789 | 0.64595 | 0.069579 | 3.7069 | 5.7271 | 7.297 | 4.3664 | 3.8879 | 2.7676 | 16.5681 | 17.6594 | 17.6594
2693 | -0.083548 | 0.33046 | 0.46671 | 0.62948 | 3.4791 | 5.1524 | 3.7455 | 5.5241 | 4.076 | 2.412 | 16.5676 | 13.7126 | 16.5676
2694 | 0.94347 | 1.3007 | 0.82728 | 0.90332 | 3.705 | 6.4533 | 6.5803 | 6.3515 | 5.1879 | 2.0415 | 18.5513 | 17.5147 | 18.5513
2695 | 0.0087606 | 0.32791 | 0.50349 | 0.62851 | 2.9347 | 5.2657 | 6.5816 | 5.5219 | 3.8398 | 1.6882 | 15.4106 | 15.0444 | 15.4106
2696 | 1.1584 | 0.45432 | 0.87665 | 0.6752 | 4.195 | 6.7188 | 6.4247 | 5.6284 | 4.0575 | 2.0388 | 18.581 | 16.7159 | 18.581
2697 | 0.083518 | -0.88413 | 0.53328 | 0.18831 | 3.899 | 5.3586 | 6.2487 | 4.6501 | 5.045 | 1.7088 | 15.6166 | 16.9015 | 16.9015
2698 | -0.23213 | 0.084851 | 0.40822 | 0.53381 | 3.9964 | 4.9739 | 5.6525 | 5.3227 | 4.8147 | 1.4714 | 15.7643 | 15.935 | 15.935
2699 | -1.223 | 0.32653 | 0.11066 | 0.62799 | 5.4451 | 3.9656 | 6.3929 | 5.5208 | 4.0753 | 2.4311 | 17.3625 | 18.3444 | 18.3444
2700 | 1.7211 | 1.4068 | 0.95738 | 0.92026 | 3.2489 | 7.3612 | 5.7992 | 6.4391 | 3.7848 | 2.1622 | 19.2113 | 14.995 | 19.2113
2701 | -0.067902 | -0.031325 | 0.47293 | 0.48751 | 3.1176 | 5.1715 | 4.9165 | 5.2307 | 5.1005 | 1.2355 | 14.7553 | 14.3701 | 14.7553
2702 | 2.045 | 0.80622 | 0.97957 | 0.78994 | 3.3889 | 7.6842 | 4.6077 | 5.9302 | 5.5459 | 1.4087 | 18.412 | 14.9512 | 18.412
2703 | -0.86138 | 0.62521 | 0.19452 | 0.73408 | 3.1226 | 4.2907 | 5.1786 | 5.7744 | 4.2926 | 2.0054 | 15.1931 | 14.5992 | 15.1931
2704 | 1.3341 | 0.79196 | 0.90892 | 0.78581 | 5.0257 | 6.9288 | 7.4752 | 5.9179 | 3.975 | 2.486 | 20.3584 | 18.9619 | 20.3584
2705 | -0.13548 | -0.74985 | 0.44612 | 0.22667 | 2.8834 | 5.0894 | 6.4719 | 4.7287 | 4.3338 | 2.3714 | 15.073 | 16.0606 | 16.0606
2706 | -0.64437 | 0.86882 | 0.25967 | 0.80753 | 5.73 | 4.511 | 4.5029 | 5.9842 | 3.7501 | 1.7965 | 18.0217 | 15.7795 | 18.0217
2707 | 0.75166 | 0.62782 | 0.77387 | 0.73494 | 3.9149 | 6.2106 | 4.6689 | 5.7766 | 4.8084 | 1.7755 | 17.6775 | 15.1677 | 17.6775
2708 | -0.22817 | -0.7326 | 0.40976 | 0.2319 | 4.0006 | 4.9786 | 6.0463 | 4.7392 | 4.5408 | 1.9486 | 15.6669 | 16.5363 | 16.5363
2709 | 0.58923 | -0.098895 | 0.72215 | 0.46061 | 4.1043 | 6.0027 | 6.139 | 5.1783 | 4.7685 | 2.094 | 17.3793 | 17.1058 | 17.3793
2710 | 1.5473 | 1.0667 | 0.9391 | 0.85695 | 3.1811 | 7.1727 | 6.1153 | 6.1541 | 3.8744 | 1.9384 | 18.4463 | 15.1093 | 18.4463
2711 | 1.0576 | -0.28255 | 0.85487 | 0.38876 | 4.5404 | 6.5952 | 5.5633 | 5.0409 | 4.4559 | 2.0829 | 18.2595 | 16.6425 | 18.2595
2712 | -0.20421 | -0.42493 | 0.41909 | 0.33544 | 3.8507 | 5.007 | 6.6762 | 4.9398 | 4.1624 | 1.6149 | 15.4123 | 16.3042 | 16.3042
2713 | 2.5437 | 1.5435 | 0.99452 | 0.93864 | 5.1114 | 8.1018 | 4.555 | 6.5496 | 4.8793 | 1.2442 | 21.0071 | 15.7899 | 21.0071
2714 | -0.75859 | -0.048356 | 0.22405 | 0.48072 | 4.8723 | 4.3928 | 5.1974 | 5.2174 | 4.4259 | 1.4841 | 15.9666 | 15.9797 | 15.9797
2715 | 0.72772 | 0.15155 | 0.76661 | 0.56023 | 5.6975 | 6.18 | 5.5278 | 5.3765 | 4.6925 | 2.3966 | 19.6506 | 18.3144 | 19.6506
2716 | 1.0744 | 0.75479 | 0.85869 | 0.77481 | 3.9274 | 6.6161 | 6.4343 | 5.8859 | 3.7983 | 1.5857 | 18.0151 | 15.7457 | 18.0151
2717 | 1.7991 | 2.0672 | 0.964 | 0.98064 | 4.9123 | 7.4425 | 3.5289 | 6.941 | 4.9005 | 2.8338 | 22.1296 | 16.1753 | 22.1296
2718 | -0.37285 | 0.24064 | 0.35463 | 0.59508 | 5.3835 | 4.81 | 4.5966 | 5.4494 | 4.3155 | 2.034 | 17.677 | 16.3296 | 17.677
2719 | 1.4643 | 1.5686 | 0.92844 | 0.94163 | 4.4959 | 7.0792 | 6.0983 | 6.5696 | 4.2224 | 2.3899 | 20.5347 | 17.2066 | 20.5347
2720 | -1.603 | -0.79045 | 0.054464 | 0.21463 | 3.2422 | 3.6842 | 6.107 | 4.7044 | 3.6585 | 1.8017 | 13.4324 | 14.8093 | 14.8093
2721 | -1.0678 | 0.053265 | 0.1428 | 0.52124 | 2.3384 | 4.0984 | 6.0823 | 5.2974 | 4.3334 | 1.5061 | 13.2403 | 14.2602 | 14.2602
2722 | 0.90171 | 0.044779 | 0.81639 | 0.51786 | 3.455 | 6.4008 | 5.0199 | 5.2907 | 3.4691 | 1.6454 | 16.7918 | 13.5894 | 16.7918
2723 | -0.97897 | -0.31157 | 0.1638 | 0.37768 | 3.6891 | 4.179 | 5.9119 | 5.0199 | 4.1225 | 1.5146 | 14.4026 | 15.2381 | 15.2381
2724 | 0.61814 | -0.44706 | 0.73176 | 0.32741 | 3.8381 | 6.0398 | 4.842 | 4.9245 | 3.4381 | 2.1697 | 16.972 | 14.2879 | 16.972
2725 | 0.25871 | -0.3412 | 0.60207 | 0.36648 | 3.499 | 5.5795 | 5.9189 | 4.9987 | 3.1018 | 1.5426 | 15.6198 | 14.0623 | 15.6198
2726 | 0.047634 | -0.70565 | 0.519 | 0.2402 | 4.3341 | 5.3139 | 5.5855 | 4.7557 | 3.754 | 1.5299 | 15.9335 | 15.2034 | 15.9335
2727 | -0.96048 | -1.223 | 0.16841 | 0.11066 | 4.6096 | 4.1962 | 7.0157 | 4.4756 | 4.4863 | 1.79 | 15.0715 | 17.9017 | 17.9017
2728 | -0.12289 | -0.44777 | 0.4511 | 0.32716 | 3.7425 | 5.1046 | 6.8414 | 4.924 | 5.263 | 2.0698 | 15.8409 | 17.9167 | 17.9167
2729 | 0.92602 | 0.43979 | 0.82278 | 0.66996 | 4.0417 | 6.4314 | 7.0561 | 5.6161 | 3.6179 | 1.7037 | 17.7929 | 16.4195 | 17.7929
2730 | -0.35722 | 0.5039 | 0.36047 | 0.69283 | 3.2349 | 4.8279 | 5.543 | 5.6705 | 4.3028 | 1.7718 | 15.5051 | 14.8525 | 15.5051
2731 | -0.79702 | -0.61892 | 0.21272 | 0.26799 | 3.8987 | 4.3541 | 6.191 | 4.8103 | 5.3817 | 2.2895 | 15.3526 | 17.7609 | 17.7609
2732 | 0.040292 | -0.030115 | 0.51607 | 0.48799 | 5.0785 | 5.3048 | 5.1948 | 5.2316 | 4.4294 | 2.2144 | 17.8293 | 16.9172 | 17.8293
2733 | -0.41889 | -0.49569 | 0.33765 | 0.31006 | 4.3085 | 4.7576 | 6.213 | 4.8914 | 3.3163 | 2.3965 | 16.3541 | 16.2344 | 16.3541
2734 | 0.93893 | 1.6033 | 0.82612 | 0.94557 | 3.0046 | 6.4476 | 6.1569 | 6.5971 | 4.6852 | 2.3959 | 18.4451 | 16.2425 | 18.4451
2735 | -0.74489 | -1.8906 | 0.22817 | 0.029341 | 3.1765 | 4.4067 | 5.854 | 4.2297 | 4.5218 | 1.7508 | 13.5637 | 15.303 | 15.303
2736 | 0.86493 | -0.93709 | 0.80646 | 0.17436 | 5.6435 | 6.3544 | 6.0072 | 4.6206 | 5.1306 | 2.2071 | 18.8256 | 18.9883 | 18.9883
2737 | 0.83977 | 0.97722 | 0.79948 | 0.83577 | 4.4058 | 6.3226 | 7.4801 | 6.0775 | 4.2092 | 2.0877 | 18.8935 | 18.1828 | 18.8935
2738 | -1.6608 | -2.6066 | 0.048381 | 0.0045718 | 4.0826 | 3.6469 | 4.4945 | 4.0874 | 4.5849 | 2.1354 | 13.9522 | 15.2973 | 15.2973
2739 | -0.97234 | -0.41386 | 0.16544 | 0.33949 | 4.5788 | 4.1852 | 6.1917 | 4.9474 | 4.2026 | 2.464 | 16.1755 | 17.4371 | 17.4371
2740 | 1.4791 | 1.6791 | 0.93044 | 0.95343 | 4.6326 | 7.096 | 6.0637 | 6.6562 | 4.8554 | 2.1463 | 20.5311 | 17.6979 | 20.5311
2741 | -0.038381 | 1.2551 | 0.48469 | 0.89528 | 2.6824 | 5.2076 | 5.0765 | 6.3135 | 4.3711 | 1.3528 | 15.5564 | 13.4829 | 15.5564
2742 | -0.64086 | -0.36551 | 0.26081 | 0.35737 | 4.0798 | 4.5147 | 5.3587 | 4.9814 | 4.0117 | 1.467 | 15.0429 | 14.9172 | 15.0429
2743 | 2.3945 | 1.6815 | 0.99168 | 0.95366 | 4.2162 | 7.9874 | 6.0637 | 6.6581 | 3.6471 | 2.5939 | 21.4555 | 16.5209 | 21.4555
2744 | -0.72841 | -0.95124 | 0.23318 | 0.17074 | 3.2681 | 4.4236 | 6.4297 | 4.6129 | 4.5788 | 1.5851 | 13.8896 | 15.8617 | 15.8617
2745 | -1.8804 | -0.13453 | 0.030024 | 0.44649 | 2.6715 | 3.5177 | 6.8039 | 5.1511 | 4.0525 | 2.0515 | 13.3919 | 15.5795 | 15.5795
2746 | -0.52989 | -0.86267 | 0.29809 | 0.19416 | 2.6845 | 4.6341 | 7.1547 | 4.6623 | 4.8203 | 1.7837 | 13.7646 | 16.4431 | 16.4431
2747 | 0.19428 | -0.10644 | 0.57702 | 0.45761 | 4.0082 | 5.4978 | 3.9495 | 5.1726 | 4.7157 | 2.4559 | 17.1345 | 15.1293 | 17.1345
2748 | -0.97484 | -1.0249 | 0.16482 | 0.1527 | 4.6587 | 4.1829 | 4.3832 | 4.5735 | 3.8101 | 1.4727 | 14.8877 | 14.3247 | 14.8877
2749 | 0.32686 | -0.65778 | 0.62811 | 0.25534 | 5.064 | 5.6663 | 4.3693 | 4.7856 | 3.9592 | 1.6931 | 17.209 | 15.0856 | 17.209
2750 | -1.3848 | -0.1484 | 0.083057 | 0.44101 | 2.4192 | 3.8381 | 5.401 | 5.1406 | 4.1326 | 2.5285 | 13.9264 | 14.4813 | 14.4813
2751 | -0.47597 | -0.32246 | 0.31705 | 0.37355 | 2.9926 | 4.6936 | 4.4936 | 5.0121 | 3.4873 | 2.506 | 15.2043 | 13.4795 | 15.2043
2752 | 0.4679 | -0.16272 | 0.68007 | 0.43537 | 3.6899 | 5.8469 | 5.8807 | 5.1298 | 3.5766 | 1.6823 | 16.3489 | 14.8295 | 16.3489
2753 | -1.7164 | -1.0127 | 0.04304 | 0.1556 | 4.8975 | 3.6122 | 7.1926 | 4.5799 | 5.5555 | 2.4776 | 15.5672 | 20.1232 | 20.1232
2754 | -1.7837 | -1.1099 | 0.037239 | 0.13353 | 2.8359 | 3.5721 | 5.481 | 4.5301 | 3.6667 | 1.2938 | 12.2319 | 13.2775 | 13.2775
2755 | 0.21812 | 0.45576 | 0.58633 | 0.67572 | 5.0098 | 5.528 | 5.2839 | 5.6296 | 3.7184 | 2.1482 | 18.3157 | 16.1604 | 18.3157
2756 | 0.11992 | -0.0027014 | 0.54772 | 0.49892 | 4.3319 | 5.4042 | 4.1382 | 5.2531 | 4.2421 | 1.6754 | 16.6646 | 14.3876 | 16.6646
2757 | -0.57094 | -0.55204 | 0.28402 | 0.29046 | 3.4893 | 4.5894 | 6.2531 | 4.8538 | 4.527 | 1.5438 | 14.4763 | 15.8132 | 15.8132
2758 | 1.6766 | 0.76803 | 0.95319 | 0.77877 | 4.7947 | 7.3139 | 6.1178 | 5.8973 | 3.7106 | 2.3067 | 20.3126 | 16.9298 | 20.3126
2759 | 0.7363 | 0.58963 | 0.76923 | 0.72228 | 4.4682 | 6.191 | 6.7138 | 5.7438 | 4.0235 | 1.3016 | 17.7046 | 16.5071 | 17.7046
2760 | 0.44765 | 2.561 | 0.6728 | 0.99478 | 4.865 | 5.821 | 4.7138 | 7.2513 | 4.2113 | 2.4523 | 20.3895 | 16.2423 | 20.3895
2761 | 0.91898 | 0.095275 | 0.82095 | 0.53795 | 4.9795 | 6.4225 | 6.3588 | 5.331 | 5.386 | 2.0099 | 18.7429 | 18.7342 | 18.7429
2762 | -0.27436 | 1.2411 | 0.39191 | 0.89272 | 3.4234 | 4.9241 | 4.8241 | 6.3017 | 3.8365 | 2.3463 | 16.9956 | 14.4304 | 16.9956
2763 | -1.3841 | -0.45651 | 0.083157 | 0.32401 | 2.7121 | 3.8386 | 3.8881 | 4.918 | 4.3127 | 1.8429 | 13.3116 | 12.7557 | 13.3116
2764 | -1.0428 | -1.8964 | 0.14851 | 0.028957 | 3.49 | 4.1207 | 5.7676 | 4.2281 | 4.7373 | 2.3147 | 14.1536 | 16.3096 | 16.3096
2765 | 0.73571 | 1.404 | 0.76905 | 0.91983 | 4.6548 | 6.1902 | 5.5962 | 6.4368 | 4.3441 | 2.6039 | 19.8857 | 17.1989 | 19.8857
2766 | -1.1437 | -1.5799 | 0.12638 | 0.057064 | 5.7038 | 4.0322 | 6.2473 | 4.3286 | 3.9034 | 2.2019 | 16.2665 | 18.0564 | 18.0564
2767 | -0.44839 | -0.67517 | 0.32694 | 0.24979 | 4.0897 | 4.7244 | 3.2486 | 4.7746 | 4.0313 | 1.9584 | 15.5471 | 13.328 | 15.5471
2768 | -2.2574 | -0.060177 | 0.011992 | 0.47601 | 4.1488 | 3.3409 | 6.8238 | 5.2082 | 3.9874 | 2.0842 | 14.7821 | 17.0442 | 17.0442
2769 | -0.30741 | -1.0997 | 0.37927 | 0.13574 | 4.0046 | 4.8855 | 4.9916 | 4.5352 | 5.1461 | 2.1309 | 15.5562 | 16.2732 | 16.2732
2770 | -0.16508 | 0.23607 | 0.43444 | 0.59331 | 4.1302 | 5.0538 | 6.2686 | 5.4457 | 3.123 | 1.9854 | 16.6151 | 15.5072 | 16.6151
2771 | -0.66649 | 0.90837 | 0.25255 | 0.81816 | 3.1203 | 4.4877 | 6.6591 | 6.0183 | 5.2846 | 1.6773 | 15.3036 | 16.7412 | 16.7412
2772 | 0.50369 | 0.85273 | 0.69276 | 0.8031 | 4.6924 | 5.8929 | 4.7948 | 5.9703 | 3.7639 | 2.0105 | 18.5661 | 15.2616 | 18.5661
2773 | 0.77988 | 0.40867 | 0.78227 | 0.65861 | 3.025 | 6.2465 | 6.5053 | 5.5898 | 3.2609 | 2.034 | 16.8953 | 14.8252 | 16.8953
2774 | -0.27217 | -1.8741 | 0.39275 | 0.030458 | 3.3875 | 4.9267 | 3.0962 | 4.2343 | 4.1694 | 1.8734 | 14.4219 | 12.5265 | 14.4219
2775 | -0.4792 | -0.82326 | 0.3159 | 0.20518 | 3.8508 | 4.69 | 6.5842 | 4.6851 | 5.1799 | 2.2904 | 15.5163 | 17.9053 | 17.9053
2776 | 0.12625 | -0.5863 | 0.55023 | 0.27884 | 3.1877 | 5.4121 | 6.9533 | 4.8313 | 3.1326 | 2.5429 | 15.974 | 15.8164 | 15.974
2777 | -0.82538 | -0.012475 | 0.20458 | 0.49502 | 4.5752 | 4.326 | 6.6504 | 5.2454 | 3.0502 | 1.9769 | 16.1236 | 16.2528 | 16.2528
2778 | 0.32721 | -0.75052 | 0.62824 | 0.22647 | 3.3303 | 5.6668 | 4.1288 | 4.7283 | 4.6393 | 1.8735 | 15.5988 | 13.9718 | 15.5988
2779 | 1.7387 | 1.11 | 0.95896 | 0.8665 | 3.4756 | 7.3798 | 7.0524 | 6.1909 | 4.4312 | 2.4589 | 19.5052 | 17.4181 | 19.5052
2780 | -0.061119 | -0.93987 | 0.47563 | 0.17364 | 2.903 | 5.1798 | 4.5924 | 4.6191 | 3.8383 | 2.1653 | 14.8672 | 13.499 | 14.8672
2781 | 0.72621 | 0.67757 | 0.76614 | 0.75098 | 3.9639 | 6.1781 | 4.8983 | 5.8194 | 4.8763 | 2.06 | 18.0214 | 15.7985 | 18.0214
2782 | 0.52222 | 0.91287 | 0.69924 | 0.81935 | 3.4635 | 5.9167 | 5.5923 | 6.0222 | 4.8768 | 1.9644 | 17.3668 | 15.897 | 17.3668
2783 | -0.4879 | -1.5094 | 0.31281 | 0.065602 | 5.1192 | 4.6804 | 5.7782 | 4.3547 | 3.9732 | 2.1973 | 16.3516 | 17.0679 | 17.0679
2784 | 1.6413 | 1.0643 | 0.94964 | 0.85641 | 4.103 | 7.2759 | 6.5651 | 6.152 | 3.6951 | 1.8468 | 19.3778 | 16.21 | 19.3778
2785 | 0.12777 | 0.5774 | 0.55084 | 0.71816 | 3.7414 | 5.414 | 2.8904 | 5.7333 | 5.0268 | 2.2016 | 17.0903 | 13.8601 | 17.0903
2786 | 1.759 | 2.2748 | 0.96071 | 0.98854 | 4.5545 | 7.401 | 3.9212 | 7.0791 | 5.9494 | 1.7531 | 20.7876 | 16.1782 | 20.7876
2787 | 0.36645 | 1.1408 | 0.64299 | 0.87303 | 3.5704 | 5.7169 | 4.4312 | 6.2171 | 3.817 | 2.2164 | 17.7209 | 14.035 | 17.7209
2788 | 0.85831 | 1.1948 | 0.80464 | 0.88391 | 4.3948 | 6.346 | 4.7256 | 6.2628 | 4.1332 | 1.6682 | 18.6718 | 14.9218 | 18.6718
2789 | 0.20957 | 0.38874 | 0.583 | 0.65126 | 3.0293 | 5.5172 | 6.6101 | 5.573 | 4.7447 | 1.8368 | 15.9562 | 16.2209 | 16.2209
2790 | 0.06296 | -1.1525 | 0.5251 | 0.12457 | 3.9503 | 5.333 | 5.8908 | 4.5091 | 4.7919 | 2.1699 | 15.9622 | 16.8028 | 16.8028
2791 | -0.84179 | -0.5713 | 0.19995 | 0.2839 | 4.3578 | 4.3098 | 5.8418 | 4.8411 | 4.4442 | 1.9218 | 15.4305 | 16.5655 | 16.5655
2792 | 0.83175 | 1.5144 | 0.79723 | 0.93504 | 3.4478 | 6.3124 | 6.5797 | 6.5263 | 4 | 1.9452 | 18.2318 | 15.9727 | 18.2318
2793 | -1.5952 | -1.0041 | 0.055331 | 0.15767 | 4.7155 | 3.6893 | 5.7373 | 4.5844 | 4.3737 | 2.0666 | 15.0559 | 16.8932 | 16.8932
2794 | 0.90885 | 0.5288 | 0.81829 | 0.70153 | 3.3686 | 6.4098 | 6.337 | 5.6918 | 3.9048 | 1.6346 | 17.1048 | 15.245 | 17.1048
2795 | -0.26717 | 1.1671 | 0.39467 | 0.87842 | 4.0419 | 4.9326 | 7.1243 | 6.2394 | 3.9379 | 1.8043 | 17.0182 | 16.9085 | 17.0182
2796 | 1.9958 | 1.3638 | 0.97702 | 0.91368 | 4.2151 | 7.6377 | 7.0036 | 6.4038 | 3.6008 | 2.2806 | 20.5372 | 17.1001 | 20.5372
2797 | 3.1269 | 1.6974 | 0.99912 | 0.95519 | 3.7291 | 8.4644 | 6.0223 | 6.6703 | 5.149 | 1.8544 | 20.7183 | 16.7548 | 20.7183
2798 | 1.2862 | 0.4688 | 0.90081 | 0.68039 | 4.5095 | 6.8723 | 5.4449 | 5.6407 | 3.2227 | 2.0354 | 19.0578 | 15.2125 | 19.0578
2799 | -0.89764 | -0.30891 | 0.18469 | 0.3787 | 2.7638 | 4.2557 | 7.1568 | 5.0218 | 4.7405 | 1.6942 | 13.7355 | 16.3553 | 16.3553
2800 | -0.71911 | 0.27317 | 0.23604 | 0.60764 | 3.8053 | 4.4331 | 3.4999 | 5.4764 | 3.5123 | 1.6817 | 15.3964 | 12.4992 | 15.3964
2801 | 0.55023 | 1.0976 | 0.70892 | 0.8638 | 5.0253 | 5.9526 | 6.8403 | 6.1804 | 4.2368 | 2.169 | 19.3273 | 18.2713 | 19.3273
2802 | -0.9053 | -0.21658 | 0.18265 | 0.41427 | 3.1148 | 4.2483 | 4.5284 | 5.0894 | 5.9815 | 2.8148 | 15.2674 | 16.4395 | 16.4395
2803 | -0.8661 | 0.26598 | 0.19322 | 0.60487 | 3.6873 | 4.2861 | 6.7586 | 5.4704 | 4.8884 | 1.7795 | 15.2233 | 17.1139 | 17.1139
2804 | -0.65305 | -0.99582 | 0.25686 | 0.15967 | 4.2959 | 4.5018 | 5.9989 | 4.5888 | 5.1002 | 1.5798 | 14.9663 | 16.9748 | 16.9748
2805 | 0.54576 | 1.5651 | 0.70738 | 0.94122 | 3.4814 | 5.9469 | 7.5927 | 6.5668 | 4.1571 | 1.6227 | 17.6178 | 16.8538 | 17.6178
2806 | 0.30847 | -0.08778 | 0.62114 | 0.46503 | 4.3185 | 5.6429 | 4.7436 | 5.1869 | 4.9469 | 2.399 | 17.5473 | 16.408 | 17.5473
2807 | -0.19153 | 0.51976 | 0.42405 | 0.69838 | 3.4146 | 5.0221 | 6.035 | 5.6841 | 4.546 | 1.795 | 15.9158 | 15.7905 | 15.9158
2808 | 0.53097 | 0.88078 | 0.70228 | 0.81078 | 3.6557 | 5.9279 | 6.2296 | 5.9945 | 3.465 | 1.6004 | 17.1786 | 14.9507 | 17.1786
2809 | -0.14145 | -0.059616 | 0.44376 | 0.47623 | 2.9061 | 5.0822 | 6.3041 | 5.2087 | 3.5911 | 1.9803 | 15.1772 | 14.7816 | 15.1772
2810 | -0.0019637 | -0.97713 | 0.49922 | 0.16425 | 3.7602 | 5.2525 | 7.4031 | 4.5988 | 5.2779 | 2.0811 | 15.6926 | 18.5223 | 18.5223
2811 | 0.156 | 1.3145 | 0.56198 | 0.90566 | 3.7951 | 5.4495 | 6.3098 | 6.363 | 3.8226 | 1.7143 | 17.3219 | 15.6418 | 17.3219
2812 | -0.83496 | -0.40836 | 0.20187 | 0.3415 | 2.7647 | 4.3166 | 7.5676 | 4.9513 | 4.5258 | 2.099 | 14.1315 | 16.9571 | 16.9571
2813 | -0.49206 | -1.0799 | 0.31134 | 0.1401 | 2.8296 | 4.6757 | 5.4308 | 4.5451 | 3.4102 | 2.2937 | 14.3441 | 13.9642 | 14.3441
2814 | -1.5806 | 0.045565 | 0.056981 | 0.51817 | 4.2655 | 3.699 | 3.746 | 5.2913 | 3.1544 | 2.2654 | 15.5212 | 13.4312 | 15.5212
2815 | -0.88324 | 0.61275 | 0.18855 | 0.72998 | 4.5425 | 4.2695 | 5.8782 | 5.7637 | 3.2382 | 2.7635 | 17.3392 | 16.4223 | 17.3392
2816 | 0.15605 | -0.58993 | 0.562 | 0.27762 | 3.7422 | 5.4496 | 6.5607 | 4.829 | 3.0718 | 1.5589 | 15.5797 | 14.9337 | 15.5797
2817 | -0.98319 | -0.51813 | 0.16276 | 0.30218 | 4.0391 | 4.1751 | 3.8011 | 4.8763 | 5.4821 | 2.4755 | 15.566 | 15.7979 | 15.7979
2818 | 0.3782 | -2.1436 | 0.64736 | 0.016031 | 4.3099 | 5.732 | 7.6436 | 4.1671 | 3.2603 | 1.8657 | 16.0746 | 17.0795 | 17.0795
2819 | 2.4322 | 0.76883 | 0.9925 | 0.779 | 4.5365 | 8.0171 | 5.8569 | 5.898 | 4.2524 | 1.991 | 20.4427 | 16.6369 | 20.4427
2820 | -1.648 | -1.0583 | 0.049676 | 0.14496 | 3.7433 | 3.655 | 5.5165 | 4.5562 | 4.5271 | 2.2607 | 14.2151 | 16.0476 | 16.0476
2821 | -0.091027 | -0.0061452 | 0.46374 | 0.49755 | 5.1001 | 5.1433 | 4.553 | 5.2504 | 5.2736 | 2.664 | 18.1577 | 17.5907 | 18.1577
2822 | -0.98444 | -0.12166 | 0.16245 | 0.45158 | 3.8033 | 4.174 | 6.78 | 5.1609 | 3.7252 | 1.5798 | 14.718 | 15.8882 | 15.8882
2823 | 0.59166 | 0.58226 | 0.72296 | 0.7198 | 4.0576 | 6.0058 | 6.449 | 5.7375 | 4.4977 | 1.5803 | 17.3812 | 16.5846 | 17.3812
2824 | 0.37309 | -1.2629 | 0.64546 | 0.10331 | 5.0445 | 5.7254 | 5.8016 | 4.4573 | 6.151 | 1.9352 | 17.1625 | 18.9324 | 18.9324
2825 | 1.1656 | -0.15862 | 0.87811 | 0.43698 | 3.1268 | 6.7275 | 5.0275 | 5.1329 | 4.9352 | 2.3118 | 17.2989 | 15.4013 | 17.2989
2826 | -0.015382 | 1.5262 | 0.49386 | 0.93652 | 5.3283 | 5.2359 | 4.7469 | 6.5358 | 4.5131 | 1.8982 | 18.9983 | 16.4865 | 18.9983
2827 | -0.37019 | 0.45198 | 0.35562 | 0.67436 | 3.6848 | 4.8131 | 4.5327 | 5.6264 | 3.709 | 2.107 | 16.2313 | 14.0335 | 16.2313
2828 | -0.43584 | -0.39423 | 0.33148 | 0.3467 | 4.6838 | 4.7385 | 5.101 | 4.9611 | 3.9242 | 1.3196 | 15.7031 | 15.0286 | 15.7031
2829 | 1.478 | 0.83854 | 0.93029 | 0.79914 | 5.0469 | 7.0948 | 4.4648 | 5.9581 | 4.0508 | 2.2134 | 20.3132 | 15.7759 | 20.3132
2830 | 0.29888 | 0.32363 | 0.61748 | 0.62689 | 3.61 | 5.6306 | 5.7593 | 5.5184 | 3.907 | 1.9319 | 16.6909 | 15.2083 | 16.6909
2831 | 0.33803 | 0.65568 | 0.63233 | 0.74398 | 4.954 | 5.6806 | 6.5935 | 5.8005 | 4.8984 | 2.6599 | 19.0951 | 19.1058 | 19.1058
2832 | 0.18543 | 1.2522 | 0.57355 | 0.89476 | 2.2377 | 5.4866 | 4.2025 | 6.3111 | 5.1951 | 1.6846 | 15.7199 | 13.3199 | 15.7199
2833 | -0.64698 | -1.0638 | 0.25882 | 0.14372 | 4.1915 | 4.5082 | 7.355 | 4.5534 | 3.9108 | 2.3209 | 15.574 | 17.7782 | 17.7782
2834 | -0.42226 | 0.093413 | 0.33642 | 0.53721 | 3.4376 | 4.7538 | 5.1673 | 5.3295 | 4.395 | 2.3129 | 15.8339 | 15.3129 | 15.8339
2835 | 1.8569 | 2.6282 | 0.96834 | 0.99571 | 3.0394 | 7.5014 | 7.3702 | 7.2885 | 4.067 | 2.203 | 20.0324 | 16.6797 | 20.0324
2836 | -0.26069 | 0.23144 | 0.39716 | 0.59151 | 3.6677 | 4.9402 | 5.8269 | 5.4419 | 4.0676 | 1.5368 | 15.5865 | 15.0991 | 15.5865
2837 | -0.80275 | -0.087912 | 0.21106 | 0.46497 | 5.1073 | 4.3484 | 4.0325 | 5.1868 | 4.4835 | 1.736 | 16.3784 | 15.3592 | 16.3784
2838 | -1.1545 | -0.8129 | 0.12415 | 0.20814 | 3.1391 | 4.023 | 5.3702 | 4.6912 | 3.983 | 2.0735 | 13.9268 | 14.5658 | 14.5658
2839 | 0.44152 | 0.33972 | 0.67058 | 0.63297 | 4.666 | 5.8131 | 7.712 | 5.5318 | 3.9275 | 1.8764 | 17.8872 | 18.1818 | 18.1818
2840 | 0.23393 | -1.0017 | 0.59248 | 0.15824 | 4.6144 | 5.548 | 6.1331 | 4.5857 | 5.2421 | 1.6861 | 16.4343 | 17.6757 | 17.6757
2841 | 1.5631 | 0.32628 | 0.94099 | 0.62789 | 3.7258 | 7.1903 | 6.6454 | 5.5206 | 3.9082 | 2.5544 | 18.9911 | 16.8339 | 18.9911
2842 | 0.22514 | -0.22716 | 0.58906 | 0.41015 | 2.5994 | 5.5369 | 5.0125 | 5.0816 | 3.4345 | 1.208 | 14.4259 | 12.2545 | 14.4259
2843 | -0.87908 | -0.85817 | 0.18968 | 0.1954 | 5.3277 | 4.2735 | 6.7141 | 4.6649 | 3.4909 | 1.441 | 15.7072 | 16.9737 | 16.9737
2844 | 1.2036 | 0.54488 | 0.88563 | 0.70708 | 3.0908 | 6.7735 | 6.8964 | 5.7055 | 3.6853 | 1.9057 | 17.4755 | 15.5781 | 17.4755
2845 | -0.066319 | -1.1109 | 0.47356 | 0.1333 | 3.3581 | 5.1734 | 5.2291 | 4.5295 | 5.3165 | 2.1877 | 15.2488 | 16.0915 | 16.0915
2846 | 1.6818 | -0.76125 | 0.9537 | 0.22325 | 3.5519 | 7.3195 | 5.8394 | 4.7218 | 5.6551 | 2.0647 | 17.6579 | 17.1111 | 17.6579
2847 | -0.56873 | -1.0933 | 0.28477 | 0.13713 | 2.4315 | 4.5918 | 6.1573 | 4.5384 | 3.4004 | 2.8238 | 14.3855 | 14.8129 | 14.8129
2848 | -0.55204 | 1.102 | 0.29046 | 0.86476 | 3.748 | 4.6099 | 7.4521 | 6.1841 | 3.3593 | 1.9154 | 16.4574 | 16.4748 | 16.4748
2849 | -1.1243 | -1.0493 | 0.13045 | 0.14703 | 4.1623 | 4.0489 | 5.9637 | 4.5608 | 4.1452 | 1.8412 | 14.6133 | 16.1125 | 16.1125
2850 | -0.76295 | 0.26228 | 0.22275 | 0.60345 | 5.4756 | 4.3884 | 5.6638 | 5.4673 | 4.6171 | 2.1619 | 17.4932 | 17.9184 | 17.9184
2851 | -0.92774 | -2.0515 | 0.17677 | 0.020108 | 3.7929 | 4.227 | 4.1737 | 4.1881 | 4.6221 | 2.7488 | 14.9569 | 15.3375 | 15.3375
2852 | -2.0676 | -1.5766 | 0.019341 | 0.057442 | 3.8586 | 3.4232 | 6.1275 | 4.3298 | 6.617 | 2.4159 | 14.0274 | 19.0191 | 19.0191
2853 | -0.23167 | -0.41719 | 0.4084 | 0.33827 | 4.4295 | 4.9744 | 6.4694 | 4.9451 | 3.5775 | 2.5354 | 16.8845 | 17.0119 | 17.0119
2854 | 0.57697 | -0.12416 | 0.71802 | 0.45059 | 3.8516 | 5.987 | 4.0164 | 5.159 | 3.7826 | 2.1619 | 17.1595 | 13.8126 | 17.1595
2855 | 0.77631 | -0.49774 | 0.78122 | 0.30933 | 3.782 | 6.242 | 4.1232 | 4.89 | 4.8474 | 2.319 | 17.2329 | 15.0715 | 17.2329
2856 | -0.46174 | -1.0979 | 0.32213 | 0.13611 | 4.3729 | 4.7095 | 5.0052 | 4.536 | 4.3109 | 2.4278 | 16.0461 | 16.1167 | 16.1167
2857 | 0.098405 | 0.49334 | 0.53919 | 0.68911 | 4.0358 | 5.3772 | 4.351 | 5.6616 | 3.8717 | 1.6441 | 16.7187 | 13.9025 | 16.7187
2858 | 0.80388 | 0.9677 | 0.78927 | 0.8334 | 4.5421 | 6.277 | 6.4872 | 6.0693 | 3.9383 | 2.5122 | 19.4006 | 17.4799 | 19.4006
2859 | 0.76422 | 0.54909 | 0.77763 | 0.70853 | 3.2857 | 6.2266 | 7.5806 | 5.7091 | 4.8277 | 1.9989 | 17.2203 | 17.693 | 17.693
2860 | 1.5371 | 2.0038 | 0.93786 | 0.97745 | 2.7009 | 7.1613 | 3.4945 | 6.8968 | 5.134 | 1.6008 | 18.3598 | 12.9302 | 18.3598
2861 | -0.36105 | -1.2715 | 0.35903 | 0.10178 | 4.4368 | 4.8235 | 7.3753 | 4.4535 | 5.0951 | 1.7706 | 15.4844 | 18.6778 | 18.6778
2862 | 2.3596 | 1.0075 | 0.99085 | 0.84314 | 4.1882 | 7.9593 | 5.1055 | 6.1034 | 4.7355 | 2.7017 | 20.9526 | 16.7308 | 20.9526
2863 | -0.25178 | 1.5957 | 0.40061 | 0.94473 | 5.3611 | 4.9507 | 6.75 | 6.5911 | 3.1326 | 1.8959 | 18.7988 | 17.1397 | 18.7988
2864 | -2.3041 | -1.5646 | 0.010609 | 0.058841 | 5.5522 | 3.3226 | 5.5537 | 4.3342 | 4.7578 | 1.9354 | 15.1444 | 17.7992 | 17.7992
2865 | 0.31059 | -0.19485 | 0.62194 | 0.42275 | 2.3144 | 5.6456 | 5.9141 | 5.1056 | 3.3069 | 1.4898 | 14.5554 | 13.0252 | 14.5554
2866 | -2.1996 | -1.4611 | 0.013916 | 0.072 | 3.6538 | 3.3645 | 4.6153 | 4.3734 | 3.5589 | 2.2481 | 13.6398 | 14.0761 | 14.0761
2867 | -1.0016 | -0.8177 | 0.15826 | 0.20676 | 4.8034 | 4.1582 | 7.6263 | 4.6883 | 4.61 | 2.0213 | 15.6712 | 19.061 | 19.061
2868 | -0.56765 | -0.0035121 | 0.28514 | 0.4986 | 3.6323 | 4.593 | 6.9288 | 5.2525 | 3.9978 | 1.9481 | 15.4259 | 16.5071 | 16.5071
2869 | 1.1366 | 1.234 | 0.87214 | 0.8914 | 3.3184 | 6.6922 | 6.5166 | 6.2958 | 4.9277 | 2.5541 | 18.8606 | 17.3168 | 18.8606
2870 | -0.88496 | 0.38401 | 0.18809 | 0.64951 | 3.5753 | 4.2679 | 4.87 | 5.569 | 4.1177 | 1.9517 | 15.3639 | 14.5147 | 15.3639
2871 | -1.3798 | -0.2217 | 0.083817 | 0.41227 | 3.2578 | 3.8419 | 7.7068 | 5.0856 | 3.9143 | 1.608 | 13.7933 | 16.4869 | 16.4869
2872 | 1.2063 | -0.10102 | 0.88615 | 0.45977 | 5.0682 | 6.7767 | 6.0408 | 5.1767 | 3.9127 | 2.3238 | 19.3454 | 17.3454 | 19.3454
2873 | -1.1987 | -1.3379 | 0.11532 | 0.090463 | 3.7152 | 3.9857 | 7.6906 | 4.4242 | 4.5358 | 1.4122 | 13.5373 | 17.3538 | 17.3538
2874 | 0.033054 | -0.38338 | 0.51318 | 0.35072 | 3.2399 | 5.2958 | 6.8024 | 4.9688 | 3.1642 | 1.6803 | 15.1848 | 14.8869 | 15.1848
2875 | 0.63694 | -0.45978 | 0.73792 | 0.32284 | 4.5111 | 6.0639 | 6.8955 | 4.9158 | 5.2379 | 2.252 | 17.7427 | 18.8964 | 18.8964
2876 | 0.61298 | 0.99279 | 0.73005 | 0.83959 | 4.7184 | 6.0332 | 6.6321 | 6.0908 | 4.7944 | 2.4483 | 19.2906 | 18.5932 | 19.2906
2877 | 0.16154 | -0.34024 | 0.56417 | 0.36684 | 3.2471 | 5.4565 | 4.1159 | 4.9993 | 3.7086 | 1.5275 | 15.2304 | 12.599 | 15.2304
2878 | -0.1881 | 0.85093 | 0.4254 | 0.8026 | 4.1325 | 5.0262 | 4.6071 | 5.9688 | 4.9634 | 1.7762 | 16.9037 | 15.4791 | 16.9037
2879 | 0.70995 | 0.10013 | 0.76113 | 0.53988 | 3.178 | 6.1573 | 5.1419 | 5.3349 | 4.1042 | 1.7967 | 16.467 | 14.2208 | 16.467
2880 | 0.89875 | 1.4156 | 0.81561 | 0.92156 | 4.6932 | 6.3971 | 2.7095 | 6.4463 | 4.1522 | 1.919 | 19.4555 | 13.4739 | 19.4555
2881 | 0.17474 | 0.9757 | 0.56936 | 0.83539 | 3.9288 | 5.4731 | 5.5361 | 6.0762 | 4.0261 | 2.4202 | 17.8984 | 15.9113 | 17.8984
2882 | 0.4416 | -0.097108 | 0.67061 | 0.46132 | 2.9917 | 5.8132 | 5.9644 | 5.1797 | 4.4971 | 2.72 | 16.7046 | 16.1731 | 16.7046
2883 | 1.3139 | -1.2435 | 0.90556 | 0.10684 | 3.0368 | 6.905 | 2.3438 | 4.4662 | 4.1107 | 1.9353 | 16.3432 | 11.4265 | 16.3432
2884 | 0.94554 | 0.62626 | 0.82781 | 0.73443 | 3.0006 | 6.4558 | 5.7955 | 5.7753 | 4.1251 | 1.6428 | 16.8746 | 14.564 | 16.8746
2885 | 0.46347 | 1.2297 | 0.67849 | 0.8906 | 2.9928 | 5.8413 | 5.7948 | 6.2922 | 4.442 | 1.679 | 16.8052 | 14.9086 | 16.8052
2886 | -0.14373 | 0.029855 | 0.44286 | 0.51191 | 4.0321 | 5.0795 | 6.8252 | 5.2788 | 4.5772 | 2.3129 | 16.7033 | 17.7474 | 17.7474
2887 | 0.94719 | 2.0572 | 0.82823 | 0.98017 | 3.4679 | 6.4579 | 5.7063 | 6.9342 | 5.1742 | 1.2802 | 18.1402 | 15.6286 | 18.1402
2888 | -0.68051 | -0.021481 | 0.24809 | 0.49143 | 3.7342 | 4.4731 | 6.0553 | 5.2384 | 3.8104 | 1.8604 | 15.3061 | 15.4604 | 15.4604
2889 | 0.89237 | 0.42665 | 0.8139 | 0.66518 | 4.9593 | 6.389 | 5.022 | 5.605 | 3.8579 | 2.0206 | 18.9739 | 15.8598 | 18.9739
2890 | 0.26622 | 1.3538 | 0.60496 | 0.91209 | 4.5592 | 5.589 | 5.1953 | 6.3955 | 4.9891 | 1.6254 | 18.1692 | 16.369 | 18.1692
2891 | 1.5266 | 0.33656 | 0.93657 | 0.63178 | 3.8926 | 7.1496 | 5.388 | 5.5292 | 3.5141 | 2.6105 | 19.1818 | 15.4052 | 19.1818
2892 | -0.47538 | -0.50283 | 0.31726 | 0.30754 | 4.1672 | 4.6943 | 7.2986 | 4.8866 | 3.9345 | 1.7349 | 15.4829 | 17.1352 | 17.1352
2893 | 2.0381 | 1.796 | 0.97923 | 0.96376 | 4.5891 | 7.6778 | 6.8232 | 6.7454 | 3.4932 | 2.7101 | 21.7224 | 17.6157 | 21.7224
2894 | 0.14868 | -0.42357 | 0.5591 | 0.33594 | 5.0682 | 5.4403 | 4.056 | 4.9407 | 3.8162 | 2.0172 | 17.4663 | 14.9575 | 17.4663
2895 | -0.57175 | 0.75561 | 0.28375 | 0.77506 | 4.3511 | 4.5885 | 5.95 | 5.8866 | 4.0942 | 1.5098 | 16.3361 | 15.905 | 16.3361
2896 | -0.50685 | -0.61687 | 0.30613 | 0.26866 | 3.6236 | 4.6594 | 4.9525 | 4.8116 | 5.8643 | 2.457 | 15.5515 | 16.8974 | 16.8974
2897 | 0.15498 | 0.65863 | 0.56158 | 0.74493 | 4.5582 | 5.4482 | 6.4652 | 5.8031 | 3.2146 | 2.4873 | 18.2968 | 16.7253 | 18.2968
2898 | -2.0159 | -1.3244 | 0.021905 | 0.092678 | 4.5656 | 3.4479 | 3.9036 | 4.43 | 3.7938 | 1.7437 | 14.1873 | 14.0068 | 14.1873
2899 | 0.83053 | 1.3184 | 0.79688 | 0.90632 | 3.8144 | 6.3108 | 6.0253 | 6.3662 | 4.3787 | 1.7241 | 18.2156 | 15.9425 | 18.2156
2900 | -0.17716 | -0.02103 | 0.42969 | 0.49161 | 3.91 | 5.0393 | 4.978 | 5.2387 | 4.7543 | 1.5791 | 15.7672 | 15.2215 | 15.7672
2901 | -0.0065932 | -0.57611 | 0.49737 | 0.28227 | 4.65 | 5.2467 | 5.7659 | 4.838 | 3.6334 | 2.4428 | 17.1774 | 16.492 | 17.1774
2902 | -0.75181 | -0.67358 | 0.22608 | 0.25029 | 3.7435 | 4.3997 | 7.4755 | 4.7756 | 5.0201 | 1.6063 | 14.5252 | 17.8455 | 17.8455
2903 | 0.24109 | 1.3193 | 0.59526 | 0.90647 | 3.6262 | 5.5571 | 4.78 | 6.367 | 3.7243 | 2.0512 | 17.6015 | 14.1817 | 17.6015
2904 | -0.62889 | -0.35178 | 0.26471 | 0.3625 | 3.4433 | 4.5273 | 5.4986 | 4.9911 | 5.2747 | 1.7605 | 14.7223 | 15.9771 | 15.9771
2905 | 0.34558 | -0.52036 | 0.63517 | 0.30141 | 3.595 | 5.6902 | 5.5412 | 4.8748 | 3.5936 | 1.5173 | 15.6773 | 14.247 | 15.6773
2906 | 0.77985 | -0.31783 | 0.78226 | 0.37531 | 4.6805 | 6.2465 | 4.9472 | 5.0154 | 3.673 | 1.7092 | 17.6516 | 15.0099 | 17.6516
2907 | -1.3086 | -0.78525 | 0.095328 | 0.21615 | 4.7086 | 3.8967 | 7.2592 | 4.7075 | 3.3433 | 2.0289 | 15.3417 | 17.34 | 17.34
2908 | 1.4577 | 0.92 | 0.92753 | 0.82121 | 4.3732 | 7.0717 | 7.5352 | 6.0283 | 4.6954 | 1.786 | 19.2592 | 18.3898 | 19.2592
2909 | -0.12779 | 1.4018 | 0.44916 | 0.91951 | 4.2676 | 5.0987 | 4.3313 | 6.435 | 5.4464 | 1.5313 | 17.3326 | 15.5765 | 17.3326
2910 | -0.69545 | 0.29319 | 0.24339 | 0.61531 | 5.2592 | 4.4575 | 3.3558 | 5.493 | 5.8469 | 2.7012 | 17.911 | 17.1632 | 17.911
2911 | 1.4504 | 1.5729 | 0.92652 | 0.94213 | 3.8251 | 7.0634 | 3.6434 | 6.573 | 5.4016 | 1.8626 | 19.3241 | 14.7327 | 19.3241
2912 | -0.47696 | -0.0281 | 0.31669 | 0.48879 | 3.4004 | 4.6925 | 6.4197 | 5.2332 | 4.2126 | 1.5404 | 14.8665 | 15.573 | 15.573
2913 | -2.0892 | 0.28375 | 0.018343 | 0.6117 | 3.8507 | 3.4131 | 3.7234 | 5.4851 | 3.6971 | 2.4017 | 15.1506 | 13.6729 | 15.1506
2914 | -0.67369 | -0.17746 | 0.25025 | 0.42958 | 4.5041 | 4.4802 | 4.1571 | 5.1187 | 6.709 | 1.3196 | 15.4225 | 16.6898 | 16.6898
2915 | -0.087468 | 0.48527 | 0.46515 | 0.68626 | 3.3227 | 5.1476 | 4.5797 | 5.6547 | 5.4558 | 2.4164 | 16.5414 | 15.7746 | 16.5414
2916 | -0.5061 | -0.49715 | 0.30639 | 0.30954 | 4.2019 | 4.6602 | 4.9836 | 4.8904 | 5.0557 | 2.0672 | 15.8197 | 16.3084 | 16.3084
2917 | 1.671 | 1.9844 | 0.95264 | 0.9764 | 4.4306 | 7.3079 | 3.9304 | 6.8831 | 5.4346 | 2.7218 | 21.3434 | 16.5174 | 21.3434
2918 | 0.64251 | -0.21677 | 0.73973 | 0.41419 | 4.1402 | 6.071 | 6.9927 | 5.0893 | 5.0747 | 2.5288 | 17.8293 | 18.7364 | 18.7364
2919 | -0.0065079 | 0.56687 | 0.4974 | 0.7146 | 3.3127 | 5.2468 | 5.1833 | 5.7243 | 3.6652 | 2.3027 | 16.5866 | 14.4639 | 16.5866
2920 | -0.67099 | -0.16687 | 0.25111 | 0.43374 | 4.5569 | 4.483 | 5.1893 | 5.1266 | 3.0774 | 1.5691 | 15.7356 | 14.3926 | 15.7356
2921 | 0.12503 | 1.2622 | 0.54975 | 0.89655 | 3.9471 | 5.4106 | 4.5316 | 6.3194 | 4.5954 | 2.312 | 17.989 | 15.3861 | 17.989
2922 | -1.3367 | -0.60116 | 0.090658 | 0.27387 | 3.5854 | 3.8748 | 6.0423 | 4.8217 | 5.306 | 1.317 | 13.5989 | 16.2507 | 16.2507
2923 | 2.0075 | 0.97979 | 0.97765 | 0.83641 | 4.262 | 7.6488 | 4.3018 | 6.0797 | 4.3919 | 2.5033 | 20.4937 | 15.459 | 20.4937
2924 | -1.2432 | -1.1942 | 0.10689 | 0.11621 | 4.1702 | 3.9491 | 4.3097 | 4.4891 | 3.4924 | 2.0985 | 14.7069 | 14.0709 | 14.7069
2925 | -1.1933 | -0.16972 | 0.11638 | 0.43262 | 3.8023 | 3.9902 | 3.7859 | 5.1245 | 4.6403 | 2.0918 | 15.0089 | 14.3205 | 15.0089
2926 | 0.70632 | 1.5851 | 0.76 | 0.94353 | 4.2797 | 6.1527 | 5.8723 | 6.5827 | 4.918 | 2.495 | 19.51 | 17.5649 | 19.51
2927 | 0.11984 | 0.99116 | 0.5477 | 0.8392 | 3.8601 | 5.4041 | 4.7961 | 6.0894 | 4.5039 | 1.5419 | 16.8956 | 14.702 | 16.8956
2928 | -0.008207 | 0.079429 | 0.49673 | 0.53165 | 3.6023 | 5.2447 | 4.7914 | 5.3183 | 4.234 | 1.5814 | 15.7467 | 14.209 | 15.7467
2929 | -0.73512 | -0.89744 | 0.23113 | 0.18474 | 3.4328 | 4.4167 | 7.0121 | 4.6426 | 4.8393 | 2.0797 | 14.5719 | 17.364 | 17.364
2930 | -0.89101 | -1.7023 | 0.18646 | 0.044347 | 3.9655 | 4.262 | 6.9986 | 4.2865 | 3.5638 | 2.1175 | 14.6316 | 16.6454 | 16.6454
2931 | -0.51047 | 1.3589 | 0.30486 | 0.91291 | 5.0606 | 4.6554 | 3.3804 | 6.3997 | 4.0396 | 2.086 | 18.2017 | 14.5665 | 18.2017
2932 | 0.046168 | 2.7846 | 0.51841 | 0.99732 | 3.5378 | 5.3121 | 6.2511 | 7.3705 | 5.2303 | 1.6539 | 17.8743 | 16.6731 | 17.8743
2933 | 0.59521 | 1.4121 | 0.72415 | 0.92104 | 3.5451 | 6.0104 | 6.2519 | 6.4434 | 5.1994 | 1.3259 | 17.3248 | 16.3222 | 17.3248
2934 | -0.23168 | -0.55696 | 0.40839 | 0.28878 | 3.4725 | 4.9744 | 4.5561 | 4.8505 | 3.3919 | 2.5597 | 15.8572 | 13.9802 | 15.8572
2935 | -1.7812 | 0.053883 | 0.037438 | 0.52149 | 2.7747 | 3.5736 | 4.1094 | 5.2979 | 4.7706 | 2.0685 | 13.7147 | 13.7232 | 13.7232
2936 | 1.3415 | 0.023763 | 0.91012 | 0.50948 | 4.824 | 6.9374 | 6.4633 | 5.274 | 5.1596 | 1.8516 | 18.8871 | 18.2986 | 18.8871
2937 | -1.8462 | -2.3008 | 0.032431 | 0.010701 | 4.9773 | 3.5365 | 6.1053 | 4.1354 | 4.5078 | 2.0805 | 14.7297 | 17.6709 | 17.6709
2938 | -0.50006 | 0.4035 | 0.30852 | 0.65671 | 4.8524 | 4.6669 | 5.471 | 5.5854 | 3.8278 | 1.9739 | 17.0786 | 16.1252 | 17.0786
2939 | 0.48586 | 1.282 | 0.68647 | 0.90007 | 3.7579 | 5.87 | 6.4395 | 6.3359 | 4.1423 | 1.2843 | 17.2481 | 15.624 | 17.2481
2940 | 0.19142 | -1.1718 | 0.5759 | 0.12063 | 2.7688 | 5.4942 | 6.2338 | 4.4998 | 4.2436 | 1.4043 | 14.1671 | 14.6505 | 14.6505
2941 | -0.05325 | 1.8035 | 0.47877 | 0.96434 | 3.7145 | 5.1894 | 4.2348 | 6.751 | 3.8052 | 2.3407 | 17.9956 | 14.0951 | 17.9956
2942 | 0.70959 | 0.45149 | 0.76102 | 0.67418 | 3.0871 | 6.1569 | 4.4321 | 5.626 | 5.6979 | 1.2516 | 16.1216 | 14.4687 | 16.1216
2943 | 2.294 | 0.4174 | 0.98911 | 0.66181 | 4.9474 | 7.9052 | 5.2729 | 5.5971 | 3.9473 | 1.769 | 20.2187 | 15.9366 | 20.2187
2944 | -0.016775 | -0.80237 | 0.49331 | 0.21117 | 2.7763 | 5.2342 | 5.8412 | 4.6973 | 3.7579 | 2.2319 | 14.9397 | 14.6073 | 14.9397
2945 | -0.40055 | -0.38723 | 0.34438 | 0.34929 | 4.4982 | 4.7784 | 4.5663 | 4.9661 | 3.6559 | 1.7295 | 15.9722 | 14.4499 | 15.9722
2946 | -0.35392 | 0.42004 | 0.3617 | 0.66277 | 4.281 | 4.8317 | 7.4931 | 5.5994 | 4.0021 | 1.9684 | 16.6805 | 17.7447 | 17.7447
2947 | 0.8262 | -1.0005 | 0.79566 | 0.15853 | 3.5829 | 6.3054 | 6.4891 | 4.5863 | 4.6355 | 2.4766 | 16.9513 | 17.1843 | 17.1843
2948 | 2.1134 | 0.42032 | 0.98272 | 0.66287 | 3.0226 | 7.7473 | 5.3322 | 5.5996 | 5.0192 | 2.5051 | 18.8747 | 15.8791 | 18.8747
2949 | -0.50781 | -0.44166 | 0.30579 | 0.32937 | 4.7364 | 4.6583 | 5.5786 | 4.9282 | 4.9045 | 2.0918 | 16.4148 | 17.3114 | 17.3114
2950 | 2.0644 | 1.4556 | 0.98051 | 0.92725 | 3.8207 | 7.7023 | 3.674 | 6.4789 | 3.5515 | 2.6277 | 20.6296 | 13.6739 | 20.6296
2951 | -0.23345 | 0.67797 | 0.40771 | 0.7511 | 3.4715 | 4.9723 | 4.6256 | 5.8197 | 3.6322 | 1.9811 | 16.2446 | 13.7104 | 16.2446
2952 | -0.66772 | 0.31923 | 0.25216 | 0.62522 | 3.2272 | 4.4864 | 6.5568 | 5.5147 | 3.2784 | 1.6459 | 14.8743 | 14.7084 | 14.8743
2953 | 0.43283 | 1.3317 | 0.66743 | 0.90853 | 5.0662 | 5.802 | 4.0066 | 6.3773 | 3.4148 | 2.1092 | 19.3546 | 14.5967 | 19.3546
2954 | 0.85549 | -0.2162 | 0.80386 | 0.41441 | 2.6682 | 6.3425 | 4.2872 | 5.0897 | 4.1375 | 2.5319 | 16.6323 | 13.6249 | 16.6323
2955 | 1.3631 | -0.14413 | 0.91358 | 0.4427 | 4.3079 | 6.9627 | 5.4036 | 5.1438 | 3.3553 | 2.1264 | 18.5408 | 15.1932 | 18.5408
2956 | 0.93838 | 0.28221 | 0.82598 | 0.61111 | 4.1123 | 6.4469 | 4.7382 | 5.4839 | 3.8379 | 2.541 | 18.584 | 15.2294 | 18.584
2957 | -0.30588 | -0.30104 | 0.37985 | 0.38169 | 3.7814 | 4.8873 | 5.1266 | 5.0275 | 4.1735 | 1.8597 | 15.5559 | 14.9412 | 15.5559
2958 | -0.98789 | -2.2207 | 0.1616 | 0.013185 | 2.9804 | 4.1708 | 6.9348 | 4.1509 | 4.4993 | 1.6483 | 12.9504 | 16.0628 | 16.0628
2959 | -0.082005 | -0.35329 | 0.46732 | 0.36193 | 5.0804 | 5.1543 | 7.0443 | 4.99 | 5.4489 | 1.7774 | 17.0022 | 19.3512 | 19.3512
2960 | 1.7442 | 0.85672 | 0.95944 | 0.8042 | 5.2337 | 7.3855 | 5.0444 | 5.9738 | 4.6523 | 2.1065 | 20.6994 | 17.0368 | 20.6994
2961 | -1.0537 | -0.78836 | 0.146 | 0.21524 | 5.1259 | 4.111 | 3.8932 | 4.7056 | 4.0141 | 2.1259 | 16.0684 | 15.1591 | 16.0684
2962 | 0.66375 | 1.5146 | 0.74657 | 0.93507 | 4.8199 | 6.0982 | 5.5721 | 6.5265 | 4.2932 | 2.227 | 19.6717 | 16.9123 | 19.6717
2963 | 0.013262 | -1.4904 | 0.50529 | 0.068058 | 3.235 | 5.2713 | 6.5636 | 4.362 | 3.9122 | 2.3679 | 15.2361 | 16.0787 | 16.0787
2964 | -1.5014 | -1.2385 | 0.066621 | 0.10776 | 4.4319 | 3.7533 | 3.881 | 4.4684 | 5.1043 | 1.8037 | 14.4572 | 15.2208 | 15.2208
2965 | 1.6089 | 1.1901 | 0.94619 | 0.883 | 3.5309 | 7.2407 | 4.7097 | 6.2588 | 5.0553 | 2.1033 | 19.1337 | 15.3992 | 19.1337
2966 | 0.32348 | -0.88262 | 0.62684 | 0.18872 | 3.9588 | 5.662 | 6.4188 | 4.651 | 3.5346 | 2.5606 | 16.8325 | 16.4728 | 16.8325
2967 | 0.34213 | 0.68675 | 0.63388 | 0.75388 | 3.4922 | 5.6858 | 5.8644 | 5.8273 | 3.5958 | 2.6649 | 17.6703 | 15.6173 | 17.6703
2968 | 1.1994 | 1.2398 | 0.88481 | 0.89248 | 4.4121 | 6.7684 | 6.2688 | 6.3006 | 3.8594 | 2.1779 | 19.6591 | 16.7183 | 19.6591
2969 | 0.41682 | -2.2226 | 0.66159 | 0.01312 | 4.346 | 5.7814 | 4.2806 | 4.1505 | 3.9207 | 1.227 | 15.5049 | 13.7743 | 15.5049
2970 | 0.16219 | 0.13715 | 0.56442 | 0.55454 | 4.1686 | 5.4573 | 7.5146 | 5.3648 | 5.7437 | 2.1204 | 17.1111 | 19.5473 | 19.5473
2971 | 0.76468 | 0.20291 | 0.77777 | 0.5804 | 3.3308 | 6.2272 | 7.5491 | 5.4184 | 3.5441 | 2.2765 | 17.2528 | 16.7004 | 17.2528
2972 | -2.9363 | -3.392 | 0.0016609 | 0.00034692 | 2.7133 | 3.1422 | 5.5681 | 4.0237 | 4.1201 | 1.5868 | 11.466 | 13.9882 | 13.9882
2973 | -1.2895 | -1.0368 | 0.09861 | 0.14991 | 3.5385 | 3.9118 | 6.4238 | 4.5673 | 4.1449 | 2.6082 | 14.6257 | 16.7153 | 16.7153
2974 | -1.8875 | 0.0053421 | 0.029543 | 0.50213 | 4.6373 | 3.5139 | 6.8596 | 5.2594 | 4.9007 | 2.2587 | 15.6693 | 18.6563 | 18.6563
2975 | -0.60253 | -1.5018 | 0.27341 | 0.066573 | 3.272 | 4.5554 | 6.9232 | 4.3576 | 4.4078 | 1.9032 | 14.0882 | 16.5062 | 16.5062
2976 | -0.57933 | 0.078586 | 0.28118 | 0.53132 | 3.4099 | 4.5804 | 3.7342 | 5.3176 | 3.5004 | 1.8061 | 15.114 | 12.4505 | 15.114
2977 | 0.075377 | -0.15025 | 0.53004 | 0.44029 | 3.737 | 5.3484 | 4.4816 | 5.1392 | 5.0257 | 2.0147 | 16.2394 | 15.2591 | 16.2394
2978 | -1.5026 | -0.4319 | 0.066472 | 0.33291 | 4.1754 | 3.7525 | 4.1957 | 4.9349 | 4.2004 | 2.0141 | 14.8769 | 14.5857 | 14.8769
2979 | -0.50947 | 1.107 | 0.30521 | 0.86584 | 3.8718 | 4.6565 | 5.8501 | 6.1884 | 4.3686 | 2.422 | 17.1386 | 16.5125 | 17.1386
2980 | -2.2387 | -1.5054 | 0.012588 | 0.066111 | 4.1472 | 3.3484 | 6.4538 | 4.3562 | 3.8014 | 1.9364 | 13.7883 | 16.3389 | 16.3389
2981 | -2.1995 | -1.3195 | 0.01392 | 0.093499 | 3.5527 | 3.3645 | 6.3644 | 4.4322 | 4.1685 | 1.6482 | 12.9976 | 15.7338 | 15.7338
2982 | -0.47727 | -1.4208 | 0.31658 | 0.077683 | 3.1981 | 4.6922 | 6.5451 | 4.3895 | 4.6485 | 1.8303 | 14.1101 | 16.222 | 16.222
2983 | 0.32517 | 1.4396 | 0.62748 | 0.92501 | 5.1913 | 5.6642 | 6.7245 | 6.4659 | 3.3688 | 2.4229 | 19.7442 | 17.7075 | 19.7442
2984 | 0.43935 | 0.092418 | 0.6698 | 0.53682 | 4.4315 | 5.8103 | 5.8864 | 5.3287 | 3.4149 | 2.2588 | 17.8294 | 15.9916 | 17.8294
2985 | 0.20564 | 0.39486 | 0.58146 | 0.65353 | 3.8351 | 5.5122 | 3.8173 | 5.5781 | 4.6693 | 1.7404 | 16.6658 | 14.0621 | 16.6658
2986 | -0.20177 | -2.1926 | 0.42005 | 0.014169 | 5.3896 | 5.0099 | 5.8744 | 4.1566 | 4.118 | 1.3067 | 15.8629 | 16.6887 | 16.6887
2987 | 0.64296 | -1.9595 | 0.73988 | 0.02503 | 3.9598 | 6.0716 | 7.2839 | 4.2111 | 4.681 | 2.0797 | 16.3223 | 18.0045 | 18.0045
2988 | -0.077902 | 0.90187 | 0.46895 | 0.81644 | 3.3556 | 5.1593 | 4.6422 | 6.0127 | 4.1221 | 1.8188 | 16.3463 | 13.9387 | 16.3463
2989 | -0.10625 | -0.25812 | 0.45769 | 0.39816 | 2.762 | 5.1248 | 3.9918 | 5.0588 | 3.6405 | 1.8633 | 14.8088 | 12.2575 | 14.8088
2990 | -0.43346 | -0.1681 | 0.33234 | 0.43325 | 3.5826 | 4.7412 | 5.964 | 5.1257 | 3.545 | 2.025 | 15.4745 | 15.1167 | 15.4745
2991 | 0.65229 | 1.0187 | 0.74289 | 0.84583 | 4.171 | 6.0835 | 3.5227 | 6.113 | 3.1617 | 1.4576 | 17.8252 | 12.3129 | 17.8252
2992 | -0.0372 | -0.097819 | 0.48516 | 0.46104 | 2.8871 | 5.2091 | 7.4624 | 5.1792 | 5.2824 | 2.3949 | 15.6703 | 18.0269 | 18.0269
2993 | 0.16333 | 0.83452 | 0.56487 | 0.79801 | 3.8858 | 5.4588 | 5.9584 | 5.9547 | 3.8012 | 1.862 | 17.1612 | 15.5074 | 17.1612
2994 | 1.151 | 0.17982 | 0.87514 | 0.57135 | 3.4208 | 6.7098 | 7.428 | 5.3995 | 4.045 | 2.2355 | 17.7656 | 17.1292 | 17.7656
2995 | 1.8492 | 2.7321 | 0.96779 | 0.99685 | 5.3869 | 7.4936 | 5.4325 | 7.3438 | 5.3446 | 1.9596 | 22.1838 | 18.1237 | 22.1838
2996 | -0.67155 | -1.0587 | 0.25094 | 0.14486 | 3.4441 | 4.4824 | 5.5733 | 4.5559 | 3.6198 | 1.8651 | 14.3475 | 14.5022 | 14.5022
2997 | -0.40903 | -1.1803 | 0.34126 | 0.11894 | 2.9937 | 4.7688 | 4.7137 | 4.4957 | 4.5053 | 1.4269 | 13.6851 | 13.6396 | 13.6851
2998 | 0.13803 | 0.034749 | 0.55489 | 0.51386 | 4.393 | 5.4269 | 5.4791 | 5.2827 | 3.8506 | 2.7112 | 17.8137 | 16.4338 | 17.8137
2999 | -0.53752 | -0.42706 | 0.29545 | 0.33467 | 5.1138 | 4.6257 | 3.9636 | 4.9383 | 3.6336 | 2.2206 | 16.8983 | 14.9316 | 16.8983
3000 | 1.0384 | -0.1499 | 0.85045 | 0.44042 | 3.3684 | 6.5715 | 6.595 | 5.1394 | 4.0344 | 2.4035 | 17.4828 | 16.4012 | 17.4828
3001 | 0.76828 | -0.17278 | 0.77884 | 0.43141 | 3.5045 | 6.2318 | 6.1488 | 5.1222 | 3.8862 | 2.6342 | 17.4926 | 16.1737 | 17.4926
3002 | -0.70419 | 0.12135 | 0.24066 | 0.54829 | 3.9922 | 4.4485 | 7.4591 | 5.352 | 5.1279 | 1.9822 | 15.7749 | 18.5613 | 18.5613
3003 | -1.5228 | -1.0863 | 0.063908 | 0.13868 | 4.5913 | 3.7384 | 4.0153 | 4.5419 | 5.5362 | 1.578 | 14.4496 | 15.7208 | 15.7208
3004 | 0.80135 | 0.62705 | 0.78854 | 0.73469 | 4.716 | 6.2738 | 6.7132 | 5.7759 | 5.9662 | 1.4747 | 18.2405 | 18.8701 | 18.8701
3005 | -0.53172 | -0.029513 | 0.29746 | 0.48823 | 3.8163 | 4.6321 | 7.4873 | 5.2321 | 4.3368 | 1.7487 | 15.4292 | 17.3892 | 17.3892
3006 | 0.44857 | 0.45376 | 0.67313 | 0.675 | 4.8389 | 5.8221 | 7.6906 | 5.6279 | 3.5507 | 2.0382 | 18.3271 | 18.1184 | 18.3271
3007 | 0.87669 | 2.9541 | 0.80967 | 0.99843 | 4.3402 | 6.3692 | 6.7714 | 7.4521 | 4.6218 | 1.8661 | 20.0276 | 17.5995 | 20.0276
3008 | 0.041136 | -0.30531 | 0.51641 | 0.38006 | 3.5337 | 5.3058 | 6.4755 | 5.0244 | 5.4528 | 2.553 | 16.4169 | 18.0151 | 18.0151
3009 | -0.28474 | -0.43607 | 0.38792 | 0.33139 | 3.7618 | 4.912 | 5.039 | 4.9321 | 4.1957 | 2.1187 | 15.7245 | 15.1152 | 15.7245
3010 | 3.5538 | 2.2461 | 0.99981 | 0.98765 | 4.3833 | 8.6512 | 5.2311 | 7.0607 | 3.1775 | 1.9296 | 22.0248 | 14.7215 | 22.0248
3011 | -0.22354 | 0.37108 | 0.41156 | 0.64471 | 3.3654 | 4.9841 | 5.4726 | 5.5581 | 4.8636 | 2.5396 | 16.4471 | 16.2412 | 16.4471
3012 | -1.3389 | -1.9377 | 0.090297 | 0.026328 | 3.7845 | 3.8731 | 4.8847 | 4.2168 | 4.2521 | 2.4028 | 14.2772 | 15.3241 | 15.3241
3013 | 0.18906 | -0.35925 | 0.57498 | 0.3597 | 3.6512 | 5.4912 | 7.3239 | 4.9858 | 4.1955 | 2.3443 | 16.4726 | 17.5149 | 17.5149
3014 | -0.25472 | -0.13197 | 0.39947 | 0.4475 | 3.0981 | 4.9472 | 4.6729 | 5.1531 | 4.6744 | 2.3517 | 15.5501 | 14.7971 | 15.5501
3015 | 0.18752 | -0.12052 | 0.57437 | 0.45204 | 5.4877 | 5.4893 | 4.8132 | 5.1618 | 3.3578 | 1.9417 | 18.0805 | 15.6004 | 18.0805
3016 | 0.90652 | 0.072897 | 0.81767 | 0.52906 | 4.4184 | 6.4068 | 5.0485 | 5.3131 | 3.3189 | 1.9238 | 18.0622 | 14.7096 | 18.0622
3017 | 0.6538 | -0.36043 | 0.74338 | 0.35926 | 4.1541 | 6.0855 | 5.4234 | 4.985 | 3.6618 | 1.7484 | 16.973 | 14.9877 | 16.973
3018 | -0.40795 | -0.1046 | 0.34165 | 0.45835 | 2.7269 | 4.77 | 6.1239 | 5.174 | 3.7694 | 1.8539 | 14.5248 | 14.4742 | 14.5248
3019 | 0.55995 | -0.12282 | 0.71224 | 0.45113 | 4.9549 | 5.9651 | 6.5449 | 5.16 | 4.1747 | 1.7807 | 17.8607 | 17.4552 | 17.8607
3020 | -0.8332 | -0.70062 | 0.20237 | 0.24177 | 4.6357 | 4.3183 | 6.0097 | 4.7588 | 5.1221 | 2.0925 | 15.8052 | 17.86 | 17.86
3021 | 1.7564 | 2.3685 | 0.96049 | 0.99107 | 5.1656 | 7.3982 | 5.2888 | 7.1378 | 4.0808 | 1.6437 | 21.3454 | 16.1789 | 21.3454
3022 | 0.66228 | 1.253 | 0.7461 | 0.8949 | 4.4103 | 6.0964 | 4.7839 | 6.3117 | 3.7962 | 1.5868 | 18.4052 | 14.5773 | 18.4052
3023 | 0.67755 | -0.037318 | 0.75097 | 0.48512 | 3.2377 | 6.1159 | 6.2375 | 5.226 | 4.1283 | 2.225 | 16.8046 | 15.8285 | 16.8046
3024 | 0.41916 | 1.1916 | 0.66245 | 0.88329 | 5.1147 | 5.7844 | 6.019 | 6.2601 | 3.9958 | 2.0383 | 19.1975 | 17.1678 | 19.1975
3025 | -0.6053 | 0.58023 | 0.27249 | 0.71912 | 2.8215 | 4.5525 | 5.8266 | 5.7358 | 4.681 | 1.5735 | 14.6833 | 14.9027 | 14.9027
3026 | -0.92428 | -0.19194 | 0.17767 | 0.42389 | 4.0631 | 4.2303 | 7.0662 | 5.1078 | 3.3654 | 1.9991 | 15.4003 | 16.4938 | 16.4938
3027 | -1.1745 | -1.2335 | 0.1201 | 0.10869 | 5.2052 | 4.006 | 5.0148 | 4.4707 | 5.0949 | 2.4894 | 16.1714 | 17.8044 | 17.8044
3028 | 2.3138 | -0.10364 | 0.98966 | 0.45873 | 4.7825 | 7.9217 | 6.6828 | 5.1747 | 4.0627 | 1.5304 | 19.4093 | 17.0584 | 19.4093
3029 | 0.083514 | -0.60169 | 0.53328 | 0.27369 | 4.8418 | 5.3586 | 5.8079 | 4.8214 | 5.7339 | 2.144 | 17.1658 | 18.5276 | 18.5276
3030 | 0.56947 | 1.4264 | 0.71548 | 0.92312 | 3.8699 | 5.9773 | 5.6146 | 6.4551 | 6.3831 | 2.3554 | 18.6578 | 18.2231 | 18.6578
3031 | 1.4656 | 0.85063 | 0.92862 | 0.80251 | 5.104 | 7.0807 | 5.9082 | 5.9685 | 4.7005 | 2.1215 | 20.2747 | 17.8343 | 20.2747
3032 | 0.37091 | 0.80534 | 0.64465 | 0.78969 | 4.6045 | 5.7226 | 6.2277 | 5.9295 | 4.0562 | 2.0973 | 18.3539 | 16.9857 | 18.3539
3033 | 0.038619 | -0.39296 | 0.5154 | 0.34718 | 3.9629 | 5.3027 | 4.6977 | 4.962 | 4.6816 | 2.0583 | 16.2859 | 15.4004 | 16.2859
3034 | -1.765 | -1.2682 | 0.038783 | 0.10236 | 5.2503 | 3.5831 | 4.7307 | 4.4549 | 3.503 | 1.8289 | 15.1172 | 15.3128 | 15.3128
3035 | -1.2593 | -2.1931 | 0.10396 | 0.014149 | 3.9239 | 3.936 | 5.4678 | 4.1565 | 3.9872 | 2.3245 | 14.341 | 15.7035 | 15.7035
3036 | -1.5873 | -1.2259 | 0.056219 | 0.11011 | 2.9988 | 3.6946 | 2.8929 | 4.4743 | 3.989 | 1.9561 | 13.1237 | 11.8368 | 13.1237
3037 | 2.6716 | 2.0839 | 0.99623 | 0.98142 | 5.2303 | 8.1928 | 3.7196 | 6.9526 | 5.1491 | 2.1212 | 22.4968 | 16.2202 | 22.4968
3038 | 1.225 | 0.81978 | 0.88971 | 0.79383 | 4.6596 | 6.7992 | 6.7676 | 5.9419 | 3.6032 | 1.6091 | 19.0099 | 16.6395 | 19.0099
3039 | 0.63213 | 0.83305 | 0.73635 | 0.79759 | 3.6225 | 6.0577 | 7.341 | 5.9534 | 4.2806 | 1.7687 | 17.4023 | 17.0128 | 17.4023
3040 | 0.35093 | 0.039728 | 0.63718 | 0.51585 | 3.9449 | 5.6971 | 4.5865 | 5.2866 | 3.8547 | 2.3185 | 17.2471 | 14.7045 | 17.2471
3041 | -0.8015 | -0.70482 | 0.21142 | 0.24046 | 4.1618 | 4.3497 | 5.8021 | 4.7562 | 3.2107 | 2.0716 | 15.3392 | 15.2462 | 15.3392
3042 | 0.18529 | 0.37625 | 0.5735 | 0.64664 | 3.7046 | 5.4865 | 4.3333 | 5.5625 | 4.7558 | 1.9634 | 16.717 | 14.7571 | 16.717
3043 | 0.46576 | 0.88719 | 0.67931 | 0.81251 | 5.3541 | 5.8442 | 4.2737 | 6 | 3.6503 | 2.4349 | 19.6332 | 15.7129 | 19.6332
3044 | 0.6209 | 1.2414 | 0.73267 | 0.89276 | 4.8106 | 6.0433 | 5.1119 | 6.3019 | 3.8619 | 1.6671 | 18.823 | 15.4515 | 18.823
3045 | 0.21076 | -0.10695 | 0.58346 | 0.45741 | 3.6175 | 5.5187 | 4.7179 | 5.1722 | 5.2353 | 2.352 | 16.6603 | 15.9227 | 16.6603
3046 | -0.58901 | -0.42488 | 0.27793 | 0.33546 | 4.2307 | 4.5699 | 6.8108 | 4.9398 | 3.4615 | 1.7229 | 15.4633 | 16.2259 | 16.2259
3047 | -1.2021 | -0.81773 | 0.11467 | 0.20676 | 4.6759 | 3.9829 | 5.8287 | 4.6883 | 4.3744 | 2.0402 | 15.3874 | 16.9192 | 16.9192
3048 | -0.038487 | 0.00085668 | 0.48465 | 0.50034 | 4.1311 | 5.2075 | 4.8154 | 5.2559 | 4.4652 | 1.9734 | 16.568 | 15.3852 | 16.568
3049 | 0.26126 | 1.9485 | 0.60306 | 0.97432 | 3.4871 | 5.5828 | 5.8038 | 6.8575 | 3.4147 | 2.5308 | 18.4581 | 15.2364 | 18.4581
3050 | -0.44122 | -0.29063 | 0.32953 | 0.38567 | 3.5411 | 4.7325 | 6.8514 | 5.0351 | 3.2911 | 1.4108 | 14.7194 | 15.0944 | 15.0944
3051 | 1.2379 | 0.63506 | 0.89212 | 0.73731 | 4.8621 | 6.8147 | 6.9713 | 5.7828 | 3.4995 | 2.1485 | 19.6081 | 17.4814 | 19.6081
3052 | -0.48978 | 0.4607 | 0.31214 | 0.67749 | 4.3449 | 4.6783 | 6.7086 | 5.6338 | 4.2131 | 2.3403 | 16.9972 | 17.6068 | 17.6068
3053 | 1.2397 | 0.97774 | 0.89246 | 0.8359 | 5.53 | 6.8169 | 4.7592 | 6.0779 | 4.9804 | 2.5888 | 21.0136 | 17.8584 | 21.0136
3054 | 0.48459 | 0.57696 | 0.68602 | 0.71802 | 2.8881 | 5.8684 | 6.1677 | 5.733 | 5.1512 | 2.0106 | 16.5 | 16.2175 | 16.5
3055 | -0.44165 | 0.23435 | 0.32937 | 0.59264 | 3.9914 | 4.732 | 6.4923 | 5.4443 | 4.1823 | 2.2346 | 16.4023 | 16.9007 | 16.9007
3056 | -0.22576 | -1.0474 | 0.41069 | 0.14746 | 4.9787 | 4.9814 | 6.758 | 4.5618 | 3.2922 | 1.7008 | 16.2227 | 16.7296 | 16.7296
3057 | 0.56266 | -1.0405 | 0.71317 | 0.14904 | 3.6743 | 5.9686 | 6.7631 | 4.5653 | 4.499 | 2.0836 | 16.2918 | 17.02 | 17.02
3058 | -2.3078 | -0.90394 | 0.010504 | 0.18301 | 2.0917 | 3.3212 | 7.6728 | 4.639 | 4.7637 | 2.0187 | 12.0705 | 16.5468 | 16.5468
3059 | -0.3505 | 0.58592 | 0.36298 | 0.72104 | 3.8987 | 4.8357 | 5.3189 | 5.7407 | 5.1646 | 2.2671 | 16.7421 | 16.6493 | 16.7421
3060 | 0.20069 | 1.1261 | 0.57953 | 0.86993 | 3.3279 | 5.5059 | 6.1241 | 6.2046 | 4.1741 | 2.2155 | 17.254 | 15.8416 | 17.254
3061 | 0.93473 | 0.4849 | 0.82504 | 0.68613 | 3.2649 | 6.4423 | 6.4307 | 5.6544 | 5.3885 | 2.1666 | 17.5282 | 17.2506 | 17.5282
3062 | 1.0195 | -0.017346 | 0.84601 | 0.49308 | 5.5359 | 6.5481 | 5.4009 | 5.2416 | 3.3066 | 2.5404 | 19.8661 | 16.7838 | 19.8661
3063 | -1.7689 | -1.8671 | 0.038458 | 0.030942 | 3.3792 | 3.5808 | 7.5472 | 4.2362 | 4.6421 | 1.627 | 12.8232 | 17.1955 | 17.1955
3064 | -0.39973 | 0.38351 | 0.34468 | 0.64933 | 3.2532 | 4.7794 | 7.1861 | 5.5686 | 4.3939 | 1.6021 | 15.2032 | 16.4354 | 16.4354
3065 | -0.55193 | -0.62777 | 0.2905 | 0.26508 | 3.7124 | 4.61 | 4.9857 | 4.8046 | 4.566 | 1.9064 | 15.0333 | 15.1705 | 15.1705
3066 | -1.9199 | -2.0346 | 0.027437 | 0.020946 | 3.0722 | 3.4966 | 7.1809 | 4.1922 | 6.1128 | 2.7561 | 13.5172 | 19.122 | 19.122
3067 | 1.2216 | 2.198 | 0.88907 | 0.98602 | 4.5434 | 6.7951 | 7.0936 | 7.0293 | 4.7873 | 2.1977 | 20.5655 | 18.6221 | 20.5655
3068 | 0.23275 | -0.37124 | 0.59202 | 0.35523 | 3.8868 | 5.5465 | 7.8357 | 4.9773 | 3.8761 | 2.6605 | 17.0711 | 18.2591 | 18.2591
3069 | -0.46286 | -0.19828 | 0.32173 | 0.42141 | 5.1671 | 4.7082 | 4.4605 | 5.1031 | 3.7289 | 1.7542 | 16.7326 | 15.1108 | 16.7326
3070 | -0.040507 | -0.10218 | 0.48384 | 0.45931 | 3.3943 | 5.205 | 4.7367 | 5.1758 | 4.2507 | 1.4372 | 15.2123 | 13.8189 | 15.2123
3071 | -0.05775 | -0.13079 | 0.47697 | 0.44797 | 4.4214 | 5.1839 | 3.8147 | 5.154 | 4.625 | 1.8826 | 16.6419 | 14.7437 | 16.6419
3072 | -0.36827 | -0.30082 | 0.35634 | 0.38178 | 4.7523 | 4.8153 | 5.5714 | 5.0277 | 4.3785 | 2.177 | 16.7722 | 16.8792 | 16.8792
3073 | 0.17337 | -0.0016477 | 0.56882 | 0.49934 | 3.902 | 5.4714 | 7.032 | 5.2539 | 5.2245 | 2.3715 | 16.9989 | 18.53 | 18.53
3074 | -0.46287 | -0.71943 | 0.32173 | 0.23594 | 3.5614 | 4.7082 | 7.1699 | 4.7472 | 4.8068 | 1.5192 | 14.536 | 17.0574 | 17.0574
3075 | 2.7388 | 1.2513 | 0.99692 | 0.89459 | 3.9257 | 8.2379 | 6.36 | 6.3103 | 6.1312 | 2.5408 | 21.0148 | 18.9577 | 21.0148
3076 | 0.34959 | -0.82957 | 0.63668 | 0.20339 | 4.1195 | 5.6954 | 5.0904 | 4.6814 | 3.9097 | 1.8803 | 16.3766 | 14.9999 | 16.3766
3077 | 2.1362 | 0.17938 | 0.98367 | 0.57118 | 3.644 | 7.768 | 4.4637 | 5.3992 | 5.3735 | 1.7519 | 18.563 | 15.233 | 18.563
3078 | 0.36747 | -0.25624 | 0.64337 | 0.39888 | 4.0399 | 5.7182 | 5.7921 | 5.0602 | 4.1606 | 1.8249 | 16.6432 | 15.8176 | 16.6432
3079 | 0.84053 | -0.19048 | 0.7997 | 0.42447 | 2.7701 | 6.3235 | 5.7054 | 5.1089 | 4.6739 | 2.2328 | 16.4353 | 15.3822 | 16.4353
3080 | 1.5343 | -0.32877 | 0.93752 | 0.37117 | 4.7605 | 7.1582 | 5.684 | 5.0075 | 4.4247 | 1.2227 | 18.1489 | 16.0919 | 18.1489
3081 | 0.17894 | 0.57052 | 0.57101 | 0.71584 | 3.4626 | 5.4784 | 4.6308 | 5.7275 | 3.4942 | 1.546 | 16.2145 | 13.1337 | 16.2145
3082 | -0.093401 | 0.081089 | 0.46279 | 0.53231 | 4.1134 | 5.1404 | 3.9542 | 5.3196 | 5.1831 | 1.6183 | 16.1918 | 14.8691 | 16.1918
3083 | 0.64144 | 1.8137 | 0.73938 | 0.96514 | 2.9815 | 6.0696 | 5.9279 | 6.7586 | 3.5108 | 2.1891 | 17.999 | 14.6093 | 17.999
3084 | 0.65221 | 0.85429 | 0.74287 | 0.80353 | 3.2076 | 6.0835 | 5.0755 | 5.9717 | 3.611 | 2.5534 | 17.8162 | 14.4475 | 17.8162
3085 | -0.44726 | -0.25583 | 0.32734 | 0.39904 | 3.5796 | 4.7257 | 6.0033 | 5.0604 | 4.3218 | 1.3796 | 14.7453 | 15.2843 | 15.2843
3086 | -0.059685 | 0.29265 | 0.4762 | 0.61511 | 3.1741 | 5.1815 | 5.2708 | 5.4925 | 5.4168 | 2.1203 | 15.9684 | 15.982 | 15.982
3087 | 0.26389 | -1.2684 | 0.60407 | 0.10232 | 5.2808 | 5.5861 | 5.6305 | 4.4548 | 5.3163 | 1.974 | 17.2957 | 18.2015 | 18.2015
3088 | -0.35793 | -1.3922 | 0.3602 | 0.081925 | 2.5574 | 4.8271 | 4.7266 | 4.4013 | 4.2536 | 1.8789 | 13.6647 | 13.4165 | 13.6647
3089 | 0.43121 | 0.24181 | 0.66684 | 0.59554 | 4.8253 | 5.7999 | 4.2659 | 5.4504 | 3.7293 | 1.7765 | 17.8521 | 14.5969 | 17.8521
3090 | 0.010926 | -0.45503 | 0.50436 | 0.32454 | 3.4911 | 5.2684 | 7.1031 | 4.919 | 3.8204 | 1.5618 | 15.2403 | 15.9764 | 15.9764
3091 | -1.8319 | -1.6265 | 0.03348 | 0.051926 | 3.4143 | 3.5445 | 4.6335 | 4.3121 | 6.4807 | 2.0462 | 13.3172 | 16.5748 | 16.5748
3092 | -0.14464 | 0.32235 | 0.4425 | 0.62641 | 4.0374 | 5.0784 | 6.3548 | 5.5173 | 3.2345 | 1.9345 | 16.5675 | 15.5611 | 16.5675
3093 | -0.18694 | 1.2339 | 0.42585 | 0.89138 | 4.3666 | 5.0276 | 6.9637 | 6.2957 | 3.5477 | 1.4975 | 17.1874 | 16.3755 | 17.1874
3094 | -0.95155 | 1.4099 | 0.17066 | 0.92071 | 2.8024 | 4.2046 | 5.0386 | 6.4416 | 5.2521 | 2.759 | 16.2076 | 15.8521 | 16.2076
3095 | 0.63767 | 0.26671 | 0.73816 | 0.60516 | 4.5491 | 6.0648 | 6.1082 | 5.471 | 4.5697 | 1.9709 | 18.0558 | 17.1979 | 18.0558
3096 | -1.3851 | -2.1302 | 0.083011 | 0.016579 | 2.8807 | 3.8379 | 5.3439 | 4.17 | 4.6112 | 1.7993 | 12.688 | 14.6352 | 14.6352
3097 | -1.1219 | -0.91043 | 0.13096 | 0.1813 | 3.9625 | 4.051 | 5.0517 | 4.6354 | 4.964 | 1.9885 | 14.6374 | 15.9668 | 15.9668
3098 | -0.017086 | 0.14982 | 0.49318 | 0.55955 | 2.6124 | 5.2338 | 6.8611 | 5.3751 | 3.5573 | 1.7362 | 14.9574 | 14.7669 | 14.9574
3099 | 1.6311 | -0.32606 | 0.94857 | 0.37219 | 4.7302 | 7.2648 | 7.4589 | 5.0095 | 4.0031 | 1.5519 | 18.5564 | 17.7441 | 18.5564
3100 | 0.64003 | -0.26456 | 0.73892 | 0.39568 | 3.1586 | 6.0678 | 7.391 | 5.0541 | 4.4579 | 2.067 | 16.3475 | 17.0744 | 17.0744
3101 | 0.88736 | 0.64685 | 0.81256 | 0.74113 | 4.2046 | 6.3827 | 5.0065 | 5.7929 | 3.3257 | 2.7471 | 19.1274 | 15.2839 | 19.1274
3102 | 0.80956 | 1.2231 | 0.7909 | 0.88935 | 2.942 | 6.2842 | 6.814 | 6.2866 | 4.4343 | 1.8334 | 17.3462 | 16.0237 | 17.3462
3103 | -1.1411 | -0.025266 | 0.12691 | 0.48992 | 5.2253 | 4.0344 | 7.2398 | 5.2354 | 3.9511 | 1.8093 | 16.3044 | 18.2255 | 18.2255
3104 | 0.64141 | -1.1426 | 0.73937 | 0.1266 | 5.0754 | 6.0696 | 2.522 | 4.5139 | 3.707 | 1.9103 | 17.5692 | 13.2147 | 17.5692
3105 | 0.44778 | 1.1689 | 0.67285 | 0.87879 | 3.8927 | 5.8211 | 4.5106 | 6.2409 | 3.5602 | 2.0676 | 18.0224 | 14.0311 | 18.0224
3106 | 0.18814 | 1.128 | 0.57462 | 0.87034 | 2.7698 | 5.4901 | 4.9424 | 6.2062 | 3.9329 | 1.623 | 16.0891 | 13.2681 | 16.0891
3107 | -0.36757 | -0.21066 | 0.3566 | 0.41658 | 3.8135 | 4.8161 | 3.6402 | 5.0938 | 3.7625 | 1.7995 | 15.5229 | 13.0156 | 15.5229
3108 | 0.56158 | 0.46594 | 0.7128 | 0.67937 | 3.6547 | 5.9672 | 4.9959 | 5.6383 | 3.3458 | 2.0995 | 17.3597 | 14.096 | 17.3597
3109 | 0.98767 | -0.224 | 0.83834 | 0.41138 | 3.7642 | 6.5085 | 3.9792 | 5.0839 | 3.3971 | 2.2196 | 17.5763 | 13.3602 | 17.5763
3110 | -0.64797 | 0.18721 | 0.2585 | 0.57425 | 4.6713 | 4.5072 | 5.0698 | 5.4056 | 4.2686 | 2.3385 | 16.9225 | 16.3482 | 16.9225
3111 | -1.0455 | 0.11699 | 0.14789 | 0.54657 | 4.3775 | 4.1183 | 6.3235 | 5.3485 | 5.7887 | 2.1631 | 16.0074 | 18.6527 | 18.6527
3112 | 1.6529 | 1.7857 | 0.95083 | 0.96293 | 4.565 | 7.2885 | 6.5823 | 6.7377 | 5.3624 | 1.7136 | 20.3047 | 18.2233 | 20.3047
3113 | 1.5081 | 0.88299 | 0.93424 | 0.81138 | 3.1767 | 7.1289 | 6.1992 | 5.9964 | 4.3516 | 2.0807 | 18.3826 | 15.8081 | 18.3826
3114 | -1.2005 | -0.4173 | 0.11497 | 0.33823 | 4.1992 | 3.9842 | 5.4532 | 4.9451 | 4.14 | 2.233 | 15.3614 | 16.0254 | 16.0254
3115 | 0.13793 | -1.7075 | 0.55485 | 0.043866 | 3.2925 | 5.4268 | 7.1402 | 4.2848 | 4.4981 | 2.14 | 15.1442 | 17.0708 | 17.0708
3116 | 1.4984 | 0.21446 | 0.93298 | 0.58491 | 4.5591 | 7.1179 | 4.2705 | 5.4279 | 4.0167 | 2.0559 | 19.1607 | 14.9022 | 19.1607
3117 | 0.14793 | 0.51784 | 0.5588 | 0.69772 | 3.3165 | 5.4394 | 3.5255 | 5.6824 | 4.2199 | 1.2903 | 15.7286 | 12.3522 | 15.7286
3118 | 0.080289 | -0.060346 | 0.532 | 0.47594 | 5.2135 | 5.3546 | 7.017 | 5.2081 | 4.5924 | 1.8137 | 17.5899 | 18.6366 | 18.6366
3119 | -0.46856 | 1.4815 | 0.31969 | 0.93077 | 4.4853 | 4.7019 | 7.0083 | 6.4999 | 3.5761 | 2.1236 | 17.8107 | 17.1933 | 17.8107
3120 | 1.6069 | -0.11303 | 0.94597 | 0.455 | 3.2789 | 7.2385 | 6.7558 | 5.1675 | 4.1807 | 2.5815 | 18.2664 | 16.7969 | 18.2664
3121 | 1.5474 | 0.89056 | 0.93911 | 0.81342 | 5.0103 | 7.1728 | 5.1558 | 6.0029 | 4.4416 | 2.2636 | 20.4495 | 16.8712 | 20.4495
3122 | 3.0799 | 1.4228 | 0.99896 | 0.9226 | 4.1125 | 8.44 | 5.9177 | 6.4522 | 4.0489 | 2.133 | 21.1378 | 16.2122 | 21.1378
3123 | -0.83179 | -0.62915 | 0.20276 | 0.26463 | 2.8781 | 4.3197 | 3.1589 | 4.8037 | 5.4223 | 1.6916 | 13.6931 | 13.151 | 13.6931
3124 | 0.61611 | 0.486 | 0.73109 | 0.68652 | 4.7119 | 6.0372 | 4.019 | 5.6553 | 4.7823 | 2.1992 | 18.6035 | 15.7123 | 18.6035
3125 | -0.16408 | -0.42681 | 0.43483 | 0.33476 | 4.6563 | 5.055 | 5.6644 | 4.9385 | 5.1306 | 1.7352 | 16.3849 | 17.1864 | 17.1864
3126 | 0.37806 | 1.1201 | 0.64731 | 0.86866 | 5.7842 | 5.7318 | 6.6971 | 6.1995 | 4.8624 | 1.7346 | 19.4501 | 19.0783 | 19.4501
3127 | -0.17857 | -0.6319 | 0.42914 | 0.26373 | 4.4334 | 5.0376 | 7.3348 | 4.802 | 3.9044 | 2.1278 | 16.4008 | 17.8005 | 17.8005
3128 | 1.5623 | 1.4045 | 0.9409 | 0.91992 | 4.9223 | 7.1894 | 7.4626 | 6.4373 | 4.8883 | 2.2938 | 20.8427 | 19.567 | 20.8427
3129 | -0.43083 | -1.3564 | 0.3333 | 0.087489 | 3.4049 | 4.7442 | 3.6009 | 4.4163 | 3.6155 | 2.2076 | 14.773 | 12.8289 | 14.773
3130 | 1.239 | 1.1046 | 0.89233 | 0.86534 | 3.3551 | 6.816 | 5.6719 | 6.1864 | 3.5272 | 1.6256 | 17.9831 | 14.1798 | 17.9831
3131 | -0.17614 | -0.41882 | 0.43009 | 0.33768 | 4.8405 | 5.0405 | 4.8053 | 4.944 | 4.4152 | 2.3838 | 17.2088 | 16.4448 | 17.2088
3132 | 1.0321 | 0.67383 | 0.84898 | 0.74979 | 4.4347 | 6.5637 | 3.206 | 5.8162 | 5.096 | 1.9999 | 18.8143 | 14.7365 | 18.8143
3133 | -0.67629 | -0.21307 | 0.24943 | 0.41563 | 5.3337 | 4.4775 | 6.2871 | 5.092 | 6.5967 | 1.9678 | 16.871 | 20.1853 | 20.1853
3134 | -1.848 | -1.4578 | 0.032298 | 0.07245 | 3.4768 | 3.5355 | 5.4634 | 4.3747 | 5.5171 | 2.2693 | 13.6563 | 16.7266 | 16.7266
3135 | 0.91913 | -0.045607 | 0.82099 | 0.48181 | 4.6288 | 6.4227 | 5.5891 | 5.2195 | 4.1398 | 1.8309 | 18.1019 | 16.1885 | 18.1019
3136 | 0.15993 | -0.33759 | 0.56353 | 0.36784 | 3.1425 | 5.4545 | 5.5859 | 5.0012 | 4.1059 | 1.5614 | 15.1596 | 14.3956 | 15.1596
3137 | -0.16754 | -0.68606 | 0.43347 | 0.24634 | 2.8275 | 5.0508 | 4.1475 | 4.7678 | 5.5549 | 2.3013 | 14.9475 | 14.8313 | 14.9475
3138 | 1.6806 | 1.0335 | 0.95358 | 0.84931 | 4.0163 | 7.3182 | 5.9117 | 6.1257 | 4.6686 | 1.9736 | 19.4337 | 16.5702 | 19.4337
3139 | -0.67341 | -0.62555 | 0.25034 | 0.26581 | 4.8365 | 4.4805 | 4.1096 | 4.806 | 4.6895 | 2.6279 | 16.7508 | 16.2634 | 16.7508
3140 | -1.915 | -2.8749 | 0.027745 | 0.0020207 | 4.2126 | 3.4992 | 7.2692 | 4.0577 | 5.6195 | 1.6116 | 13.3811 | 18.7129 | 18.7129
3141 | -0.71162 | -0.10807 | 0.23835 | 0.45697 | 3.1286 | 4.4408 | 6.1369 | 5.1713 | 4.2181 | 1.7516 | 14.4923 | 15.2352 | 15.2352
3142 | 1.9839 | 1.0508 | 0.97637 | 0.85331 | 3.3942 | 7.6263 | 5.0305 | 6.1404 | 3.8815 | 1.9066 | 19.0675 | 14.2128 | 19.0675
3143 | 1.4412 | 0.68137 | 0.92524 | 0.75218 | 5.4553 | 7.0529 | 4.3403 | 5.8226 | 4.1989 | 2.2255 | 20.5564 | 16.22 | 20.5564
3144 | 0.29206 | 0.70599 | 0.61488 | 0.7599 | 3.1365 | 5.6219 | 5.6449 | 5.8438 | 4.149 | 2.334 | 16.9363 | 15.2645 | 16.9363
3145 | -0.40167 | 0.54692 | 0.34396 | 0.70778 | 4.1547 | 4.7772 | 6.8018 | 5.7073 | 4.4041 | 1.6128 | 16.2518 | 16.9734 | 16.9734
3146 | 0.24883 | 0.56687 | 0.59825 | 0.7146 | 5.0037 | 5.567 | 4.1241 | 5.7243 | 4.5456 | 2.0528 | 18.3478 | 15.7263 | 18.3478
3147 | -0.1645 | -0.50126 | 0.43467 | 0.30809 | 4.1108 | 5.0545 | 7.3288 | 4.8876 | 4.8789 | 2.8161 | 16.869 | 19.1346 | 19.1346
3148 | 0.89293 | -0.039109 | 0.81405 | 0.4844 | 4.2045 | 6.3897 | 6.0511 | 5.2246 | 4.7555 | 2.2022 | 18.0211 | 17.2133 | 18.0211
3149 | -1.1475 | -0.9585 | 0.12558 | 0.16891 | 4.1007 | 4.0289 | 6.8091 | 4.6089 | 4.0247 | 1.8454 | 14.5839 | 16.7798 | 16.7798
3150 | -1.461 | -0.070431 | 0.072003 | 0.47193 | 5.4232 | 3.782 | 5.3019 | 5.2003 | 4.6326 | 2.4229 | 16.8284 | 17.7807 | 17.7807
3151 | -0.54832 | 0.85274 | 0.29174 | 0.8031 | 4.1002 | 4.614 | 2.7978 | 5.9704 | 3.1685 | 2.2352 | 16.9197 | 12.3018 | 16.9197
3152 | -0.47436 | 0.14461 | 0.31762 | 0.55749 | 3.3517 | 4.6954 | 4.311 | 5.3709 | 5.1091 | 1.9423 | 15.3603 | 14.7141 | 15.3603
3153 | 0.46119 | -0.18866 | 0.67767 | 0.42518 | 3.2867 | 5.8383 | 5.5103 | 5.1103 | 5.5043 | 1.8139 | 16.0492 | 16.1152 | 16.1152
3154 | -0.56118 | 0.41373 | 0.28734 | 0.66047 | 4.1615 | 4.6 | 4.8846 | 5.5941 | 3.5217 | 2.4925 | 16.848 | 15.0603 | 16.848
3155 | 1.7266 | 1.6482 | 0.95788 | 0.95035 | 4.0871 | 7.367 | 4.3118 | 6.6323 | 5.1032 | 2.4959 | 20.5822 | 15.998 | 20.5822
3156 | -0.34509 | -0.64301 | 0.36501 | 0.26011 | 4.544 | 4.8419 | 5.6073 | 4.7949 | 3.5702 | 2.2483 | 16.4292 | 15.9699 | 16.4292
3157 | -1.8165 | -1.3137 | 0.034647 | 0.09447 | 3.951 | 3.5532 | 5.1413 | 4.4347 | 4.9087 | 1.2472 | 13.1862 | 15.2482 | 15.2482
3158 | -1.0303 | -1.0269 | 0.15144 | 0.15222 | 3.79 | 4.1321 | 7.6888 | 4.5724 | 3.8792 | 2.2357 | 14.7302 | 17.5938 | 17.5938
3159 | -1.4465 | 0.13626 | 0.074015 | 0.55419 | 2.9077 | 3.7925 | 6.4506 | 5.3641 | 3.2254 | 1.9808 | 14.0451 | 14.5644 | 14.5644
3160 | -0.84841 | -2.1798 | 0.19811 | 0.014637 | 4.1046 | 4.3034 | 6.2833 | 4.1593 | 3.7209 | 1.3502 | 13.9175 | 15.459 | 15.459
3161 | -1.6864 | -0.84708 | 0.045856 | 0.19847 | 4.8259 | 3.6307 | 6.4939 | 4.6713 | 4.6036 | 1.3708 | 14.4987 | 17.2943 | 17.2943
3162 | 0.29334 | -0.13899 | 0.61537 | 0.44473 | 5.5066 | 5.6236 | 5.3179 | 5.1477 | 3.3759 | 2.2516 | 18.5295 | 16.452 | 18.5295
3163 | 0.79092 | 0.24531 | 0.7855 | 0.59689 | 3.3413 | 6.2606 | 6.1747 | 5.4533 | 3.8309 | 2.1556 | 17.2107 | 15.5024 | 17.2107
3164 | 0.93293 | 1.3428 | 0.82457 | 0.91033 | 4.7105 | 6.44 | 5.8109 | 6.3864 | 4.2213 | 1.8503 | 19.3872 | 16.5929 | 19.3872
3165 | 0.73391 | 1.1502 | 0.7685 | 0.87496 | 5.3602 | 6.1879 | 6.0892 | 6.2251 | 3.3575 | 1.7545 | 19.5277 | 16.5614 | 19.5277
3166 | -0.21009 | -0.26052 | 0.4168 | 0.39723 | 2.5283 | 5 | 5.1931 | 5.057 | 3.9277 | 1.9974 | 14.5828 | 13.6466 | 14.5828
3167 | -0.23743 | -0.42842 | 0.40616 | 0.33417 | 3.7849 | 4.9676 | 4.1911 | 4.9373 | 4.655 | 2.4389 | 16.1288 | 15.0699 | 16.1288
3168 | -0.58268 | -1.4048 | 0.28005 | 0.080038 | 4.1163 | 4.5767 | 6.1286 | 4.3961 | 4.3689 | 2.3318 | 15.421 | 16.9457 | 16.9457
3169 | -1.0676 | -1.4859 | 0.14286 | 0.068654 | 2.9366 | 4.0986 | 5.5256 | 4.3637 | 3.7103 | 2.1511 | 13.5501 | 14.3236 | 14.3236
3170 | -0.81639 | -0.45752 | 0.20714 | 0.32365 | 4.3384 | 4.3349 | 3.3894 | 4.9173 | 3.507 | 1.5381 | 15.1287 | 12.7729 | 15.1287
3171 | 0.71817 | 0.26268 | 0.76367 | 0.6036 | 3.9812 | 6.1678 | 5.1924 | 5.4677 | 4.5897 | 1.7449 | 17.3616 | 15.5083 | 17.3616
3172 | -1.3141 | -0.35679 | 0.094412 | 0.36062 | 4.0144 | 3.8925 | 4.9921 | 4.9876 | 4.6498 | 1.7966 | 14.691 | 15.4529 | 15.4529
3173 | -0.17646 | -0.48158 | 0.42997 | 0.31505 | 5.2702 | 5.0402 | 4.8891 | 4.9009 | 4.7438 | 1.3191 | 16.5303 | 16.2222 | 16.5303
3174 | -0.93202 | 0.36919 | 0.17566 | 0.64401 | 4.364 | 4.2229 | 6.0673 | 5.5565 | 3.9988 | 2.1023 | 16.2458 | 16.5325 | 16.5325
3175 | 1.0495 | 0.8978 | 0.85302 | 0.81535 | 3.676 | 6.5852 | 7.2042 | 6.0092 | 5.0824 | 1.696 | 17.9664 | 17.6586 | 17.9664
3176 | -0.76145 | -0.12752 | 0.22319 | 0.44926 | 2.7937 | 4.3899 | 4.9707 | 5.1564 | 4.3385 | 1.6361 | 13.9761 | 13.7389 | 13.9761
3177 | -0.78889 | -0.34328 | 0.21509 | 0.36569 | 5.4429 | 4.3623 | 4.4485 | 4.9972 | 4.4186 | 2.4763 | 17.2786 | 16.7862 | 17.2786
3178 | -1.1644 | -0.6718 | 0.12213 | 0.25086 | 3.7981 | 4.0145 | 7.3359 | 4.7767 | 4.9699 | 1.7542 | 14.3436 | 17.8581 | 17.8581
3179 | 0.33545 | 0.76636 | 0.63136 | 0.77827 | 3.8512 | 5.6773 | 4.5021 | 5.8959 | 4.2374 | 1.31 | 16.7344 | 13.9007 | 16.7344
3180 | -1.3053 | -1.6653 | 0.095903 | 0.04793 | 3.5857 | 3.8994 | 6.989 | 4.2988 | 4.6783 | 1.8754 | 13.6593 | 17.1284 | 17.1284
3181 | 0.15856 | 1.9426 | 0.56299 | 0.97396 | 4.7426 | 5.4528 | 6.2531 | 6.8532 | 5.1005 | 1.977 | 19.0255 | 18.0733 | 19.0255
3182 | -0.64058 | -0.071962 | 0.2609 | 0.47132 | 4.6437 | 4.515 | 6.4293 | 5.1991 | 4.8933 | 1.2969 | 15.6547 | 17.2633 | 17.2633
3183 | 0.33582 | 0.26474 | 0.6315 | 0.6044 | 3.3667 | 5.6778 | 7.2281 | 5.4694 | 4.5549 | 1.7888 | 16.3026 | 16.9384 | 16.9384
3184 | -2.4024 | -1.6302 | 0.0081444 | 0.05153 | 2.5336 | 3.2866 | 4.7161 | 4.3108 | 4.4095 | 1.6501 | 11.7812 | 13.3093 | 13.3093
3185 | -0.9135 | 0.056868 | 0.18049 | 0.52267 | 3.2535 | 4.2405 | 5.1043 | 5.3003 | 4.3335 | 1.6982 | 14.4925 | 14.3896 | 14.4925
3186 | -0.47647 | -0.98841 | 0.31687 | 0.16148 | 3.2251 | 4.6931 | 3.8407 | 4.5928 | 4.629 | 1.6101 | 14.1211 | 13.305 | 14.1211
3187 | 0.57193 | 0.56959 | 0.71631 | 0.71552 | 2.9342 | 5.9805 | 6.1705 | 5.7267 | 3.6745 | 1.6134 | 16.2548 | 14.3926 | 16.2548
3188 | -0.53705 | 0.42882 | 0.29562 | 0.66597 | 3.3387 | 4.6262 | 7.1177 | 5.6068 | 5.149 | 1.891 | 15.4627 | 17.4964 | 17.4964
3189 | -0.07523 | 0.57132 | 0.47002 | 0.71611 | 3.6011 | 5.1625 | 5.5873 | 5.7281 | 5.0291 | 1.9642 | 16.4559 | 16.1816 | 16.4559
3190 | 0.11367 | 1.3079 | 0.54525 | 0.90455 | 3.3624 | 5.3963 | 5.9176 | 6.3575 | 3.3416 | 1.4331 | 16.5494 | 14.0546 | 16.5494
3191 | 0.64819 | 0.51522 | 0.74157 | 0.6968 | 4.2828 | 6.0783 | 3.4918 | 5.6802 | 4.6269 | 1.9579 | 17.9992 | 14.3594 | 17.9992
3192 | 1.535 | 0.59137 | 0.93761 | 0.72286 | 5.3123 | 7.159 | 5.9307 | 5.7453 | 3.3247 | 1.6264 | 19.843 | 16.1941 | 19.843
3193 | 1.1239 | -0.066335 | 0.86948 | 0.47356 | 3.3277 | 6.6768 | 6.539 | 5.2035 | 3.7009 | 1.6667 | 16.8747 | 15.2343 | 16.8747
3194 | 2.0621 | 2.6165 | 0.9804 | 0.99556 | 4.2631 | 7.7002 | 5.8683 | 7.2821 | 6.399 | 2.2599 | 21.5053 | 18.7903 | 21.5053
3195 | -0.4669 | 0.26944 | 0.32029 | 0.6062 | 3.0511 | 4.7037 | 5.2841 | 5.4733 | 4.0699 | 1.7789 | 15.0069 | 14.184 | 15.0069
3196 | -0.79335 | -0.34507 | 0.21379 | 0.36502 | 3.2401 | 4.3578 | 5.1846 | 4.9959 | 4.1224 | 1.5281 | 14.1219 | 14.0753 | 14.1219
3197 | -0.96288 | -0.9839 | 0.1678 | 0.16258 | 4.4565 | 4.194 | 5.6438 | 4.5952 | 3.9437 | 1.9392 | 15.1849 | 15.9832 | 15.9832
3198 | -1.1458 | -0.33674 | 0.12594 | 0.36815 | 3.6874 | 4.0304 | 7.5504 | 5.0018 | 3.3819 | 2.5732 | 15.2928 | 17.1929 | 17.1929
3199 | -0.20764 | -0.40337 | 0.41775 | 0.34334 | 4.7286 | 5.0029 | 6.592 | 4.9548 | 4.4142 | 2.2283 | 16.9146 | 17.9631 | 17.9631
3200 | 0.44587 | -0.61312 | 0.67216 | 0.2699 | 2.8055 | 5.8187 | 6.0738 | 4.814 | 4.2453 | 2.2473 | 15.6856 | 15.372 | 15.6856
3201 | -1.2361 | 0.34377 | 0.1082 | 0.63449 | 3.5271 | 3.9548 | 5.5767 | 5.5352 | 3.2159 | 1.9103 | 14.9274 | 14.2301 | 14.9274
3202 | -1.23 | -1.3471 | 0.10935 | 0.088969 | 4.1432 | 3.9598 | 5.8189 | 4.4203 | 3.7457 | 2.1467 | 14.67 | 15.8545 | 15.8545
3203 | -0.83277 | -1.8773 | 0.20249 | 0.030239 | 3.9496 | 4.3187 | 6.6367 | 4.2334 | 4.1536 | 1.302 | 13.8037 | 16.0419 | 16.0419
3204 | 1.1463 | 1.1355 | 0.87416 | 0.87191 | 4.698 | 6.704 | 5.5455 | 6.2126 | 3.8082 | 2.7437 | 20.3583 | 16.7953 | 20.3583
3205 | -0.46099 | -0.17272 | 0.3224 | 0.43144 | 3.3768 | 4.7103 | 4.7203 | 5.1222 | 3.7373 | 1.4719 | 14.6812 | 13.3063 | 14.6812
3206 | -0.9862 | -0.1989 | 0.16202 | 0.42117 | 4.5867 | 4.1723 | 6.7601 | 5.1026 | 3.3296 | 2.6351 | 16.4967 | 17.3115 | 17.3115
3207 | -0.72782 | -1.599 | 0.23336 | 0.054913 | 4.6897 | 4.4242 | 6.6308 | 4.3218 | 3.4187 | 2.2029 | 15.6385 | 16.9422 | 16.9422
3208 | -1.283 | -0.14258 | 0.099739 | 0.44331 | 4.6554 | 3.917 | 7.4029 | 5.145 | 3.8754 | 1.3216 | 15.039 | 17.2554 | 17.2554
3209 | 0.94045 | 0.34177 | 0.82651 | 0.63374 | 4.9277 | 6.4495 | 6.577 | 5.5335 | 4.322 | 1.5466 | 18.4573 | 17.3734 | 18.4573
3210 | 0.28025 | -0.27856 | 0.61036 | 0.39029 | 3.5871 | 5.6069 | 6.0639 | 5.0438 | 4.3556 | 1.662 | 15.8998 | 15.6686 | 15.8998
3211 | 0.64719 | -0.22896 | 0.74125 | 0.40945 | 4.9094 | 6.077 | 5.3573 | 5.0803 | 3.836 | 2.337 | 18.4036 | 16.4397 | 18.4036
3212 | 0.7718 | -0.24652 | 0.77988 | 0.40264 | 4.3738 | 6.2362 | 7.7496 | 5.0673 | 4.0761 | 1.3267 | 17.004 | 17.5261 | 17.5261
3213 | -0.76826 | -0.65215 | 0.22117 | 0.25715 | 4.9738 | 4.383 | 3.2781 | 4.7891 | 6.1635 | 1.3969 | 15.5429 | 15.8124 | 15.8124
3214 | 1.324 | 1.1202 | 0.90726 | 0.8687 | 5.2554 | 6.917 | 6.4743 | 6.1997 | 4.1484 | 1.7107 | 20.0828 | 17.5888 | 20.0828
3215 | 0.6017 | -0.75986 | 0.72631 | 0.22367 | 4.4602 | 6.0187 | 6.1644 | 4.7227 | 3.3388 | 2.2153 | 17.4168 | 16.1787 | 17.4168
3216 | -0.3588 | -0.11983 | 0.35987 | 0.45231 | 2.6758 | 4.8261 | 5.8006 | 5.1623 | 4.0673 | 2.3404 | 15.0046 | 14.8841 | 15.0046
3217 | -1.3768 | -1.2572 | 0.084287 | 0.10434 | 4.4749 | 3.8442 | 6.5569 | 4.4599 | 4.0991 | 1.7812 | 14.5601 | 16.912 | 16.912
3218 | 1.2556 | 0.03775 | 0.89538 | 0.51506 | 3.9337 | 6.8359 | 5.1226 | 5.2851 | 3.8524 | 1.6259 | 17.6806 | 14.5346 | 17.6806
3219 | 0.35523 | -0.37641 | 0.63879 | 0.35331 | 2.5049 | 5.7026 | 3.893 | 4.9737 | 4.2484 | 2.3821 | 15.5632 | 13.0283 | 15.5632
3220 | -0.72792 | 0.011816 | 0.23333 | 0.50471 | 4.1968 | 4.4241 | 4.0707 | 5.2646 | 4.6022 | 2.6224 | 16.5079 | 15.4922 | 16.5079
3221 | -0.28506 | -1.0338 | 0.3878 | 0.15061 | 3.2464 | 4.9116 | 6.4976 | 4.5688 | 3.163 | 2.3748 | 15.1016 | 15.2818 | 15.2818
3222 | 0.24862 | -0.89598 | 0.59817 | 0.18513 | 4.19 | 5.5667 | 4.4624 | 4.6435 | 3.681 | 1.9684 | 16.3686 | 14.3019 | 16.3686
3223 | 0.94963 | 0.7604 | 0.82885 | 0.77649 | 5.0891 | 6.461 | 6.3667 | 5.8907 | 3.2777 | 2.2111 | 19.6519 | 16.9446 | 19.6519
3224 | -1.2285 | -0.13108 | 0.10963 | 0.44786 | 2.4749 | 3.9611 | 4.2975 | 5.1537 | 5.7049 | 1.3145 | 12.9042 | 13.7918 | 13.7918
3225 | 1.8884 | 0.59789 | 0.97051 | 0.72504 | 4.8874 | 7.5329 | 4.7478 | 5.7509 | 4.4612 | 2.2034 | 20.3745 | 16.2998 | 20.3745
3226 | -1.3096 | -2.1856 | 0.095169 | 0.014423 | 4.0687 | 3.896 | 6.0302 | 4.1581 | 4.1485 | 2.1045 | 14.2273 | 16.3518 | 16.3518
3227 | 0.29237 | -0.65405 | 0.615 | 0.25654 | 3.6356 | 5.6223 | 6.4668 | 4.7879 | 4.3593 | 1.7482 | 15.794 | 16.2099 | 16.2099
3228 | 1.0364 | 0.66509 | 0.85 | 0.747 | 3.5013 | 6.5691 | 3.6054 | 5.8086 | 3.6212 | 1.7732 | 17.6522 | 12.5011 | 17.6522
3229 | -3.1919 | -3.0427 | 0.00070682 | 0.0011722 | 4.4699 | 3.098 | 5.3951 | 4.0438 | 6.0366 | 2.1315 | 13.7432 | 18.033 | 18.033
3230 | -1.1256 | -1.1892 | 0.13017 | 0.11718 | 2.9433 | 4.0478 | 4.9608 | 4.4915 | 4.068 | 2.357 | 13.8396 | 14.3291 | 14.3291
3231 | 0.9392 | -0.83528 | 0.82619 | 0.20178 | 2.9426 | 6.4479 | 6.298 | 4.6781 | 4.071 | 2.0807 | 16.1493 | 15.3923 | 16.1493
3232 | 2.2492 | 1.1789 | 0.98775 | 0.88077 | 3.866 | 7.8673 | 6.92 | 6.2493 | 4.7665 | 1.5008 | 19.4835 | 17.0534 | 19.4835
3233 | -0.72498 | -0.14904 | 0.23423 | 0.44076 | 5.0636 | 4.4271 | 5.6065 | 5.1401 | 4.5707 | 2.5925 | 17.2232 | 17.8333 | 17.8333
3234 | 0.69382 | 0.14457 | 0.7561 | 0.55748 | 4.3372 | 6.1367 | 6.081 | 5.3708 | 5.2078 | 1.4458 | 17.2906 | 17.0719 | 17.2906
3235 | 1.53 | 0.0064021 | 0.93699 | 0.50255 | 4.2019 | 7.1533 | 5.631 | 5.2603 | 5.0381 | 2.6117 | 19.2272 | 17.4827 | 19.2272
3236 | -0.88894 | -0.68162 | 0.18702 | 0.24774 | 5.1248 | 4.264 | 7.4387 | 4.7706 | 4.6206 | 2.0676 | 16.2271 | 19.2518 | 19.2518
3237 | 0.42683 | -0.74203 | 0.66525 | 0.22904 | 4.2335 | 5.7943 | 3.8549 | 4.7334 | 3.8918 | 1.5907 | 16.3519 | 13.571 | 16.3519
3238 | 1.8726 | 1.0185 | 0.96944 | 0.84578 | 4.7816 | 7.5171 | 5.9135 | 6.1129 | 3.6026 | 1.9919 | 20.4034 | 16.2895 | 20.4034
3239 | 0.50587 | 1.072 | 0.69353 | 0.85815 | 3.5887 | 5.8957 | 7.4206 | 6.1586 | 3.7473 | 2.629 | 18.272 | 17.3856 | 18.272
3240 | -0.1224 | -0.70868 | 0.45129 | 0.23926 | 4.3545 | 5.1052 | 5.8826 | 4.7538 | 4.9364 | 1.7624 | 15.9759 | 16.9358 | 16.9358
3241 | -0.32392 | 0.75356 | 0.373 | 0.77444 | 3.9333 | 4.8664 | 5.2468 | 5.8848 | 3.877 | 1.3837 | 16.0682 | 14.4407 | 16.0682
3242 | 0.97387 | 1.0768 | 0.83494 | 0.85922 | 3.8697 | 6.4913 | 4.564 | 6.1627 | 4.2341 | 1.9656 | 18.4893 | 14.6334 | 18.4893
3243 | 2.6152 | 2.1219 | 0.99554 | 0.98308 | 2.5992 | 8.1535 | 7.2746 | 6.9785 | 4.5632 | 2.1102 | 19.8414 | 16.5471 | 19.8414
3244 | -0.66387 | 0.10546 | 0.25339 | 0.54199 | 3.2273 | 4.4904 | 3.6615 | 5.3392 | 5.9937 | 1.7603 | 14.8172 | 14.6427 | 14.8172
3245 | -0.61648 | 0.55429 | 0.26879 | 0.71031 | 4.7518 | 4.5405 | 2.9778 | 5.7136 | 4.3632 | 1.9936 | 16.9995 | 14.0864 | 16.9995
3246 | -0.43385 | 0.25218 | 0.3322 | 0.59955 | 4.9536 | 4.7408 | 5.644 | 5.459 | 5.6985 | 1.783 | 16.9364 | 18.0791 | 18.0791
3247 | -0.30507 | 0.11837 | 0.38016 | 0.54711 | 4.1983 | 4.8883 | 5.5062 | 5.3496 | 5.4644 | 2.3906 | 16.8268 | 17.5595 | 17.5595
3248 | 0.57655 | -0.3995 | 0.71788 | 0.34476 | 4.4918 | 5.9864 | 6.0316 | 4.9575 | 4.2753 | 2.0202 | 17.4558 | 16.819 | 17.4558
3249 | -1.2701 | -0.33625 | 0.10203 | 0.36834 | 4.6871 | 3.9274 | 6.8017 | 5.0022 | 3.5946 | 1.4034 | 15.02 | 16.4867 | 16.4867
3250 | 1.2405 | 0.074197 | 0.89261 | 0.52957 | 2.8582 | 6.8178 | 5.5547 | 5.3141 | 3.7422 | 2.1388 | 17.1289 | 14.2939 | 17.1289
3251 | -0.66081 | -0.23656 | 0.25437 | 0.4065 | 4.9992 | 4.4937 | 5.067 | 5.0746 | 4.3475 | 1.3948 | 15.9623 | 15.8085 | 15.9623
3252 | -0.90028 | -0.60913 | 0.18398 | 0.27122 | 4.7244 | 4.2531 | 5.8527 | 4.8166 | 4.5764 | 2.0762 | 15.8703 | 17.2297 | 17.2297
3253 | 0.23427 | 0.84307 | 0.59261 | 0.80041 | 4.558 | 5.5485 | 5.2311 | 5.962 | 4.785 | 2.3247 | 18.3932 | 16.8988 | 18.3932
3254 | 1.8483 | 0.62748 | 0.96772 | 0.73483 | 3.7565 | 7.4926 | 4.5821 | 5.7763 | 4.9405 | 1.575 | 18.6005 | 14.8542 | 18.6005
3255 | -1.1295 | 0.20343 | 0.12934 | 0.5806 | 3.0946 | 4.0444 | 4.7881 | 5.4188 | 4.3296 | 2.5184 | 15.0762 | 14.7307 | 15.0762
3256 | 0.25631 | 0.0048085 | 0.60115 | 0.50192 | 3.1318 | 5.5765 | 4.0743 | 5.259 | 3.6213 | 2.2125 | 16.1799 | 13.04 | 16.1799
3257 | -0.010459 | -0.39146 | 0.49583 | 0.34773 | 4.1942 | 5.242 | 3.3906 | 4.9631 | 4.599 | 2.4336 | 16.8329 | 14.6175 | 16.8329
3258 | 0.5066 | -0.19374 | 0.69378 | 0.42319 | 3.8338 | 5.8966 | 5.7634 | 5.1065 | 3.9128 | 2.5498 | 17.3867 | 16.0598 | 17.3867
3259 | -0.11428 | -0.060003 | 0.45451 | 0.47608 | 4.5664 | 5.1151 | 6.4588 | 5.2084 | 4.3369 | 1.3614 | 16.2512 | 16.7235 | 16.7235
3260 | 1.1035 | 0.79314 | 0.86509 | 0.78615 | 4.151 | 6.6518 | 4.3058 | 5.919 | 3.6697 | 1.85 | 18.5718 | 13.9765 | 18.5718
3261 | -1.1044 | -0.41808 | 0.1347 | 0.33794 | 3.1964 | 4.0661 | 5.6625 | 4.9445 | 5.7078 | 1.3541 | 13.5611 | 15.9207 | 15.9207
3262 | -0.17076 | -0.72589 | 0.43221 | 0.23395 | 3.1531 | 5.047 | 4.9466 | 4.7433 | 3.2964 | 1.5828 | 14.5261 | 12.9788 | 14.5261
3263 | -0.89229 | -3.0486 | 0.18612 | 0.0011494 | 4.2895 | 4.2608 | 6.3134 | 4.0434 | 5.5667 | 1.5952 | 14.1889 | 17.7648 | 17.7648
3264 | -0.7947 | -0.34677 | 0.21339 | 0.36438 | 5.2761 | 4.3565 | 5.7868 | 4.9947 | 5.4857 | 2.3386 | 16.9658 | 18.8872 | 18.8872
3265 | -1.0558 | -0.58024 | 0.14552 | 0.28088 | 4.0826 | 4.1091 | 5.3397 | 4.8353 | 5.0294 | 1.6389 | 14.6658 | 16.0906 | 16.0906
3266 | 0.48122 | -0.010258 | 0.68482 | 0.49591 | 5.0548 | 5.864 | 6.295 | 5.2472 | 5.2327 | 1.9456 | 18.1115 | 18.528 | 18.528
3267 | 0.75094 | 0.19104 | 0.77366 | 0.57575 | 5.3043 | 6.2097 | 5.8239 | 5.4087 | 3.6544 | 2.3184 | 19.241 | 17.101 | 19.241
3268 | 0.39224 | 0.34452 | 0.65256 | 0.63477 | 3.9866 | 5.7499 | 6.0894 | 5.5358 | 3.9657 | 1.9485 | 17.2209 | 15.9902 | 17.2209
3269 | -1.5997 | -0.88052 | 0.054834 | 0.18929 | 3.5785 | 3.6864 | 5.1809 | 4.6522 | 3.4601 | 1.5609 | 13.478 | 13.7804 | 13.7804
3270 | 0.23999 | -0.79838 | 0.59483 | 0.21233 | 3.5585 | 5.5557 | 6.2459 | 4.6997 | 3.9245 | 2.2518 | 16.0658 | 15.9807 | 16.0658
3271 | -0.26545 | -0.41143 | 0.39533 | 0.34038 | 4.1482 | 4.9346 | 7.1758 | 4.9491 | 3.5653 | 1.9001 | 15.932 | 16.7894 | 16.7894
3272 | -1.7986 | -1.2771 | 0.036042 | 0.10078 | 5.28 | 3.5635 | 4.1017 | 4.4509 | 4.627 | 2.5827 | 15.8772 | 16.5915 | 16.5915
3273 | 1.1004 | 1.3666 | 0.86441 | 0.91412 | 3.7974 | 6.6479 | 6.4094 | 6.4061 | 3.879 | 1.9569 | 18.8083 | 16.0427 | 18.8083
3274 | -0.42123 | -0.91105 | 0.33679 | 0.18113 | 3.1882 | 4.755 | 4.6489 | 4.635 | 5.0853 | 1.4094 | 13.9877 | 14.3318 | 14.3318
3275 | 0.3413 | 0.75322 | 0.63356 | 0.77434 | 3.9934 | 5.6848 | 3.221 | 5.8845 | 4.6164 | 2.8152 | 18.3779 | 14.6459 | 18.3779
3276 | 1.7546 | 1.3679 | 0.96034 | 0.91434 | 2.7827 | 7.3964 | 4.9028 | 6.4072 | 4.3336 | 2.8802 | 19.4665 | 14.8993 | 19.4665
3277 | -0.11915 | -1.5689 | 0.45258 | 0.058335 | 4.7027 | 5.1092 | 5.2367 | 4.3326 | 4.0075 | 1.7671 | 15.9116 | 15.714 | 15.9116
3278 | 0.22215 | 0.26179 | 0.5879 | 0.60326 | 4.3282 | 5.5331 | 3.3956 | 5.4669 | 3.9483 | 1.5204 | 16.8486 | 13.1925 | 16.8486
3279 | -0.0039803 | -1.0623 | 0.49841 | 0.14404 | 3.4966 | 5.25 | 7.0616 | 4.5541 | 4.2949 | 2.0542 | 15.3549 | 16.9074 | 16.9074
3280 | 1.0189 | 0.37583 | 0.84588 | 0.64648 | 5.531 | 6.5474 | 6.7228 | 5.5621 | 5.8088 | 2.1849 | 19.8254 | 20.2475 | 20.2475
3281 | 0.75054 | 0.23581 | 0.77353 | 0.59321 | 3.7619 | 6.2091 | 5.6882 | 5.4455 | 4.7371 | 1.9503 | 17.3668 | 16.1374 | 17.3668
3282 | -0.26532 | -0.59759 | 0.39538 | 0.27506 | 4.7618 | 4.9347 | 6.6457 | 4.824 | 5.105 | 2.5856 | 17.1061 | 19.0981 | 19.0981
3283 | 1.2592 | 1.2633 | 0.89601 | 0.89677 | 4.6979 | 6.8401 | 6.1266 | 6.3203 | 5.509 | 1.6427 | 19.501 | 17.9762 | 19.501
3284 | 0.34704 | 0.63995 | 0.63572 | 0.7389 | 3.5376 | 5.6921 | 6.3116 | 5.787 | 3.342 | 2.5571 | 17.5739 | 15.7483 | 17.5739
3285 | -0.92138 | -0.99042 | 0.17843 | 0.16099 | 4.695 | 4.233 | 5.0492 | 4.5917 | 5.0435 | 1.7225 | 15.2422 | 16.5102 | 16.5102
3286 | 0.59666 | 0.44126 | 0.72463 | 0.67049 | 3.4488 | 6.0122 | 6.1326 | 5.6173 | 3.7222 | 2.3404 | 17.4187 | 15.644 | 17.4187
3287 | 0.95674 | 0.17706 | 0.83065 | 0.57027 | 3.7899 | 6.4699 | 5.456 | 5.3973 | 5.5785 | 1.327 | 16.984 | 16.1514 | 16.984
3288 | -1.2051 | -0.44697 | 0.11409 | 0.32745 | 4.9809 | 3.9804 | 6.7263 | 4.9245 | 5.7595 | 2.1934 | 16.0793 | 19.6602 | 19.6602
3289 | 0.26568 | -0.16999 | 0.60476 | 0.43251 | 4.891 | 5.5884 | 4.4389 | 5.1243 | 3.9645 | 2.5506 | 18.1543 | 15.845 | 18.1543
3290 | -0.057741 | 1.6634 | 0.47698 | 0.95189 | 4.2242 | 5.1839 | 7.1363 | 6.6441 | 4.3323 | 1.9625 | 18.0146 | 17.6553 | 18.0146
3291 | -1.1525 | -1.6594 | 0.12455 | 0.048517 | 4.0122 | 4.0246 | 7.214 | 4.3008 | 4.8722 | 2.1703 | 14.5079 | 18.2687 | 18.2687
3292 | 1.2332 | 1.3507 | 0.89125 | 0.91161 | 3.9745 | 6.809 | 6.0429 | 6.393 | 3.6043 | 1.5688 | 18.7453 | 15.1905 | 18.7453
3293 | -0.63684 | -0.12047 | 0.26211 | 0.45205 | 4.3742 | 4.5189 | 7.1037 | 5.1618 | 5.2886 | 2.6587 | 16.7136 | 19.4251 | 19.4251
3294 | 0.73516 | 0.34134 | 0.76888 | 0.63357 | 2.518 | 6.1895 | 3.6675 | 5.5332 | 4.9457 | 2.0821 | 16.3227 | 13.2132 | 16.3227
3295 | -1.004 | -1.784 | 0.15769 | 0.037208 | 4.4512 | 4.156 | 6.9468 | 4.2607 | 3.2392 | 1.8038 | 14.6716 | 16.441 | 16.441
3296 | 0.0091422 | -1.0306 | 0.50365 | 0.15136 | 4.5201 | 5.2662 | 4.4809 | 4.5705 | 6.2054 | 1.6241 | 15.9808 | 16.8304 | 16.8304
3297 | -0.085242 | -0.08809 | 0.46603 | 0.4649 | 3.1702 | 5.1503 | 5.5092 | 5.1867 | 4.2586 | 1.5745 | 15.0817 | 14.5124 | 15.0817
3298 | -0.39022 | -0.16893 | 0.34819 | 0.43293 | 4.3012 | 4.7902 | 5.2729 | 5.1251 | 3.8635 | 2.6386 | 16.8551 | 16.0763 | 16.8551
3299 | 0.62215 | 1.6507 | 0.73308 | 0.9506 | 4.4643 | 6.0449 | 5.9871 | 6.6342 | 4.0225 | 2.1852 | 19.3286 | 16.659 | 19.3286
3300 | -0.092987 | -0.54262 | 0.46296 | 0.2937 | 4.0125 | 5.1409 | 6.9257 | 4.86 | 3.3635 | 1.2543 | 15.2677 | 15.556 | 15.556
3301 | 1.8366 | 1.8955 | 0.96687 | 0.97099 | 3.8198 | 7.4808 | 5.9491 | 6.8191 | 5.3139 | 1.7034 | 19.8232 | 16.7863 | 19.8232
3302 | 1.2832 | 0.55144 | 0.90029 | 0.70933 | 3.156 | 6.8687 | 5.8195 | 5.7111 | 4.312 | 2.2327 | 17.9686 | 15.5202 | 17.9686
3303 | -0.36502 | -1.2857 | 0.35755 | 0.099272 | 2.8402 | 4.819 | 4.5369 | 4.4471 | 5.3022 | 2.0514 | 14.1577 | 14.7306 | 14.7306
3304 | 0.6792 | 0.22251 | 0.75149 | 0.58804 | 4.5126 | 6.118 | 7.0922 | 5.4345 | 4.4236 | 2.214 | 18.2791 | 18.2424 | 18.2791
3305 | 0.053378 | 0.3673 | 0.52128 | 0.6433 | 3.8164 | 5.321 | 5.5738 | 5.5549 | 3.5773 | 2.2691 | 16.9615 | 15.2366 | 16.9615
3306 | -1.08 | -0.44225 | 0.14007 | 0.32915 | 4.89 | 4.0876 | 6.1906 | 4.9278 | 3.5615 | 2.5025 | 16.4079 | 17.1447 | 17.1447
3307 | -0.036652 | -2.4295 | 0.48538 | 0.0075607 | 4.1173 | 5.2097 | 5.7763 | 4.1132 | 4.2542 | 2.0971 | 15.5373 | 16.245 | 16.245
3308 | -0.55049 | 0.072387 | 0.29099 | 0.52885 | 4.5936 | 4.6116 | 5.9747 | 5.3127 | 5.1726 | 2.156 | 16.6739 | 17.8969 | 17.8969
3309 | -0.093335 | 0.47515 | 0.46282 | 0.68266 | 4.2304 | 5.1405 | 6.3104 | 5.6461 | 4.087 | 2.7789 | 17.7958 | 17.4067 | 17.7958
3310 | -0.85127 | -0.61285 | 0.19731 | 0.26999 | 4.1474 | 4.3006 | 6.5327 | 4.8142 | 4.8818 | 1.5192 | 14.7813 | 17.081 | 17.081
3311 | -0.29049 | 0.4163 | 0.38572 | 0.6614 | 3.7271 | 4.9053 | 6.6063 | 5.5962 | 4.6843 | 1.8602 | 16.0888 | 16.8779 | 16.8779
3312 | 0.33776 | 1.5078 | 0.63223 | 0.9342 | 3.3583 | 5.6803 | 7.0773 | 6.5211 | 5.6506 | 2.2263 | 17.7859 | 18.3125 | 18.3125
3313 | 0.6442 | 0.81645 | 0.74028 | 0.79288 | 4.658 | 6.0732 | 5.8807 | 5.9391 | 4.9068 | 1.9735 | 18.6437 | 17.419 | 18.6437
3314 | -0.91598 | 0.72461 | 0.17984 | 0.76565 | 4.7264 | 4.2382 | 6.3739 | 5.8599 | 4.3363 | 2.3247 | 17.1492 | 17.7614 | 17.7614
3315 | -0.56039 | -0.8521 | 0.28761 | 0.19708 | 2.8198 | 4.6008 | 6.9684 | 4.6684 | 3.7608 | 1.722 | 13.811 | 15.2711 | 15.2711
3316 | -0.25366 | -0.56397 | 0.39988 | 0.28639 | 4.5183 | 4.9485 | 5.5581 | 4.8459 | 4.4909 | 1.8612 | 16.174 | 16.4286 | 16.4286
3317 | 1.0502 | -0.1317 | 0.8532 | 0.44761 | 2.8258 | 6.5862 | 6.7492 | 5.1533 | 3.9744 | 2.5087 | 17.074 | 16.0581 | 17.074
3318 | 0.36051 | 0.25604 | 0.64077 | 0.60104 | 5.0103 | 5.7093 | 7.6088 | 5.4622 | 5.6613 | 1.4586 | 17.6403 | 19.7389 | 19.7389
3319 | 1.0476 | -0.5684 | 0.85259 | 0.28488 | 4.7439 | 6.5829 | 6.8786 | 4.843 | 5.1664 | 2.1796 | 18.3494 | 18.9685 | 18.9685
3320 | -1.4885 | -1.5596 | 0.068307 | 0.059426 | 5.4095 | 3.7624 | 5.6189 | 4.336 | 5.8659 | 1.5657 | 15.0736 | 18.4601 | 18.4601
3321 | 0.65205 | 0.88266 | 0.74281 | 0.81129 | 4.2958 | 6.0832 | 4.1878 | 5.9961 | 4.3919 | 2.0538 | 18.4289 | 14.9293 | 18.4289
3322 | -0.67275 | -1.0493 | 0.25055 | 0.14703 | 4.9626 | 4.4812 | 6.9354 | 4.5608 | 4.0007 | 1.928 | 15.9326 | 17.8267 | 17.8267
3323 | -0.12034 | 0.5251 | 0.45211 | 0.70024 | 4.1919 | 5.1077 | 6.0363 | 5.6886 | 4.4447 | 2.407 | 17.3953 | 17.08 | 17.3953
3324 | 1.5666 | 1.6945 | 0.9414 | 0.95492 | 3.6561 | 7.1941 | 4.8372 | 6.6682 | 3.4783 | 1.6454 | 19.1637 | 13.617 | 19.1637
3325 | 0.6635 | 0.35398 | 0.74649 | 0.63832 | 4.5568 | 6.0979 | 6.3122 | 5.5438 | 4.5478 | 1.7857 | 17.9841 | 17.2025 | 17.9841
3326 | -0.31465 | -1.3043 | 0.37651 | 0.096067 | 4.495 | 4.8771 | 6.8182 | 4.4389 | 4.551 | 1.5199 | 15.3309 | 17.3841 | 17.3841
3327 | 2.1605 | -0.04471 | 0.98463 | 0.48217 | 5.4269 | 7.7898 | 4.0417 | 5.2202 | 4.0151 | 2.3556 | 20.7925 | 15.8392 | 20.7925
3328 | 1.3732 | 0.37088 | 0.91515 | 0.64464 | 4.269 | 6.9744 | 3.747 | 5.5579 | 3.4977 | 1.8031 | 18.6045 | 13.3169 | 18.6045
3329 | 0.32801 | -0.85884 | 0.62855 | 0.19522 | 4.1677 | 5.6678 | 6.9333 | 4.6645 | 3.1221 | 2.0641 | 16.5641 | 16.2872 | 16.5641
3330 | -1.0631 | -0.83803 | 0.14388 | 0.20101 | 3.5362 | 4.1026 | 5.026 | 4.6765 | 3.5037 | 2.0926 | 14.408 | 14.1585 | 14.408
3331 | 1.2515 | 1.5161 | 0.89463 | 0.93525 | 5.6676 | 6.831 | 5.9764 | 6.5277 | 3.3984 | 2.5025 | 21.5288 | 17.545 | 21.5288
3332 | -0.23583 | 0.052525 | 0.40678 | 0.52094 | 3.0424 | 4.9695 | 3.4562 | 5.2968 | 4.3997 | 1.6327 | 14.9413 | 12.5309 | 14.9413
3333 | 0.19881 | 0.082417 | 0.5788 | 0.53284 | 3.3914 | 5.5036 | 6.5179 | 5.3207 | 4.7691 | 2.1659 | 16.3816 | 16.8444 | 16.8444
3334 | 0.038665 | 0.28323 | 0.51542 | 0.6115 | 4.8072 | 5.3028 | 6.4878 | 5.4847 | 3.5596 | 2.5504 | 18.1451 | 17.405 | 18.1451
3335 | -0.40576 | -0.061457 | 0.34246 | 0.4755 | 5.2327 | 4.7725 | 7.5873 | 5.2072 | 4.3654 | 2.1026 | 17.315 | 19.288 | 19.288
3336 | 0.77054 | 1.112 | 0.77951 | 0.86693 | 4.2755 | 6.2346 | 5.0583 | 6.1926 | 5.482 | 1.774 | 18.4768 | 16.5898 | 18.4768
3337 | 0.17964 | -0.32317 | 0.57128 | 0.37328 | 5.1669 | 5.4793 | 7.2356 | 5.0116 | 3.3509 | 2.0623 | 17.7201 | 17.8158 | 17.8158
3338 | 0.18171 | 0.35119 | 0.5721 | 0.63728 | 4.1193 | 5.4819 | 6.6993 | 5.5414 | 4.6651 | 2.0501 | 17.1928 | 17.5339 | 17.5339
3339 | -0.32424 | 0.81336 | 0.37288 | 0.792 | 4.2444 | 4.866 | 7.6985 | 5.9364 | 4.3634 | 2.2993 | 17.3461 | 18.6056 | 18.6056
3340 | -0.040831 | -1.3118 | 0.48372 | 0.094797 | 3.9083 | 5.2046 | 7.7745 | 4.4356 | 3.8887 | 1.4861 | 15.0346 | 17.0576 | 17.0576
3341 | 0.83632 | 1.8035 | 0.79851 | 0.96434 | 4.6742 | 6.3182 | 4.9751 | 6.751 | 3.6633 | 2.4011 | 20.1445 | 15.7136 | 20.1445
3342 | -1.1775 | -0.56014 | 0.11949 | 0.28769 | 3.6524 | 4.0034 | 5.1725 | 4.8484 | 4.062 | 2.0309 | 14.5352 | 14.9178 | 14.9178
3343 | -0.13962 | -0.32051 | 0.44448 | 0.37429 | 4.1823 | 5.0844 | 4.6682 | 5.0135 | 5.3137 | 1.5281 | 15.8083 | 15.6924 | 15.8083
3344 | 2.6192 | 0.68111 | 0.99559 | 0.7521 | 3.2044 | 8.1563 | 6.6652 | 5.8224 | 4.0607 | 2.5091 | 19.6923 | 16.4395 | 19.6923
3345 | 2.352 | 0.91149 | 0.99066 | 0.81898 | 3.4358 | 7.9532 | 5.9464 | 6.021 | 5.4329 | 1.7318 | 19.1418 | 16.547 | 19.1418
3346 | 0.18135 | 1.9138 | 0.57196 | 0.97218 | 2.5754 | 5.4815 | 5.4897 | 6.8324 | 4.9895 | 1.9385 | 16.8279 | 14.9932 | 16.8279
3347 | -0.20778 | 0.12336 | 0.4177 | 0.54909 | 4.165 | 5.0028 | 3.3947 | 5.3537 | 4.4081 | 2.5657 | 17.0871 | 14.5334 | 17.0871
3348 | -1.8296 | -1.7096 | 0.033656 | 0.043667 | 5.0558 | 3.5458 | 4.7664 | 4.2841 | 5.2739 | 2.2874 | 15.1732 | 17.3835 | 17.3835
3349 | -0.34221 | -0.94178 | 0.3661 | 0.17315 | 4.4085 | 4.8452 | 4.2734 | 4.618 | 4.295 | 1.4916 | 15.3633 | 14.4685 | 15.3633
3350 | -0.31122 | -0.04928 | 0.37782 | 0.48035 | 3.8457 | 4.8811 | 7.0055 | 5.2167 | 3.8037 | 1.9318 | 15.8753 | 16.5867 | 16.5867
3351 | -1.1505 | -1.0124 | 0.12496 | 0.15567 | 2.8744 | 4.0263 | 7.1111 | 4.58 | 3.2571 | 1.9139 | 13.3946 | 15.1564 | 15.1564
3352 | 1.202 | 0.96054 | 0.88532 | 0.83161 | 4.6837 | 6.7716 | 4.8424 | 6.0631 | 4.6181 | 1.6114 | 19.1299 | 15.7557 | 19.1299
3353 | 0.86917 | -0.18435 | 0.80762 | 0.42687 | 2.8005 | 6.3597 | 6.6371 | 5.1135 | 5.6306 | 1.8906 | 16.1643 | 16.9588 | 16.9588
3354 | 0.089863 | 0.91268 | 0.5358 | 0.8193 | 4.719 | 5.3665 | 5.4792 | 6.022 | 3.206 | 2.2076 | 18.3151 | 15.6118 | 18.3151
3355 | 0.72574 | 0.048857 | 0.766 | 0.51948 | 3.8953 | 6.1775 | 7.5078 | 5.2939 | 3.4106 | 1.7959 | 17.1626 | 16.6095 | 17.1626
3356 | 0.95814 | 0.013341 | 0.831 | 0.50532 | 3.5906 | 6.4716 | 4.3658 | 5.2658 | 4.0618 | 1.5124 | 16.8404 | 13.5306 | 16.8404
3357 | 0.92601 | 1.0997 | 0.82278 | 0.86426 | 2.1589 | 6.4313 | 6.1267 | 6.1822 | 4.5793 | 2.4082 | 17.1805 | 15.273 | 17.1805
3358 | 0.77419 | 0.69721 | 0.78059 | 0.75716 | 3.4281 | 6.2393 | 6.5645 | 5.8363 | 3.485 | 1.6191 | 17.1228 | 15.0968 | 17.1228
3359 | 0.69486 | -0.13955 | 0.75643 | 0.44451 | 5.5919 | 6.138 | 3.6851 | 5.1473 | 4.447 | 2.257 | 19.1343 | 15.9811 | 19.1343
3360 | -1.0488 | -0.77565 | 0.14713 | 0.21898 | 3.4222 | 4.1154 | 4.4305 | 4.7132 | 3.9317 | 2.1248 | 14.3755 | 13.9092 | 14.3755
3361 | 0.83227 | 0.030186 | 0.79737 | 0.51204 | 4.9538 | 6.3131 | 4.9778 | 5.2791 | 4.3104 | 1.364 | 17.9099 | 15.6059 | 17.9099
3362 | 0.71328 | 0.010643 | 0.76216 | 0.50425 | 3.6193 | 6.1616 | 6.6433 | 5.2636 | 3.412 | 1.7918 | 16.8363 | 15.4664 | 16.8363
3363 | -0.6944 | 0.85856 | 0.24371 | 0.80471 | 3.6056 | 4.4586 | 7.2043 | 5.9754 | 4.024 | 2.0897 | 16.1293 | 16.9236 | 16.9236
3364 | 0.16937 | 0.18681 | 0.56725 | 0.5741 | 3.3612 | 5.4664 | 6.8192 | 5.4052 | 3.606 | 2.3966 | 16.6295 | 16.183 | 16.6295
3365 | 0.53568 | -0.58575 | 0.70391 | 0.27902 | 4.1818 | 5.934 | 5.3574 | 4.8317 | 5.2863 | 2.3648 | 17.3122 | 17.1903 | 17.3122
3366 | 0.52424 | -1.2511 | 0.69994 | 0.10545 | 3.3489 | 5.9193 | 2.765 | 4.4627 | 3.4193 | 2.1905 | 15.9214 | 11.7237 | 15.9214
3367 | 0.075252 | 0.3602 | 0.52999 | 0.64065 | 3.5893 | 5.3483 | 6.4275 | 5.549 | 4.1186 | 1.6559 | 16.1424 | 15.7913 | 16.1424
3368 | 0.63987 | -0.58052 | 0.73887 | 0.28078 | 3.3785 | 6.0676 | 6.7614 | 4.8351 | 4.5458 | 1.8349 | 16.1161 | 16.5206 | 16.5206
3369 | 2.0116 | 2.3458 | 0.97787 | 0.99051 | 3.4821 | 7.6527 | 7.0896 | 7.1238 | 5.6929 | 2.3037 | 20.5623 | 18.5683 | 20.5623
3370 | -0.15689 | 0.44399 | 0.43766 | 0.67147 | 4.1587 | 5.0636 | 6.7062 | 5.6196 | 5.4815 | 1.437 | 16.2789 | 17.7834 | 17.7834
3371 | 0.53249 | 2.1869 | 0.70281 | 0.98562 | 3.3686 | 5.9299 | 4.1666 | 7.022 | 5.1137 | 2.5519 | 18.8723 | 15.2009 | 18.8723
3372 | 0.0832 | -0.64918 | 0.53315 | 0.25811 | 3.0769 | 5.3582 | 5.6968 | 4.791 | 3.6061 | 1.5684 | 14.7945 | 13.9482 | 14.7945
3373 | -1.9084 | -0.4181 | 0.028172 | 0.33794 | 4.8637 | 3.5027 | 5.6657 | 4.9445 | 4.2241 | 2.2311 | 15.542 | 16.9846 | 16.9846
3374 | 0.77574 | 1.4342 | 0.78105 | 0.92425 | 3.8415 | 6.2412 | 4.9545 | 6.4615 | 3.8635 | 1.9304 | 18.4746 | 14.5898 | 18.4746
3375 | -1.3338 | -0.93551 | 0.091128 | 0.17476 | 4.4763 | 3.8771 | 5.4665 | 4.6215 | 4.1043 | 1.7321 | 14.7069 | 15.7792 | 15.7792
3376 | 0.062467 | -0.37653 | 0.5249 | 0.35326 | 4.8989 | 5.3324 | 5.4944 | 4.9736 | 3.5845 | 2.132 | 17.3368 | 16.1097 | 17.3368
3377 | 0.40712 | 0.27485 | 0.65804 | 0.60829 | 3.2338 | 5.769 | 5.0036 | 5.4778 | 3.522 | 2.2362 | 16.7168 | 13.9957 | 16.7168
3378 | 0.24152 | 1.2055 | 0.59542 | 0.886 | 5.0155 | 5.5577 | 6.27 | 6.2718 | 3.3811 | 1.3506 | 18.1956 | 16.0171 | 18.1956
3379 | 0.4262 | 1.5543 | 0.66502 | 0.93994 | 3.8557 | 5.7935 | 6.8746 | 6.5582 | 3.6574 | 1.9735 | 18.1808 | 16.3611 | 18.1808
3380 | 0.76192 | -0.36257 | 0.77695 | 0.35846 | 2.8588 | 6.2237 | 4.8888 | 4.9835 | 4.1346 | 1.6656 | 15.7316 | 13.5478 | 15.7316
3381 | -1.2839 | -1.1171 | 0.099594 | 0.13198 | 4.1019 | 3.9163 | 5.1366 | 4.5265 | 3.8968 | 1.9292 | 14.4739 | 15.0644 | 15.0644
3382 | -1.0781 | -1.2016 | 0.14049 | 0.11476 | 4.7728 | 4.0893 | 5.9389 | 4.4856 | 4.8387 | 1.8271 | 15.1748 | 17.3775 | 17.3775
3383 | -0.42805 | 0.044405 | 0.33431 | 0.51771 | 4.6245 | 4.7473 | 2.9213 | 5.2904 | 5.5992 | 2.0188 | 16.6809 | 15.1638 | 16.6809
3384 | 2.5818 | 2.6195 | 0.99509 | 0.9956 | 2.8813 | 8.1296 | 6.6925 | 7.2838 | 3.5777 | 1.6369 | 19.9316 | 14.7884 | 19.9316
3385 | -1.2634 | -0.83894 | 0.10321 | 0.20075 | 4.0788 | 3.9327 | 6.9518 | 4.676 | 4.6885 | 1.2539 | 13.9414 | 16.9731 | 16.9731
3386 | 0.28446 | 0.21799 | 0.61197 | 0.58628 | 4.8744 | 5.6123 | 6.0361 | 5.4308 | 3.5059 | 1.9918 | 17.9093 | 16.4082 | 17.9093
3387 | -2.0738 | -0.53546 | 0.01905 | 0.29617 | 4.1431 | 3.4202 | 6.3743 | 4.8647 | 4.3451 | 2.1137 | 14.5418 | 16.9761 | 16.9761
3388 | 0.29529 | 0.13322 | 0.61611 | 0.55299 | 4.1659 | 5.6261 | 5.1116 | 5.3616 | 3.9413 | 2.2125 | 17.3662 | 15.4314 | 17.3662
3389 | -0.61376 | 0.62849 | 0.26969 | 0.73516 | 5.1638 | 4.5434 | 7.2784 | 5.7772 | 4.6293 | 1.8898 | 17.3742 | 18.9613 | 18.9613
3390 | 0.93377 | 0.64544 | 0.82479 | 0.74068 | 4.9352 | 6.4411 | 5.6728 | 5.7917 | 4.2739 | 2.1709 | 19.339 | 17.0529 | 19.339
3391 | 0.051007 | 0.74864 | 0.52034 | 0.77296 | 5.4055 | 5.3181 | 6.6731 | 5.8806 | 3.5243 | 2.5285 | 19.1326 | 18.1313 | 19.1326
3392 | -0.82486 | -0.47927 | 0.20473 | 0.31587 | 3.588 | 4.3265 | 4.857 | 4.9025 | 4.9314 | 2.5057 | 15.3227 | 15.882 | 15.882
3393 | -0.28582 | -0.10793 | 0.38751 | 0.45702 | 4.8572 | 4.9107 | 5.9299 | 5.1714 | 5.792 | 1.9885 | 16.9279 | 18.5676 | 18.5676
3394 | 1.0888 | 0.80517 | 0.86187 | 0.78964 | 4.1227 | 6.6337 | 7.1169 | 5.9293 | 4.0085 | 2.2557 | 18.9414 | 17.5038 | 18.9414
3395 | 0.65301 | 1.2633 | 0.74313 | 0.89676 | 3.7393 | 6.0845 | 4.4279 | 6.3203 | 4.4208 | 2.4397 | 18.5838 | 15.0276 | 18.5838
3396 | 0.71765 | 0.94894 | 0.76351 | 0.82867 | 4.2961 | 6.1672 | 3.9562 | 6.0532 | 4.4669 | 2.171 | 18.6875 | 14.8903 | 18.6875
3397 | 0.040086 | -0.30995 | 0.51599 | 0.3783 | 5.3135 | 5.3045 | 3.9908 | 5.0211 | 3.3896 | 2.4752 | 18.1144 | 15.1692 | 18.1144
3398 | -0.46099 | 0.35693 | 0.3224 | 0.63943 | 5.1308 | 4.7103 | 5.0177 | 5.5462 | 4.4055 | 2.2615 | 17.6488 | 16.8155 | 17.6488
3399 | 0.35564 | -0.62029 | 0.63895 | 0.26753 | 2.9072 | 5.7031 | 4.9386 | 4.8094 | 3.8562 | 1.7352 | 15.1549 | 13.4372 | 15.1549
3400 | -1.8629 | 0.22408 | 0.031241 | 0.58865 | 3.9548 | 3.5273 | 5.3314 | 5.4358 | 3.3354 | 1.7754 | 14.6934 | 14.397 | 14.6934
3401 | -0.69414 | 0.90186 | 0.2438 | 0.81643 | 4.6718 | 4.4589 | 7.7409 | 6.0127 | 3.8985 | 2.2336 | 17.377 | 18.5448 | 18.5448
3402 | -1.135 | -0.33323 | 0.12818 | 0.36948 | 3.6241 | 4.0396 | 5.4206 | 5.0043 | 4.2995 | 2.2867 | 14.9547 | 15.6309 | 15.6309
3403 | 0.062738 | -0.14129 | 0.52501 | 0.44382 | 3.4422 | 5.3327 | 7.1023 | 5.146 | 4.0847 | 2.0942 | 16.0151 | 16.7234 | 16.7234
3404 | -1.3691 | -0.77512 | 0.08549 | 0.21913 | 3.5335 | 3.85 | 6.7485 | 4.7135 | 4.1738 | 1.2788 | 13.3758 | 15.7346 | 15.7346
3405 | -1.6109 | -0.034767 | 0.053596 | 0.48613 | 3.5343 | 3.679 | 4.6616 | 5.228 | 4.1937 | 1.7516 | 14.1928 | 14.1413 | 14.1928
3406 | -0.086449 | 0.55589 | 0.46555 | 0.71086 | 3.9367 | 5.1489 | 6.0067 | 5.7149 | 5.2117 | 1.2779 | 16.0784 | 16.4331 | 16.4331
3407 | -1.5105 | -0.77677 | 0.065457 | 0.21865 | 2.4574 | 3.7469 | 5.0233 | 4.7125 | 3.7579 | 2.4117 | 13.3286 | 13.6503 | 13.6503
3408 | -0.59651 | -2.1975 | 0.27542 | 0.013993 | 3.5975 | 4.5619 | 2.9662 | 4.1556 | 4.2823 | 1.7364 | 14.0513 | 12.5824 | 14.0513
3409 | 0.87853 | -0.26308 | 0.81017 | 0.39624 | 3.0631 | 6.3716 | 6.8853 | 5.0551 | 4.8246 | 2.1561 | 16.6459 | 16.9291 | 16.9291
3410 | 0.0068992 | 0.016559 | 0.50275 | 0.50661 | 3.2307 | 5.2634 | 5.3515 | 5.2683 | 5.0033 | 2.3087 | 16.0711 | 15.8942 | 16.0711
3411 | -2.0664 | -1.9961 | 0.019397 | 0.022963 | 4.4002 | 3.4237 | 5.5381 | 4.2017 | 3.2902 | 1.3177 | 13.3434 | 14.5463 | 14.5463
3412 | -1.3967 | -2.0053 | 0.081251 | 0.022466 | 4.5671 | 3.8292 | 6.2989 | 4.1994 | 5.686 | 1.5377 | 14.1335 | 18.0898 | 18.0898
3413 | -1.1519 | -0.088992 | 0.12469 | 0.46454 | 4.0777 | 4.0252 | 5.6913 | 5.186 | 4.1251 | 1.4807 | 14.7696 | 15.3748 | 15.3748
3414 | 0.64003 | 1.5099 | 0.73892 | 0.93446 | 3.2838 | 6.0678 | 6.6932 | 6.5227 | 3.4331 | 1.5643 | 17.4386 | 14.9743 | 17.4386
3415 | 1.8874 | 1.3515 | 0.97044 | 0.91172 | 2.6909 | 7.5319 | 4.9404 | 6.3936 | 4.9564 | 1.985 | 18.6014 | 14.5727 | 18.6014
3416 | -0.22472 | 0.51331 | 0.4111 | 0.69613 | 4.5087 | 4.9827 | 2.8549 | 5.6786 | 4.4396 | 2.7604 | 17.9304 | 14.5637 | 17.9304
3417 | -1.1629 | -0.83401 | 0.12243 | 0.20214 | 4.5875 | 4.0158 | 3.8101 | 4.6788 | 5.0154 | 2.4671 | 15.7493 | 15.8801 | 15.8801
3418 | -0.5456 | -0.019383 | 0.29267 | 0.49227 | 2.8564 | 4.6169 | 6.7841 | 5.24 | 4.6125 | 1.8621 | 14.5755 | 16.1152 | 16.1152
3419 | -1.4455 | -0.76983 | 0.074164 | 0.2207 | 4.7435 | 3.7933 | 5.5167 | 4.7167 | 5.0819 | 2.4204 | 15.6738 | 17.7625 | 17.7625
3420 | -0.39642 | 0.25584 | 0.3459 | 0.60096 | 4.5982 | 4.7831 | 4.3784 | 5.462 | 4.1709 | 2.103 | 16.9463 | 15.2505 | 16.9463
3421 | -0.76737 | 0.18479 | 0.22143 | 0.5733 | 3.6725 | 4.3839 | 7.3305 | 5.4036 | 3.3234 | 2.3906 | 15.8507 | 16.7171 | 16.7171
3422 | -0.16766 | -1.2309 | 0.43342 | 0.10918 | 3.8092 | 5.0507 | 5.8623 | 4.472 | 3.5693 | 1.7214 | 15.0532 | 14.9622 | 15.0532
3423 | -0.5906 | -1.6838 | 0.27739 | 0.046111 | 4.2499 | 4.5682 | 5.4725 | 4.2926 | 4.9938 | 2.0343 | 15.145 | 16.7506 | 16.7506
3424 | -0.38309 | 0.70501 | 0.35083 | 0.7596 | 5.3184 | 4.7983 | 7.0343 | 5.843 | 4.1134 | 2.1766 | 18.1363 | 18.6426 | 18.6426
3425 | -0.69028 | -0.41305 | 0.24501 | 0.33979 | 3.4446 | 4.4629 | 5.6681 | 4.948 | 3.6993 | 1.9024 | 14.7579 | 14.7144 | 14.7579
3426 | 1.4159 | 2.2158 | 0.9216 | 0.98665 | 2.6562 | 7.0239 | 5.6212 | 7.041 | 4.8692 | 2.1117 | 18.8328 | 15.2583 | 18.8328
3427 | 1.6073 | 0.54228 | 0.94601 | 0.70619 | 4.7153 | 7.2389 | 4.8405 | 5.7033 | 5.1333 | 2.5598 | 20.2174 | 17.2489 | 20.2174
3428 | 0.40516 | -0.77479 | 0.65732 | 0.21923 | 4.5338 | 5.7665 | 4.7025 | 4.7137 | 5.261 | 1.8599 | 16.8739 | 16.3571 | 16.8739
3429 | 0.13094 | -0.48077 | 0.55209 | 0.31534 | 4.5388 | 5.418 | 7.621 | 4.9015 | 3.8844 | 1.6714 | 16.5296 | 17.7156 | 17.7156
3430 | -0.2047 | -0.46385 | 0.4189 | 0.32138 | 3.9398 | 5.0064 | 4.8818 | 4.913 | 4.3774 | 2.5238 | 16.383 | 15.7229 | 16.383
3431 | 1.0766 | 1.396 | 0.85917 | 0.91864 | 5.0006 | 6.6187 | 5.4086 | 6.4302 | 4.1787 | 2.1534 | 20.2029 | 16.7413 | 20.2029
3432 | -2.0556 | -1.5268 | 0.019911 | 0.063403 | 4.6507 | 3.4288 | 6.2858 | 4.3481 | 3.3015 | 1.5127 | 13.9403 | 15.7506 | 15.7506
3433 | -0.19794 | -0.42432 | 0.42154 | 0.33567 | 3.5944 | 5.0145 | 7.5503 | 4.9402 | 4.7756 | 2.0637 | 15.6128 | 17.984 | 17.984
3434 | -0.61662 | 0.31758 | 0.26874 | 0.6246 | 3.5124 | 4.5404 | 5.6205 | 5.5133 | 5.2867 | 1.4883 | 15.0544 | 15.9079 | 15.9079
3435 | -2.6019 | -0.25484 | 0.0046355 | 0.39942 | 3.3194 | 3.2232 | 3.5232 | 5.0612 | 5.1052 | 2.773 | 14.3768 | 14.7208 | 14.7208
3436 | -0.81185 | 0.30801 | 0.20844 | 0.62096 | 3.4647 | 4.3394 | 4.5416 | 5.5053 | 5.0085 | 1.5168 | 14.8262 | 14.5316 | 14.8262
3437 | 1.3985 | 0.73012 | 0.91902 | 0.76734 | 3.9943 | 7.0038 | 7.4149 | 5.8646 | 3.8211 | 2.5161 | 19.3789 | 17.7465 | 19.3789
3438 | -0.92661 | -0.51615 | 0.17706 | 0.30287 | 3.9676 | 4.2281 | 3.9549 | 4.8776 | 5.0157 | 2.2548 | 15.3281 | 15.1929 | 15.3281
3439 | -0.33686 | 1.3822 | 0.36811 | 0.91655 | 5.3146 | 4.8514 | 2.9947 | 6.4189 | 5.8927 | 2.6776 | 19.2625 | 16.8796 | 19.2625
3440 | -0.79212 | -0.64788 | 0.21415 | 0.25853 | 2.9398 | 4.359 | 5.7213 | 4.7918 | 4.0693 | 2.1321 | 14.2227 | 14.8625 | 14.8625
3441 | -0.029384 | 0.042384 | 0.48828 | 0.5169 | 4.7721 | 5.2187 | 6.6913 | 5.2888 | 3.8494 | 2.7563 | 18.0358 | 18.0691 | 18.0691
3442 | -0.46815 | -1.077 | 0.31984 | 0.14074 | 4.3913 | 4.7023 | 6.4079 | 4.5466 | 3.6512 | 1.8551 | 15.4954 | 16.3056 | 16.3056
3443 | 0.88191 | 0.21556 | 0.81109 | 0.58534 | 3.3154 | 6.3758 | 6.4994 | 5.4288 | 4.7737 | 2.3401 | 17.4601 | 16.9286 | 17.4601
3444 | -0.78451 | 0.33906 | 0.21637 | 0.63272 | 4.0703 | 4.3667 | 4.9573 | 5.5313 | 3.4064 | 2.1579 | 16.1262 | 14.592 | 16.1262
3445 | 1.1289 | -0.036692 | 0.87054 | 0.48537 | 4.2299 | 6.6829 | 5.4983 | 5.2265 | 4.3609 | 1.5428 | 17.682 | 15.6318 | 17.682
3446 | -0.48969 | 0.29589 | 0.31218 | 0.61634 | 5.5011 | 4.6784 | 5.886 | 5.4952 | 4.4026 | 1.6691 | 17.3438 | 17.4588 | 17.4588
3447 | 1.0779 | 1.7539 | 0.85947 | 0.96028 | 2.8479 | 6.6204 | 5.5206 | 6.7136 | 5.6689 | 2.3173 | 18.4992 | 16.3547 | 18.4992
3448 | 0.60421 | 1.1979 | 0.72715 | 0.88453 | 4.1647 | 6.0219 | 3.4679 | 6.2654 | 4.4056 | 2.3405 | 18.7926 | 14.3788 | 18.7926
3449 | 0.40747 | 1.125 | 0.65817 | 0.8697 | 4.4477 | 5.7694 | 6.7963 | 6.2037 | 4.481 | 2.3391 | 18.7599 | 18.0641 | 18.7599
3450 | -2.0385 | -0.57555 | 0.020751 | 0.28246 | 3.8966 | 3.4369 | 6.5022 | 4.8383 | 3.8786 | 1.9164 | 14.0883 | 16.1939 | 16.1939
3451 | -0.1474 | -0.40549 | 0.44141 | 0.34256 | 4.415 | 5.0751 | 4.6879 | 4.9533 | 3.1849 | 2.3345 | 16.7778 | 14.6222 | 16.7778
3452 | -0.35325 | -1.1241 | 0.36195 | 0.13049 | 3.9567 | 4.8325 | 5.7524 | 4.523 | 3.6429 | 2.0191 | 15.3313 | 15.3712 | 15.3712
3453 | -1.3475 | -2.4011 | 0.088909 | 0.0081734 | 4.5282 | 3.8665 | 4.9054 | 4.1178 | 3.4356 | 1.6944 | 14.2069 | 14.5636 | 14.5636
3454 | -0.67194 | 0.62994 | 0.25081 | 0.73563 | 4.2888 | 4.482 | 4.9645 | 5.7784 | 3.7637 | 2.2503 | 16.7995 | 15.2674 | 16.7995
3455 | 0.46492 | 0.53454 | 0.679 | 0.70352 | 4.1184 | 5.8431 | 5.8557 | 5.6967 | 4.3547 | 1.6682 | 17.3264 | 15.997 | 17.3264
3456 | 0.39194 | 0.33282 | 0.65245 | 0.63036 | 4.0551 | 5.7496 | 4.9876 | 5.526 | 3.2872 | 2.1192 | 17.4499 | 14.4491 | 17.4499
3457 | -0.75275 | 0.38672 | 0.2258 | 0.65052 | 3.656 | 4.3987 | 7.5009 | 5.5713 | 3.2356 | 2.4036 | 16.0296 | 16.7961 | 16.7961
3458 | -0.2305 | 1.034 | 0.40885 | 0.84944 | 4.6212 | 4.9758 | 5.3819 | 6.1261 | 3.9711 | 1.9934 | 17.7166 | 15.9677 | 17.7166
3459 | 0.11309 | 0.55204 | 0.54502 | 0.70954 | 4.4424 | 5.3956 | 6.983 | 5.7116 | 4.4503 | 2.1372 | 17.6868 | 18.0129 | 18.0129
3460 | -1.6188 | -1.3249 | 0.052746 | 0.092598 | 4.5892 | 3.6738 | 7.3331 | 4.4298 | 5.9624 | 2.2615 | 14.9544 | 20.1463 | 20.1463
3461 | 0.42672 | -0.69249 | 0.66521 | 0.24432 | 5.4386 | 5.7941 | 4.4379 | 4.7638 | 4.9578 | 1.8078 | 17.8044 | 16.6421 | 17.8044
3462 | -0.16451 | -0.24028 | 0.43466 | 0.40506 | 4.2704 | 5.0545 | 5.5658 | 5.0719 | 3.5359 | 1.7946 | 16.1913 | 15.1666 | 16.1913
3463 | -0.71794 | -0.5931 | 0.2364 | 0.27656 | 3.625 | 4.4343 | 6.8696 | 4.8269 | 3.8963 | 1.4906 | 14.3768 | 15.8815 | 15.8815
3464 | 0.17347 | 1.2627 | 0.56886 | 0.89665 | 2.9534 | 5.4715 | 5.8186 | 6.3198 | 4.2171 | 1.7621 | 16.5069 | 14.7513 | 16.5069
3465 | 0.78842 | 0.2982 | 0.78477 | 0.61722 | 3.2694 | 6.2574 | 5.4423 | 5.4971 | 3.5105 | 1.1961 | 16.22 | 13.4182 | 16.22
3466 | -0.9732 | -0.62938 | 0.16523 | 0.26455 | 5.0322 | 4.1844 | 3.468 | 4.8036 | 3.7977 | 1.9539 | 15.974 | 14.2518 | 15.974
3467 | -0.26427 | -0.79758 | 0.39579 | 0.21256 | 4.7487 | 4.936 | 6.5924 | 4.7002 | 3.1418 | 2.0099 | 16.3947 | 16.4928 | 16.4928
3468 | -0.80882 | -0.04606 | 0.20931 | 0.48163 | 4.9024 | 4.3424 | 5.9317 | 5.2192 | 4.4953 | 2.717 | 17.1809 | 18.0463 | 18.0463
3469 | -1.0727 | -2.0356 | 0.14169 | 0.020896 | 2.9079 | 4.0941 | 6.4315 | 4.192 | 4.5149 | 2.5636 | 13.7575 | 16.4179 | 16.4179
3470 | 0.84912 | 0.9004 | 0.80209 | 0.81605 | 3.4982 | 6.3344 | 4.5561 | 6.0114 | 5.3162 | 1.6883 | 17.5323 | 15.0587 | 17.5323
3471 | 0.025243 | -0.52424 | 0.51007 | 0.30006 | 4.1205 | 5.2861 | 5.8087 | 4.8722 | 3.7094 | 1.1324 | 15.4112 | 14.7709 | 15.4112
3472 | -0.77419 | -0.064631 | 0.21941 | 0.47423 | 4.5191 | 4.377 | 5.2071 | 5.2048 | 3.4477 | 1.3868 | 15.4877 | 14.5608 | 15.4877
3473 | 1.1341 | 1.3976 | 0.87163 | 0.91888 | 3.1216 | 6.6892 | 3.96 | 6.4316 | 4.9152 | 2.1885 | 18.4309 | 14.1853 | 18.4309
3474 | -0.13599 | -0.11843 | 0.44592 | 0.45286 | 5.2808 | 5.0888 | 7.3961 | 5.1634 | 4.5783 | 1.7575 | 17.2905 | 19.0127 | 19.0127
3475 | 0.0040867 | -0.16122 | 0.50163 | 0.43596 | 3.5858 | 5.2599 | 5.6079 | 5.1309 | 4.3137 | 2.0471 | 16.0238 | 15.5546 | 16.0238
3476 | -0.25007 | 0.18445 | 0.40126 | 0.57317 | 4.8148 | 4.9527 | 5.2635 | 5.4033 | 6.8005 | 1.8564 | 17.0271 | 18.7351 | 18.7351
3477 | 0.64475 | 0.35105 | 0.74046 | 0.63722 | 3.5898 | 6.0739 | 6.9682 | 5.5413 | 4.4679 | 1.4565 | 16.6615 | 16.4824 | 16.6615
3478 | -1.224 | -0.87759 | 0.11047 | 0.19008 | 4.4775 | 3.9648 | 5.3357 | 4.6538 | 5.1886 | 2.1404 | 15.2366 | 17.1422 | 17.1422
3479 | 1.075 | 1.0787 | 0.85882 | 0.85965 | 3.5531 | 6.6168 | 7.588 | 6.1643 | 4.5947 | 2.3982 | 18.7324 | 18.134 | 18.7324
3480 | -0.12074 | -0.74368 | 0.45195 | 0.22854 | 4.4032 | 5.1072 | 4.7365 | 4.7324 | 4.797 | 1.5397 | 15.7826 | 15.4764 | 15.7826
3481 | -0.011701 | -0.25497 | 0.49533 | 0.39937 | 4.6634 | 5.2404 | 4.3418 | 5.0611 | 4.296 | 1.554 | 16.5189 | 14.8552 | 16.5189
3482 | -0.1417 | -0.43863 | 0.44366 | 0.33046 | 4.9067 | 5.0819 | 4.2281 | 4.9303 | 4.0554 | 2.3142 | 17.233 | 15.5042 | 17.233
3483 | -0.031207 | 0.54428 | 0.48755 | 0.70687 | 4.9417 | 5.2164 | 7.2308 | 5.705 | 3.9186 | 1.3216 | 17.1847 | 17.4126 | 17.4126
3484 | -1.7903 | -2.0087 | 0.036704 | 0.022285 | 2.5638 | 3.5683 | 6.918 | 4.1986 | 4.9668 | 2.7038 | 13.0344 | 17.1524 | 17.1524
3485 | -0.062463 | 0.08929 | 0.4751 | 0.53557 | 3.3162 | 5.1781 | 6.1016 | 5.3262 | 4.8517 | 1.7792 | 15.5997 | 16.0487 | 16.0487
3486 | -0.93245 | -1.2447 | 0.17555 | 0.10662 | 3.4084 | 4.2225 | 5.5657 | 4.4656 | 4.701 | 1.6489 | 13.7454 | 15.324 | 15.324
3487 | 1.1313 | 1.5825 | 0.87103 | 0.94323 | 4.4927 | 6.6858 | 6.0888 | 6.5806 | 5.9646 | 2.4009 | 20.16 | 18.947 | 20.16
3488 | -0.012188 | 1.327 | 0.49514 | 0.90775 | 4.9058 | 5.2398 | 6.7063 | 6.3734 | 4.4128 | 2.647 | 19.166 | 18.6719 | 19.166
3489 | -0.68015 | 0.46851 | 0.2482 | 0.68029 | 3.2561 | 4.4734 | 4.8469 | 5.6404 | 4.8704 | 1.9729 | 15.343 | 14.9464 | 15.343
3490 | -1.293 | -0.89439 | 0.098011 | 0.18556 | 3.766 | 3.9091 | 4.6899 | 4.6444 | 4.7904 | 2.087 | 14.4065 | 15.3333 | 15.3333
3491 | 0.1101 | 0.66568 | 0.54384 | 0.74719 | 5.3033 | 5.3919 | 6.3328 | 5.8091 | 3.5602 | 1.899 | 18.4033 | 17.0953 | 18.4033
3492 | -0.087762 | -0.72194 | 0.46503 | 0.23517 | 3.6316 | 5.1473 | 6.149 | 4.7457 | 4.2421 | 1.4795 | 15.004 | 15.5021 | 15.5021
3493 | 0.22917 | 0.585 | 0.59063 | 0.72073 | 4.3239 | 5.542 | 7.5493 | 5.7399 | 5.2439 | 2.5107 | 18.1164 | 19.6277 | 19.6277
3494 | -0.42827 | 0.52708 | 0.33423 | 0.70093 | 3.5674 | 4.747 | 5.4072 | 5.6903 | 3.3003 | 1.1726 | 15.1773 | 13.4474 | 15.1773
3495 | 0.61176 | 0.32867 | 0.72965 | 0.6288 | 4.9659 | 6.0316 | 6.6918 | 5.5226 | 4.0467 | 1.4547 | 17.9748 | 17.1592 | 17.9748
3496 | 0.26148 | 1.1808 | 0.60314 | 0.88116 | 3.5098 | 5.583 | 5.6472 | 6.251 | 3.8104 | 2.2027 | 17.5465 | 15.1701 | 17.5465
3497 | -0.29698 | 0.83385 | 0.38324 | 0.79782 | 3.8476 | 4.8977 | 5.7844 | 5.9541 | 3.8803 | 1.8487 | 16.548 | 15.361 | 16.548
3498 | 1.006 | 0.81644 | 0.84278 | 0.79288 | 3.9199 | 6.5313 | 5.2688 | 5.9391 | 4.1007 | 2.1155 | 18.5057 | 15.4048 | 18.5057
3499 | -0.045198 | 0.14419 | 0.48197 | 0.55732 | 3.3548 | 5.1993 | 6.2114 | 5.3705 | 4.1952 | 2.4214 | 16.3459 | 16.1828 | 16.3459
3500 | 0.88174 | 0.87421 | 0.81104 | 0.809 | 3.7166 | 6.3756 | 5.2646 | 5.9889 | 4.7587 | 1.854 | 17.9351 | 15.5941 | 17.9351
3501 | -0.34376 | 1.1226 | 0.36552 | 0.86919 | 5.1259 | 4.8434 | 5.4697 | 6.2016 | 6.7137 | 2.553 | 18.724 | 19.8623 | 19.8623
3502 | 0.12201 | 0.22398 | 0.54856 | 0.58861 | 3.1308 | 5.4068 | 5.783 | 5.4357 | 3.7441 | 1.9288 | 15.9021 | 14.5866 | 15.9021
3503 | -0.65798 | -0.6897 | 0.25528 | 0.24519 | 3.1662 | 4.4966 | 6.6218 | 4.7656 | 3.6439 | 1.6812 | 14.1096 | 15.113 | 15.113
3504 | -1.5659 | -1.0008 | 0.058687 | 0.15846 | 3.827 | 3.7089 | 3.9895 | 4.5862 | 3.7339 | 1.8996 | 14.0218 | 13.45 | 14.0218
3505 | -0.59681 | 0.69398 | 0.27532 | 0.75615 | 3.5251 | 4.5616 | 5.6595 | 5.8335 | 3.3557 | 2.1403 | 16.0604 | 14.6806 | 16.0604
3506 | -1.5541 | 0.58777 | 0.060079 | 0.72166 | 4.5729 | 3.7169 | 4.9447 | 5.7422 | 3.8633 | 1.7585 | 15.7905 | 15.1393 | 15.7905
3507 | -0.13189 | -0.21556 | 0.44754 | 0.41467 | 3.4561 | 5.0938 | 7.3256 | 5.0902 | 3.6144 | 2.1017 | 15.7418 | 16.4978 | 16.4978
3508 | 0.38876 | 0.37805 | 0.65127 | 0.6473 | 4.0404 | 5.7455 | 6.1538 | 5.564 | 3.1306 | 2.3634 | 17.7132 | 15.6882 | 17.7132
3509 | 1.697 | 1.1321 | 0.95515 | 0.8712 | 3.1327 | 7.3357 | 4.8586 | 6.2097 | 5.519 | 1.5513 | 18.2294 | 15.0616 | 18.2294
3510 | 1.1652 | 0.61853 | 0.87802 | 0.73189 | 5.2469 | 6.727 | 4.556 | 5.7686 | 4.7706 | 2.1748 | 19.9173 | 16.7484 | 19.9173
3511 | 0.85087 | 0.67402 | 0.80258 | 0.74985 | 4.7086 | 6.3366 | 4.8529 | 5.8163 | 3.3978 | 2.1283 | 18.9898 | 15.0876 | 18.9898
3512 | 1.7441 | 1.7739 | 0.95942 | 0.96196 | 5.3333 | 7.3853 | 6.6046 | 6.7288 | 4.6365 | 1.9918 | 21.4392 | 18.5661 | 21.4392
3513 | 0.36744 | 0.86871 | 0.64336 | 0.8075 | 4.3173 | 5.7182 | 5.6175 | 5.9841 | 4.9951 | 1.9137 | 17.9333 | 16.8436 | 17.9333
3514 | 0.40196 | -0.25182 | 0.65614 | 0.40059 | 4.0708 | 5.7624 | 4.2577 | 5.0634 | 4.0049 | 1.3045 | 16.2011 | 13.6379 | 16.2011
3515 | 0.36711 | -0.46402 | 0.64323 | 0.32132 | 3.378 | 5.7178 | 6.1758 | 4.9129 | 4.4432 | 1.331 | 15.3396 | 15.328 | 15.3396
3516 | -0.72089 | 0.25191 | 0.23549 | 0.59944 | 3.4067 | 4.4313 | 6.0853 | 5.4588 | 3.2667 | 1.8313 | 15.128 | 14.5901 | 15.128
3517 | -0.94578 | -0.55597 | 0.17213 | 0.28911 | 4.3527 | 4.21 | 6.3057 | 4.8512 | 3.8435 | 1.6175 | 15.0314 | 16.1195 | 16.1195
3518 | 0.72442 | 0.73914 | 0.7656 | 0.77009 | 4.23 | 6.1758 | 6.3212 | 5.8724 | 3.6005 | 2.3606 | 18.6388 | 16.5123 | 18.6388
3519 | 0.42725 | -0.43173 | 0.6654 | 0.33297 | 3.6359 | 5.7948 | 6.5096 | 4.935 | 3.196 | 1.5347 | 15.9005 | 14.8763 | 15.9005
3520 | -1.9221 | -0.48604 | 0.027298 | 0.31347 | 3.9795 | 3.4955 | 6.5294 | 4.8979 | 4.2155 | 1.7494 | 14.1222 | 16.4738 | 16.4738
3521 | 0.65332 | -0.68486 | 0.74322 | 0.24672 | 3.2686 | 6.0849 | 4.9231 | 4.7686 | 5.2684 | 2.5914 | 16.7134 | 16.0514 | 16.7134
3522 | -1.2493 | 0.28192 | 0.10578 | 0.611 | 3.5793 | 3.9441 | 6.235 | 5.4836 | 5.6955 | 1.9815 | 14.9885 | 17.4913 | 17.4913
3523 | 0.88233 | 0.048855 | 0.8112 | 0.51948 | 3.1298 | 6.3764 | 6.2244 | 5.2939 | 5.2201 | 1.6272 | 16.4272 | 16.2015 | 16.4272
3524 | -2.1304 | -1.0136 | 0.01657 | 0.15538 | 3.865 | 3.3944 | 5.1405 | 4.5794 | 5.081 | 1.9591 | 13.7979 | 16.0455 | 16.0455
3525 | -0.086913 | 0.20568 | 0.46537 | 0.58148 | 5.1772 | 5.1483 | 5.419 | 5.4207 | 3.6189 | 1.733 | 17.4792 | 15.9481 | 17.4792
3526 | -1.3697 | -2.7085 | 0.085398 | 0.0033794 | 3.9807 | 3.8496 | 4.5514 | 4.0749 | 5.2017 | 2.2164 | 14.1216 | 15.9502 | 15.9502
3527 | -0.046809 | 1.0676 | 0.48133 | 0.85714 | 2.9891 | 5.1973 | 6.3182 | 6.1548 | 3.9782 | 2.0748 | 16.4159 | 15.3603 | 16.4159
3528 | 0.47571 | -0.25733 | 0.68286 | 0.39846 | 3.0016 | 5.857 | 5.6244 | 5.0594 | 4.9229 | 1.3959 | 15.3139 | 14.9448 | 15.3139
3529 | 2.9158 | 0.87881 | 0.99823 | 0.81025 | 4.3972 | 8.3484 | 4.2126 | 5.9928 | 3.259 | 1.1096 | 19.8479 | 12.9784 | 19.8479
3530 | 0.39794 | 0.020801 | 0.65466 | 0.5083 | 4.1583 | 5.7572 | 5.7165 | 5.2716 | 3.8667 | 1.581 | 16.7682 | 15.3225 | 16.7682
3531 | 0.68636 | -0.33346 | 0.75376 | 0.36939 | 4.9532 | 6.1272 | 6.5498 | 5.0042 | 4.3771 | 2.0589 | 18.1434 | 17.939 | 18.1434
3532 | 0.96264 | 0.64327 | 0.83214 | 0.73998 | 4.8234 | 6.4772 | 5.0894 | 5.7899 | 3.963 | 1.6725 | 18.7631 | 15.5484 | 18.7631
3533 | 0.6714 | 0.14065 | 0.74902 | 0.55593 | 4.9246 | 6.108 | 6.3036 | 5.3676 | 4.5446 | 1.8497 | 18.25 | 17.6225 | 18.25
3534 | -1.6422 | -1.5407 | 0.050279 | 0.06169 | 5.1361 | 3.6587 | 6.9381 | 4.3429 | 5.3577 | 1.9484 | 15.0862 | 19.3803 | 19.3803
3535 | -0.90753 | -1.5703 | 0.18206 | 0.058168 | 3.506 | 4.2462 | 5.6833 | 4.3321 | 3.605 | 2.0679 | 14.1522 | 14.8622 | 14.8622
3536 | 0.64566 | -0.61368 | 0.74075 | 0.26971 | 2.7061 | 6.0751 | 5.9221 | 4.8136 | 3.1524 | 2.086 | 15.6808 | 13.8667 | 15.6808
3537 | 0.36333 | -0.26955 | 0.64182 | 0.39375 | 4.0221 | 5.7129 | 4.1656 | 5.0504 | 3.8819 | 2.2631 | 17.0485 | 14.3327 | 17.0485
3538 | 0.25177 | -0.78112 | 0.59939 | 0.21736 | 4.4321 | 5.5707 | 6.2898 | 4.7099 | 3.7586 | 1.3293 | 16.0419 | 15.8098 | 16.0419
3539 | -0.16076 | -0.033097 | 0.43614 | 0.4868 | 4.534 | 5.059 | 5.3466 | 5.2293 | 5.5296 | 1.8162 | 16.6385 | 17.2264 | 17.2264
3540 | -1.975 | -1.2325 | 0.024132 | 0.10889 | 4.6179 | 3.4682 | 5.5531 | 4.4712 | 4.3922 | 2.5971 | 15.1545 | 17.1604 | 17.1604
3541 | 0.43658 | 1.1693 | 0.66879 | 0.87886 | 3.0099 | 5.8068 | 4.0006 | 6.2412 | 3.8027 | 1.6461 | 16.704 | 12.4593 | 16.704
3542 | -0.91284 | 0.63577 | 0.18066 | 0.73754 | 3.5254 | 4.2411 | 6.954 | 5.7834 | 4.4713 | 2.455 | 16.005 | 17.4058 | 17.4058
3543 | -0.80907 | 0.35458 | 0.20924 | 0.63855 | 4.4685 | 4.3421 | 5.0494 | 5.5443 | 4.096 | 1.8134 | 16.1684 | 15.4273 | 16.1684
3544 | -1.152 | 0.33182 | 0.12467 | 0.62999 | 3.3997 | 4.0251 | 5.1742 | 5.5252 | 3.6729 | 1.7287 | 14.6787 | 13.9755 | 14.6787
3545 | 1.0493 | 0.0090048 | 0.85298 | 0.50359 | 4.6307 | 6.585 | 5.883 | 5.2623 | 3.6106 | 2.4418 | 18.9199 | 16.5661 | 18.9199
3546 | 0.31316 | -0.33427 | 0.62292 | 0.36909 | 4.3231 | 5.6488 | 5.6387 | 5.0036 | 4.4252 | 2.0834 | 17.0589 | 16.4704 | 17.0589
3547 | -1.5617 | -0.69769 | 0.059175 | 0.24268 | 2.5224 | 3.7117 | 5.3312 | 4.7606 | 4.5833 | 2.2399 | 13.2347 | 14.6769 | 14.6769
3548 | 1.4188 | -0.041236 | 0.92203 | 0.48355 | 4.2674 | 7.0273 | 5.3401 | 5.2229 | 4.1785 | 1.9456 | 18.4632 | 15.7315 | 18.4632
3549 | 0.14941 | -0.30715 | 0.55938 | 0.37936 | 3.4992 | 5.4412 | 5.8148 | 5.0231 | 4.4109 | 2.4084 | 16.3719 | 16.1333 | 16.3719
3550 | -1.1001 | -1.4868 | 0.13564 | 0.06854 | 4.1566 | 4.0699 | 7.1385 | 4.3634 | 4.79 | 2.4019 | 14.9918 | 18.487 | 18.487
3551 | -1.5589 | -1.8968 | 0.059508 | 0.028929 | 3.9369 | 3.7136 | 5.237 | 4.2279 | 5.0739 | 2.0259 | 13.9045 | 16.2738 | 16.2738
3552 | 1.8793 | 1.4189 | 0.9699 | 0.92204 | 3.4689 | 7.5238 | 7.0203 | 6.449 | 3.1684 | 1.9019 | 19.3436 | 15.5594 | 19.3436
3553 | -1.3432 | -1.0764 | 0.089601 | 0.14088 | 4.2909 | 3.8698 | 6.3121 | 4.5469 | 5.0175 | 1.4739 | 14.1816 | 17.0945 | 17.0945
3554 | -0.012563 | -1.8213 | 0.49499 | 0.034281 | 3.2984 | 5.2394 | 4.3856 | 4.2495 | 3.7979 | 2.0957 | 14.883 | 13.5776 | 14.883
3555 | 0.64266 | -1.2762 | 0.73978 | 0.10095 | 3.7825 | 6.0712 | 5.3858 | 4.4513 | 4.6594 | 1.8107 | 16.1157 | 15.6383 | 16.1157
3556 | 1.0123 | -0.80991 | 0.84431 | 0.209 | 4.3018 | 6.5392 | 4.3212 | 4.6929 | 5.0343 | 1.7582 | 17.2921 | 15.4155 | 17.2921
3557 | -0.48453 | -0.18147 | 0.31401 | 0.428 | 4.0992 | 4.6841 | 5.9188 | 5.1156 | 5.2923 | 1.8998 | 15.7987 | 17.2101 | 17.2101
3558 | 1.6011 | 0.80406 | 0.94532 | 0.78932 | 3.8648 | 7.2321 | 3.4692 | 5.9284 | 4.9021 | 2.2977 | 19.323 | 14.5337 | 19.323
3559 | -0.96825 | -0.69756 | 0.16646 | 0.24273 | 5.7184 | 4.189 | 5.9037 | 4.7607 | 4.0973 | 2.1503 | 16.8184 | 17.8697 | 17.8697
3560 | -0.059325 | 0.59789 | 0.47635 | 0.72504 | 4.4178 | 5.182 | 6.38 | 5.7509 | 6.2851 | 1.4545 | 16.8052 | 18.5374 | 18.5374
3561 | -0.73704 | -0.35172 | 0.23055 | 0.36252 | 5.0299 | 4.4147 | 6.3212 | 4.9912 | 4.4025 | 1.3049 | 15.7406 | 17.0584 | 17.0584
3562 | -0.31669 | -0.29355 | 0.37574 | 0.38455 | 3.756 | 4.8748 | 6.2508 | 5.0329 | 4.6616 | 1.5378 | 15.2015 | 16.2062 | 16.2062
3563 | -1.3848 | -1.5038 | 0.083054 | 0.066314 | 3.2039 | 3.8381 | 6.042 | 4.3568 | 4.3994 | 2.2736 | 13.6724 | 15.9188 | 15.9188
3564 | -1.4268 | -1.157 | 0.076824 | 0.12363 | 3.5789 | 3.8069 | 5.7896 | 4.5069 | 5.198 | 1.6786 | 13.5714 | 16.2452 | 16.2452
3565 | -2.1845 | -3.145 | 0.014463 | 0.0008304 | 4.2789 | 3.3709 | 7.4675 | 4.0368 | 4.3572 | 1.6494 | 13.336 | 17.753 | 17.753
3566 | 0.56586 | 0.1915 | 0.71425 | 0.57593 | 5.2848 | 5.9727 | 6.1463 | 5.4091 | 5.2914 | 1.4064 | 18.073 | 18.129 | 18.129
3567 | -0.66427 | -0.16338 | 0.25326 | 0.43511 | 2.9748 | 4.49 | 5.0856 | 5.1293 | 5.5433 | 1.7209 | 14.315 | 15.3246 | 15.3246
3568 | -0.32215 | 0.17763 | 0.37367 | 0.57049 | 3.1418 | 4.8684 | 6.7017 | 5.3977 | 3.6982 | 1.6642 | 15.0722 | 15.206 | 15.206
3569 | -0.85427 | -0.15812 | 0.19648 | 0.43718 | 4.5171 | 4.2976 | 7.3086 | 5.1332 | 4.6833 | 2.3808 | 16.3287 | 18.8897 | 18.8897
3570 | -0.27628 | 0.11781 | 0.39117 | 0.54689 | 2.9922 | 4.9219 | 6.3308 | 5.3492 | 5.2249 | 1.9135 | 15.1768 | 16.4614 | 16.4614
3571 | 0.74184 | 0.78721 | 0.77091 | 0.78442 | 3.3446 | 6.198 | 5.5526 | 5.9139 | 4.5006 | 1.7196 | 17.1761 | 15.1174 | 17.1761
3572 | -0.39995 | -0.67602 | 0.3446 | 0.24951 | 4.1535 | 4.7791 | 5.9886 | 4.7741 | 4.6333 | 2.1547 | 15.8614 | 16.93 | 16.93
3573 | 0.86223 | -0.57827 | 0.80572 | 0.28154 | 4.5342 | 6.351 | 5.9089 | 4.8366 | 4.7276 | 2.5864 | 18.3081 | 17.7572 | 18.3081
3574 | 0.2288 | 2.0447 | 0.59049 | 0.97956 | 3.8277 | 5.5415 | 7.1662 | 6.9255 | 3.9931 | 1.4049 | 17.6996 | 16.3919 | 17.6996
3575 | -1.0926 | -0.45845 | 0.13727 | 0.32331 | 2.6064 | 4.0765 | 3.9802 | 4.9167 | 4.1251 | 2.7534 | 14.3529 | 13.4651 | 14.3529
3576 | -0.43467 | -2.4738 | 0.3319 | 0.0066841 | 5.5159 | 4.7398 | 6.2414 | 4.1062 | 4.2035 | 1.3189 | 15.6808 | 17.2797 | 17.2797
3577 | 0.43329 | 1.468 | 0.6676 | 0.92895 | 4.5476 | 5.8025 | 3.7841 | 6.489 | 3.9204 | 1.79 | 18.6291 | 14.0421 | 18.6291
3578 | -1.0271 | -0.43187 | 0.15218 | 0.33292 | 4.4531 | 4.1349 | 4.6168 | 4.935 | 3.0548 | 2.3846 | 15.9076 | 14.5092 | 15.9076
3579 | -0.59951 | -0.79931 | 0.27442 | 0.21205 | 3.9931 | 4.5587 | 4.1844 | 4.6991 | 4.7341 | 2.6138 | 15.8647 | 15.5253 | 15.8647
3580 | 0.22878 | 0.64268 | 0.59048 | 0.73978 | 2.8744 | 5.5415 | 4.4696 | 5.7894 | 3.321 | 2.4933 | 16.6986 | 13.1583 | 16.6986
3581 | 1.4941 | -0.30328 | 0.93242 | 0.38084 | 2.6586 | 7.113 | 5.3786 | 5.0259 | 3.9405 | 2.1354 | 16.9329 | 14.1131 | 16.9329
3582 | -0.49446 | -0.57161 | 0.31049 | 0.28379 | 4.9766 | 4.6731 | 3.5543 | 4.8409 | 3.4627 | 2.3773 | 16.8679 | 14.3709 | 16.8679
3583 | 0.61805 | 1.2137 | 0.73173 | 0.88756 | 4.6278 | 6.0397 | 6.1082 | 6.2787 | 4.4284 | 2.5961 | 19.5422 | 17.7605 | 19.5422
3584 | 1.2168 | 1.0311 | 0.88815 | 0.84874 | 3.9835 | 6.7893 | 6.843 | 6.1236 | 3.7937 | 1.2677 | 18.1641 | 15.8878 | 18.1641
3585 | 1.8369 | 1.4407 | 0.96688 | 0.92516 | 3.1693 | 7.4811 | 6.465 | 6.4668 | 5.121 | 2.3238 | 19.441 | 17.0792 | 19.441
3586 | -0.4477 | -0.49816 | 0.32718 | 0.30919 | 4.384 | 4.7252 | 4.2817 | 4.8897 | 3.9107 | 2.2129 | 16.2118 | 14.7893 | 16.2118
3587 | 1.9046 | 1.7182 | 0.97158 | 0.95712 | 4.0976 | 7.5489 | 6.164 | 6.6863 | 4.3883 | 1.8654 | 20.1983 | 16.5153 | 20.1983
3588 | 1.3295 | 2.1751 | 0.90815 | 0.98519 | 4.1305 | 6.9233 | 7.1402 | 7.0141 | 4.6231 | 2.0602 | 20.1282 | 17.954 | 20.1282
3589 | -0.4177 | 0.054964 | 0.33808 | 0.52192 | 3.573 | 4.759 | 4.5068 | 5.2988 | 4.425 | 2.2429 | 15.8737 | 14.7477 | 15.8737
3590 | 2.1654 | 0.79114 | 0.98482 | 0.78557 | 4.7314 | 7.7942 | 5.9118 | 5.9172 | 4.4127 | 2.2904 | 20.7332 | 17.3463 | 20.7332
3591 | -2.9366 | -1.8612 | 0.0016592 | 0.031359 | 3.9819 | 3.1421 | 5.9362 | 4.2379 | 5.527 | 1.4985 | 12.8605 | 16.9437 | 16.9437
3592 | -0.70247 | 0.88465 | 0.24119 | 0.81183 | 4.787 | 4.4503 | 5.3158 | 5.9978 | 4.3192 | 1.7651 | 17.0001 | 16.187 | 17.0001
3593 | 0.70111 | 0.44287 | 0.75838 | 0.67107 | 5.1985 | 6.146 | 5.0672 | 5.6187 | 4.0676 | 2.5686 | 19.5318 | 16.9019 | 19.5318
3594 | 0.69359 | -0.14397 | 0.75603 | 0.44276 | 3.5214 | 6.1364 | 7.2898 | 5.1439 | 4.6313 | 1.4203 | 16.2221 | 16.8629 | 16.8629
3595 | -1.5786 | -1.8902 | 0.057209 | 0.029362 | 4.1467 | 3.7003 | 6.4173 | 4.2298 | 4.5683 | 1.7674 | 13.8441 | 16.8995 | 16.8995
3596 | 0.3917 | 0.44487 | 0.65236 | 0.67179 | 3.3636 | 5.7493 | 3.4214 | 5.6204 | 4.0309 | 2.2067 | 16.9399 | 13.0226 | 16.9399
3597 | -0.53676 | 0.90695 | 0.29572 | 0.81778 | 3.1451 | 4.6266 | 3.9909 | 6.0171 | 5.2946 | 2.0039 | 15.7926 | 14.4345 | 15.7926
3598 | 0.43536 | 0.79916 | 0.66835 | 0.7879 | 3.0661 | 5.8052 | 5.2862 | 5.9242 | 4.306 | 2.0189 | 16.8143 | 14.6771 | 16.8143
3599 | -0.50178 | 0.30559 | 0.30791 | 0.62004 | 2.6754 | 4.665 | 6.0815 | 5.5033 | 4.4328 | 1.6842 | 14.5279 | 14.8738 | 14.8738
3600 | 0.72599 | 0.28248 | 0.76608 | 0.61121 | 5.1129 | 6.1778 | 5.4123 | 5.4841 | 3.6265 | 1.6495 | 18.4243 | 15.8012 | 18.4243
3601 | 0.22338 | -0.74547 | 0.58838 | 0.22799 | 4.0992 | 5.5347 | 6.3124 | 4.7313 | 3.2279 | 1.7718 | 16.137 | 15.4112 | 16.137
3602 | 0.30491 | 0.66426 | 0.61978 | 0.74674 | 3.7727 | 5.6383 | 6.9255 | 5.8079 | 3.8952 | 2.4013 | 17.6202 | 16.9947 | 17.6202
3603 | 1.5254 | 0.33182 | 0.93643 | 0.62999 | 3.3139 | 7.1483 | 5.5372 | 5.5252 | 3.4962 | 2.5668 | 18.5542 | 14.9141 | 18.5542
3604 | 1.2986 | 1.0675 | 0.90296 | 0.85713 | 3.4691 | 6.8869 | 5.936 | 6.1548 | 5.3533 | 1.7884 | 18.2992 | 16.5469 | 18.2992
3605 | 0.41035 | -0.011806 | 0.65923 | 0.49529 | 4.0569 | 5.7731 | 6.6684 | 5.246 | 4.0463 | 2.217 | 17.293 | 16.9886 | 17.293
3606 | 1.5788 | 1.6617 | 0.94281 | 0.95171 | 2.8696 | 7.2076 | 5.9298 | 6.6427 | 3.4915 | 2.1545 | 18.8744 | 14.4454 | 18.8744
3607 | -0.2153 | -0.84221 | 0.41477 | 0.19984 | 4.4144 | 4.9938 | 6.3125 | 4.6741 | 5.5089 | 2.2163 | 16.2987 | 18.4522 | 18.4522
3608 | 1.3815 | -1.0477 | 0.91644 | 0.14739 | 2.8216 | 6.9842 | 5.3033 | 4.5616 | 6.1055 | 2.6386 | 17.006 | 16.869 | 17.006
3609 | -0.43146 | 0.34429 | 0.33307 | 0.63468 | 3.9773 | 4.7434 | 5.2652 | 5.5356 | 5.0828 | 1.6438 | 15.9002 | 15.9691 | 15.9691
3610 | -0.67104 | -0.72439 | 0.2511 | 0.23441 | 5.0005 | 4.4829 | 6.1176 | 4.7442 | 4.3028 | 1.9951 | 16.2226 | 17.4159 | 17.4159
3611 | 0.7018 | 1.3843 | 0.7586 | 0.91687 | 2.9814 | 6.1469 | 7.3321 | 6.4207 | 5.2674 | 1.7964 | 17.3454 | 17.3774 | 17.3774
3612 | -1.6105 | -0.14532 | 0.053646 | 0.44223 | 5.2536 | 3.6793 | 6.2674 | 5.1429 | 4.4077 | 2.7785 | 16.8543 | 18.7072 | 18.7072
3613 | -0.14048 | -0.93721 | 0.44414 | 0.17433 | 4.1001 | 5.0834 | 3.647 | 4.6205 | 4.8794 | 1.4718 | 15.2759 | 14.0984 | 15.2759
3614 | 1.9988 | 1.0566 | 0.97719 | 0.85465 | 4.6095 | 7.6406 | 5.9735 | 6.1454 | 4.0579 | 2.4489 | 20.8443 | 17.0898 | 20.8443
3615 | -0.88018 | -0.83638 | 0.18938 | 0.20147 | 3.0135 | 4.2725 | 6.792 | 4.6775 | 4.0198 | 2.4588 | 14.4223 | 16.2841 | 16.2841
3616 | 0.86 | 1.0058 | 0.80511 | 0.84275 | 4.8578 | 6.3482 | 6.0253 | 6.102 | 3.8743 | 1.7545 | 19.0625 | 16.5119 | 19.0625
3617 | 0.92184 | 0.32496 | 0.82169 | 0.6274 | 4.3509 | 6.4261 | 4.0598 | 5.5195 | 5.1181 | 1.5894 | 17.8859 | 15.1182 | 17.8859
3618 | -1.143 | 0.76828 | 0.12652 | 0.77884 | 4.45 | 4.0328 | 4.5818 | 5.8975 | 3.8597 | 2.7525 | 17.1329 | 15.644 | 17.1329
3619 | -0.1151 | -0.33747 | 0.45418 | 0.36788 | 3.586 | 5.1141 | 4.5637 | 5.0013 | 3.8373 | 1.5037 | 15.2051 | 13.4907 | 15.2051
3620 | 0.32738 | -0.75153 | 0.62831 | 0.22617 | 5.0064 | 5.667 | 4.1744 | 4.7277 | 3.5342 | 1.7995 | 17.2006 | 14.5145 | 17.2006
3621 | -0.41433 | -0.38818 | 0.33932 | 0.34894 | 4.6884 | 4.7628 | 4.8491 | 4.9654 | 3.3765 | 1.6729 | 16.0895 | 14.587 | 16.0895
3622 | -0.12373 | -0.85527 | 0.45076 | 0.1962 | 4.0032 | 5.1036 | 6.6638 | 4.6666 | 3.1267 | 1.5131 | 15.2865 | 15.3068 | 15.3068
3623 | 2.9207 | 1.9219 | 0.99825 | 0.97269 | 4.1368 | 8.3512 | 3.4965 | 6.8383 | 4.2838 | 1.8302 | 21.1565 | 13.7472 | 21.1565
3624 | 0.60896 | 0.29112 | 0.72873 | 0.61452 | 2.7259 | 6.028 | 6.1235 | 5.4913 | 5.3826 | 1.9736 | 16.2188 | 16.2056 | 16.2188
3625 | -0.14618 | 0.69271 | 0.44189 | 0.75575 | 4.3028 | 5.0765 | 6.7507 | 5.8324 | 3.7517 | 2.6951 | 17.9069 | 17.5003 | 17.9069
3626 | 0.0386 | -0.62991 | 0.5154 | 0.26438 | 3.0567 | 5.3027 | 5.4318 | 4.8032 | 4.2471 | 2.6144 | 15.7769 | 15.3499 | 15.7769
3627 | 1.184 | 1.4854 | 0.8818 | 0.93128 | 2.611 | 6.7499 | 5.3762 | 6.503 | 4.364 | 2.4634 | 18.3273 | 14.8147 | 18.3273
3628 | 2.4719 | 1.3208 | 0.99328 | 0.90671 | 2.3972 | 8.0479 | 3.93 | 6.3682 | 3.633 | 2.0195 | 18.8328 | 11.9798 | 18.8328
3629 | 1.2299 | 0.25228 | 0.89064 | 0.59959 | 4.9701 | 6.8051 | 5.3181 | 5.4591 | 3.9373 | 1.5244 | 18.7587 | 15.7498 | 18.7587
3630 | -0.73944 | 0.38151 | 0.22982 | 0.64859 | 3.6592 | 4.4123 | 4.5221 | 5.5669 | 4.2321 | 1.7052 | 15.3436 | 14.1186 | 15.3436
3631 | -0.20374 | 0.61401 | 0.41928 | 0.7304 | 4.543 | 5.0076 | 6.6672 | 5.7647 | 4.0336 | 2.6631 | 17.9785 | 17.907 | 17.9785
3632 | -0.40899 | -0.8674 | 0.34128 | 0.19286 | 3.8788 | 4.7688 | 4.8705 | 4.6596 | 5.0131 | 1.7151 | 15.0225 | 15.4775 | 15.4775
3633 | -0.47692 | -1.538 | 0.31671 | 0.062024 | 3.3712 | 4.6926 | 4.2773 | 4.344 | 4.28 | 2.4331 | 14.8408 | 14.3616 | 14.8408
3634 | 0.158 | -0.19567 | 0.56277 | 0.42243 | 3.6058 | 5.452 | 7.269 | 5.105 | 4.9325 | 2.4235 | 16.5863 | 18.2308 | 18.2308
3635 | 0.79303 | 0.5705 | 0.78612 | 0.71583 | 3.4079 | 6.2632 | 5.2025 | 5.7274 | 5.312 | 1.741 | 17.1396 | 15.6634 | 17.1396
3636 | -0.61888 | -0.35293 | 0.268 | 0.36207 | 4.002 | 4.538 | 6.5974 | 4.9903 | 4.051 | 1.8553 | 15.3856 | 16.5058 | 16.5058
3637 | -0.31451 | 0.015421 | 0.37657 | 0.50615 | 3.6437 | 4.8773 | 5.606 | 5.2674 | 4.0415 | 1.8376 | 15.626 | 15.1288 | 15.626
3638 | 2.7767 | 1.8815 | 0.99725 | 0.97004 | 5.4677 | 8.2626 | 6.9546 | 6.8088 | 3.5765 | 2.2954 | 22.8345 | 18.2942 | 22.8345
3639 | -1.2258 | -1.2892 | 0.11013 | 0.09867 | 3.9978 | 3.9633 | 5.4141 | 4.4455 | 4.5391 | 1.6039 | 14.0106 | 15.555 | 15.555
3640 | 0.029724 | 1.3878 | 0.51186 | 0.91739 | 3.0248 | 5.2917 | 6.9281 | 6.4235 | 4.8258 | 2.045 | 16.7849 | 16.8237 | 16.8237
3641 | -0.22452 | -0.017043 | 0.41118 | 0.4932 | 4.5832 | 4.9829 | 6.4618 | 5.2419 | 3.4874 | 2.0619 | 16.8698 | 16.5944 | 16.8698
3642 | 1.692 | 0.9591 | 0.95467 | 0.83125 | 3.3989 | 7.3303 | 6.7955 | 6.0619 | 3.5519 | 2.4121 | 19.2032 | 16.1584 | 19.2032
3643 | 0.95774 | 0.49563 | 0.8309 | 0.68992 | 4.4118 | 6.4711 | 4.6012 | 5.6635 | 3.3083 | 2.0121 | 18.5585 | 14.3333 | 18.5585
3644 | -0.064898 | -0.32471 | 0.47413 | 0.3727 | 3.8426 | 5.1751 | 5.9272 | 5.0105 | 4.6746 | 2.3791 | 16.4072 | 16.8235 | 16.8235
3645 | -0.29916 | 0.66941 | 0.38241 | 0.74838 | 3.985 | 4.8951 | 4.9719 | 5.8124 | 4.076 | 1.4247 | 16.1172 | 14.4577 | 16.1172
3646 | -0.084953 | 0.96422 | 0.46615 | 0.83253 | 4.5374 | 5.1507 | 6.5841 | 6.0663 | 4.494 | 2.3101 | 18.0645 | 17.9255 | 18.0645
3647 | -1.1679 | 0.23283 | 0.12143 | 0.59205 | 3.8532 | 4.0116 | 5.8604 | 5.443 | 3.2507 | 1.4689 | 14.7768 | 14.4333 | 14.7768
3648 | -1.096 | -1.3125 | 0.13654 | 0.094675 | 4.4596 | 4.0735 | 5.9777 | 4.4352 | 5.3494 | 1.9488 | 14.9172 | 17.7355 | 17.7355
3649 | -2.6272 | -1.4109 | 0.0043042 | 0.07914 | 4.9681 | 3.216 | 4.8922 | 4.3936 | 4.7514 | 2.027 | 14.6047 | 16.6387 | 16.6387
3650 | -1.735 | -0.88311 | 0.041373 | 0.18859 | 3.172 | 3.601 | 6.7108 | 4.6507 | 4.8053 | 2.0444 | 13.4681 | 16.7325 | 16.7325
3651 | -0.49887 | 1.1184 | 0.30893 | 0.86829 | 3.4438 | 4.6682 | 6.5136 | 6.1981 | 4.811 | 2.4449 | 16.755 | 17.2134 | 17.2134
3652 | -1.2068 | 0.004607 | 0.11375 | 0.50184 | 4.8203 | 3.979 | 4.7892 | 5.2589 | 4.3852 | 1.897 | 15.9552 | 15.8918 | 15.9552
3653 | 0.76721 | 0.81975 | 0.77852 | 0.79382 | 3.1757 | 6.2304 | 5.5315 | 5.9419 | 4.6432 | 1.7582 | 17.1062 | 15.1087 | 17.1062
3654 | 1.1693 | 0.68177 | 0.87886 | 0.75231 | 3.7994 | 6.732 | 4.607 | 5.823 | 4.024 | 1.9582 | 18.3126 | 14.3886 | 18.3126
3655 | -0.62702 | -1.7327 | 0.26532 | 0.04157 | 5.1574 | 4.5293 | 5.648 | 4.2767 | 5.0398 | 1.5566 | 15.52 | 17.4017 | 17.4017
3656 | 0.87268 | 0.16296 | 0.80858 | 0.56473 | 3.835 | 6.3642 | 7.1574 | 5.3858 | 3.6948 | 2.4322 | 18.0172 | 17.1194 | 18.0172
3657 | 0.38816 | -0.25011 | 0.65105 | 0.40125 | 4.4245 | 5.7447 | 5.0731 | 5.0647 | 4.435 | 1.2459 | 16.4798 | 15.1786 | 16.4798
3658 | -0.28523 | -0.65774 | 0.38773 | 0.25535 | 2.6612 | 4.9114 | 4.3696 | 4.7856 | 5.0072 | 2.1434 | 14.5016 | 14.1814 | 14.5016
3659 | -0.90725 | -1.1329 | 0.18214 | 0.12862 | 3.9742 | 4.2465 | 5.9987 | 4.5187 | 4.0456 | 1.8647 | 14.6041 | 15.8832 | 15.8832
3660 | -2.0526 | -2.2284 | 0.020056 | 0.012926 | 3.7576 | 3.4302 | 5.3404 | 4.1493 | 3.4275 | 1.793 | 13.1301 | 14.3186 | 14.3186
3661 | -0.20202 | -1.8848 | 0.41995 | 0.02973 | 4.5337 | 5.0096 | 5.5758 | 4.2313 | 3.6864 | 1.2856 | 15.0603 | 15.0816 | 15.0816
3662 | 1.1719 | -0.26358 | 0.87938 | 0.39605 | 3.1585 | 6.7352 | 5.9272 | 5.0548 | 4.5389 | 1.9087 | 16.8572 | 15.5334 | 16.8572
3663 | 0.1026 | 1.2869 | 0.54086 | 0.90094 | 4.3869 | 5.3825 | 5.6401 | 6.3401 | 4.8009 | 1.4285 | 17.5379 | 16.2564 | 17.5379
3664 | 0.51725 | 1.0571 | 0.69751 | 0.85476 | 4.6382 | 5.9103 | 6.5097 | 6.1459 | 5.2627 | 1.9189 | 18.6133 | 18.3296 | 18.6133
3665 | -0.68529 | -1.7999 | 0.24658 | 0.03594 | 3.2348 | 4.4681 | 5.6882 | 4.2559 | 5.1072 | 2.4594 | 14.4182 | 16.4896 | 16.4896
3666 | 0.78164 | 0.97464 | 0.78279 | 0.83513 | 2.9243 | 6.2488 | 5.4873 | 6.0753 | 4.3391 | 2.0763 | 17.3246 | 14.827 | 17.3246
3667 | -0.82106 | -2.6977 | 0.20581 | 0.0034905 | 4.8302 | 4.3303 | 4.4581 | 4.0762 | 4.4074 | 2.3912 | 15.6278 | 16.0869 | 16.0869
3668 | -1.1528 | -0.70618 | 0.12449 | 0.24004 | 3.1608 | 4.0244 | 5.8801 | 4.7554 | 4.998 | 1.8456 | 13.7862 | 15.8845 | 15.8845
3669 | 0.90545 | 1.85 | 0.81739 | 0.96784 | 3.4169 | 6.4055 | 4.9318 | 6.7857 | 4.8064 | 1.9916 | 18.5996 | 15.1466 | 18.5996
3670 | 1.5793 | 1.3993 | 0.94286 | 0.91914 | 4.7173 | 7.2081 | 3.513 | 6.433 | 5.2952 | 2.654 | 21.0123 | 16.1794 | 21.0123
3671 | 0.091231 | -0.20597 | 0.53635 | 0.41841 | 3.7354 | 5.3682 | 4.9861 | 5.0973 | 3.9613 | 1.5849 | 15.7858 | 14.2676 | 15.7858
3672 | -0.10396 | -1.5864 | 0.4586 | 0.056319 | 3.4003 | 5.1276 | 3.5256 | 4.3262 | 3.7013 | 2.2569 | 15.111 | 12.8841 | 15.111
3673 | -1.7826 | -1.5408 | 0.037329 | 0.061687 | 3.8572 | 3.5728 | 3.7958 | 4.3429 | 3.8413 | 1.3428 | 13.1156 | 12.837 | 13.1156
3674 | 0.10898 | 0.6511 | 0.54339 | 0.74251 | 3.8718 | 5.3905 | 4.9717 | 5.7966 | 4.7651 | 2.5173 | 17.5762 | 16.1259 | 17.5762
3675 | 0.31112 | 0.49828 | 0.62214 | 0.69086 | 4.6294 | 5.6462 | 5.0267 | 5.6658 | 3.5988 | 2.0229 | 17.9643 | 15.2779 | 17.9643
3676 | 0.05856 | 0.31788 | 0.52335 | 0.62471 | 3.2979 | 5.3275 | 4.2677 | 5.5136 | 4.1445 | 2.6661 | 16.805 | 14.3761 | 16.805
3677 | -0.58797 | -1.2385 | 0.27828 | 0.10776 | 5.3992 | 4.571 | 4.0315 | 4.4684 | 3.2244 | 1.4616 | 15.9003 | 14.1168 | 15.9003
3678 | -0.053063 | -0.15442 | 0.47884 | 0.43864 | 5.1259 | 5.1896 | 5.9577 | 5.136 | 4.7417 | 1.966 | 17.4175 | 17.7913 | 17.7913
3679 | -0.71027 | 0.2332 | 0.23877 | 0.5922 | 4.306 | 4.4422 | 5.1752 | 5.4433 | 4.151 | 2.0027 | 16.1942 | 15.6349 | 16.1942
3680 | 0.058359 | -0.92021 | 0.52327 | 0.17873 | 4.7975 | 5.3272 | 5.266 | 4.6299 | 4.177 | 2.01 | 16.7646 | 16.2505 | 16.7646
3681 | -0.6059 | -0.071881 | 0.27229 | 0.47135 | 3.2993 | 4.5518 | 4.0132 | 5.1992 | 3.1035 | 2.1426 | 15.1929 | 12.5585 | 15.1929
3682 | 0.59209 | 0.2577 | 0.72311 | 0.60168 | 3.8038 | 6.0064 | 5.6332 | 5.4635 | 4.5933 | 1.4616 | 16.7353 | 15.4919 | 16.7353
3683 | -0.56232 | -0.19918 | 0.28695 | 0.42106 | 4.4896 | 4.5987 | 6.47 | 5.1024 | 4.5965 | 2.2571 | 16.4479 | 17.8132 | 17.8132
3684 | 1.1762 | -0.75764 | 0.88025 | 0.22433 | 2.596 | 6.7404 | 7.4152 | 4.724 | 4.7306 | 2.0514 | 16.1119 | 16.7932 | 16.7932
3685 | -0.53884 | 0.061515 | 0.295 | 0.52453 | 3.5501 | 4.6243 | 7.9281 | 5.304 | 5.1551 | 1.9454 | 15.4237 | 18.5786 | 18.5786
3686 | 0.069525 | -0.35553 | 0.52771 | 0.3611 | 4.4419 | 5.3411 | 3.3879 | 4.9884 | 3.2736 | 2.2424 | 17.0139 | 13.3458 | 17.0139
3687 | 0.19806 | 0.63367 | 0.5785 | 0.73685 | 3.6886 | 5.5026 | 7.3229 | 5.7816 | 5.0544 | 1.8095 | 16.7823 | 17.8754 | 17.8754
3688 | -0.90898 | -1.6859 | 0.18168 | 0.045908 | 3.9199 | 4.2448 | 6.9636 | 4.2919 | 4.8249 | 1.7988 | 14.2554 | 17.5072 | 17.5072
3689 | 0.0056069 | 0.27615 | 0.50224 | 0.60878 | 2.7327 | 5.2618 | 2.8239 | 5.4788 | 5.6946 | 1.808 | 15.2814 | 13.0592 | 15.2814
3690 | -0.095079 | 0.803 | 0.46213 | 0.78901 | 3.4485 | 5.1384 | 4.1443 | 5.9275 | 4.7779 | 1.6181 | 16.1325 | 13.9888 | 16.1325
3691 | 0.34093 | 0.39725 | 0.63342 | 0.65441 | 4.8478 | 5.6843 | 6.4532 | 5.5801 | 4.033 | 1.9744 | 18.0867 | 17.3084 | 18.0867
3692 | -0.86785 | 0.52522 | 0.19274 | 0.70028 | 3.1147 | 4.2844 | 6.6004 | 5.6887 | 4.7602 | 2.5873 | 15.6752 | 17.0626 | 17.0626
3693 | 2.3731 | 0.87087 | 0.99118 | 0.80809 | 5.4049 | 7.9702 | 6.609 | 5.986 | 6.1637 | 2.509 | 21.87 | 20.6866 | 21.87
3694 | 1.1728 | 0.27011 | 0.87956 | 0.60646 | 4.9387 | 6.7362 | 5.3158 | 5.4738 | 3.2879 | 2.3756 | 19.5243 | 15.918 | 19.5243
3695 | -0.39659 | -1.3623 | 0.34583 | 0.086547 | 4.3366 | 4.7829 | 6.4528 | 4.4138 | 4.3732 | 2.0565 | 15.5899 | 17.2192 | 17.2192
3696 | -0.59349 | -2.4979 | 0.27642 | 0.0062458 | 4.055 | 4.5651 | 5.5417 | 4.1026 | 4.7963 | 2.341 | 15.0636 | 16.7339 | 16.7339
3697 | -0.67465 | 0.31824 | 0.24995 | 0.62485 | 3.7242 | 4.4792 | 3.3074 | 5.5139 | 4.6022 | 1.1347 | 14.8519 | 12.7684 | 14.8519
3698 | -1.1999 | -0.46814 | 0.11508 | 0.31984 | 5.5026 | 3.9847 | 7.0124 | 4.91 | 3.3363 | 2.2571 | 16.6545 | 18.1085 | 18.1085
3699 | 1.0485 | 0.45412 | 0.85281 | 0.67513 | 4.3632 | 6.5841 | 3.8435 | 5.6282 | 3.8354 | 2.306 | 18.8814 | 14.348 | 18.8814
3700 | 0.92262 | 0.40466 | 0.8219 | 0.65714 | 3.5742 | 6.4271 | 4.6817 | 5.5864 | 4.8824 | 2.4479 | 18.0356 | 15.5862 | 18.0356
3701 | 1.1071 | 0.14028 | 0.86587 | 0.55578 | 3.4007 | 6.6561 | 5.1423 | 5.3673 | 4.7082 | 1.49 | 16.9141 | 14.7412 | 16.9141
3702 | -1.2927 | -2.2233 | 0.098053 | 0.013099 | 2.945 | 3.9093 | 5.7584 | 4.1504 | 3.1055 | 1.3973 | 12.402 | 13.2063 | 13.2063
3703 | -0.046632 | 0.063876 | 0.4814 | 0.52547 | 4.8227 | 5.1975 | 5.2114 | 5.3059 | 3.7382 | 1.8622 | 17.1882 | 15.6344 | 17.1882
3704 | -0.94056 | -0.49687 | 0.17347 | 0.30964 | 2.7053 | 4.2149 | 5.8771 | 4.8906 | 4.2323 | 2.1499 | 13.9607 | 14.9645 | 14.9645
3705 | 0.76678 | 0.95097 | 0.7784 | 0.82919 | 4.1412 | 6.2298 | 3.0178 | 6.0549 | 4.288 | 1.5296 | 17.9556 | 12.9766 | 17.9556
3706 | 0.44242 | 0.36899 | 0.67091 | 0.64393 | 4.9955 | 5.8143 | 5.705 | 5.5564 | 3.9635 | 2.0447 | 18.4108 | 16.7088 | 18.4108
3707 | 0.52514 | -0.35811 | 0.70026 | 0.36013 | 5.2326 | 5.9204 | 5.2198 | 4.9866 | 3.7957 | 2.0312 | 18.1708 | 16.2793 | 18.1708
3708 | -0.4236 | 0.29733 | 0.33593 | 0.61689 | 5.148 | 4.7523 | 5.1976 | 5.4964 | 4.1359 | 1.7705 | 17.1672 | 16.252 | 17.1672
3709 | -0.22388 | -1.1429 | 0.41142 | 0.12653 | 4.4482 | 4.9837 | 5.0868 | 4.5138 | 4.6194 | 2.0482 | 15.9938 | 16.2025 | 16.2025
3710 | -1.6918 | -1.8849 | 0.045345 | 0.029721 | 5.2607 | 3.6274 | 5.9843 | 4.2312 | 4.0792 | 1.6045 | 14.7239 | 16.9287 | 16.9287
3711 | 0.31119 | -1.4161 | 0.62217 | 0.078366 | 3.0788 | 5.6463 | 3.55 | 4.3915 | 5.7027 | 1.6381 | 14.7546 | 13.9696 | 14.7546
3712 | -1.2185 | -0.7913 | 0.11153 | 0.21438 | 4.1596 | 3.9693 | 5.8027 | 4.7039 | 3.5303 | 2.4803 | 15.3131 | 15.9728 | 15.9728
3713 | 0.29889 | 0.32527 | 0.61749 | 0.62751 | 3.1183 | 5.6306 | 6.7195 | 5.5197 | 3.4671 | 1.7965 | 16.0651 | 15.1013 | 16.0651
3714 | -0.53069 | -0.3751 | 0.29782 | 0.35379 | 3.9988 | 4.6332 | 5.6141 | 4.9746 | 4.2265 | 1.8584 | 15.465 | 15.6978 | 15.6978
3715 | 0.70718 | 0.61104 | 0.76027 | 0.72941 | 4.5158 | 6.1538 | 6.3679 | 5.7622 | 3.6388 | 2.0399 | 18.4717 | 16.5624 | 18.4717
3716 | 0.2648 | -0.42615 | 0.60442 | 0.335 | 3.6707 | 5.5873 | 5.4689 | 4.9389 | 3.7031 | 2.3085 | 16.5054 | 15.1512 | 16.5054
3717 | 0.0325 | -0.88259 | 0.51296 | 0.18873 | 3.1145 | 5.2951 | 7.1669 | 4.651 | 4.202 | 1.9715 | 15.0321 | 16.4549 | 16.4549
3718 | -0.90902 | 0.40484 | 0.18167 | 0.6572 | 5.0951 | 4.2448 | 6.4248 | 5.5865 | 4.0482 | 1.7818 | 16.7082 | 17.3499 | 17.3499
3719 | 0.14353 | -0.29361 | 0.55706 | 0.38453 | 3.1076 | 5.4338 | 6.3224 | 5.0329 | 3.1013 | 1.9546 | 15.529 | 14.4859 | 15.529
3720 | 0.46953 | 0.39485 | 0.68066 | 0.65352 | 3.9338 | 5.849 | 6.0797 | 5.5781 | 3.9685 | 2.3712 | 17.7321 | 16.3532 | 17.7321
3721 | -0.33125 | 0.10748 | 0.37023 | 0.54279 | 3.7023 | 4.8579 | 5.8788 | 5.3408 | 4.5008 | 2.1918 | 16.0928 | 16.2738 | 16.2738
3722 | -0.19719 | -0.85511 | 0.42184 | 0.19625 | 3.8332 | 5.0154 | 5.39 | 4.6667 | 4.3681 | 1.987 | 15.5023 | 15.5783 | 15.5783
3723 | -1.4976 | 0.76696 | 0.067125 | 0.77845 | 3.4911 | 3.756 | 7.1212 | 5.8964 | 4.2012 | 2.5357 | 15.6792 | 17.3492 | 17.3492
3724 | -0.37018 | -1.5512 | 0.35562 | 0.060425 | 4.2861 | 4.8131 | 4.701 | 4.3391 | 4.3028 | 2.1417 | 15.58 | 15.4316 | 15.58
3725 | -0.52281 | -0.90536 | 0.30055 | 0.18264 | 3.4186 | 4.6418 | 6.6817 | 4.6382 | 5.149 | 2.3146 | 15.0133 | 17.5639 | 17.5639
3726 | 0.34237 | -0.79966 | 0.63396 | 0.21195 | 4.7043 | 5.6861 | 7.726 | 4.6989 | 3.5683 | 2.3506 | 17.44 | 18.3491 | 18.3491
3727 | 1.1512 | 1.8131 | 0.87517 | 0.96509 | 4.5893 | 6.71 | 4.7013 | 6.7582 | 4.0659 | 1.5365 | 19.594 | 14.893 | 19.594
3728 | -0.23849 | 0.39459 | 0.40575 | 0.65343 | 3.2417 | 4.9664 | 3.5013 | 5.5779 | 3.1774 | 2.0331 | 15.8191 | 11.9535 | 15.8191
3729 | 0.67731 | 1.7385 | 0.7509 | 0.95894 | 3.3451 | 6.1156 | 5.902 | 6.7019 | 3.9721 | 1.9296 | 18.0922 | 15.1488 | 18.0922
3730 | 0.60751 | 0.99371 | 0.72824 | 0.83982 | 3.3716 | 6.0261 | 3.4414 | 6.0916 | 4.034 | 1.9248 | 17.4141 | 12.7717 | 17.4141
3731 | -2.5066 | -1.6936 | 0.0060947 | 0.045172 | 3.8259 | 3.2519 | 6.8002 | 4.2894 | 4.5592 | 1.892 | 13.2593 | 17.0774 | 17.0774
3732 | 0.033991 | 0.84987 | 0.51356 | 0.8023 | 3.378 | 5.2969 | 6.8074 | 5.9679 | 3.3434 | 2.2968 | 16.9395 | 15.8255 | 16.9395
3733 | 0.83628 | -0.37468 | 0.7985 | 0.35395 | 3.6947 | 6.3181 | 6.6193 | 4.9749 | 3.8538 | 2.2401 | 17.2279 | 16.408 | 17.2279
3734 | -0.74723 | -0.18936 | 0.22746 | 0.42491 | 3.6783 | 4.4043 | 4.9351 | 5.1097 | 4.5659 | 2.3542 | 15.5466 | 15.5335 | 15.5466
3735 | 1.3208 | -0.84127 | 0.90672 | 0.2001 | 4.1703 | 6.9132 | 6.4462 | 4.6746 | 5.0745 | 2.1201 | 17.8782 | 17.8111 | 17.8782
3736 | -2.5011 | -0.99462 | 0.0061896 | 0.15996 | 3.0269 | 3.2537 | 5.4064 | 4.5895 | 3.5588 | 2.4968 | 13.3668 | 14.4889 | 14.4889
3737 | -2.2155 | 0.00082999 | 0.013365 | 0.50033 | 4.6212 | 3.3579 | 4.2267 | 5.2559 | 4.6923 | 2.2439 | 15.4789 | 15.7841 | 15.7841
3738 | -0.87614 | -0.2138 | 0.19048 | 0.41535 | 3.8757 | 4.2764 | 4.5486 | 5.0915 | 4.4631 | 2.0269 | 15.2705 | 14.9144 | 15.2705
3739 | 0.26992 | 1.1053 | 0.60639 | 0.86548 | 3.0168 | 5.5938 | 5.3862 | 6.1869 | 4.0893 | 2.0611 | 16.8586 | 14.5534 | 16.8586
3740 | 0.22681 | 0.069631 | 0.58971 | 0.52776 | 3.6211 | 5.539 | 5.2253 | 5.3105 | 5.4192 | 1.9709 | 16.4415 | 16.2365 | 16.4415
3741 | 1.3769 | 1.8384 | 0.91573 | 0.967 | 4.1245 | 6.9788 | 4.9497 | 6.777 | 5.4421 | 2.4029 | 20.2832 | 16.9192 | 20.2832
3742 | 0.30805 | 0.49232 | 0.62098 | 0.68875 | 4.0777 | 5.6423 | 5.8569 | 5.6607 | 3.7753 | 2.2793 | 17.6601 | 15.9892 | 17.6601
3743 | 0.92045 | 1.752 | 0.82133 | 0.96012 | 4.2637 | 6.4244 | 6.156 | 6.7122 | 5.1239 | 1.9931 | 19.3934 | 17.5367 | 19.3934
3744 | -0.75966 | -1.5125 | 0.22373 | 0.065209 | 3.0367 | 4.3917 | 4.8412 | 4.3536 | 4.5923 | 1.4875 | 13.2695 | 13.9577 | 13.9577
3745 | -0.1283 | -0.6624 | 0.44895 | 0.25386 | 3.4478 | 5.0981 | 5.4679 | 4.7826 | 3.6562 | 1.6085 | 14.937 | 14.1804 | 14.937
3746 | -0.68642 | -2.3533 | 0.24622 | 0.0093033 | 4.3475 | 4.4669 | 6.4938 | 4.1259 | 3.7739 | 2.5012 | 15.4415 | 17.1164 | 17.1164
3747 | -0.50564 | 0.44754 | 0.30655 | 0.67276 | 4.1472 | 4.6607 | 6.8773 | 5.6227 | 3.9145 | 1.7336 | 16.1642 | 16.6726 | 16.6726
3748 | -1.2768 | -0.82365 | 0.10084 | 0.20507 | 2.7583 | 3.922 | 6.4444 | 4.6849 | 4.3258 | 1.9628 | 13.328 | 15.4913 | 15.4913
3749 | 0.61619 | 0.68834 | 0.73111 | 0.75438 | 3.8526 | 6.0373 | 7.2159 | 5.8286 | 3.8894 | 1.7971 | 17.5156 | 16.755 | 17.5156
3750 | -0.92852 | -2.2388 | 0.17657 | 0.012584 | 3.5708 | 4.2263 | 6.7352 | 4.1473 | 5.4274 | 2.5679 | 14.5122 | 18.3012 | 18.3012
3751 | 0.34849 | -0.20499 | 0.63626 | 0.41879 | 4.0748 | 5.694 | 7.5441 | 5.0981 | 4.0013 | 1.7422 | 16.6091 | 17.3624 | 17.3624
3752 | -0.46207 | -0.37443 | 0.32201 | 0.35404 | 3.8019 | 4.7091 | 3.3085 | 4.9751 | 4.741 | 2.3615 | 15.8476 | 14.213 | 15.8476
3753 | 0.47072 | -1.0245 | 0.68108 | 0.1528 | 5.337 | 5.8506 | 6.7802 | 4.5737 | 3.4992 | 1.3804 | 17.1417 | 16.9969 | 17.1417
3754 | 0.56979 | 0.37376 | 0.71559 | 0.64571 | 5.2807 | 5.9777 | 3.5942 | 5.5604 | 3.6926 | 2.5335 | 19.3522 | 15.1009 | 19.3522
3755 | 0.013292 | 1.7446 | 0.5053 | 0.95948 | 2.5436 | 5.2713 | 5.4478 | 6.7066 | 4.1876 | 2.1881 | 16.7096 | 14.3672 | 16.7096
3756 | 0.38037 | -0.80651 | 0.64817 | 0.20997 | 4.3462 | 5.7347 | 6.5474 | 4.6949 | 4.6807 | 2.0181 | 16.7939 | 17.5924 | 17.5924
3757 | -0.47844 | 0.34598 | 0.31617 | 0.63532 | 4.5172 | 4.6909 | 6.2104 | 5.5371 | 3.7648 | 1.608 | 16.3531 | 16.1004 | 16.3531
3758 | 0.91225 | 1.3873 | 0.81918 | 0.91733 | 3.7578 | 6.4141 | 6.8452 | 6.4231 | 3.8111 | 2.5367 | 19.1317 | 16.9507 | 19.1317
3759 | -0.024739 | -1.3958 | 0.49013 | 0.081393 | 2.9087 | 5.2244 | 3.6367 | 4.3998 | 5.121 | 2.053 | 14.5858 | 13.7194 | 14.5858
3760 | 0.19683 | 0.11271 | 0.57802 | 0.54487 | 3.771 | 5.5011 | 6.0866 | 5.3451 | 4.1193 | 2.4111 | 17.0281 | 16.388 | 17.0281
3761 | -0.092174 | 0.013373 | 0.46328 | 0.50533 | 3.484 | 5.1419 | 7.1793 | 5.2658 | 4.7226 | 1.2964 | 15.188 | 16.6823 | 16.6823
3762 | 0.73642 | 0.52841 | 0.76926 | 0.70139 | 4.4476 | 6.1911 | 6.8762 | 5.6915 | 5.5787 | 2.1331 | 18.4632 | 19.0355 | 19.0355
3763 | -1.3919 | 0.044404 | 0.081975 | 0.51771 | 4.4149 | 3.8328 | 5.3385 | 5.2904 | 5.1857 | 2.2846 | 15.8227 | 17.2238 | 17.2238
3764 | 0.78517 | -0.45607 | 0.78382 | 0.32417 | 4.4597 | 6.2532 | 7.5344 | 4.9183 | 3.6101 | 1.5582 | 17.1894 | 17.1623 | 17.1894
3765 | -0.33874 | -0.26101 | 0.3674 | 0.39704 | 4.0112 | 4.8492 | 5.0084 | 5.0567 | 4.3501 | 1.7294 | 15.6465 | 15.0991 | 15.6465
3766 | 0.28995 | 0.20723 | 0.61407 | 0.58208 | 3.1513 | 5.6193 | 6.2233 | 5.422 | 4.4033 | 2.7524 | 16.9448 | 16.5301 | 16.9448
3767 | -0.43959 | 0.15923 | 0.33012 | 0.56326 | 3.8815 | 4.7343 | 3.4595 | 5.3827 | 3.7708 | 1.8808 | 15.8793 | 12.9925 | 15.8793
3768 | -0.043209 | 1.0964 | 0.48277 | 0.86355 | 2.4031 | 5.2017 | 5.321 | 6.1794 | 5.0138 | 2.1631 | 15.9472 | 14.9009 | 15.9472
3769 | 1.104 | -0.01373 | 0.8652 | 0.49452 | 4.4459 | 6.6524 | 6.2093 | 5.2445 | 4.2352 | 1.841 | 18.1837 | 16.7313 | 18.1837
3770 | -0.62863 | 0.58359 | 0.26479 | 0.72025 | 4.9546 | 4.5276 | 6.9706 | 5.7387 | 3.9949 | 1.4773 | 16.6981 | 17.3973 | 17.3973
3771 | -0.33799 | 0.75979 | 0.36768 | 0.77631 | 3.4869 | 4.8501 | 6.3689 | 5.8902 | 3.9504 | 1.8686 | 16.0958 | 15.6748 | 16.0958
3772 | -0.24263 | -0.50311 | 0.40415 | 0.30744 | 2.4752 | 4.9615 | 6.2517 | 4.8864 | 3.2893 | 2.1766 | 14.4997 | 14.1928 | 14.4997
3773 | 0.32655 | 0.60053 | 0.628 | 0.72592 | 3.8101 | 5.6659 | 6.4304 | 5.7532 | 4.0266 | 1.6901 | 16.9193 | 15.9572 | 16.9193
3774 | 0.37391 | 0.90178 | 0.64577 | 0.81641 | 4.1559 | 5.7265 | 5.9424 | 6.0126 | 4.4096 | 1.7638 | 17.6588 | 16.2716 | 17.6588
3775 | -0.012233 | 1.1054 | 0.49512 | 0.86551 | 3.6256 | 5.2398 | 7.2352 | 6.187 | 3.731 | 1.9271 | 16.9796 | 16.519 | 16.9796
3776 | -2.2678 | -1.8924 | 0.01167 | 0.029221 | 4.0673 | 3.3367 | 6.2602 | 4.2292 | 4.9801 | 2.3233 | 13.9565 | 17.6309 | 17.6309
3777 | 0.86257 | 1.6765 | 0.80581 | 0.95318 | 5.2461 | 6.3514 | 5.8268 | 6.6543 | 4.3752 | 2.1537 | 20.4054 | 17.6019 | 20.4054
3778 | 0.44283 | 1.3111 | 0.67106 | 0.90508 | 3.5214 | 5.8148 | 6.4679 | 6.3601 | 3.9708 | 1.7636 | 17.4599 | 15.7237 | 17.4599
3779 | 0.63088 | 0.18965 | 0.73594 | 0.57521 | 4.9231 | 6.0561 | 6.3141 | 5.4076 | 3.7385 | 1.8598 | 18.2466 | 16.8356 | 18.2466
3780 | 1.1371 | 0.23435 | 0.87226 | 0.59264 | 4.6078 | 6.6929 | 6.1039 | 5.4443 | 5.539 | 2.1658 | 18.9107 | 18.4164 | 18.9107
3781 | 1.8778 | 2.6593 | 0.9698 | 0.99609 | 5.0757 | 7.5223 | 6.2932 | 7.3054 | 4.6345 | 1.3978 | 21.3013 | 17.4012 | 21.3013
3782 | 0.80858 | 0.58102 | 0.79062 | 0.71939 | 4.0175 | 6.283 | 5.585 | 5.7365 | 4.6191 | 2.6974 | 18.7343 | 16.9189 | 18.7343
3783 | -0.45179 | -1.8865 | 0.32571 | 0.029615 | 3.4114 | 4.7206 | 3.5179 | 4.2308 | 4.4305 | 2.1989 | 14.5617 | 13.5587 | 14.5617
3784 | -0.19477 | -0.019375 | 0.42279 | 0.49227 | 3.3531 | 5.0183 | 5.9283 | 5.24 | 4.3823 | 1.642 | 15.2534 | 15.3057 | 15.3057
3785 | 0.53933 | 0.72666 | 0.70517 | 0.76628 | 3.745 | 5.9386 | 5.6016 | 5.8616 | 3.9334 | 1.404 | 16.9494 | 14.684 | 16.9494
3786 | 2.1011 | 1.0667 | 0.98218 | 0.85695 | 3.7899 | 7.7362 | 7.3377 | 6.1541 | 3.743 | 2.0628 | 19.743 | 16.9335 | 19.743
3787 | -1.2051 | -1.0459 | 0.11408 | 0.14779 | 3.4318 | 3.9804 | 4.5839 | 4.5625 | 4.8769 | 2.449 | 14.4237 | 15.3415 | 15.3415
3788 | -1.1485 | -1.8543 | 0.12539 | 0.03185 | 4.6783 | 4.0281 | 6.0974 | 4.2399 | 4.7862 | 2.2511 | 15.1975 | 17.813 | 17.813
3789 | -1.9286 | 0.086677 | 0.026888 | 0.53454 | 2.9959 | 3.492 | 4.9153 | 5.3241 | 4.3847 | 1.9804 | 13.7925 | 14.2763 | 14.2763
3790 | 1.6638 | 0.46556 | 0.95192 | 0.67924 | 4.1309 | 7.3001 | 4.4468 | 5.6379 | 4.0292 | 1.807 | 18.8759 | 14.4139 | 18.8759
3791 | -0.15712 | -0.069513 | 0.43758 | 0.47229 | 5.4345 | 5.0634 | 3.912 | 5.201 | 3.4455 | 2.454 | 18.1528 | 15.246 | 18.1528
3792 | 0.44323 | 0.77551 | 0.6712 | 0.78098 | 3.3353 | 5.8153 | 6.8507 | 5.9038 | 4.952 | 1.3899 | 16.4443 | 16.5279 | 16.5279
3793 | -0.11529 | 1.0353 | 0.45411 | 0.84973 | 4.8473 | 5.1138 | 5.7073 | 6.1272 | 3.7044 | 2.4024 | 18.4907 | 16.6614 | 18.4907
3794 | 0.94064 | 2.0679 | 0.82656 | 0.98067 | 4.2456 | 6.4497 | 6.0774 | 6.9415 | 4.5971 | 2.4594 | 20.0963 | 17.3796 | 20.0963
3795 | 0.87849 | -0.073964 | 0.81016 | 0.47052 | 4.7906 | 6.3715 | 4.9173 | 5.1976 | 3.3089 | 1.5006 | 17.8603 | 14.5174 | 17.8603
3796 | -0.62824 | 0.60863 | 0.26492 | 0.72862 | 4.5272 | 4.528 | 5.5368 | 5.7601 | 3.3317 | 1.427 | 16.2424 | 14.8228 | 16.2424
3797 | 0.031722 | -0.16796 | 0.51265 | 0.43331 | 4.0468 | 5.2941 | 6.6883 | 5.1258 | 4.4049 | 1.4613 | 15.928 | 16.6012 | 16.6012
3798 | -0.49129 | -1.0513 | 0.31161 | 0.14657 | 3.4648 | 4.6766 | 7.3751 | 4.5598 | 5.8554 | 1.7592 | 14.4604 | 18.4545 | 18.4545
3799 | 2.3969 | 1.8218 | 0.99173 | 0.96576 | 5.1282 | 7.9893 | 5.6952 | 6.7647 | 4.5958 | 1.6641 | 21.5463 | 17.0833 | 21.5463
3800 | -1.5356 | -0.76793 | 0.062317 | 0.22126 | 2.648 | 3.7295 | 7.2162 | 4.7178 | 5.2438 | 1.3209 | 12.4162 | 16.4288 | 16.4288
3801 | 0.4859 | 1.0961 | 0.68648 | 0.86348 | 3.3311 | 5.8701 | 4.7381 | 6.1791 | 4.4839 | 2.066 | 17.4463 | 14.6191 | 17.4463
3802 | -2.9142 | -2.4416 | 0.0017832 | 0.0073111 | 4.5324 | 3.1467 | 3.7522 | 4.1112 | 4.4975 | 2.3104 | 14.1007 | 15.0926 | 15.0926
3803 | 1.1442 | 0.88821 | 0.87374 | 0.81279 | 4.6394 | 6.7016 | 5.7228 | 6.0009 | 4.6635 | 2.223 | 19.5649 | 17.2487 | 19.5649
3804 | 0.29944 | 1.1656 | 0.6177 | 0.87811 | 4.1568 | 5.6313 | 5.3691 | 6.2381 | 3.891 | 2.2787 | 18.305 | 15.6956 | 18.305
3805 | 0.85385 | 1.1064 | 0.80341 | 0.86572 | 5.0753 | 6.3404 | 5.5981 | 6.1879 | 4.6508 | 2.669 | 20.2726 | 17.9932 | 20.2726
3806 | 1.2938 | 0.31714 | 0.90213 | 0.62443 | 3.7958 | 6.8812 | 6.0066 | 5.5129 | 5.0915 | 2.1385 | 18.3285 | 17.0324 | 18.3285
3807 | -0.94499 | -1.651 | 0.17233 | 0.049369 | 2.968 | 4.2107 | 6.2409 | 4.3037 | 4.5447 | 2.4262 | 13.9085 | 16.1797 | 16.1797
3808 | 1.3614 | -1.3625 | 0.9133 | 0.086524 | 4.2514 | 6.9607 | 5.0432 | 4.4137 | 5.5843 | 2.1214 | 17.7472 | 17.0003 | 17.7472
3809 | 0.072405 | -0.43893 | 0.52886 | 0.33036 | 4.2883 | 5.3447 | 4.6975 | 4.9301 | 3.7523 | 2.4708 | 17.0339 | 15.2089 | 17.0339
3810 | -0.43328 | -0.8098 | 0.3324 | 0.20903 | 3.57 | 4.7414 | 6.3051 | 4.693 | 4.2937 | 2.1901 | 15.1944 | 16.3588 | 16.3588
3811 | -0.28324 | -1.4043 | 0.3885 | 0.080112 | 2.4045 | 4.9137 | 6.5663 | 4.3963 | 5.0212 | 2.1798 | 13.8943 | 16.1718 | 16.1718
3812 | 0.28711 | 1.6409 | 0.61299 | 0.94959 | 4.6181 | 5.6156 | 5.6063 | 6.6265 | 3.2196 | 1.7986 | 18.6589 | 15.2427 | 18.6589
3813 | 0.90753 | 0.68856 | 0.81794 | 0.75445 | 4.8516 | 6.4081 | 3.9231 | 5.8288 | 4.0995 | 1.3823 | 18.4709 | 14.2566 | 18.4709
3814 | 0.11422 | 0.21023 | 0.54547 | 0.58326 | 3.5522 | 5.397 | 6.4439 | 5.4244 | 3.1668 | 2.2318 | 16.6055 | 15.3948 | 16.6055
3815 | -0.86942 | -1.0786 | 0.19231 | 0.14039 | 3.1152 | 4.2829 | 4.0997 | 4.5458 | 3.6697 | 1.4845 | 13.4284 | 12.3692 | 13.4284
3816 | 0.75086 | 1.0643 | 0.77363 | 0.8564 | 4.1228 | 6.2096 | 5.0276 | 6.152 | 3.918 | 2.6717 | 19.1561 | 15.7401 | 19.1561
3817 | -0.094721 | 0.26871 | 0.46227 | 0.60592 | 3.9105 | 5.1388 | 5.3994 | 5.4727 | 6.0445 | 1.4429 | 15.9648 | 16.7973 | 16.7973
3818 | -1.5437 | -0.031717 | 0.061336 | 0.48735 | 4.8782 | 3.724 | 5.4699 | 5.2304 | 4.6274 | 2.5586 | 16.3912 | 17.5342 | 17.5342
3819 | 0.37302 | -0.55473 | 0.64543 | 0.28954 | 4.9758 | 5.7253 | 5.9114 | 4.852 | 5.6373 | 1.8205 | 17.3736 | 18.345 | 18.345
3820 | 1.8217 | 0.50461 | 0.96575 | 0.69309 | 4.0735 | 7.4657 | 6.7081 | 5.6712 | 3.0612 | 1.8952 | 19.1055 | 15.7381 | 19.1055
3821 | -0.34043 | 0.69528 | 0.36677 | 0.75656 | 3.5514 | 4.8473 | 6.2003 | 5.8346 | 5.0611 | 1.5199 | 15.7532 | 16.3326 | 16.3326
3822 | -0.84385 | 0.59724 | 0.19938 | 0.72483 | 2.2775 | 4.3078 | 2.9558 | 5.7504 | 3.7979 | 2.5315 | 14.8672 | 11.5627 | 14.8672
3823 | -1.5307 | -1.4814 | 0.06292 | 0.069248 | 5.1606 | 3.7329 | 6.1922 | 4.3655 | 4.1723 | 1.848 | 15.107 | 17.3731 | 17.3731
3824 | -0.18482 | -0.3562 | 0.42668 | 0.36084 | 3.4094 | 5.0301 | 5.7063 | 4.988 | 3.5055 | 1.3907 | 14.8182 | 14.0118 | 14.8182
3825 | -0.82354 | -0.65075 | 0.2051 | 0.2576 | 4.8392 | 4.3278 | 3.1545 | 4.79 | 4.3725 | 1.8581 | 15.815 | 14.2242 | 15.815
3826 | 0.63075 | 1.3721 | 0.7359 | 0.91499 | 4.1719 | 6.056 | 6.5111 | 6.4107 | 3.7641 | 2.6048 | 19.2432 | 17.0519 | 19.2432
3827 | -0.20208 | -0.69405 | 0.41993 | 0.24383 | 4.4295 | 5.0096 | 6.189 | 4.7629 | 5.1758 | 2.1103 | 16.3123 | 17.9047 | 17.9047
3828 | 0.71151 | -0.6863 | 0.76161 | 0.24626 | 3.3899 | 6.1593 | 6.7552 | 4.7677 | 4.0545 | 1.6259 | 15.9429 | 15.8255 | 15.9429
3829 | -0.8757 | 0.56 | 0.1906 | 0.71226 | 3.7406 | 4.2768 | 6.6888 | 5.7184 | 4.8497 | 1.5097 | 15.2456 | 16.7888 | 16.7888
3830 | 0.01697 | 0.67958 | 0.50677 | 0.75162 | 3.4164 | 5.2759 | 6.1268 | 5.8211 | 3.4281 | 2.2052 | 16.7186 | 15.1765 | 16.7186
3831 | -0.9278 | -0.78762 | 0.17675 | 0.21546 | 2.8698 | 4.2269 | 7.0728 | 4.7061 | 4.0488 | 1.7157 | 13.5185 | 15.7071 | 15.7071
3832 | -0.22069 | 0.2088 | 0.41267 | 0.5827 | 2.9824 | 4.9874 | 5.982 | 5.4232 | 3.9147 | 1.9905 | 15.3836 | 14.8696 | 15.3836
3833 | 1.0391 | -0.37196 | 0.85062 | 0.35496 | 3.1421 | 6.5724 | 5.2284 | 4.9768 | 4.5773 | 1.793 | 16.4843 | 14.7408 | 16.4843
3834 | 1.8123 | -1.3158 | 0.96503 | 0.094122 | 4.5881 | 7.4561 | 4.0505 | 4.4338 | 3.6785 | 2.0128 | 18.4908 | 14.3299 | 18.4908
3835 | 0.73121 | 0.12233 | 0.76768 | 0.54868 | 3.7006 | 6.1845 | 5.8706 | 5.3528 | 4.3394 | 2.284 | 17.5219 | 16.1947 | 17.5219
3836 | -1.4324 | -1.0462 | 0.07602 | 0.14774 | 4.6123 | 3.8028 | 5.6718 | 4.5624 | 5.3643 | 1.3947 | 14.3722 | 17.0431 | 17.0431
3837 | -0.18682 | 0.61571 | 0.4259 | 0.73096 | 4.3306 | 5.0278 | 6.4267 | 5.7662 | 4.5799 | 1.8284 | 16.9529 | 17.1656 | 17.1656
3838 | 0.38941 | -0.042754 | 0.65151 | 0.48295 | 4.3739 | 5.7463 | 4.958 | 5.2218 | 4.6767 | 2.0886 | 17.4306 | 16.0972 | 17.4306
3839 | -0.49717 | 0.010841 | 0.30953 | 0.50433 | 4.363 | 4.6701 | 5.333 | 5.2638 | 3.3244 | 1.7896 | 16.0864 | 14.81 | 16.0864
3840 | 0.11076 | -0.50605 | 0.5441 | 0.30641 | 3.5219 | 5.3927 | 5.8841 | 4.8844 | 3.7414 | 1.6392 | 15.4382 | 14.7865 | 15.4382
3841 | -1.0137 | -1.4338 | 0.15537 | 0.07581 | 3.0449 | 4.1472 | 4.3468 | 4.3843 | 4.1009 | 1.2784 | 12.8547 | 12.771 | 12.8547
3842 | -0.92468 | -0.58892 | 0.17757 | 0.27796 | 4.8407 | 4.2299 | 4.3025 | 4.8296 | 4.5698 | 2.5042 | 16.4045 | 16.2172 | 16.4045
3843 | 1.0312 | -0.026724 | 0.84877 | 0.48934 | 4.948 | 6.5626 | 5.5027 | 5.2343 | 4.091 | 2.1894 | 18.9343 | 16.7312 | 18.9343
3844 | 0.6843 | 1.0181 | 0.75311 | 0.84568 | 4.8783 | 6.1245 | 4.3714 | 6.1125 | 3.839 | 2.0004 | 19.1157 | 15.0892 | 19.1157
3845 | -0.75401 | -1.15 | 0.22542 | 0.12506 | 3.712 | 4.3974 | 4.0648 | 4.5103 | 3.8115 | 1.9343 | 14.5541 | 13.5226 | 14.5541
3846 | -1.2814 | -1.1487 | 0.10002 | 0.12534 | 3.0386 | 3.9183 | 4.3908 | 4.5109 | 4.1544 | 2.6769 | 14.1448 | 14.2607 | 14.2607
3847 | 0.34709 | -0.58086 | 0.63574 | 0.28067 | 3.4361 | 5.6922 | 4.4372 | 4.8349 | 5.9487 | 1.4559 | 15.419 | 15.2779 | 15.419
3848 | 0.33304 | -0.026673 | 0.63045 | 0.48936 | 4.6112 | 5.6742 | 5.9294 | 5.2343 | 3.5347 | 2.4916 | 18.0113 | 16.5668 | 18.0113
3849 | -0.59933 | -1.6166 | 0.27448 | 0.052983 | 5.2913 | 4.5589 | 6.5714 | 4.3156 | 4.3053 | 2.2164 | 16.3821 | 18.3843 | 18.3843
3850 | 0.14174 | -0.55877 | 0.55636 | 0.28816 | 3.6844 | 5.4316 | 5.5745 | 4.8493 | 3.9841 | 2.2753 | 16.2407 | 15.5183 | 16.2407
3851 | -1.3299 | -1.33 | 0.09178 | 0.091766 | 5.0003 | 3.8801 | 6.0079 | 4.4276 | 3.4274 | 2.1879 | 15.496 | 16.6235 | 16.6235
3852 | -0.44129 | -1.0849 | 0.3295 | 0.13899 | 4.4618 | 4.7324 | 6.9189 | 4.5426 | 4.6116 | 1.5964 | 15.3332 | 17.5887 | 17.5887
3853 | 1.218 | -0.19786 | 0.88839 | 0.42158 | 4.0054 | 6.7909 | 6.6107 | 5.1034 | 5.7537 | 2.1919 | 18.0916 | 18.5617 | 18.5617
3854 | -0.74005 | -0.76646 | 0.22963 | 0.2217 | 3.4682 | 4.4116 | 5.4463 | 4.7187 | 4.401 | 2.0271 | 14.6256 | 15.3425 | 15.3425
3855 | 0.28112 | 0.71494 | 0.61069 | 0.76268 | 4.3197 | 5.608 | 5.6413 | 5.8516 | 4.4128 | 2.2082 | 17.9875 | 16.582 | 17.9875
3856 | -1.9817 | -2.0649 | 0.023755 | 0.019467 | 4.9818 | 3.4648 | 6.2834 | 4.1849 | 5.8853 | 1.9864 | 14.6179 | 19.1369 | 19.1369
3857 | -0.47028 | 0.48404 | 0.31908 | 0.68582 | 3.5807 | 4.6999 | 6.066 | 5.6536 | 4.9069 | 2.3056 | 16.2398 | 16.859 | 16.859
3858 | -0.54149 | -0.96879 | 0.29409 | 0.16632 | 3.5338 | 4.6214 | 6.0514 | 4.6033 | 4.0681 | 1.3754 | 14.134 | 15.0288 | 15.0288
3859 | -0.73922 | -0.99252 | 0.22989 | 0.16047 | 5.0393 | 4.4125 | 5.8831 | 4.5906 | 3.8738 | 2.1156 | 16.158 | 16.9118 | 16.9118
3860 | 0.33202 | -0.65277 | 0.63006 | 0.25695 | 3.2913 | 5.6729 | 4.3545 | 4.7887 | 4.3713 | 2.0687 | 15.8216 | 14.0858 | 15.8216
3861 | -1.0008 | -0.60397 | 0.15846 | 0.27293 | 4.5258 | 4.1589 | 6.6433 | 4.8199 | 3.9401 | 2.7465 | 16.2511 | 17.8556 | 17.8556
3862 | 0.43034 | -0.10345 | 0.66652 | 0.4588 | 3.1778 | 5.7988 | 6.7144 | 5.1749 | 3.9307 | 1.3316 | 15.483 | 15.1546 | 15.483
3863 | 0.89341 | 0.4432 | 0.81418 | 0.67119 | 3.5549 | 6.3903 | 7.3038 | 5.619 | 3.8657 | 2.4021 | 17.9663 | 17.1265 | 17.9663
3864 | 0.19255 | 0.014594 | 0.57635 | 0.50582 | 2.847 | 5.4956 | 6.8397 | 5.2667 | 5.5216 | 2.8389 | 16.4482 | 18.0471 | 18.0471
3865 | -0.86212 | -1.7016 | 0.19431 | 0.044412 | 3.7577 | 4.29 | 6.9999 | 4.2868 | 4.5152 | 1.4608 | 13.7952 | 16.7336 | 16.7336
3866 | -1.0413 | -1.0969 | 0.14888 | 0.13634 | 2.7603 | 4.1222 | 6.9498 | 4.5365 | 4.3393 | 2.1255 | 13.5445 | 16.1749 | 16.1749
3867 | 0.55772 | -0.15701 | 0.71148 | 0.43762 | 2.6922 | 5.9622 | 6.0181 | 5.1341 | 4.8618 | 2.3216 | 16.1101 | 15.8937 | 16.1101
3868 | -0.083389 | -1.1588 | 0.46677 | 0.12327 | 4.3262 | 5.1526 | 6.6578 | 4.5061 | 5.0096 | 2.3654 | 16.3503 | 18.3591 | 18.3591
3869 | 0.2404 | -1.2744 | 0.59499 | 0.10126 | 4.3338 | 5.5563 | 5.7999 | 4.4521 | 3.7464 | 2.2611 | 16.6033 | 16.1411 | 16.6033
3870 | -0.86512 | 0.010034 | 0.19349 | 0.504 | 3.6645 | 4.2871 | 6.9091 | 5.2631 | 5.5338 | 2.3087 | 15.5234 | 18.4161 | 18.4161
3871 | 0.77345 | -0.63388 | 0.78037 | 0.26308 | 4.865 | 6.2383 | 3.9348 | 4.8007 | 3.4218 | 1.9018 | 17.8059 | 14.1235 | 17.8059
3872 | -0.34842 | -0.74844 | 0.36376 | 0.2271 | 3.7399 | 4.8381 | 5.9379 | 4.7295 | 3.6978 | 1.7692 | 15.0768 | 15.1449 | 15.1449
3873 | -0.67455 | 0.34541 | 0.24998 | 0.63511 | 4.6592 | 4.4793 | 3.9847 | 5.5366 | 4.0661 | 2.1745 | 16.8495 | 14.8844 | 16.8495
3874 | -0.03357 | 0.33409 | 0.48661 | 0.63085 | 3.2624 | 5.2135 | 6.3613 | 5.5271 | 4.323 | 1.6398 | 15.6428 | 15.5864 | 15.6428
3875 | 0.87408 | 0.10303 | 0.80896 | 0.54103 | 3.8182 | 6.366 | 5.6554 | 5.3373 | 5.1902 | 2.1445 | 17.666 | 16.8084 | 17.666
3876 | -0.56555 | -1.2451 | 0.28585 | 0.10655 | 3.3611 | 4.5952 | 7.3304 | 4.4654 | 4.4128 | 2.1517 | 14.5735 | 17.256 | 17.256
3877 | -0.54133 | -1.1058 | 0.29414 | 0.1344 | 3.6151 | 4.6216 | 6.342 | 4.5321 | 4.0278 | 2.05 | 14.8188 | 16.0349 | 16.0349
3878 | -1.8542 | -1.75 | 0.031855 | 0.040056 | 4.0252 | 3.5321 | 7.2722 | 4.2712 | 3.7905 | 1.7845 | 13.613 | 16.8724 | 16.8724
3879 | -0.63048 | -1.5769 | 0.26419 | 0.057406 | 4.576 | 4.5257 | 4.682 | 4.3297 | 3.7575 | 1.742 | 15.1734 | 14.7575 | 15.1734
3880 | 0.18441 | -0.42179 | 0.57315 | 0.33659 | 4.6246 | 5.4853 | 6.0312 | 4.9419 | 5.1965 | 2.5429 | 17.5948 | 18.3952 | 18.3952
3881 | 0.53645 | 1.3998 | 0.70418 | 0.91921 | 3.8361 | 5.9349 | 5.2663 | 6.4333 | 3.7383 | 1.6359 | 17.8403 | 14.4766 | 17.8403
3882 | 1.2776 | 0.3526 | 0.89931 | 0.63781 | 3.7267 | 6.8621 | 5.5233 | 5.5426 | 5.3294 | 1.6541 | 17.7855 | 16.2335 | 17.7855
3883 | 1.1976 | 1.3287 | 0.88446 | 0.90803 | 4.7967 | 6.7662 | 5.5541 | 6.3748 | 4.6987 | 2.1699 | 20.1076 | 17.2194 | 20.1076
3884 | 0.53044 | -0.12249 | 0.7021 | 0.45126 | 3.4497 | 5.9272 | 6.9333 | 5.1603 | 4.3609 | 1.7735 | 16.3108 | 16.5174 | 16.5174
3885 | 1.8415 | 0.18597 | 0.96723 | 0.57377 | 4.4485 | 7.4858 | 5.4921 | 5.4045 | 4.2762 | 1.5098 | 18.8486 | 15.7266 | 18.8486
3886 | -0.98803 | -0.83313 | 0.16157 | 0.20239 | 4.1995 | 4.1707 | 7.4786 | 4.6794 | 5.7648 | 1.8338 | 14.8833 | 19.2767 | 19.2767
3887 | -0.68061 | 1.1798 | 0.24806 | 0.88096 | 4.0472 | 4.4729 | 3.4428 | 6.2501 | 5.3108 | 1.9407 | 16.711 | 14.7416 | 16.711
3888 | 0.094149 | -1.0901 | 0.5375 | 0.13783 | 4.0116 | 5.3719 | 6.2991 | 4.54 | 3.8347 | 2.5712 | 16.4947 | 16.7167 | 16.7167
3889 | -0.74903 | -0.25151 | 0.22692 | 0.40071 | 3.3344 | 4.4025 | 7.2464 | 5.0636 | 4.3707 | 1.4427 | 14.2432 | 16.3942 | 16.3942
3890 | 0.35544 | 0.57635 | 0.63887 | 0.71781 | 4.0935 | 5.7028 | 5.6973 | 5.7324 | 4.081 | 2.4901 | 18.019 | 16.3619 | 18.019
3891 | 0.68919 | -0.59528 | 0.75465 | 0.27583 | 4.7261 | 6.1308 | 7.2859 | 4.8255 | 4.0624 | 1.6967 | 17.3791 | 17.7711 | 17.7711
3892 | 0.77325 | 0.82404 | 0.78031 | 0.79504 | 2.9009 | 6.2381 | 6.9575 | 5.9456 | 4.706 | 1.6493 | 16.7339 | 16.2137 | 16.7339
3893 | -0.8203 | -0.068976 | 0.20602 | 0.4725 | 5.0921 | 4.331 | 4.2229 | 5.2014 | 3.8415 | 1.3587 | 15.9832 | 14.5152 | 15.9832
3894 | -0.14006 | -0.69914 | 0.4443 | 0.24223 | 4.2739 | 5.0839 | 6.7075 | 4.7597 | 3.3886 | 1.9277 | 16.0452 | 16.2977 | 16.2977
3895 | 0.26747 | 2.0099 | 0.60545 | 0.97778 | 2.8867 | 5.5906 | 4.589 | 6.9011 | 4.4792 | 2.0869 | 17.4654 | 14.0418 | 17.4654
3896 | 0.37071 | -0.032402 | 0.64457 | 0.48708 | 5.514 | 5.7224 | 4.3092 | 5.2298 | 3.7374 | 1.8955 | 18.3618 | 15.4562 | 18.3618
3897 | 2.1832 | 0.61763 | 0.98549 | 0.73159 | 4.4583 | 7.8099 | 5.9916 | 5.7678 | 5.6363 | 1.9938 | 20.0299 | 18.0799 | 20.0299
3898 | -0.29658 | -0.66261 | 0.38339 | 0.25379 | 2.7522 | 4.8982 | 6.0479 | 4.7825 | 4.342 | 1.8273 | 14.2602 | 14.9695 | 14.9695
3899 | -0.20416 | 0.7362 | 0.41911 | 0.76919 | 5.0902 | 5.0071 | 7.5549 | 5.8699 | 5.0163 | 2.048 | 18.0152 | 19.7094 | 19.7094
3900 | -0.96875 | 0.29658 | 0.16634 | 0.61661 | 4.607 | 4.1885 | 7.1617 | 5.4958 | 3.8742 | 2.1516 | 16.4428 | 17.7945 | 17.7945
3901 | 1.5896 | 0.83655 | 0.94404 | 0.79858 | 4.0082 | 7.2195 | 3.5958 | 5.9564 | 3.4482 | 1.7432 | 18.9273 | 12.7954 | 18.9273
3902 | -0.94912 | -0.37284 | 0.17128 | 0.35463 | 3.7544 | 4.2069 | 5.1001 | 4.9762 | 3.8447 | 2.1449 | 15.0823 | 14.8441 | 15.0823
3903 | -0.27064 | -0.50105 | 0.39333 | 0.30817 | 4.362 | 4.9285 | 7.5982 | 4.8878 | 4.525 | 1.6379 | 15.8162 | 18.1231 | 18.1231
3904 | -1.6304 | -1.6943 | 0.051507 | 0.045105 | 4.9378 | 3.6663 | 6.7725 | 4.2892 | 6.0516 | 1.6834 | 14.5767 | 19.4454 | 19.4454
3905 | 1.5404 | 1.0488 | 0.93827 | 0.85286 | 4.1586 | 7.165 | 5.729 | 6.1388 | 5.3125 | 1.5369 | 18.9992 | 16.7369 | 18.9992
3906 | 0.0472 | 0.17719 | 0.51882 | 0.57032 | 3.4088 | 5.3134 | 4.0913 | 5.3974 | 4.9678 | 2.3267 | 16.4463 | 14.7947 | 16.4463
3907 | 0.66482 | 1.0673 | 0.74692 | 0.85708 | 2.841 | 6.0996 | 6.0523 | 6.1546 | 5.0662 | 1.7495 | 16.8446 | 15.7089 | 16.8446
3908 | 0.28999 | 1.4525 | 0.61409 | 0.92682 | 5.5876 | 5.6193 | 5.7007 | 6.4764 | 4.352 | 1.9817 | 19.665 | 17.6219 | 19.665
3909 | -1.2779 | 0.79052 | 0.10065 | 0.78539 | 4.2798 | 3.9211 | 5.5323 | 5.9167 | 4.6884 | 2.272 | 16.3897 | 16.7725 | 16.7725
3910 | 0.83175 | 0.76242 | 0.79722 | 0.77709 | 4.2377 | 6.3124 | 5.8165 | 5.8925 | 4.6978 | 2.1839 | 18.6266 | 16.936 | 18.6266
3911 | -0.13891 | -0.21099 | 0.44476 | 0.41645 | 4.1965 | 5.0853 | 4.5586 | 5.0936 | 4.6592 | 1.7992 | 16.1746 | 15.2135 | 16.1746
3912 | -0.46447 | -0.21074 | 0.32116 | 0.41655 | 5.235 | 4.7064 | 4.854 | 5.0938 | 4.5087 | 2.1132 | 17.1484 | 16.7109 | 17.1484
3913 | -1.9117 | -0.92287 | 0.027957 | 0.17804 | 5.0179 | 3.5009 | 3.5223 | 4.6285 | 3.452 | 1.7717 | 14.919 | 13.764 | 14.919
3914 | 1.2109 | 0.27477 | 0.88704 | 0.60825 | 3.1569 | 6.7823 | 6.256 | 5.4777 | 5.645 | 1.7826 | 17.1996 | 16.8406 | 17.1996
3915 | 0.46342 | 2.0053 | 0.67847 | 0.97754 | 3.0451 | 5.8412 | 5.5446 | 6.8979 | 4.857 | 2.4276 | 18.2118 | 15.8743 | 18.2118
3916 | -3.4288 | -2.3358 | 0.00030315 | 0.0097502 | 2.802 | 3.0679 | 6.4006 | 4.129 | 4.5401 | 2.0503 | 12.0492 | 15.793 | 15.793
3917 | -1.3686 | 0.17433 | 0.085556 | 0.5692 | 3.3846 | 3.8504 | 6.8591 | 5.395 | 3.8951 | 1.545 | 14.175 | 15.6838 | 15.6838
3918 | 0.54405 | 0.81273 | 0.70679 | 0.79181 | 4.5141 | 5.9447 | 5.6642 | 5.9359 | 3.1025 | 2.5247 | 18.9193 | 15.8055 | 18.9193
3919 | -0.19906 | -1.3777 | 0.42111 | 0.084148 | 2.673 | 5.0132 | 3.807 | 4.4073 | 5.6868 | 1.6374 | 13.7309 | 13.8043 | 13.8043
3920 | 0.2003 | -0.66424 | 0.57938 | 0.25327 | 4.9143 | 5.5054 | 6.9502 | 4.7815 | 3.4123 | 2.4936 | 17.6948 | 17.7704 | 17.7704
3921 | 0.42429 | -0.17829 | 0.66432 | 0.42925 | 3.3142 | 5.791 | 6.0735 | 5.118 | 3.6288 | 1.7219 | 15.9451 | 14.7383 | 15.9451
3922 | 0.71054 | 1.1478 | 0.76132 | 0.87448 | 4.2484 | 6.1581 | 5.8793 | 6.2231 | 4.8174 | 1.7896 | 18.4192 | 16.7347 | 18.4192
3923 | 0.14654 | 0.069794 | 0.55825 | 0.52782 | 4.2718 | 5.4376 | 4.4217 | 5.3106 | 3.201 | 2.0436 | 17.0636 | 13.9381 | 17.0636
3924 | 0.35074 | -1.132 | 0.63711 | 0.12881 | 3.9346 | 5.6968 | 6.2817 | 4.5191 | 3.2736 | 1.778 | 15.9286 | 15.2679 | 15.9286
3925 | -0.15541 | 0.51187 | 0.43825 | 0.69563 | 4.4698 | 5.0654 | 5.3943 | 5.6773 | 3.8 | 2.5226 | 17.7352 | 16.1867 | 17.7352
3926 | 0.04668 | -0.2531 | 0.51862 | 0.4001 | 5.0659 | 5.3127 | 5.7811 | 5.0625 | 3.1448 | 1.7911 | 17.2321 | 15.7829 | 17.2321
3927 | -0.23808 | -1.1581 | 0.40591 | 0.12341 | 4.2822 | 4.9668 | 6.6449 | 4.5064 | 4.3431 | 1.8396 | 15.5951 | 17.1098 | 17.1098
3928 | 1.1365 | 0.9545 | 0.87213 | 0.83008 | 5.0716 | 6.6921 | 4.7625 | 6.0579 | 3.817 | 2.2875 | 20.1093 | 15.9387 | 20.1093
3929 | -0.056209 | -0.21803 | 0.47759 | 0.4137 | 5.2445 | 5.1858 | 6.0899 | 5.0884 | 4.4799 | 1.326 | 16.8446 | 17.1404 | 17.1404
3930 | 0.56871 | -0.13128 | 0.71522 | 0.44778 | 4.1844 | 5.9764 | 6.6607 | 5.1536 | 4.1254 | 2.3343 | 17.6486 | 17.3048 | 17.6486
3931 | 1.2315 | 0.74452 | 0.89092 | 0.77172 | 3.5246 | 6.807 | 2.7564 | 5.877 | 4.2887 | 1.2811 | 17.4897 | 11.8509 | 17.4897
3932 | 1.2291 | 0.32789 | 0.89048 | 0.6285 | 3.4683 | 6.8041 | 7.1817 | 5.5219 | 4.8478 | 1.8579 | 17.6522 | 17.3557 | 17.6522
3933 | -0.032098 | -0.583 | 0.4872 | 0.27995 | 5.3589 | 5.2153 | 5.3023 | 4.8335 | 3.7013 | 2.2172 | 17.6249 | 16.5797 | 17.6249
3934 | -1.8341 | -0.70407 | 0.033318 | 0.2407 | 5.2214 | 3.5433 | 6.9317 | 4.7567 | 4.1934 | 1.1872 | 14.7086 | 17.5337 | 17.5337
3935 | 0.33301 | -1.0638 | 0.63043 | 0.1437 | 4.3244 | 5.6742 | 6.0056 | 4.5533 | 4.4533 | 1.996 | 16.5479 | 16.7794 | 16.7794
3936 | -0.0048862 | -0.68803 | 0.49805 | 0.24572 | 3.2518 | 5.2488 | 7.519 | 4.7666 | 5.3402 | 1.9962 | 15.2635 | 18.1073 | 18.1073
3937 | 0.80829 | 1.1342 | 0.79054 | 0.87165 | 3.5715 | 6.2826 | 5.0284 | 6.2115 | 5.5245 | 1.9202 | 17.9858 | 16.0445 | 17.9858
3938 | 0.30468 | 0.94217 | 0.61969 | 0.82695 | 3.3997 | 5.638 | 5.5929 | 6.0474 | 4.763 | 2.0023 | 17.0874 | 15.7579 | 17.0874
3939 | -1.106 | -0.44384 | 0.13437 | 0.32858 | 4.0813 | 4.0648 | 6.3536 | 4.9267 | 4.3642 | 1.3976 | 14.4705 | 16.1967 | 16.1967
3940 | -0.99676 | -0.60178 | 0.15944 | 0.27366 | 4.7419 | 4.1626 | 4.5541 | 4.8213 | 3.7071 | 2.2992 | 16.025 | 15.3023 | 16.025
3941 | 0.58249 | 2.0775 | 0.71988 | 0.98112 | 2.6363 | 5.994 | 6.5179 | 6.9482 | 3.8798 | 2.0464 | 17.6249 | 15.0805 | 17.6249
3942 | -0.23363 | 0.1208 | 0.40763 | 0.54808 | 4.2425 | 4.9721 | 6.6674 | 5.3516 | 4.6962 | 2.0771 | 16.6433 | 17.6832 | 17.6832
3943 | 0.96252 | 1.4403 | 0.83211 | 0.92511 | 3.9515 | 6.4771 | 4.9597 | 6.4665 | 4.4593 | 1.9433 | 18.8384 | 15.3138 | 18.8384
3944 | 1.8582 | 2.3564 | 0.96843 | 0.99077 | 2.9798 | 7.5026 | 4.3938 | 7.1304 | 5.4519 | 2.0335 | 19.6463 | 14.859 | 19.6463
3945 | 0.52007 | -0.17979 | 0.69849 | 0.42866 | 4.0252 | 5.9139 | 5.2715 | 5.1169 | 3.4411 | 1.9636 | 17.0196 | 14.7014 | 17.0196
3946 | -2.0963 | 0.135 | 0.018028 | 0.55369 | 3.8251 | 3.4098 | 4.966 | 5.3631 | 4.3927 | 1.8669 | 14.4649 | 15.0508 | 15.0508
3947 | -2.5273 | -0.51608 | 0.0057473 | 0.3029 | 3.5889 | 3.2455 | 7.4853 | 4.8777 | 3.6999 | 2.0927 | 13.8048 | 16.8668 | 16.8668
3948 | 1.4873 | 1.9442 | 0.93153 | 0.97406 | 4.103 | 7.1054 | 6.2304 | 6.8544 | 3.4932 | 2.4678 | 20.5306 | 16.2944 | 20.5306
3949 | 0.76924 | -0.38982 | 0.77913 | 0.34833 | 3.9368 | 6.233 | 6.0586 | 4.9642 | 4.9295 | 2.6201 | 17.7541 | 17.545 | 17.7541
3950 | 1.5409 | 1.2393 | 0.93833 | 0.89238 | 3.9259 | 7.1656 | 5.1239 | 6.3002 | 4.4536 | 1.698 | 19.0897 | 15.2015 | 19.0897
3951 | 2.0393 | 0.681 | 0.97929 | 0.75206 | 4.9727 | 7.6789 | 5.6738 | 5.8223 | 5.1673 | 1.5235 | 19.9974 | 17.3373 | 19.9974
3952 | 0.62909 | 2.9789 | 0.73536 | 0.99855 | 4.8402 | 6.0538 | 4.4022 | 7.4633 | 3.3665 | 2.8702 | 21.2275 | 15.4791 | 21.2275
3953 | -1.0653 | -1.3845 | 0.14338 | 0.083097 | 4.5732 | 4.1007 | 5.6486 | 4.4045 | 4.5818 | 1.5614 | 14.6398 | 16.3651 | 16.3651
3954 | -0.029218 | -0.25182 | 0.48835 | 0.40059 | 3.5586 | 5.2189 | 7.0267 | 5.0634 | 3.5909 | 1.8442 | 15.685 | 16.0203 | 16.0203
3955 | -1.1676 | -1.0513 | 0.12149 | 0.14655 | 3.5698 | 4.0119 | 6.2203 | 4.5597 | 3.6846 | 2.1321 | 14.2735 | 15.6069 | 15.6069
3956 | -0.11196 | -1.0456 | 0.45543 | 0.14786 | 3.086 | 5.1179 | 5.9721 | 4.5627 | 4.2696 | 1.9252 | 14.6917 | 15.2528 | 15.2528
3957 | -0.79701 | -0.87963 | 0.21272 | 0.18953 | 4.9444 | 4.3542 | 5.7357 | 4.6527 | 5.2483 | 2.192 | 16.1432 | 18.1204 | 18.1204
3958 | -0.63743 | -1.4493 | 0.26192 | 0.073634 | 3.7907 | 4.5183 | 7.4141 | 4.3781 | 4.7593 | 1.8287 | 14.5158 | 17.7928 | 17.7928
3959 | 0.09439 | 0.56703 | 0.5376 | 0.71465 | 3.2913 | 5.3722 | 4.6563 | 5.7245 | 4.1042 | 1.4189 | 15.8069 | 13.4707 | 15.8069
3960 | -0.37407 | 0.20433 | 0.35417 | 0.58095 | 3.83 | 4.8086 | 4.6639 | 5.4196 | 4.8672 | 2.0736 | 16.1317 | 15.4347 | 16.1317
3961 | -0.722 | 0.097862 | 0.23515 | 0.53898 | 4.1939 | 4.4301 | 5.6248 | 5.3331 | 3.9622 | 1.888 | 15.8451 | 15.6688 | 15.8451
3962 | -0.46671 | 0.78953 | 0.32035 | 0.7851 | 4.5819 | 4.7039 | 5.4302 | 5.9159 | 5.3144 | 1.7668 | 16.9685 | 17.0933 | 17.0933
3963 | 1.1057 | 0.9211 | 0.86557 | 0.8215 | 4.196 | 6.6545 | 4.7471 | 6.0292 | 3.9991 | 1.6937 | 18.5734 | 14.6359 | 18.5734
3964 | -0.72992 | -0.55431 | 0.23272 | 0.28968 | 2.4206 | 4.422 | 7.3314 | 4.8523 | 4.3641 | 2.5816 | 14.2764 | 16.6977 | 16.6977
3965 | 2.6966 | 1.0586 | 0.9965 | 0.85511 | 4.6638 | 8.2098 | 5.3241 | 6.1472 | 4.5357 | 2.4599 | 21.4806 | 16.9834 | 21.4806
3966 | 0.45338 | -1.187 | 0.67486 | 0.11761 | 4.1968 | 5.8283 | 5.2992 | 4.4925 | 5.099 | 2.5969 | 17.1145 | 17.1918 | 17.1918
3967 | -0.40852 | 0.63655 | 0.34145 | 0.73779 | 3.4805 | 4.7694 | 4.9277 | 5.7841 | 3.8798 | 1.2734 | 15.3074 | 13.5614 | 15.3074
3968 | -1.6927 | -2.2121 | 0.045257 | 0.013481 | 4.5899 | 3.6268 | 6.7906 | 4.1526 | 4.1479 | 1.5849 | 13.9542 | 17.1132 | 17.1132
3969 | -1.6345 | -1.322 | 0.05108 | 0.09308 | 3.4129 | 3.6637 | 6.6825 | 4.4311 | 3.9141 | 2.4864 | 13.9941 | 16.496 | 16.496
3970 | 0.87362 | 0.47072 | 0.80884 | 0.68108 | 4.007 | 6.3654 | 7.1023 | 5.6423 | 3.9651 | 1.8955 | 17.9103 | 16.97 | 17.9103
3971 | -0.051277 | -1.1096 | 0.47955 | 0.13359 | 5.3261 | 5.1918 | 3.8699 | 4.5302 | 3.7428 | 2.147 | 17.1952 | 15.0858 | 17.1952
3972 | -1.0022 | -0.2381 | 0.15812 | 0.4059 | 3.8682 | 4.1576 | 5.3841 | 5.0735 | 4.4215 | 1.562 | 14.6613 | 15.2358 | 15.2358
3973 | 0.86677 | 1.6192 | 0.80697 | 0.9473 | 5.137 | 6.3567 | 5.4598 | 6.6096 | 3.4983 | 2.084 | 20.1873 | 16.1791 | 20.1873
3974 | -1.6861 | -2.7383 | 0.04589 | 0.0030875 | 4.2238 | 3.6309 | 6.0518 | 4.0716 | 5.2488 | 1.6324 | 13.5587 | 17.1568 | 17.1568
3975 | -0.54578 | -0.10323 | 0.29261 | 0.45889 | 4.3883 | 4.6167 | 6.0923 | 5.175 | 4.1166 | 1.4848 | 15.6649 | 16.082 | 16.082
3976 | -0.22192 | -0.90246 | 0.41219 | 0.18341 | 5.2812 | 4.986 | 6.8483 | 4.6398 | 5.1507 | 2.0651 | 16.972 | 19.3452 | 19.3452
3977 | 0.48006 | -0.69804 | 0.68441 | 0.24258 | 3.5703 | 5.8626 | 4.5008 | 4.7604 | 3.6865 | 2.1587 | 16.3519 | 13.9163 | 16.3519
3978 | -0.41109 | -0.66868 | 0.3405 | 0.25185 | 2.4107 | 4.7665 | 6.1111 | 4.7787 | 4.2198 | 2.2122 | 14.168 | 14.9538 | 14.9538
3979 | -0.29291 | -0.44035 | 0.38479 | 0.32984 | 4.3927 | 4.9024 | 6.268 | 4.9291 | 5.8333 | 1.928 | 16.1522 | 18.422 | 18.422
3980 | 0.26571 | -0.13748 | 0.60477 | 0.44533 | 3.6667 | 5.5884 | 6.8173 | 5.1489 | 4.2304 | 2.2022 | 16.6063 | 16.9167 | 16.9167
3981 | -0.81748 | -1.528 | 0.20683 | 0.063258 | 4.4471 | 4.3338 | 6.0348 | 4.3477 | 4.2202 | 2.137 | 15.2656 | 16.8391 | 16.8391
3982 | -0.64156 | -1.8558 | 0.26058 | 0.03174 | 3.6383 | 4.5139 | 5.8615 | 4.2395 | 5.8313 | 2.4417 | 14.8333 | 17.7728 | 17.7728
3983 | -0.39941 | -0.83849 | 0.3448 | 0.20088 | 3.4569 | 4.7797 | 3.9632 | 4.6762 | 5.8978 | 1.1736 | 14.0865 | 14.4915 | 14.4915
3984 | -1.8648 | -1.3116 | 0.031102 | 0.094826 | 4.6565 | 3.5262 | 5.0792 | 4.4356 | 4.4041 | 2.5422 | 15.1605 | 16.682 | 16.682
3985 | -0.81213 | 0.0080351 | 0.20836 | 0.50321 | 3.0155 | 4.3391 | 5.5004 | 5.2616 | 3.7648 | 1.8652 | 14.4814 | 14.146 | 14.4814
3986 | -0.74372 | -0.41758 | 0.22852 | 0.33813 | 3.8646 | 4.4079 | 4.6108 | 4.9449 | 4.3086 | 1.6021 | 14.8195 | 14.3862 | 14.8195
3987 | -0.91786 | 0.47588 | 0.17935 | 0.68292 | 4.5804 | 4.2364 | 4.752 | 5.6467 | 4.7542 | 1.8372 | 16.3006 | 15.9237 | 16.3006
3988 | 1.3775 | 1.1833 | 0.91582 | 0.88166 | 4.1781 | 6.9794 | 6.6074 | 6.2531 | 5.0183 | 2.0269 | 19.4375 | 17.8307 | 19.4375
3989 | -0.038892 | -0.59745 | 0.48449 | 0.2751 | 2.3713 | 5.207 | 6.1128 | 4.8241 | 3.4756 | 2.4185 | 14.8209 | 14.3782 | 14.8209
3990 | -1.9658 | -1.263 | 0.024661 | 0.1033 | 4.3118 | 3.4729 | 4.8551 | 4.4573 | 5.8876 | 1.5007 | 13.7426 | 16.5551 | 16.5551
3991 | -0.82831 | 0.493 | 0.20375 | 0.68899 | 4.1806 | 4.3231 | 7.2793 | 5.6613 | 5.643 | 2.5302 | 16.6952 | 19.6331 | 19.6331
3992 | 0.2889 | 0.50356 | 0.61367 | 0.69271 | 3.4859 | 5.6179 | 4.8169 | 5.6703 | 3.153 | 1.3706 | 16.1446 | 12.8263 | 16.1446
3993 | -1.5415 | -0.67204 | 0.061598 | 0.25078 | 3.7118 | 3.7255 | 4.0441 | 4.7766 | 4.8835 | 1.1663 | 13.3802 | 13.8058 | 13.8058
3994 | 0.1695 | -0.089899 | 0.5673 | 0.46418 | 4.5531 | 5.4665 | 5.9926 | 5.1853 | 4.0328 | 2.1445 | 17.3494 | 16.723 | 17.3494
3995 | 0.61502 | 0.62936 | 0.73073 | 0.73544 | 3.5485 | 6.0358 | 5.6338 | 5.7779 | 4.3139 | 1.6702 | 17.0324 | 15.1664 | 17.0324
3996 | 0.59902 | 0.34685 | 0.72542 | 0.63565 | 3.9115 | 6.0153 | 4.6385 | 5.5378 | 4.9934 | 2.3155 | 17.78 | 15.8589 | 17.78
3997 | 0.96675 | 0.64948 | 0.83316 | 0.74199 | 5.162 | 6.4824 | 6.355 | 5.7952 | 4.1372 | 1.479 | 18.9186 | 17.1332 | 18.9186
3998 | -2.0087 | -2.3329 | 0.022282 | 0.0098257 | 4.2931 | 3.4514 | 5.4379 | 4.1295 | 3.783 | 1.821 | 13.695 | 15.3351 | 15.3351
3999 | 0.68806 | 0.89156 | 0.75429 | 0.81369 | 4.1409 | 6.1293 | 5.7837 | 6.0038 | 5.922 | 2.1804 | 18.4545 | 18.0271 | 18.4545
4000 | -0.88023 | -0.4402 | 0.18937 | 0.3299 | 2.8352 | 4.2724 | 6.369 | 4.9292 | 5.3545 | 1.8724 | 13.9093 | 16.4311 | 16.4311
4001 | -0.59291 | 0.88187 | 0.27662 | 0.81108 | 2.9618 | 4.5657 | 6.21 | 5.9955 | 4.6246 | 2.3166 | 15.8396 | 16.1131 | 16.1131
4002 | -1.3066 | -0.92867 | 0.095667 | 0.17653 | 2.9884 | 3.8983 | 5.3907 | 4.6252 | 4.0331 | 2.2181 | 13.7301 | 14.6304 | 14.6304
4003 | 1.3894 | 1.7785 | 0.91765 | 0.96234 | 4.2951 | 6.9933 | 2.6026 | 6.7322 | 5.9378 | 1.7194 | 19.7401 | 14.555 | 19.7401
4004 | 0.18436 | -1.3155 | 0.57313 | 0.09417 | 3.8496 | 5.4853 | 5.6749 | 4.4339 | 4.6635 | 2.742 | 16.5108 | 16.9301 | 16.9301
4005 | 7.8726e-05 | -0.32156 | 0.50003 | 0.37389 | 4.2073 | 5.255 | 3.9442 | 5.0127 | 4.657 | 2.3323 | 16.8073 | 15.1408 | 16.8073
4006 | -0.69733 | -1.5024 | 0.2428 | 0.0665 | 5.0608 | 4.4556 | 6.2551 | 4.3574 | 5.1171 | 1.8295 | 15.7033 | 18.2625 | 18.2625
4007 | -1.8953 | -0.84892 | 0.029028 | 0.19796 | 4.2879 | 3.5097 | 6.0096 | 4.6702 | 4.6919 | 1.4363 | 13.9041 | 16.4257 | 16.4257
4008 | 0.25791 | -1.1054 | 0.60176 | 0.13449 | 4.6453 | 5.5785 | 4.5741 | 4.5323 | 4.0908 | 2.6153 | 17.3714 | 15.9255 | 17.3714
4009 | -1.6001 | 0.58837 | 0.054784 | 0.72186 | 3.9365 | 3.6861 | 7.3597 | 5.7427 | 4.422 | 2.0241 | 15.3894 | 17.7422 | 17.7422
4010 | 1.3321 | 0.2161 | 0.90858 | 0.58555 | 5.2285 | 6.9264 | 6.4275 | 5.4292 | 3.2026 | 2.5154 | 20.0995 | 17.374 | 20.0995
4011 | 1.0852 | 1.0882 | 0.86109 | 0.86174 | 3.9038 | 6.6294 | 5.956 | 6.1724 | 4.2522 | 2.571 | 19.2765 | 16.683 | 19.2765
4012 | -0.5935 | -1.0425 | 0.27642 | 0.1486 | 2.8903 | 4.5651 | 5.6565 | 4.5643 | 3.2037 | 1.9279 | 13.9477 | 13.6784 | 13.9477
4013 | 1.2387 | 0.43845 | 0.89228 | 0.66947 | 4.7328 | 6.8157 | 7.4224 | 5.615 | 3.4019 | 1.9732 | 19.1366 | 17.5302 | 19.1366
4014 | -1.0559 | 0.49313 | 0.14552 | 0.68904 | 2.945 | 4.1091 | 6.5163 | 5.6614 | 4.9424 | 2.4568 | 15.1723 | 16.8606 | 16.8606
4015 | -0.98278 | -1.0526 | 0.16286 | 0.14626 | 3.3432 | 4.1755 | 4.3353 | 4.5591 | 5.5296 | 1.7683 | 13.8461 | 14.9763 | 14.9763
4016 | -1.1808 | 1.4901 | 0.11885 | 0.93191 | 3.4962 | 4.0007 | 6.9768 | 6.5068 | 4.3238 | 1.9463 | 15.9501 | 16.7431 | 16.7431
4017 | 0.74049 | 0.36153 | 0.7705 | 0.64115 | 3.9649 | 6.1963 | 7.2828 | 5.5501 | 4.4824 | 1.9326 | 17.6439 | 17.6627 | 17.6627
4018 | 2.2514 | 1.8371 | 0.98782 | 0.9669 | 2.7509 | 7.8692 | 5.7942 | 6.7761 | 3.2036 | 1.5906 | 18.9868 | 13.3393 | 18.9868
4019 | 0.64182 | 0.33786 | 0.73951 | 0.63227 | 4.029 | 6.0701 | 6.9867 | 5.5303 | 4.5447 | 2.1902 | 17.8195 | 17.7505 | 17.8195
4020 | 1.671 | 2.9863 | 0.95264 | 0.99859 | 4.5898 | 7.3079 | 4.6239 | 7.4666 | 4.3723 | 2.0586 | 21.423 | 15.6446 | 21.423
4021 | 1.001 | 1.242 | 0.84158 | 0.89287 | 3.8864 | 6.5251 | 6.9241 | 6.3024 | 5.0674 | 1.5084 | 18.2223 | 17.3862 | 18.2223
4022 | -0.4972 | -1.0247 | 0.30953 | 0.15275 | 4.1223 | 4.6701 | 4.8864 | 4.5736 | 4.4833 | 1.7245 | 15.0904 | 15.2165 | 15.2165
4023 | 0.51903 | -0.10238 | 0.69813 | 0.45923 | 3.8166 | 5.9126 | 5.399 | 5.1757 | 4.3477 | 2.2209 | 17.1257 | 15.7842 | 17.1257
4024 | 0.23801 | 1.4228 | 0.59406 | 0.9226 | 3.8932 | 5.5532 | 7.1711 | 6.4522 | 3.6742 | 1.5656 | 17.4642 | 16.3041 | 17.4642
4025 | 0.062501 | -0.37878 | 0.52492 | 0.35243 | 4.9368 | 5.3324 | 5.9232 | 4.972 | 5.2529 | 2.4472 | 17.6885 | 18.5602 | 18.5602
4026 | 0.52631 | 0.29776 | 0.70066 | 0.61706 | 3.4366 | 5.9219 | 4.83 | 5.4968 | 4.3283 | 2.3314 | 17.1867 | 14.9263 | 17.1867
4027 | 1.2488 | 0.9871 | 0.89413 | 0.8382 | 5.6323 | 6.8278 | 7.1741 | 6.0859 | 3.453 | 2.465 | 21.011 | 18.7244 | 21.011
4028 | 0.39748 | 0.51113 | 0.65449 | 0.69537 | 4.2224 | 5.7566 | 4.6144 | 5.6767 | 3.4752 | 1.6904 | 17.3461 | 14.0023 | 17.3461
4029 | -1.0157 | -1.7867 | 0.15488 | 0.036997 | 4.5546 | 4.1453 | 7.0191 | 4.2599 | 5.4803 | 2.0719 | 15.0317 | 19.1259 | 19.1259
4030 | 0.60602 | 1.9386 | 0.72775 | 0.97372 | 4.6163 | 6.0242 | 7.5261 | 6.8503 | 4.7557 | 2.1764 | 19.6672 | 19.0745 | 19.6672
4031 | -0.45346 | -0.17061 | 0.32511 | 0.43226 | 3.1212 | 4.7187 | 6.8776 | 5.1238 | 3.7252 | 2.3117 | 15.2755 | 16.0358 | 16.0358
4032 | -1.1956 | -0.79418 | 0.11593 | 0.21355 | 4.1834 | 3.9883 | 6.5626 | 4.7022 | 3.7862 | 2.2569 | 15.1308 | 16.7891 | 16.7891
4033 | 0.38856 | -0.71862 | 0.6512 | 0.23619 | 3.4035 | 5.7452 | 5.7143 | 4.7477 | 4.8214 | 1.5146 | 15.4111 | 15.4539 | 15.4539
4034 | -0.65693 | -0.016712 | 0.25561 | 0.49333 | 5.248 | 4.4977 | 3.8201 | 5.2421 | 4.9299 | 1.5248 | 16.5126 | 15.5227 | 16.5126
4035 | -0.59725 | 1.9711 | 0.27517 | 0.97564 | 5.0171 | 4.5611 | 4.0796 | 6.8736 | 3.6068 | 2.1262 | 18.578 | 14.8297 | 18.578
4036 | 0.50834 | -0.27915 | 0.69439 | 0.39007 | 4.6642 | 5.8989 | 4.7887 | 5.0434 | 4.1378 | 2.1886 | 17.7951 | 15.7794 | 17.7951
4037 | -1.1057 | -0.18249 | 0.13443 | 0.4276 | 2.8936 | 4.0651 | 6.5597 | 5.1149 | 3.2937 | 2.075 | 14.1485 | 14.822 | 14.822
4038 | 0.54765 | -1.9553 | 0.70803 | 0.025271 | 2.5876 | 5.9493 | 5.1858 | 4.2122 | 3.637 | 2.3953 | 15.1444 | 13.8057 | 15.1444
4039 | 0.91472 | 0.042246 | 0.81983 | 0.51685 | 3.214 | 6.4172 | 4.5566 | 5.2886 | 5.7991 | 2.4318 | 17.3516 | 16.0015 | 17.3516
4040 | -1.6769 | -0.16289 | 0.046786 | 0.4353 | 4.3512 | 3.6367 | 5.3726 | 5.1296 | 5.3575 | 2.65 | 15.7676 | 17.7313 | 17.7313
4041 | 0.64263 | -0.23309 | 0.73977 | 0.40784 | 4.5613 | 6.0712 | 6.1788 | 5.0772 | 3.2687 | 1.6151 | 17.3248 | 15.6241 | 17.3248
4042 | -1.4567 | -1.8265 | 0.072605 | 0.033889 | 4.2807 | 3.7852 | 6.1692 | 4.248 | 3.3793 | 1.4429 | 13.7567 | 15.2721 | 15.2721
4043 | 0.3566 | -0.36675 | 0.6393 | 0.3569 | 4.3683 | 5.7043 | 5.7279 | 4.9805 | 5.3339 | 2.1279 | 17.1811 | 17.558 | 17.558
4044 | -0.93536 | -0.53335 | 0.1748 | 0.2969 | 4.6009 | 4.2198 | 6.2324 | 4.8662 | 5.5215 | 1.7037 | 15.3905 | 18.0585 | 18.0585
4045 | 0.9873 | 0.30891 | 0.83825 | 0.6213 | 3.9784 | 6.508 | 7.1378 | 5.5061 | 5.2306 | 1.9928 | 17.9853 | 18.3396 | 18.3396
4046 | -0.60138 | -0.65097 | 0.27379 | 0.25753 | 4.4419 | 4.5567 | 7.4079 | 4.7899 | 3.4345 | 2.3401 | 16.1285 | 17.6244 | 17.6244
4047 | 0.28164 | -1.0822 | 0.61089 | 0.13959 | 4.1958 | 5.6087 | 5.5433 | 4.544 | 4.0272 | 2.1968 | 16.5452 | 15.9631 | 16.5452
4048 | 1.0177 | 0.73221 | 0.84559 | 0.76798 | 3.754 | 6.5459 | 7.1336 | 5.8664 | 3.9944 | 1.6743 | 17.8406 | 16.5564 | 17.8406
4049 | 1.5366 | 1.5124 | 0.9378 | 0.93478 | 3.7135 | 7.1607 | 5.512 | 6.5248 | 3.7967 | 2.5399 | 19.939 | 15.5622 | 19.939
4050 | -1.4946 | -2.2013 | 0.06751 | 0.013858 | 3.2211 | 3.7581 | 6.4909 | 4.1548 | 4.3483 | 2.4205 | 13.5545 | 16.4808 | 16.4808
4051 | 1.9218 | 0.47904 | 0.97268 | 0.68405 | 4.9895 | 7.5659 | 6.8601 | 5.6494 | 5.2642 | 1.8985 | 20.1033 | 19.0124 | 20.1033
4052 | -1.0473 | -0.0082468 | 0.14747 | 0.49671 | 4.3921 | 4.1167 | 5.7147 | 5.2488 | 3.9329 | 2.3283 | 16.0859 | 16.3682 | 16.3682
4053 | -1.6966 | -0.89785 | 0.044884 | 0.18463 | 4.9234 | 3.6244 | 3.9675 | 4.6424 | 3.6109 | 1.8413 | 15.0315 | 14.343 | 15.0315
4054 | -0.80883 | -0.42363 | 0.20931 | 0.33592 | 3.8863 | 4.3424 | 7.5299 | 4.9407 | 3.385 | 2.6669 | 15.8362 | 17.4681 | 17.4681
4055 | 1.8611 | 2.4621 | 0.96863 | 0.99309 | 3.4274 | 7.5055 | 3.5464 | 7.1943 | 3.5858 | 2.4207 | 20.5479 | 12.9802 | 20.5479
4056 | 0.91627 | 0.54278 | 0.82024 | 0.70636 | 5.0074 | 6.4191 | 3.5349 | 5.7037 | 5.7816 | 2.2736 | 19.4038 | 16.5974 | 19.4038
4057 | -0.79682 | 0.028254 | 0.21278 | 0.51127 | 3.9305 | 4.3543 | 5.8898 | 5.2775 | 4.1287 | 1.4068 | 14.9692 | 15.3558 | 15.3558
4058 | -0.10168 | 0.64168 | 0.45951 | 0.73946 | 4.7613 | 5.1303 | 6.0737 | 5.7885 | 3.8832 | 1.8302 | 17.5104 | 16.5484 | 17.5104
4059 | 0.22506 | -0.1593 | 0.58903 | 0.43672 | 3.7466 | 5.5368 | 7.7665 | 5.1323 | 3.7331 | 1.3829 | 15.7986 | 16.629 | 16.629
4060 | -0.028235 | 0.3316 | 0.48874 | 0.6299 | 4.7454 | 5.2201 | 6.0237 | 5.525 | 4.3562 | 1.9107 | 17.4011 | 17.036 | 17.4011
4061 | 0.50369 | -0.65617 | 0.69276 | 0.25586 | 4.0778 | 5.8929 | 6.9635 | 4.7866 | 3.6647 | 2.4184 | 17.1757 | 17.1244 | 17.1757
4062 | -0.11505 | -0.71909 | 0.4542 | 0.23604 | 4.6522 | 5.1141 | 6.6334 | 4.7474 | 5.2258 | 2.4111 | 16.9248 | 18.9225 | 18.9225
4063 | 0.65268 | 0.21568 | 0.74302 | 0.58538 | 4.1274 | 6.084 | 5.3863 | 5.4289 | 4.3256 | 1.6198 | 17.2601 | 15.4591 | 17.2601
4064 | -0.21522 | -0.79349 | 0.4148 | 0.21375 | 4.4963 | 4.9939 | 3.1857 | 4.7026 | 3.7752 | 2.324 | 16.5168 | 13.7811 | 16.5168
4065 | -0.26972 | -0.59249 | 0.39369 | 0.27676 | 3.5013 | 4.9296 | 6.3521 | 4.8273 | 5.8498 | 2.7332 | 15.9914 | 18.4364 | 18.4364
4066 | -0.85606 | 0.23784 | 0.19598 | 0.594 | 3.2632 | 4.2959 | 4.6503 | 5.4471 | 4.9069 | 2.2151 | 15.2213 | 15.0355 | 15.2213
4067 | -2.1606 | 1.0079 | 0.015362 | 0.84324 | 2.572 | 3.3811 | 2.9242 | 6.1038 | 5.8177 | 2.222 | 14.2789 | 13.5359 | 14.2789
4068 | 1.3937 | 0.56416 | 0.9183 | 0.71368 | 3.4166 | 6.9983 | 5.4936 | 5.722 | 3.8228 | 1.7141 | 17.851 | 14.4471 | 17.851
4069 | -0.58738 | 1.194 | 0.27847 | 0.88376 | 3.2708 | 4.5717 | 4.3296 | 6.2621 | 4.285 | 1.4166 | 15.5212 | 13.302 | 15.5212
4070 | 1.446 | 0.73283 | 0.92592 | 0.76817 | 3.1853 | 7.0585 | 5.1927 | 5.867 | 4.8168 | 1.5943 | 17.705 | 14.7891 | 17.705
4071 | -1.9735 | -0.67358 | 0.024221 | 0.25029 | 3.8702 | 3.469 | 4.869 | 4.7756 | 4.755 | 2.0569 | 14.1717 | 15.5511 | 15.5511
4072 | -0.29485 | 0.21282 | 0.38406 | 0.58426 | 3.751 | 4.9002 | 6.5441 | 5.4265 | 4.444 | 2.6629 | 16.7406 | 17.402 | 17.402
4073 | -0.64068 | 0.72542 | 0.26086 | 0.7659 | 4.8109 | 4.5149 | 6.9237 | 5.8606 | 3.3982 | 1.6098 | 16.7961 | 16.7426 | 16.7961
4074 | -1.8116 | -0.6859 | 0.035026 | 0.24639 | 2.7428 | 3.556 | 3.5448 | 4.7679 | 3.479 | 2.1317 | 13.1984 | 11.8983 | 13.1984
4075 | -1.697 | -1.1552 | 0.044846 | 0.12401 | 4.5107 | 3.6241 | 4.4737 | 4.5078 | 5.0175 | 2.4565 | 15.0992 | 16.4584 | 16.4584
4076 | 0.071634 | -0.0034412 | 0.52855 | 0.49863 | 3.7084 | 5.3438 | 4.8117 | 5.2525 | 3.8408 | 2.8356 | 17.1403 | 15.1965 | 17.1403
4077 | -0.02914 | 1.1645 | 0.48838 | 0.87789 | 3.3579 | 5.219 | 4.9401 | 6.2372 | 3.6445 | 1.6299 | 16.444 | 13.5724 | 16.444
4078 | 0.25086 | -0.11048 | 0.59904 | 0.45601 | 4.5257 | 5.5695 | 5.6638 | 5.1695 | 3.8339 | 2.4414 | 17.7061 | 16.4648 | 17.7061
4079 | -0.2797 | -0.49727 | 0.38985 | 0.3095 | 4.6974 | 4.9179 | 4.8265 | 4.8903 | 3.9525 | 1.8591 | 16.3647 | 15.3355 | 16.3647
4080 | -1.866 | -0.67 | 0.031017 | 0.25143 | 3.7115 | 3.5256 | 6.3356 | 4.7779 | 3.6626 | 2.1875 | 14.2024 | 15.8972 | 15.8972
4081 | 0.48 | -0.31834 | 0.68439 | 0.37511 | 4.1415 | 5.8625 | 5.7226 | 5.015 | 4.095 | 2.4535 | 17.4726 | 16.4127 | 17.4726
4082 | -0.26088 | 1.1307 | 0.39709 | 0.87091 | 3.6058 | 4.94 | 5.5677 | 6.2085 | 4.5207 | 1.7524 | 16.5067 | 15.4466 | 16.5067
4083 | -1.1363 | -1.5412 | 0.12792 | 0.06163 | 4.6568 | 4.0386 | 5.5411 | 4.3427 | 3.4073 | 1.4709 | 14.509 | 15.0761 | 15.0761
4084 | -1.3891 | -1.418 | 0.082408 | 0.078094 | 4.5676 | 3.8349 | 5.8941 | 4.3907 | 5.0049 | 1.4643 | 14.2575 | 16.9309 | 16.9309
4085 | -0.95269 | 0.2691 | 0.17037 | 0.60607 | 3.1982 | 4.2035 | 4.6527 | 5.473 | 4.1004 | 1.9876 | 14.8623 | 13.9389 | 14.8623
4086 | 0.30608 | 0.54691 | 0.62023 | 0.70778 | 2.9977 | 5.6398 | 6.6158 | 5.7073 | 4.2745 | 2.2289 | 16.5737 | 16.117 | 16.5737
4087 | -0.9681 | -1.2996 | 0.1665 | 0.096868 | 3.8194 | 4.1891 | 7.3075 | 4.4409 | 3.641 | 2.4202 | 14.8697 | 17.1881 | 17.1881
4088 | -0.78619 | -0.40335 | 0.21588 | 0.34335 | 5.4891 | 4.365 | 6.7832 | 4.9548 | 3.0971 | 2.7978 | 17.6066 | 18.1672 | 18.1672
4089 | 0.57218 | -0.081685 | 0.7164 | 0.46745 | 3.6724 | 5.9808 | 6.5386 | 5.1916 | 4.1009 | 2.3001 | 17.1449 | 16.612 | 17.1449
4090 | 1.4891 | 1.7952 | 0.93177 | 0.96369 | 3.1409 | 7.1074 | 7.221 | 6.7448 | 5.7 | 2.005 | 18.9982 | 18.0669 | 18.9982
4091 | -0.54137 | -1.2158 | 0.29413 | 0.11202 | 5.4803 | 4.6215 | 5.7033 | 4.479 | 3.8914 | 1.475 | 16.0558 | 16.55 | 16.55
4092 | 1.0343 | 0.86404 | 0.8495 | 0.80622 | 4.9341 | 6.5664 | 4.7596 | 5.9801 | 4.9284 | 2.4387 | 19.9194 | 17.0608 | 19.9194
4093 | -0.2342 | 1.1183 | 0.40742 | 0.86827 | 4.4655 | 4.9714 | 6.6685 | 6.198 | 4.4315 | 2.1305 | 17.7655 | 17.696 | 17.7655
4094 | 1.2352 | 0.3935 | 0.89162 | 0.65303 | 4.7721 | 6.8114 | 7.2095 | 5.577 | 4.7676 | 2.2391 | 19.3996 | 18.9883 | 19.3996
4095 | 0.53085 | 0.38594 | 0.70224 | 0.65023 | 3.7359 | 5.9278 | 6.671 | 5.5706 | 4.4285 | 2.1687 | 17.403 | 17.0041 | 17.403
4096 | -1.3715 | -0.86363 | 0.085115 | 0.1939 | 4.8296 | 3.8482 | 6.4743 | 4.6618 | 3.4713 | 2.0734 | 15.413 | 16.8485 | 16.8485
4097 | -1.2192 | -1.5129 | 0.11138 | 0.065152 | 3.3427 | 3.9687 | 7.4127 | 4.3534 | 3.5089 | 1.8594 | 13.5242 | 16.1236 | 16.1236
4098 | -1.4993 | -1.4932 | 0.066898 | 0.067689 | 4.4575 | 3.7548 | 5.2008 | 4.3609 | 3.9398 | 2.1481 | 14.7213 | 15.7462 | 15.7462
4099 | -0.54556 | -0.85845 | 0.29268 | 0.19532 | 3.4697 | 4.617 | 3.8298 | 4.6648 | 4.5526 | 1.6526 | 14.404 | 13.5048 | 14.404
4100 | 0.77419 | 0.63179 | 0.78059 | 0.73624 | 4.9024 | 6.2393 | 5.835 | 5.78 | 5.2165 | 2.0255 | 18.9472 | 17.9794 | 18.9472
4101 | -1.7292 | -1.2352 | 0.041887 | 0.10838 | 2.8945 | 3.6045 | 5.531 | 4.47 | 4.8424 | 1.8471 | 12.816 | 15.115 | 15.115
4102 | 0.024899 | 1.1493 | 0.50993 | 0.87479 | 2.5546 | 5.2857 | 5.5996 | 6.2243 | 3.8096 | 1.7858 | 15.8505 | 13.7496 | 15.8505
4103 | -1.145 | -0.53001 | 0.1261 | 0.29805 | 4.5133 | 4.0311 | 5.6575 | 4.8684 | 3.0607 | 2.4894 | 15.9021 | 15.721 | 15.9021
4104 | -0.5223 | 0.028154 | 0.30073 | 0.51123 | 4.0323 | 4.6424 | 4.7094 | 5.2775 | 4.9744 | 1.4097 | 15.3618 | 15.1258 | 15.3618
4105 | -0.75567 | -0.40861 | 0.22492 | 0.34141 | 4.9837 | 4.3958 | 5.3747 | 4.9511 | 5.0981 | 2.2574 | 16.588 | 17.7139 | 17.7139
4106 | -1.4126 | -1.2238 | 0.078886 | 0.11051 | 2.6129 | 3.8174 | 7.3213 | 4.4752 | 3.465 | 2.285 | 13.1906 | 15.6843 | 15.6843
4107 | -0.53337 | 0.51682 | 0.29689 | 0.69736 | 3.7717 | 4.6303 | 7.0215 | 5.6816 | 4.1061 | 1.9666 | 16.0501 | 16.8659 | 16.8659
4108 | 2.076 | 2.0665 | 0.98105 | 0.98061 | 3.4914 | 7.7131 | 5.8352 | 6.9406 | 5.0541 | 2.3 | 20.445 | 16.6806 | 20.445
4109 | 1.2457 | 1.2235 | 0.89356 | 0.88942 | 3.5314 | 6.824 | 7.6837 | 6.2869 | 4.3342 | 1.7025 | 18.3448 | 17.2518 | 18.3448
4110 | 0.1099 | 0.49126 | 0.54375 | 0.68838 | 4.7473 | 5.3916 | 5.3154 | 5.6598 | 3.9955 | 1.9976 | 17.7962 | 16.0558 | 17.7962
4111 | 0.29031 | 0.23795 | 0.61421 | 0.59404 | 4.2061 | 5.6197 | 5.6669 | 5.4472 | 4.7854 | 2.0634 | 17.3364 | 16.7218 | 17.3364
4112 | 2.0495 | 2.0698 | 0.97979 | 0.98076 | 3.4448 | 7.6884 | 7.4853 | 6.9428 | 3.8308 | 1.8473 | 19.9233 | 16.6081 | 19.9233
4113 | 1.1216 | 0.75154 | 0.86898 | 0.77384 | 3.8478 | 6.6739 | 6.6526 | 5.8831 | 3.7925 | 2.0289 | 18.4337 | 16.3217 | 18.4337
4114 | -0.69564 | -0.47569 | 0.24333 | 0.31715 | 5.0316 | 4.4573 | 4.7406 | 4.9049 | 4.0609 | 2.1907 | 16.5845 | 16.0238 | 16.5845
4115 | 0.004656 | 0.093354 | 0.50186 | 0.53719 | 4.0366 | 5.2606 | 6.3814 | 5.3295 | 4.2081 | 1.937 | 16.5637 | 16.5631 | 16.5637
4116 | 0.97414 | 0.80228 | 0.83501 | 0.7888 | 3.351 | 6.4916 | 5.3723 | 5.9268 | 4.0984 | 1.4061 | 17.1756 | 14.2279 | 17.1756
4117 | 1.7086 | 0.41861 | 0.95623 | 0.66225 | 5.084 | 7.3479 | 7.2949 | 5.5982 | 4.9907 | 1.4986 | 19.5287 | 18.8682 | 19.5287
4118 | -0.57636 | 0.3896 | 0.28219 | 0.65158 | 3.0666 | 4.5836 | 6.423 | 5.5737 | 4.2104 | 1.4277 | 14.6515 | 15.1277 | 15.1277
4119 | -0.51978 | -0.013646 | 0.30161 | 0.49456 | 4.9051 | 4.6452 | 6.3703 | 5.2445 | 4.545 | 2.1902 | 16.985 | 18.0107 | 18.0107
4120 | 0.8419 | 1.0636 | 0.80008 | 0.85624 | 4.4927 | 6.3253 | 5.7688 | 6.1514 | 4.5736 | 2.3055 | 19.2749 | 17.1406 | 19.2749
4121 | 1.9489 | 3.2933 | 0.97435 | 0.9995 | 4.95 | 7.5924 | 3.5245 | 7.5924 | 3.6938 | 1.8771 | 22.012 | 14.0454 | 22.012
4122 | 1.3738 | -0.92937 | 0.91525 | 0.17635 | 5.3755 | 6.9751 | 7.1053 | 4.6249 | 4.3429 | 2.3584 | 19.334 | 19.1822 | 19.334
4123 | -0.58055 | -0.75001 | 0.28077 | 0.22662 | 4.5366 | 4.579 | 6.5311 | 4.7286 | 3.7875 | 2.5084 | 16.3525 | 17.3635 | 17.3635
4124 | -0.35966 | 0.38253 | 0.35955 | 0.64896 | 2.5941 | 4.8251 | 6.3316 | 5.5677 | 3.2994 | 1.5497 | 14.5366 | 13.7747 | 14.5366
4125 | 0.88694 | -0.018004 | 0.81244 | 0.49282 | 3.7342 | 6.3822 | 5.8562 | 5.2411 | 3.8477 | 2.2631 | 17.6206 | 15.7012 | 17.6206
4126 | 0.38884 | 1.0872 | 0.6513 | 0.86153 | 4.3939 | 5.7456 | 6.4674 | 6.1716 | 4.2323 | 2.6075 | 18.9185 | 17.701 | 18.9185
4127 | 0.14453 | 0.96656 | 0.55746 | 0.83312 | 3.3062 | 5.4351 | 4.0708 | 6.0683 | 3.6685 | 2.0018 | 16.8114 | 13.0473 | 16.8114
4128 | 1.4576 | -1.0413 | 0.92752 | 0.14888 | 3.0097 | 7.0716 | 6.2633 | 4.565 | 4.2429 | 2.0753 | 16.7215 | 15.591 | 16.7215
4129 | 0.13257 | 0.27686 | 0.55273 | 0.60905 | 4.396 | 5.4201 | 6.266 | 5.4794 | 5.0009 | 1.7385 | 17.034 | 17.4013 | 17.4013
4130 | -0.94132 | 0.29774 | 0.17327 | 0.61705 | 3.6956 | 4.2142 | 6.0477 | 5.4968 | 3.896 | 2.2873 | 15.6939 | 15.9266 | 15.9266
4131 | -0.9248 | -1.7535 | 0.17753 | 0.039761 | 3.9656 | 4.2298 | 5.9671 | 4.2702 | 5.3337 | 1.9584 | 14.4239 | 17.2248 | 17.2248
4132 | -0.61681 | -0.086845 | 0.26868 | 0.4654 | 2.8823 | 4.5402 | 7.2531 | 5.1876 | 4.0543 | 1.1519 | 13.762 | 15.3416 | 15.3416
4133 | -0.047766 | 0.54191 | 0.48095 | 0.70606 | 4.4444 | 5.1961 | 4.9427 | 5.703 | 4.3887 | 1.8552 | 17.1987 | 15.6309 | 17.1987
4134 | -0.19515 | -0.33104 | 0.42264 | 0.37031 | 2.8823 | 5.0178 | 5.5445 | 5.0059 | 4.7335 | 2.6588 | 15.5649 | 15.8191 | 15.8191
4135 | -1.0292 | -0.6658 | 0.15168 | 0.25277 | 3.743 | 4.133 | 6.5368 | 4.7805 | 3.3495 | 2.0211 | 14.6776 | 15.6504 | 15.6504
4136 | 1.2003 | 0.76795 | 0.885 | 0.77874 | 4.555 | 6.7696 | 6.5484 | 5.8972 | 4.1571 | 1.9847 | 19.2064 | 17.2451 | 19.2064
4137 | -1.2638 | -0.27449 | 0.10315 | 0.39185 | 4.9473 | 3.9324 | 3.9121 | 5.0468 | 3.8821 | 1.3537 | 15.2801 | 14.0951 | 15.2801
4138 | 0.58928 | 1.2488 | 0.72216 | 0.89413 | 4.9566 | 6.0028 | 3.2259 | 6.3082 | 3.6505 | 1.3903 | 18.6578 | 13.2232 | 18.6578
4139 | 1.0768 | -0.68925 | 0.85922 | 0.24533 | 5.057 | 6.619 | 6.3203 | 4.7658 | 4.5072 | 1.8996 | 18.3414 | 17.7841 | 18.3414
4140 | -0.08762 | 0.58179 | 0.46509 | 0.71965 | 3.455 | 5.1474 | 5.4431 | 5.7371 | 4.7399 | 2.7102 | 17.0497 | 16.3482 | 17.0497
4141 | -1.8482 | -1.3161 | 0.032288 | 0.094076 | 4.7399 | 3.5354 | 6.9403 | 4.4337 | 3.5619 | 1.3731 | 14.0821 | 16.6152 | 16.6152
4142 | 2.1189 | 1.7316 | 0.98295 | 0.95833 | 2.6278 | 7.7524 | 5.2322 | 6.6966 | 5.6654 | 2.4456 | 19.5224 | 15.971 | 19.5224
4143 | -0.25665 | 0.88878 | 0.39873 | 0.81294 | 3.3708 | 4.9449 | 6.3741 | 6.0014 | 3.7875 | 1.6539 | 15.9711 | 15.1864 | 15.9711
4144 | -1.6325 | -1.7212 | 0.051283 | 0.042607 | 3.1896 | 3.6649 | 6.3444 | 4.2804 | 5.3679 | 2.1572 | 13.2922 | 17.0592 | 17.0592
4145 | 0.016622 | 0.81419 | 0.50663 | 0.79223 | 4.68 | 5.2754 | 7.1943 | 5.9371 | 3.8792 | 1.9783 | 17.8708 | 17.7318 | 17.8708
4146 | -1.1635 | -1.7283 | 0.12231 | 0.041967 | 4.1131 | 4.0153 | 6.6749 | 4.2781 | 3.3059 | 1.5002 | 13.9067 | 15.5941 | 15.5941
4147 | 0.1109 | -0.47233 | 0.54415 | 0.31835 | 5.1741 | 5.3929 | 6.309 | 4.9072 | 3.1518 | 2.7139 | 18.188 | 17.3487 | 18.188
4148 | 2.0004 | 2.8858 | 0.97727 | 0.99805 | 4.9386 | 7.6421 | 5.6819 | 7.4201 | 5.239 | 1.5786 | 21.5794 | 17.4381 | 21.5794
4149 | 1.6523 | -0.49547 | 0.95076 | 0.31013 | 4.6404 | 7.2877 | 5.9744 | 4.8915 | 4.1568 | 1.9306 | 18.7502 | 16.7022 | 18.7502
4150 | 1.4369 | 1.4014 | 0.92463 | 0.91945 | 4.7519 | 7.048 | 5.827 | 6.4347 | 3.7571 | 1.5361 | 19.7706 | 15.872 | 19.7706
4151 | 0.015103 | -0.42419 | 0.50603 | 0.33571 | 5.0161 | 5.2735 | 6.0886 | 4.9403 | 4.071 | 1.904 | 17.1339 | 17.0797 | 17.1339
4152 | 2.1034 | 1.5673 | 0.98229 | 0.94148 | 3.1954 | 7.7383 | 6.2692 | 6.5686 | 4.9764 | 2.4218 | 19.9241 | 16.8628 | 19.9241
4153 | -0.15644 | -0.60562 | 0.43784 | 0.27238 | 3.7761 | 5.0642 | 6.6007 | 4.8188 | 4.0113 | 1.8475 | 15.5066 | 16.2356 | 16.2356
4154 | 1.8512 | 0.51545 | 0.96793 | 0.69688 | 2.8086 | 7.4956 | 6.8354 | 5.6804 | 3.2254 | 1.8896 | 17.8742 | 14.759 | 17.8742
4155 | 1.0308 | 0.4397 | 0.84867 | 0.66992 | 4.9435 | 6.5621 | 5.8474 | 5.616 | 4.245 | 2.179 | 19.3006 | 17.2149 | 19.3006
4156 | -1.1626 | -0.12483 | 0.12251 | 0.45033 | 4.7867 | 4.0161 | 4.6848 | 5.1585 | 3.9423 | 2.0642 | 16.0256 | 15.478 | 16.0256
4157 | -0.62082 | -0.60123 | 0.26736 | 0.27384 | 3.7658 | 4.5359 | 4.9763 | 4.8217 | 4.6708 | 1.8088 | 14.9322 | 15.2218 | 15.2218
4158 | -0.47774 | -2.3655 | 0.31642 | 0.009002 | 3.1057 | 4.6916 | 4.6233 | 4.1238 | 4.2347 | 2.1951 | 14.1163 | 14.1589 | 14.1589
4159 | 0.39977 | -1.0722 | 0.65534 | 0.14181 | 4.5231 | 5.7596 | 7.0717 | 4.549 | 3.2948 | 2.2501 | 17.0818 | 17.1397 | 17.1397
4160 | 1.4051 | 1.1579 | 0.92 | 0.87654 | 4.6878 | 7.0114 | 4.0589 | 6.2316 | 4.859 | 2.1713 | 20.1021 | 15.777 | 20.1021
4161 | -1.4123 | -1.1607 | 0.078924 | 0.12289 | 4.6328 | 3.8176 | 5.5899 | 4.5052 | 4.7492 | 2.7228 | 15.6783 | 17.6946 | 17.6946
4162 | 1.0411 | 0.32555 | 0.85108 | 0.62762 | 3.4973 | 6.5749 | 4.4056 | 5.52 | 4.5501 | 1.8451 | 17.4373 | 14.2982 | 17.4373
4163 | 1.432 | 0.36661 | 0.92393 | 0.64305 | 5.4775 | 7.0424 | 6.9814 | 5.5544 | 4.3968 | 2.047 | 20.1213 | 18.9027 | 20.1213
4164 | 0.50746 | 0.83055 | 0.69408 | 0.79689 | 5.1607 | 5.8977 | 6.449 | 5.9512 | 3.5629 | 2.0441 | 19.0538 | 17.2167 | 19.0538
4165 | -1.07 | -1.0789 | 0.14231 | 0.14032 | 3.6591 | 4.0965 | 6.2789 | 4.5456 | 4.14 | 2.3841 | 14.6853 | 16.4621 | 16.4621
4166 | 2.3189 | 1.1061 | 0.9898 | 0.86567 | 4.2839 | 7.926 | 7.0984 | 6.1877 | 3.3237 | 1.9103 | 20.3078 | 16.6162 | 20.3078
4167 | -0.68279 | 0.042377 | 0.24737 | 0.5169 | 3.5363 | 4.4707 | 3.8056 | 5.2888 | 4.7975 | 2.1123 | 15.4081 | 14.2517 | 15.4081
4168 | 1.8036 | 0.20806 | 0.96435 | 0.58241 | 4.816 | 7.4471 | 7.7444 | 5.4226 | 3.8682 | 1.9815 | 19.6673 | 18.4101 | 19.6673
4169 | -0.41626 | -0.23909 | 0.33861 | 0.40552 | 4.5324 | 4.7606 | 6.9565 | 5.0728 | 4.7583 | 2.4594 | 16.8252 | 18.7066 | 18.7066
4170 | 2.1997 | 1.0591 | 0.98609 | 0.85523 | 4.2135 | 7.8244 | 4.8904 | 6.1476 | 3.1161 | 2.4695 | 20.6551 | 14.6895 | 20.6551
4171 | 1.393 | 0.46406 | 0.91819 | 0.6787 | 3.8593 | 6.9974 | 5.9229 | 5.6367 | 4.7547 | 1.8658 | 18.3591 | 16.4027 | 18.3591
4172 | 0.23459 | -1.0361 | 0.59273 | 0.15007 | 5.509 | 5.5489 | 3.9367 | 4.5676 | 3.6223 | 1.9737 | 17.5992 | 15.0417 | 17.5992
4173 | -0.17619 | 0.89025 | 0.43007 | 0.81333 | 5.039 | 5.0405 | 5.1682 | 6.0027 | 3.3579 | 2.1154 | 18.1975 | 15.6805 | 18.1975
4174 | -2.2129 | -2.7792 | 0.013452 | 0.0027244 | 4.4557 | 3.359 | 4.2652 | 4.0671 | 5.0533 | 1.7539 | 13.6357 | 15.5281 | 15.5281
4175 | 0.71604 | -0.31758 | 0.76302 | 0.3754 | 2.8545 | 6.1651 | 5.0003 | 5.0156 | 4.755 | 1.9268 | 15.9619 | 14.5365 | 15.9619
4176 | 0.30744 | 1.2274 | 0.62075 | 0.89017 | 2.9364 | 5.6416 | 5.2883 | 6.2902 | 4.5697 | 2.4654 | 17.3336 | 15.2598 | 17.3336
4177 | -1.3047 | -1.7149 | 0.095994 | 0.043186 | 4.2844 | 3.8998 | 4.2138 | 4.2825 | 4.4651 | 1.1233 | 13.59 | 14.0867 | 14.0867
4178 | 0.078192 | -0.007036 | 0.53116 | 0.49719 | 3.0794 | 5.352 | 6.365 | 5.2497 | 5.3101 | 1.5047 | 15.1857 | 16.2591 | 16.2591
4179 | 0.71969 | 0.57289 | 0.76414 | 0.71664 | 2.6911 | 6.1698 | 6.312 | 5.7295 | 4.4085 | 1.3646 | 15.955 | 14.7762 | 15.955
4180 | 0.6833 | 0.38153 | 0.75279 | 0.64859 | 3.8298 | 6.1233 | 4.7525 | 5.5669 | 3.8548 | 2.1708 | 17.6907 | 14.6078 | 17.6907
4181 | 0.77054 | 0.30493 | 0.77951 | 0.61979 | 3.1478 | 6.2346 | 4.6978 | 5.5028 | 4.1859 | 1.9347 | 16.8199 | 13.9662 | 16.8199
4182 | -1.6263 | -1.5148 | 0.051947 | 0.064911 | 3.6946 | 3.669 | 4.5908 | 4.3527 | 3.7692 | 2.4828 | 14.199 | 14.5374 | 14.5374
4183 | -0.77513 | -0.88186 | 0.21913 | 0.18893 | 4.495 | 4.3761 | 6.5939 | 4.6514 | 4.3488 | 1.8264 | 15.3489 | 17.2641 | 17.2641
4184 | -0.0099047 | 1.8608 | 0.49605 | 0.96861 | 5.5728 | 5.2427 | 7.4772 | 6.7936 | 3.3457 | 2.084 | 19.693 | 18.4797 | 19.693
4185 | -0.49254 | -1.3705 | 0.31117 | 0.085271 | 5.4882 | 4.6752 | 6.4453 | 4.4104 | 5.5441 | 2.7492 | 17.323 | 20.2268 | 20.2268
4186 | -1.001 | -0.44408 | 0.15841 | 0.32849 | 3.7834 | 4.1587 | 6.5416 | 4.9265 | 4.8702 | 1.896 | 14.7647 | 17.0913 | 17.0913
4187 | 0.60271 | 1.2947 | 0.72665 | 0.90229 | 3.2745 | 6.02 | 2.7371 | 6.3465 | 4.2883 | 1.6676 | 17.3086 | 11.9675 | 17.3086
4188 | 0.37864 | -1.1531 | 0.64752 | 0.12443 | 3.577 | 5.7325 | 6.4492 | 4.5088 | 3.1281 | 1.9816 | 15.8 | 15.1359 | 15.8
4189 | -0.086078 | -1.142 | 0.4657 | 0.12673 | 4.6609 | 5.1493 | 6.4035 | 4.5142 | 3.1905 | 1.6607 | 15.9851 | 15.9155 | 15.9851
4190 | -0.95288 | -0.80541 | 0.17032 | 0.21029 | 2.4943 | 4.2033 | 4.5601 | 4.6956 | 3.6897 | 1.9904 | 13.3836 | 12.7345 | 13.3836
4191 | -0.40835 | 0.12809 | 0.34151 | 0.55096 | 3.9319 | 4.7696 | 6.2588 | 5.3575 | 4.2679 | 2.3172 | 16.3762 | 16.7758 | 16.7758
4192 | 1.426 | 0.78413 | 0.92307 | 0.78352 | 3.3638 | 7.0355 | 6.5335 | 5.9112 | 3.2409 | 2.3577 | 18.6683 | 15.496 | 18.6683
4193 | 0.28659 | 0.619 | 0.61279 | 0.73204 | 3.9111 | 5.615 | 5.1576 | 5.769 | 6.2381 | 2.1263 | 17.4214 | 17.433 | 17.433
4194 | 0.51696 | -0.19732 | 0.69741 | 0.42179 | 2.8852 | 5.9099 | 6.9277 | 5.1038 | 3.849 | 1.4915 | 15.3904 | 15.1534 | 15.3904
4195 | 0.53908 | 0.75843 | 0.70509 | 0.7759 | 4.248 | 5.9383 | 6.0319 | 5.889 | 3.1509 | 2.3492 | 18.4245 | 15.78 | 18.4245
4196 | 0.15089 | 1.228 | 0.55997 | 0.89028 | 4.2339 | 5.4431 | 6.1966 | 6.2907 | 3.6426 | 2.4298 | 18.3975 | 16.5029 | 18.3975
4197 | -1.291 | -0.31694 | 0.098355 | 0.37564 | 3.0511 | 3.9107 | 7.0871 | 5.016 | 4.6038 | 1.5229 | 13.5007 | 16.2649 | 16.2649
4198 | -1.2127 | 0.70377 | 0.11262 | 0.75921 | 4.6188 | 3.9741 | 5.7935 | 5.8419 | 3.2772 | 2.0538 | 16.4886 | 15.7433 | 16.4886
4199 | -0.12842 | -0.78685 | 0.44891 | 0.21569 | 3.8688 | 5.0979 | 4.8205 | 4.7065 | 3.9794 | 2.1182 | 15.7915 | 14.7869 | 15.7915
4200 | -0.30884 | -0.87309 | 0.37872 | 0.19131 | 4.9782 | 4.8839 | 4.9693 | 4.6564 | 4.6874 | 2.1559 | 16.6743 | 16.7908 | 16.7908
4201 | -1.7653 | -1.6256 | 0.038756 | 0.05202 | 4.2928 | 3.5829 | 3.9077 | 4.3124 | 3.2756 | 2.3187 | 14.5068 | 13.7948 | 14.5068
4202 | 0.95354 | 0.70146 | 0.82984 | 0.75849 | 3.297 | 6.4659 | 5.1521 | 5.8399 | 5.6878 | 1.9009 | 17.5038 | 16.0379 | 17.5038
4203 | 0.23414 | 1.564 | 0.59256 | 0.94109 | 3.9111 | 5.5483 | 6.8933 | 6.5659 | 3.7256 | 1.9725 | 17.9979 | 16.5026 | 17.9979
4204 | 1.0291 | 0.84454 | 0.84829 | 0.80082 | 3.6541 | 6.5601 | 5.6592 | 5.9633 | 3.923 | 2.2598 | 18.4373 | 15.4961 | 18.4373
4205 | 2.15 | 1.0188 | 0.98422 | 0.84584 | 3.9076 | 7.7804 | 3.8862 | 6.1131 | 4.3377 | 2.2185 | 20.0196 | 14.3499 | 20.0196
4206 | -0.082201 | -0.76652 | 0.46724 | 0.22168 | 3.6456 | 5.154 | 7.2203 | 4.7187 | 4.2305 | 1.9187 | 15.437 | 17.0152 | 17.0152
4207 | 0.0057767 | -0.92059 | 0.5023 | 0.17863 | 4.3912 | 5.262 | 6.1344 | 4.6297 | 5.443 | 2.2004 | 16.4834 | 18.169 | 18.169
4208 | -0.40309 | -0.75201 | 0.34344 | 0.22602 | 5.3088 | 4.7755 | 4.8953 | 4.7274 | 5.66 | 1.7811 | 16.5929 | 17.6453 | 17.6453
4209 | 0.16691 | -0.21803 | 0.56628 | 0.4137 | 2.7884 | 5.4633 | 3.5091 | 5.0884 | 4.7104 | 2.0016 | 15.3416 | 13.0096 | 15.3416
4210 | -0.97453 | -0.82846 | 0.1649 | 0.2037 | 3.6099 | 4.1831 | 4.3721 | 4.6821 | 4.1689 | 1.8387 | 14.3138 | 13.9895 | 14.3138
4211 | -1.2494 | -1.7353 | 0.10575 | 0.041344 | 2.6781 | 3.944 | 5.5418 | 4.2759 | 4.9808 | 2.2917 | 13.1897 | 15.4923 | 15.4923
4212 | -0.49544 | -0.90171 | 0.31015 | 0.1836 | 3.2905 | 4.672 | 6.3764 | 4.6402 | 4.7665 | 2.3858 | 14.9885 | 16.8192 | 16.8192
4213 | 1.2767 | -0.30476 | 0.89915 | 0.38028 | 2.8744 | 6.861 | 5.0859 | 5.0248 | 4.0893 | 2.039 | 16.7993 | 14.0886 | 16.7993
4214 | 0.019041 | -0.20447 | 0.5076 | 0.41899 | 4.3607 | 5.2784 | 5.9259 | 5.0984 | 3.1218 | 1.8242 | 16.5617 | 15.2325 | 16.5617
4215 | -1.5198 | -1.1344 | 0.06428 | 0.12831 | 2.9303 | 3.7405 | 4.3997 | 4.5179 | 3.6614 | 1.9361 | 13.1249 | 12.9276 | 13.1249
4216 | -0.11175 | 0.40231 | 0.45551 | 0.65627 | 3.3161 | 5.1181 | 6.3633 | 5.5844 | 3.5518 | 2.4449 | 16.4635 | 15.6761 | 16.4635
4217 | -1.0055 | -1.0258 | 0.15732 | 0.15248 | 4.3335 | 4.1546 | 7.3759 | 4.573 | 3.3746 | 1.1455 | 14.2066 | 16.2295 | 16.2295
4218 | 1.672 | 2.5291 | 0.95273 | 0.99428 | 4.2608 | 7.3089 | 5.262 | 7.2332 | 4.8155 | 1.091 | 19.8939 | 15.4294 | 19.8939
4219 | -0.70013 | 0.27631 | 0.24192 | 0.60885 | 3.3271 | 4.4527 | 5.4562 | 5.479 | 3.531 | 2.603 | 15.8618 | 14.9174 | 15.8618
4220 | -0.30609 | -0.97658 | 0.37977 | 0.16439 | 2.6894 | 4.8871 | 6.0863 | 4.5991 | 4.3462 | 2.0669 | 14.2425 | 15.1888 | 15.1888
4221 | -0.66634 | -1.5787 | 0.2526 | 0.057203 | 3.5476 | 4.4879 | 5.9143 | 4.329 | 4.322 | 1.8913 | 14.2558 | 15.6752 | 15.6752
4222 | 0.24841 | -0.58595 | 0.59809 | 0.27896 | 2.9234 | 5.5664 | 4.3418 | 4.8316 | 4.1847 | 2.2321 | 15.5535 | 13.682 | 15.5535
4223 | 0.12393 | -1.0679 | 0.54932 | 0.14278 | 3.8818 | 5.4092 | 4.5315 | 4.5512 | 4.0259 | 1.8469 | 15.6891 | 14.286 | 15.6891
4224 | 0.39962 | 0.43462 | 0.65528 | 0.66808 | 3.4719 | 5.7594 | 4.6825 | 5.6117 | 3.9379 | 2.6002 | 17.4432 | 14.6925 | 17.4432
4225 | 0.46739 | -0.81325 | 0.67989 | 0.20804 | 4.7867 | 5.8463 | 6.4862 | 4.691 | 3.7049 | 1.55 | 16.874 | 16.5279 | 16.874
4226 | 1.53 | 0.91831 | 0.93699 | 0.82077 | 4.1363 | 7.1534 | 4.65 | 6.0268 | 3.2949 | 2.2743 | 19.5907 | 14.3554 | 19.5907
4227 | 1.4517 | 0.86842 | 0.92671 | 0.80742 | 2.8759 | 7.065 | 6.6415 | 5.9839 | 5.0057 | 2.1462 | 18.071 | 16.6694 | 18.071
4228 | 0.14193 | -0.45166 | 0.55643 | 0.32576 | 4.6094 | 5.4318 | 4.4953 | 4.9213 | 3.6954 | 1.5007 | 16.4633 | 14.3009 | 16.4633
4229 | -0.86777 | -0.036981 | 0.19276 | 0.48525 | 2.7773 | 4.2845 | 6.1524 | 5.2263 | 4.9575 | 1.6027 | 13.8908 | 15.4899 | 15.4899
4230 | -0.26721 | -0.32913 | 0.39465 | 0.37103 | 3.2268 | 4.9325 | 7.3013 | 5.0073 | 3.3009 | 2.2503 | 15.4169 | 16.0793 | 16.0793
4231 | 0.51715 | 0.47751 | 0.69747 | 0.6835 | 4.9633 | 5.9102 | 5.8161 | 5.6481 | 3.1 | 2.5287 | 19.0502 | 16.408 | 19.0502
4232 | 0.15703 | -0.61015 | 0.56239 | 0.27088 | 2.7488 | 5.4508 | 5.5282 | 4.8159 | 4.1834 | 1.7332 | 14.7487 | 14.1935 | 14.7487
4233 | -1.665 | -0.19442 | 0.047952 | 0.42292 | 4.1388 | 3.6441 | 6.5352 | 5.1059 | 5.8037 | 2.3232 | 15.212 | 18.8009 | 18.8009
4234 | 2.1502 | 0.92285 | 0.98423 | 0.82196 | 4.4904 | 7.7806 | 6.3319 | 6.0307 | 4.3399 | 2.0194 | 20.3212 | 17.1817 | 20.3212
4235 | 0.15628 | -0.013041 | 0.56209 | 0.4948 | 3.9713 | 5.4499 | 5.908 | 5.245 | 3.8911 | 1.6127 | 16.2789 | 15.3832 | 16.2789
4236 | -0.73772 | -0.66694 | 0.23034 | 0.2524 | 4.6856 | 4.414 | 5.063 | 4.7798 | 5.5132 | 1.993 | 15.8725 | 17.2549 | 17.2549
4237 | 2.8469 | 2.392 | 0.99779 | 0.99162 | 4.3234 | 8.3068 | 5.8272 | 7.1522 | 4.1814 | 1.8905 | 21.673 | 16.2225 | 21.673
4238 | 1.1341 | 1.4277 | 0.87163 | 0.92331 | 3.4292 | 6.6893 | 3.8154 | 6.4562 | 4.7729 | 2.4988 | 19.0734 | 14.5163 | 19.0734
4239 | -1.038 | 0.65676 | 0.14964 | 0.74433 | 3.8302 | 4.1251 | 6.3335 | 5.8015 | 4.7256 | 2.1783 | 15.9351 | 17.0675 | 17.0675
4240 | 0.46206 | -0.72205 | 0.67798 | 0.23513 | 4.2304 | 5.8395 | 5.0501 | 4.7456 | 4.5726 | 1.9445 | 16.76 | 15.7975 | 16.76
4241 | 3.4062 | 2.509 | 0.99967 | 0.99395 | 5.2222 | 8.5934 | 7.1243 | 7.2216 | 3.9367 | 1.3175 | 22.3548 | 17.6007 | 22.3548
4242 | 0.45367 | -0.36773 | 0.67497 | 0.35654 | 3.3017 | 5.8287 | 5.7268 | 4.9798 | 4.7944 | 2.3112 | 16.4214 | 16.1341 | 16.4214
4243 | 0.28772 | -0.025787 | 0.61322 | 0.48971 | 4.182 | 5.6164 | 5.6679 | 5.235 | 3.5356 | 1.6503 | 16.6838 | 15.0359 | 16.6838
4244 | 0.72094 | 0.82595 | 0.76453 | 0.79558 | 3.7382 | 6.1714 | 4.7677 | 5.9473 | 4.565 | 2.1775 | 18.0343 | 15.2484 | 18.0343
4245 | 0.69537 | 0.803 | 0.75659 | 0.78901 | 5.7935 | 6.1387 | 3.693 | 5.9275 | 4.5134 | 1.8408 | 19.7005 | 15.8408 | 19.7005
4246 | 1.9298 | 0.2241 | 0.97319 | 0.58866 | 3.1684 | 7.5738 | 5.5481 | 5.4358 | 3.8238 | 2.2327 | 18.4108 | 14.773 | 18.4108
4247 | 0.14499 | 0.50212 | 0.55764 | 0.69221 | 3.1313 | 5.4357 | 5.4768 | 5.669 | 3.3457 | 1.812 | 16.048 | 13.7659 | 16.048
4248 | -0.52249 | -0.45499 | 0.30066 | 0.32456 | 3.7875 | 4.6422 | 5.9176 | 4.919 | 5.589 | 2.7087 | 16.0574 | 18.0028 | 18.0028
4249 | -0.68547 | 0.68476 | 0.24652 | 0.75325 | 4.5048 | 4.4679 | 5.7503 | 5.8256 | 6.3027 | 1.9593 | 16.7576 | 18.5172 | 18.5172
4250 | -0.89446 | -1.8326 | 0.18554 | 0.033429 | 4.1679 | 4.2587 | 5.5692 | 4.2462 | 4.1631 | 2.6182 | 15.291 | 16.5183 | 16.5183
4251 | -0.019031 | -1.0412 | 0.49241 | 0.1489 | 3.4398 | 5.2314 | 7.2059 | 4.565 | 4.8844 | 1.761 | 14.9972 | 17.291 | 17.291
4252 | 1.5574 | 1.6932 | 0.94031 | 0.95479 | 5.0341 | 7.1839 | 6.3473 | 6.6671 | 3.4753 | 1.8396 | 20.7247 | 16.6963 | 20.7247
4253 | 0.81838 | -0.10322 | 0.79343 | 0.45889 | 3.4354 | 6.2954 | 4.6088 | 5.175 | 4.4595 | 2.1349 | 17.0408 | 14.6387 | 17.0408
4254 | -0.94814 | 0.56603 | 0.17153 | 0.71431 | 3.8354 | 4.2078 | 6.3143 | 5.7236 | 3.096 | 2.0481 | 15.8149 | 15.2937 | 15.8149
4255 | 1.0444 | -0.14745 | 0.85185 | 0.44139 | 3.9817 | 6.579 | 3.5364 | 5.1413 | 4.0459 | 1.3129 | 17.0149 | 12.8769 | 17.0149
4256 | -0.39193 | -0.8339 | 0.34755 | 0.20217 | 4.707 | 4.7882 | 6.5185 | 4.6789 | 3.653 | 1.7357 | 15.9098 | 16.6142 | 16.6142
4257 | -0.82753 | -1.0535 | 0.20397 | 0.14606 | 3.256 | 4.3239 | 5.0738 | 4.5586 | 6.0052 | 2.4596 | 14.5981 | 16.7946 | 16.7946
4258 | 0.75433 | 0.30811 | 0.77467 | 0.621 | 4.8511 | 6.214 | 5.6903 | 5.5054 | 4.4075 | 2.0035 | 18.574 | 16.9524 | 18.574
4259 | -1.9236 | -1.9878 | 0.027205 | 0.023418 | 3.7039 | 3.4947 | 7.5355 | 4.2038 | 5.3425 | 2.0511 | 13.4535 | 18.6331 | 18.6331
4260 | 0.10525 | 0.91812 | 0.54191 | 0.82072 | 4.6397 | 5.3858 | 3.5669 | 6.0267 | 6.0603 | 2.5828 | 18.635 | 16.8497 | 18.635
4261 | -1.3485 | 0.71322 | 0.088741 | 0.76215 | 5.0977 | 3.8657 | 4.4297 | 5.8501 | 3.8879 | 2.2744 | 17.0878 | 15.6896 | 17.0878
4262 | -0.964 | -0.92993 | 0.16752 | 0.1762 | 4.166 | 4.1929 | 5.6128 | 4.6245 | 5.158 | 1.6966 | 14.68 | 16.6334 | 16.6334
4263 | 0.63462 | -1.0902 | 0.73716 | 0.13782 | 3.3478 | 6.0609 | 7.2159 | 4.5399 | 3.3994 | 2.4912 | 16.4399 | 16.4543 | 16.4543
4264 | 0.73843 | -0.11253 | 0.76987 | 0.4552 | 5.1352 | 6.1937 | 5.7029 | 5.1679 | 5.7234 | 1.814 | 18.3108 | 18.3755 | 18.3755
4265 | -0.7286 | 0.1016 | 0.23312 | 0.54046 | 5.415 | 4.4234 | 5.6389 | 5.3361 | 3.7358 | 1.6269 | 16.8014 | 16.4166 | 16.8014
4266 | 1.3616 | 0.17393 | 0.91334 | 0.56904 | 3.6208 | 6.9609 | 6.76 | 5.3947 | 3.574 | 2.6035 | 18.58 | 16.5583 | 18.58
4267 | -0.12785 | 0.68659 | 0.44913 | 0.75383 | 3.9578 | 5.0986 | 4.4828 | 5.8271 | 3.765 | 1.6092 | 16.4928 | 13.8148 | 16.4928
4268 | -0.0037524 | 0.070808 | 0.4985 | 0.52822 | 2.8571 | 5.2502 | 3.339 | 5.3114 | 4.3892 | 1.2688 | 14.6875 | 11.854 | 14.6875
4269 | 0.18846 | 0.62554 | 0.57474 | 0.73419 | 4.5005 | 5.4905 | 7.1897 | 5.7746 | 5.839 | 2.1655 | 17.9311 | 19.6947 | 19.6947
4270 | 1.8049 | 2.1355 | 0.96445 | 0.98364 | 3.7643 | 7.4484 | 5.0069 | 6.9877 | 4.0381 | 1.4818 | 19.6822 | 14.2911 | 19.6822
4271 | -0.7273 | -0.6346 | 0.23352 | 0.26285 | 3.9226 | 4.4247 | 5.1445 | 4.8002 | 3.9963 | 1.6647 | 14.8122 | 14.7281 | 14.8122
4272 | 1.8275 | -0.079364 | 0.96619 | 0.46837 | 4.3482 | 7.4716 | 7.1953 | 5.1934 | 3.3377 | 2.4197 | 19.4328 | 17.3009 | 19.4328
4273 | -0.71797 | -1.652 | 0.23639 | 0.04927 | 4.6 | 4.4343 | 5.1782 | 4.3033 | 4.0024 | 1.5779 | 14.9155 | 15.3586 | 15.3586
4274 | 0.13404 | 1.1003 | 0.55332 | 0.8644 | 3.8868 | 5.4219 | 4.8159 | 6.1827 | 3.6133 | 1.6518 | 17.1432 | 13.9678 | 17.1432
4275 | 0.89673 | 1.4895 | 0.81507 | 0.93182 | 4.4065 | 6.3945 | 5.8914 | 6.5063 | 3.9232 | 2.0679 | 19.3752 | 16.289 | 19.3752
4276 | -0.66552 | -2.1263 | 0.25286 | 0.016741 | 3.8681 | 4.4887 | 5.8702 | 4.1709 | 3.671 | 2.2986 | 14.8262 | 15.7078 | 15.7078
4277 | 0.5504 | -0.62717 | 0.70898 | 0.26527 | 2.6867 | 5.9529 | 7.2843 | 4.805 | 3.4634 | 2.6833 | 16.1279 | 16.1177 | 16.1279
4278 | 0.64261 | 1.0563 | 0.73976 | 0.85459 | 3.4555 | 6.0711 | 5.4107 | 6.1452 | 3.7759 | 1.8237 | 17.4955 | 14.4658 | 17.4955
4279 | 1.2521 | 1.1703 | 0.89473 | 0.87907 | 4.0216 | 6.8317 | 6.5574 | 6.2421 | 6.1527 | 2.2311 | 19.3264 | 18.9628 | 19.3264
4280 | 0.86587 | 1.6931 | 0.80672 | 0.95478 | 5.0922 | 6.3556 | 3.2064 | 6.667 | 4.367 | 1.8847 | 19.9996 | 14.5504 | 19.9996
4281 | -0.77047 | -1.8233 | 0.22051 | 0.034129 | 3.9188 | 4.3808 | 5.0464 | 4.2489 | 3.6918 | 2.1855 | 14.7341 | 14.8425 | 14.8425
4282 | 1.4725 | 1.9281 | 0.92955 | 0.97308 | 4.1545 | 7.0886 | 5.4465 | 6.8427 | 3.8303 | 1.5658 | 19.6516 | 14.9971 | 19.6516
4283 | 0.83922 | 1.4491 | 0.79933 | 0.92635 | 4.1677 | 6.3219 | 6.3646 | 6.4736 | 4.1093 | 2.601 | 19.5642 | 17.2427 | 19.5642
4284 | -0.31346 | 0.59329 | 0.37697 | 0.72351 | 3.4726 | 4.8785 | 5.1388 | 5.747 | 4.2427 | 1.792 | 15.8901 | 14.6462 | 15.8901
4285 | 1.7388 | -0.39424 | 0.95896 | 0.3467 | 2.6779 | 7.3798 | 5.7145 | 4.9611 | 4.534 | 2.0363 | 17.0551 | 14.9626 | 17.0551
4286 | 1.5139 | 1.657 | 0.93498 | 0.95124 | 3.9573 | 7.1354 | 6.1861 | 6.6391 | 5.043 | 1.4873 | 19.2191 | 16.6737 | 19.2191
4287 | 1.0357 | 0.8773 | 0.84982 | 0.80984 | 4.8734 | 6.5681 | 6.8894 | 5.9915 | 4.7033 | 2.1395 | 19.5726 | 18.6056 | 19.5726
4288 | -0.040909 | 0.91841 | 0.48368 | 0.8208 | 3.5868 | 5.2045 | 4.5874 | 6.0269 | 4.2764 | 2.2203 | 17.0385 | 14.6709 | 17.0385
4289 | 0.90451 | 1.7722 | 0.81714 | 0.96182 | 3.8633 | 6.4043 | 5.0694 | 6.7275 | 5.0973 | 2.6297 | 19.6248 | 16.6597 | 19.6248
4290 | 0.97705 | 0.75704 | 0.83573 | 0.77549 | 3.7004 | 6.4953 | 5.4181 | 5.8878 | 4.6784 | 1.9323 | 18.0158 | 15.7293 | 18.0158
4291 | -0.66918 | 0.14239 | 0.25169 | 0.55662 | 4.3505 | 4.4849 | 6.839 | 5.3691 | 4.8347 | 1.6267 | 15.8311 | 17.6509 | 17.6509
4292 | -0.11866 | -0.35092 | 0.45277 | 0.36283 | 4.4978 | 5.1097 | 4.6904 | 4.9917 | 3.5196 | 2.2303 | 16.8296 | 14.9381 | 16.8296
4293 | -0.14013 | -0.19539 | 0.44428 | 0.42254 | 4.9864 | 5.0838 | 5.1301 | 5.1052 | 4.7589 | 1.6947 | 16.8701 | 16.5701 | 16.8701
4294 | 1.6337 | 0.22982 | 0.94884 | 0.59089 | 3.3444 | 7.2676 | 6.4675 | 5.4405 | 3.5408 | 1.9042 | 17.9568 | 15.2569 | 17.9568
4295 | 0.11315 | 0.61851 | 0.54505 | 0.73188 | 3.8149 | 5.3957 | 4.9994 | 5.7686 | 5.6887 | 1.2758 | 16.255 | 15.7788 | 16.255
4296 | -0.29269 | 1.5699 | 0.38488 | 0.94178 | 3.6712 | 4.9027 | 5.0782 | 6.5707 | 3.4559 | 2.0469 | 17.1915 | 14.2522 | 17.1915
4297 | -0.55851 | -0.67716 | 0.28825 | 0.24915 | 4.0959 | 4.6029 | 5.1051 | 4.7734 | 4.3653 | 1.5079 | 14.98 | 15.0743 | 15.0743
4298 | 0.45468 | 0.69756 | 0.67533 | 0.75727 | 4.2538 | 5.83 | 4.9949 | 5.8366 | 4.2043 | 1.7877 | 17.708 | 15.2407 | 17.708
4299 | 1.2471 | 0.70831 | 0.89383 | 0.76062 | 2.9044 | 6.8258 | 5.5192 | 5.8458 | 4.0828 | 2.0365 | 17.6125 | 14.5429 | 17.6125
4300 | -0.96445 | -1.9434 | 0.16741 | 0.025982 | 2.7195 | 4.1925 | 6.6331 | 4.2153 | 6.0865 | 2.194 | 13.3212 | 17.633 | 17.633
4301 | 1.0886 | 0.72405 | 0.86184 | 0.76548 | 3.6776 | 6.6335 | 5.7452 | 5.8594 | 5.7999 | 1.6885 | 17.8591 | 16.9113 | 17.8591
4302 | 0.52889 | 1.0734 | 0.70156 | 0.85845 | 4.0586 | 5.9252 | 7.261 | 6.1598 | 4.5497 | 2.1082 | 18.2518 | 17.9775 | 18.2518
4303 | 1.6432 | 1.8198 | 0.94983 | 0.96561 | 4.2506 | 7.2779 | 7.393 | 6.7632 | 5.0291 | 2.7552 | 21.0469 | 19.4278 | 21.0469
4304 | 0.61138 | 0.6215 | 0.72953 | 0.73287 | 4.8708 | 6.0311 | 6.7297 | 5.7712 | 4.0094 | 2.3222 | 18.9953 | 17.9321 | 18.9953
4305 | -0.072174 | -0.78475 | 0.47123 | 0.2163 | 5.1461 | 5.1663 | 4.8421 | 4.7078 | 4.9154 | 1.623 | 16.6431 | 16.5266 | 16.6431
4306 | -1.9609 | -1.7054 | 0.024948 | 0.044063 | 3.7484 | 3.4754 | 4.4416 | 4.2855 | 5.5134 | 1.3334 | 12.8427 | 15.0368 | 15.0368
4307 | 1.5052 | 1.9668 | 0.93387 | 0.9754 | 3.6519 | 7.1256 | 6.108 | 6.8706 | 3.9794 | 1.6863 | 19.3343 | 15.4256 | 19.3343
4308 | -0.53519 | 0.4569 | 0.29626 | 0.67613 | 3.6213 | 4.6283 | 7.14 | 5.6306 | 4.1004 | 2.2985 | 16.1786 | 17.1602 | 17.1602
4309 | 1.8824 | 1.4527 | 0.97011 | 0.92684 | 4.6106 | 7.5269 | 5.7577 | 6.4765 | 3.3379 | 2.7389 | 21.3529 | 16.445 | 21.3529
4310 | 0.16319 | 0.95343 | 0.56481 | 0.82981 | 2.7722 | 5.4586 | 6.6836 | 6.057 | 3.8779 | 2.1648 | 16.4525 | 15.4984 | 16.4525
4311 | -0.59303 | -1.2983 | 0.27658 | 0.097091 | 2.7344 | 4.5656 | 4.7607 | 4.4415 | 4.7903 | 2.3267 | 14.0682 | 14.6121 | 14.6121
4312 | 1.5022 | 0.79178 | 0.93347 | 0.78575 | 4.3062 | 7.1221 | 5.4674 | 5.9178 | 4.9422 | 2.174 | 19.5202 | 16.8898 | 19.5202
4313 | -0.66961 | 0.21722 | 0.25155 | 0.58598 | 4.1402 | 4.4844 | 6.8599 | 5.4302 | 4.0879 | 2.0533 | 16.1081 | 17.1413 | 17.1413
4314 | -1.9909 | -0.66378 | 0.023244 | 0.25342 | 5.1454 | 3.4602 | 4.8515 | 4.7818 | 3.9182 | 2.323 | 15.7104 | 16.2381 | 16.2381
4315 | 0.047692 | 0.80291 | 0.51902 | 0.78899 | 4.356 | 5.314 | 5.7427 | 5.9274 | 5.5068 | 1.403 | 17.0004 | 17.0085 | 17.0085
4316 | 0.4806 | -1.1638 | 0.6846 | 0.12226 | 2.4914 | 5.8632 | 5.508 | 4.5036 | 3.8978 | 1.8366 | 14.6949 | 13.7338 | 14.6949
4317 | -0.42975 | -1.3022 | 0.33369 | 0.096428 | 2.9436 | 4.7454 | 5.9652 | 4.4398 | 4.1206 | 1.3852 | 13.514 | 14.4146 | 14.4146
4318 | 1.1666 | 0.45427 | 0.87831 | 0.67518 | 5.1973 | 6.7287 | 3.2532 | 5.6284 | 4.0322 | 2.4314 | 19.9858 | 14.914 | 19.9858
4319 | -1.2464 | -0.69767 | 0.1063 | 0.24269 | 3.821 | 3.9464 | 5.0443 | 4.7606 | 5.2703 | 1.5793 | 14.1074 | 15.7148 | 15.7148
4320 | -0.24346 | -1.184 | 0.40382 | 0.11821 | 4.8004 | 4.9605 | 6.1079 | 4.494 | 5.2174 | 1.9797 | 16.2345 | 18.1053 | 18.1053
4321 | -0.16639 | -0.17772 | 0.43392 | 0.42947 | 4.8576 | 5.0522 | 4.8379 | 5.1185 | 4.1096 | 1.6628 | 16.6911 | 15.468 | 16.6911
4322 | -1.1581 | -1.0522 | 0.12341 | 0.14634 | 4.6589 | 4.0199 | 5.9542 | 4.5593 | 4.3498 | 2.3861 | 15.6242 | 17.349 | 17.349
4323 | 0.27251 | 0.27139 | 0.60738 | 0.60696 | 4.0429 | 5.597 | 5.8002 | 5.4749 | 5.457 | 2.1797 | 17.2946 | 17.4799 | 17.4799
4324 | 1.7052 | 1.1124 | 0.95592 | 0.86701 | 5.5205 | 7.3444 | 7.4402 | 6.193 | 4.6556 | 1.6696 | 20.7274 | 19.2858 | 20.7274
4325 | 0.90625 | 1.2719 | 0.8176 | 0.89829 | 3.5333 | 6.4065 | 5.6426 | 6.3275 | 4.5736 | 1.7238 | 17.9911 | 15.4734 | 17.9911
4326 | -0.77793 | 0.61484 | 0.2183 | 0.73067 | 3.2685 | 4.3733 | 4.5689 | 5.7655 | 4.3664 | 2.1046 | 15.5118 | 14.3083 | 15.5118
4327 | 0.08928 | -0.1953 | 0.53557 | 0.42258 | 3.8281 | 5.3658 | 6.4082 | 5.1053 | 3.755 | 1.8567 | 16.1559 | 15.848 | 16.1559
4328 | 0.18121 | 0.5771 | 0.5719 | 0.71806 | 2.6598 | 5.4813 | 5.1083 | 5.7331 | 3.9138 | 1.4664 | 15.3406 | 13.1483 | 15.3406
4329 | 1.2397 | 0.61727 | 0.89245 | 0.73147 | 3.322 | 6.8168 | 5.0049 | 5.7675 | 4.1511 | 2.7233 | 18.6297 | 15.2013 | 18.6297
4330 | 1.7649 | -0.10289 | 0.96121 | 0.45902 | 5.4955 | 7.4072 | 6.9893 | 5.1753 | 5.755 | 1.4874 | 19.5654 | 19.7272 | 19.7272
4331 | -1.2357 | -0.49446 | 0.10829 | 0.31049 | 3.3367 | 3.9552 | 7.434 | 4.8922 | 5.1021 | 2.6895 | 14.8736 | 18.5623 | 18.5623
4332 | -0.052316 | 1.8134 | 0.47914 | 0.96511 | 3.4717 | 5.1905 | 7.3223 | 6.7584 | 3.6509 | 1.9304 | 17.351 | 16.3752 | 17.351
4333 | 0.3034 | 2.5236 | 0.61921 | 0.99419 | 4.0449 | 5.6364 | 6.7876 | 7.23 | 4.7442 | 1.9938 | 18.905 | 17.5704 | 18.905
4334 | 0.9559 | 0.81826 | 0.83044 | 0.7934 | 3.975 | 6.4688 | 6.9867 | 5.9406 | 4.6342 | 2.7731 | 19.1575 | 18.369 | 19.1575
4335 | -0.93825 | -0.20852 | 0.17406 | 0.41741 | 3.6718 | 4.2171 | 5.7899 | 5.0954 | 4.9388 | 2.2577 | 15.2419 | 16.6582 | 16.6582
4336 | -0.35239 | 1.5101 | 0.36227 | 0.93449 | 5.5577 | 4.8335 | 4.9147 | 6.5229 | 5.3902 | 2.0022 | 18.9162 | 17.8648 | 18.9162
4337 | 1.6867 | 1.4901 | 0.95417 | 0.93191 | 3.1261 | 7.3247 | 5.7397 | 6.5068 | 3.5576 | 1.8373 | 18.7949 | 14.2607 | 18.7949
4338 | 1.1236 | -0.093689 | 0.8694 | 0.46268 | 3.5913 | 6.6763 | 6.9402 | 5.1823 | 3.7581 | 2.415 | 17.865 | 16.7047 | 17.865
4339 | 0.1212 | -0.27004 | 0.54823 | 0.39357 | 4.3623 | 5.4058 | 4.9509 | 5.05 | 4.2906 | 2.3984 | 17.2165 | 16.0021 | 17.2165
4340 | -1.3295 | -0.53107 | 0.091834 | 0.29768 | 4.0737 | 3.8804 | 4.7888 | 4.8677 | 4.1899 | 2.2512 | 15.0729 | 15.3035 | 15.3035
4341 | -0.20133 | -0.95909 | 0.42022 | 0.16876 | 5.0843 | 5.0105 | 6.6685 | 4.6086 | 5.5103 | 2.7182 | 17.4215 | 19.9813 | 19.9813
4342 | -1.3218 | -0.71711 | 0.093115 | 0.23665 | 4.6157 | 3.8864 | 5.4406 | 4.7486 | 3.4402 | 2.4313 | 15.682 | 15.9277 | 15.9277
4343 | -0.072171 | -0.97953 | 0.47123 | 0.16366 | 3.4679 | 5.1663 | 6.1545 | 4.5975 | 3.9506 | 1.7282 | 14.9599 | 15.3011 | 15.3011
4344 | 1.371 | 2.4417 | 0.91481 | 0.99269 | 3.6877 | 6.9719 | 7.1932 | 7.1821 | 3.7845 | 2.0841 | 19.9258 | 16.7494 | 19.9258
4345 | -0.33499 | -0.28852 | 0.36881 | 0.38647 | 2.7733 | 4.8536 | 3.0765 | 5.0366 | 3.7948 | 2.039 | 14.7025 | 11.6836 | 14.7025
4346 | -1.1306 | -2.2651 | 0.12911 | 0.011753 | 3.7059 | 4.0435 | 4.825 | 4.1421 | 3.9404 | 1.6858 | 13.5773 | 14.1572 | 14.1572
4347 | 0.12127 | 2.224 | 0.54826 | 0.98693 | 3.6173 | 5.4059 | 7.1956 | 7.0463 | 4.6478 | 1.9956 | 18.0651 | 17.4563 | 18.0651
4348 | 1.2771 | 0.21446 | 0.89921 | 0.58491 | 4.311 | 6.8614 | 5.16 | 5.4279 | 4.0518 | 1.4101 | 18.0104 | 14.9329 | 18.0104
4349 | 0.93048 | -0.71315 | 0.82394 | 0.23788 | 2.8088 | 6.437 | 5.67 | 4.7511 | 4.9107 | 1.6964 | 15.6933 | 15.0859 | 15.6933
4350 | 0.64598 | 0.52541 | 0.74085 | 0.70035 | 3.9905 | 6.0755 | 5.5321 | 5.6889 | 3.378 | 1.9825 | 17.7374 | 14.8831 | 17.7374
4351 | -0.16733 | 2.1939 | 0.43355 | 0.98588 | 4.0786 | 5.0511 | 7.4623 | 7.0266 | 4.4613 | 1.8175 | 17.9738 | 17.8197 | 17.9738
4352 | 0.03924 | 0.27122 | 0.51565 | 0.60689 | 4.2831 | 5.3035 | 6.4884 | 5.4747 | 3.9414 | 1.7558 | 16.8171 | 16.4687 | 16.8171
4353 | 0.43775 | -0.5708 | 0.66922 | 0.28407 | 3.9447 | 5.8083 | 3.7166 | 4.8414 | 4.7892 | 1.8575 | 16.4519 | 14.308 | 16.4519
4354 | 2.1871 | 2.2527 | 0.98563 | 0.98786 | 3.7207 | 7.8133 | 6.9571 | 7.065 | 4.7561 | 2.0318 | 20.6307 | 17.4656 | 20.6307
4355 | -2.1611 | -1.7903 | 0.015345 | 0.036705 | 2.788 | 3.381 | 4.3827 | 4.2588 | 4.7042 | 2.4188 | 12.8466 | 14.2936 | 14.2936
4356 | -1.2223 | -0.19626 | 0.1108 | 0.42221 | 4.1733 | 3.9662 | 5.0586 | 5.1046 | 5.7686 | 1.9196 | 15.1636 | 16.9201 | 16.9201
4357 | 0.15521 | -0.70209 | 0.56167 | 0.24131 | 5.3247 | 5.4485 | 5.7198 | 4.7579 | 4.4368 | 2.4544 | 17.9856 | 17.9357 | 17.9856
4358 | 0.55861 | 0.22264 | 0.71179 | 0.58809 | 2.6395 | 5.9634 | 6.4815 | 5.4346 | 3.8687 | 2.541 | 16.5785 | 15.5307 | 16.5785
4359 | 0.87726 | 1.6355 | 0.80983 | 0.94903 | 3.33 | 6.37 | 4.6139 | 6.6223 | 3.8416 | 2.0406 | 18.3629 | 13.8261 | 18.3629
4360 | 0.016472 | -0.35681 | 0.50657 | 0.36062 | 3.6662 | 5.2752 | 3.8278 | 4.9875 | 3.9267 | 2.4411 | 16.3701 | 13.8618 | 16.3701
4361 | 1.1667 | 0.7884 | 0.87834 | 0.78477 | 3.505 | 6.7289 | 5.6717 | 5.9149 | 4.3228 | 2.4843 | 18.6331 | 15.9839 | 18.6331
4362 | 1.2534 | 1.6857 | 0.89496 | 0.95407 | 4.9473 | 6.8332 | 6.796 | 6.6614 | 4.0869 | 2.4924 | 20.9343 | 18.3226 | 20.9343
4363 | -0.52246 | 0.60949 | 0.30067 | 0.7289 | 4.7965 | 4.6422 | 5.7846 | 5.7609 | 3.3061 | 2.3181 | 17.5177 | 16.2053 | 17.5177
4364 | -1.5726 | -0.89953 | 0.057911 | 0.18418 | 5.1857 | 3.7044 | 5.3628 | 4.6415 | 4.6033 | 2.5211 | 16.0527 | 17.673 | 17.673
4365 | 0.21859 | -0.14107 | 0.58652 | 0.44391 | 4.4083 | 5.5286 | 3.9448 | 5.1461 | 4.5943 | 1.7793 | 16.8624 | 14.7267 | 16.8624
4366 | -0.48565 | -1.1043 | 0.31361 | 0.13474 | 4.4644 | 4.6828 | 5.4612 | 4.5329 | 3.8118 | 1.4923 | 15.1725 | 15.2297 | 15.2297
4367 | 1.3781 | 1.3205 | 0.91591 | 0.90666 | 4.5074 | 6.9801 | 5.9063 | 6.3679 | 4.4315 | 2.6315 | 20.487 | 17.4767 | 20.487
4368 | -0.96509 | -3.1941 | 0.16725 | 0.00070133 | 4.3876 | 4.1919 | 4.1782 | 4.0338 | 4.1808 | 2.1398 | 14.753 | 14.8863 | 14.8863
4369 | -0.29659 | 1.0868 | 0.38339 | 0.86144 | 4.7796 | 4.8981 | 3.9289 | 6.1712 | 4.3231 | 2.2652 | 18.1142 | 15.2969 | 18.1142
4370 | 1.2398 | 0.66796 | 0.89248 | 0.74792 | 3.3262 | 6.817 | 4.0506 | 5.8111 | 5.0733 | 1.4108 | 17.3651 | 13.8609 | 17.3651
4371 | -0.97142 | -0.68889 | 0.16567 | 0.24545 | 4.0834 | 4.186 | 6.5142 | 4.7661 | 5.8727 | 1.583 | 14.6185 | 18.0533 | 18.0533
4372 | -1.5772 | -1.4324 | 0.05738 | 0.076012 | 3.5768 | 3.7013 | 5.2995 | 4.3849 | 5.3449 | 1.6298 | 13.2928 | 15.8509 | 15.8509
4373 | 0.63613 | 0.41726 | 0.73765 | 0.66175 | 4.9993 | 6.0628 | 7.3326 | 5.597 | 3.8271 | 2.1356 | 18.7947 | 18.2946 | 18.7947
4374 | -0.61556 | -1.6669 | 0.26909 | 0.047764 | 5.6121 | 4.5415 | 5.0372 | 4.2983 | 3.9628 | 2.0496 | 16.5015 | 16.6617 | 16.6617
4375 | 1.2164 | 0.17984 | 0.88808 | 0.57136 | 3.561 | 6.7889 | 6.3542 | 5.3995 | 3.3775 | 1.8516 | 17.601 | 15.1443 | 17.601
4376 | -0.25408 | -0.83581 | 0.39972 | 0.20163 | 3.725 | 4.948 | 3.7513 | 4.6778 | 5.0065 | 2.2746 | 15.6253 | 14.7574 | 15.6253
4377 | 1.4557 | 0.57789 | 0.92726 | 0.71833 | 4.5136 | 7.0695 | 6.9626 | 5.7338 | 4.498 | 1.7431 | 19.0599 | 17.7173 | 19.0599
4378 | 0.32033 | 0.60226 | 0.62564 | 0.7265 | 5.0981 | 5.658 | 4.9438 | 5.7547 | 4.8427 | 1.3854 | 17.8961 | 16.27 | 17.8961
4379 | -0.40923 | -0.10262 | 0.34119 | 0.45913 | 4.8118 | 4.7686 | 5.3018 | 5.1755 | 4.0744 | 1.7409 | 16.4967 | 15.9288 | 16.4967
4380 | -0.70495 | 0.89653 | 0.24042 | 0.81502 | 4.9968 | 4.4477 | 4.3664 | 6.0081 | 3.3992 | 2.449 | 17.9015 | 15.2114 | 17.9015
4381 | -0.36951 | -1.0426 | 0.35587 | 0.14857 | 4.048 | 4.8138 | 6.0207 | 4.5643 | 3.9017 | 2.4055 | 15.8316 | 16.3758 | 16.3758
4382 | -0.24574 | -0.85566 | 0.40294 | 0.19609 | 5.1944 | 4.9578 | 7.1247 | 4.6664 | 5.5121 | 2.3007 | 17.1192 | 20.1319 | 20.1319
4383 | 0.73941 | -0.5865 | 0.77017 | 0.27877 | 4.5318 | 6.1949 | 4.6992 | 4.8312 | 4.7965 | 2.1062 | 17.6642 | 16.1337 | 17.6642
4384 | -0.97671 | -0.82266 | 0.16436 | 0.20535 | 3.2744 | 4.1811 | 6.722 | 4.6854 | 5.1468 | 1.7651 | 13.906 | 16.9082 | 16.9082
4385 | -0.65 | -0.98101 | 0.25784 | 0.16329 | 4.3089 | 4.505 | 4.0789 | 4.5967 | 4.1769 | 1.8165 | 15.2271 | 14.3811 | 15.2271
4386 | -1.1576 | -1.5966 | 0.12351 | 0.055173 | 3.5811 | 4.0203 | 5.9131 | 4.3226 | 4.3677 | 2.4302 | 14.3542 | 16.2921 | 16.2921
4387 | 0.67841 | 0.15777 | 0.75125 | 0.56268 | 5.2613 | 6.117 | 2.4258 | 5.3816 | 3.4579 | 2.4884 | 19.2483 | 13.6334 | 19.2483
4388 | 0.47782 | 0.82485 | 0.68361 | 0.79527 | 3.549 | 5.8597 | 7.0367 | 5.9463 | 4.1107 | 1.3358 | 16.6908 | 16.0322 | 16.6908
4389 | -0.014547 | -0.33898 | 0.4942 | 0.36731 | 4.1344 | 5.2369 | 6.3237 | 5.0002 | 4.2319 | 2.0298 | 16.4014 | 16.7198 | 16.7198
4390 | -1.1365 | -0.33036 | 0.12788 | 0.37056 | 3.6889 | 4.0384 | 6.2511 | 5.0064 | 3.5638 | 1.544 | 14.2777 | 15.0478 | 15.0478
4391 | 1.7594 | 0.94047 | 0.96074 | 0.82651 | 4.0846 | 7.4014 | 6.9139 | 6.0459 | 3.2442 | 2.6741 | 20.2059 | 16.9167 | 20.2059
4392 | -0.5764 | 0.35353 | 0.28217 | 0.63815 | 4.0864 | 4.5835 | 6.0845 | 5.5434 | 5.0274 | 2.5819 | 16.7952 | 17.7802 | 17.7802
4393 | -1.9535 | -0.97821 | 0.025383 | 0.16399 | 5.2788 | 3.4792 | 6.0579 | 4.5983 | 4.1632 | 2.337 | 15.6932 | 17.8369 | 17.8369
4394 | 1.2378 | 0.012546 | 0.8921 | 0.50501 | 3.478 | 6.8145 | 7.0696 | 5.2651 | 3.6614 | 1.6587 | 17.2164 | 15.8677 | 17.2164
4395 | 0.87912 | 0.022144 | 0.81033 | 0.50883 | 3.5904 | 6.3723 | 5.169 | 5.2727 | 4.2996 | 1.8155 | 17.051 | 14.8746 | 17.051
4396 | 0.75436 | -0.39019 | 0.77468 | 0.3482 | 4.1739 | 6.214 | 6.7441 | 4.964 | 4.8206 | 1.862 | 17.2139 | 17.6007 | 17.6007
4397 | -1.1647 | -1.1636 | 0.12208 | 0.1223 | 3.222 | 4.0143 | 6.7127 | 4.5038 | 3.183 | 1.682 | 13.422 | 14.7997 | 14.7997
4398 | 0.16525 | -1.5404 | 0.56563 | 0.061737 | 4.5263 | 5.4612 | 6.0217 | 4.3431 | 3.2682 | 1.5191 | 15.8497 | 15.3354 | 15.8497
4399 | 0.63838 | 2.2282 | 0.73839 | 0.98707 | 3.7602 | 6.0657 | 4.2407 | 7.049 | 4.3834 | 1.847 | 18.722 | 14.2313 | 18.722
4400 | 1.2593 | 1.9028 | 0.89604 | 0.97147 | 5.5002 | 6.8403 | 4.6369 | 6.8244 | 5.6198 | 2.1896 | 21.3545 | 17.9465 | 21.3545
4401 | 0.68132 | -0.51958 | 0.75217 | 0.30168 | 3.1069 | 6.1207 | 7.2785 | 4.8753 | 4.2951 | 2.2956 | 16.3985 | 16.9761 | 16.9761
4402 | -0.53114 | -0.45336 | 0.29766 | 0.32514 | 4.5407 | 4.6327 | 6.8386 | 4.9202 | 3.8867 | 1.6313 | 15.7248 | 16.8972 | 16.8972
4403 | 0.58809 | 0.075135 | 0.72177 | 0.52995 | 4.354 | 6.0012 | 7.8345 | 5.3149 | 3.637 | 1.9094 | 17.5795 | 17.7349 | 17.7349
4404 | 1.1595 | 1.9057 | 0.87687 | 0.97165 | 4.8562 | 6.7201 | 7.0094 | 6.8265 | 3.8804 | 1.1939 | 19.5967 | 16.9399 | 19.5967
4405 | 0.8068 | 0.47974 | 0.79011 | 0.68429 | 3.873 | 6.2807 | 5.9447 | 5.65 | 4.0536 | 2.1081 | 17.9118 | 15.9794 | 17.9118
4406 | 1.4851 | -0.097228 | 0.93124 | 0.46127 | 3.119 | 7.1029 | 4.7899 | 5.1796 | 4.3135 | 2.1339 | 17.5355 | 14.3564 | 17.5355
4407 | 1.6734 | 2.5781 | 0.95288 | 0.99503 | 4.245 | 7.3105 | 7.512 | 7.2609 | 4.6688 | 1.3853 | 20.2016 | 17.8111 | 20.2016
4408 | -0.30638 | -0.21623 | 0.37966 | 0.41441 | 4.1125 | 4.8867 | 6.1504 | 5.0897 | 3.4673 | 1.7084 | 15.7973 | 15.4386 | 15.7973
4409 | 0.075997 | 0.53165 | 0.53029 | 0.70251 | 4.3134 | 5.3492 | 5.8802 | 5.6942 | 5.3624 | 2.3105 | 17.6674 | 17.8666 | 17.8666
4410 | 0.60348 | 1.061 | 0.72691 | 0.85566 | 3.2853 | 6.021 | 7.5974 | 6.1492 | 3.6129 | 2.6537 | 18.1092 | 17.1493 | 18.1092
4411 | -0.15255 | -0.54453 | 0.43938 | 0.29304 | 4.1655 | 5.0689 | 5.0733 | 4.8587 | 4.623 | 1.7669 | 15.86 | 15.6288 | 15.86
4412 | 0.18678 | 1.1478 | 0.57408 | 0.87447 | 3.0796 | 5.4883 | 5.41 | 6.223 | 3.6366 | 2.0003 | 16.7913 | 14.1265 | 16.7913
4413 | -0.22383 | -0.42947 | 0.41144 | 0.33379 | 3.6231 | 4.9837 | 4.9049 | 4.9366 | 3.4036 | 2.1605 | 15.7039 | 14.092 | 15.7039
4414 | 1.1015 | 1.5559 | 0.86467 | 0.94013 | 3.6599 | 6.6494 | 4.1042 | 6.5595 | 5.9162 | 2.4125 | 19.2813 | 16.0929 | 19.2813
4415 | 1.0822 | 1.2918 | 0.86041 | 0.90178 | 4.5707 | 6.6256 | 5.6819 | 6.3441 | 4.3681 | 1.5999 | 19.1403 | 16.2207 | 19.1403
4416 | 0.41409 | 0.67809 | 0.66059 | 0.75114 | 4.7767 | 5.7779 | 6.6889 | 5.8198 | 3.3069 | 2.1147 | 18.4891 | 16.8871 | 18.4891
4417 | 1.9111 | 1.0876 | 0.972 | 0.86162 | 4.2025 | 7.5554 | 4.1957 | 6.1719 | 4.064 | 2.1858 | 20.1156 | 14.648 | 20.1156
4418 | -0.051434 | 1.4768 | 0.47949 | 0.93014 | 4.5453 | 5.1916 | 6.0789 | 6.4961 | 3.7983 | 2.3578 | 18.5907 | 16.7802 | 18.5907
4419 | -2.8231 | -1.0373 | 0.002378 | 0.1498 | 2.9924 | 3.1664 | 5.0975 | 4.567 | 4.7879 | 1.9866 | 12.7124 | 14.8644 | 14.8644
4420 | -0.17378 | -2.1591 | 0.43102 | 0.015421 | 3.5693 | 5.0434 | 6.6404 | 4.1637 | 4.5073 | 2.1854 | 14.9617 | 16.9024 | 16.9024
4421 | -1.2567 | -1.6615 | 0.10443 | 0.048304 | 4.4214 | 3.9381 | 5.8737 | 4.3001 | 3.6552 | 2.5701 | 15.2298 | 16.5205 | 16.5205
4422 | -0.3754 | -0.39176 | 0.35368 | 0.34762 | 3.9535 | 4.8071 | 3.8331 | 4.9629 | 4.8815 | 2.6054 | 16.3289 | 15.2736 | 16.3289
4423 | -1.1943 | -0.42356 | 0.11618 | 0.33595 | 3.4446 | 3.9894 | 4.5456 | 4.9407 | 4.4159 | 2.2337 | 14.6084 | 14.6399 | 14.6399
4424 | -1.4984 | -1.3294 | 0.067017 | 0.091862 | 3.3904 | 3.7554 | 6.9708 | 4.4279 | 5.6223 | 1.8084 | 13.3821 | 17.7919 | 17.7919
4425 | 0.26948 | -0.34135 | 0.60622 | 0.36642 | 3.5976 | 5.5932 | 4.8778 | 4.9985 | 3.7629 | 1.3359 | 15.5252 | 13.5741 | 15.5252
4426 | -0.17476 | -1.6786 | 0.43063 | 0.046615 | 3.6518 | 5.0422 | 6.0334 | 4.2944 | 3.5559 | 1.2598 | 14.2482 | 14.5009 | 14.5009
4427 | 0.65205 | 2.1494 | 0.74282 | 0.9842 | 4.4087 | 6.0832 | 4.9534 | 6.997 | 3.478 | 1.976 | 19.4649 | 14.8161 | 19.4649
4428 | -0.41868 | 0.26413 | 0.33773 | 0.60416 | 4.2432 | 4.7579 | 6.8155 | 5.4689 | 3.6963 | 1.391 | 15.8609 | 16.146 | 16.146
4429 | 0.2722 | -0.1486 | 0.60727 | 0.44094 | 3.7596 | 5.5967 | 7.1507 | 5.1404 | 3.6344 | 2.0917 | 16.5884 | 16.6364 | 16.6364
4430 | -0.95904 | -0.38953 | 0.16877 | 0.34844 | 2.728 | 4.1976 | 6.2209 | 4.9644 | 5.717 | 2.4541 | 14.3441 | 17.12 | 17.12
4431 | -0.19381 | -0.11747 | 0.42316 | 0.45325 | 4.7702 | 5.0194 | 7.3307 | 5.1641 | 3.5355 | 1.8607 | 16.8144 | 17.4971 | 17.4971
4432 | 0.10508 | -0.69517 | 0.54184 | 0.24347 | 2.8114 | 5.3856 | 5.9674 | 4.7622 | 4.7624 | 2.3662 | 15.3253 | 15.9074 | 15.9074
4433 | -0.72557 | 0.24618 | 0.23405 | 0.59723 | 3.9576 | 4.4265 | 7.2166 | 5.454 | 3.7445 | 2.2066 | 16.0447 | 17.1253 | 17.1253
4434 | -0.8143 | -0.27322 | 0.20774 | 0.39234 | 3.689 | 4.337 | 6.834 | 5.0477 | 4.6302 | 1.7987 | 14.8723 | 16.9519 | 16.9519
4435 | -0.52644 | 1.3809 | 0.29929 | 0.91634 | 3.0641 | 4.6379 | 7.1383 | 6.4179 | 4.6837 | 2.5497 | 16.6695 | 17.4358 | 17.4358
4436 | 1.065 | 0.76419 | 0.85656 | 0.77762 | 3.5684 | 6.6044 | 4.358 | 5.894 | 4.9924 | 2.4202 | 18.487 | 15.339 | 18.487
4437 | -1.1575 | -2.2156 | 0.12353 | 0.013359 | 3.4397 | 4.0204 | 5.614 | 4.1519 | 3.9931 | 1.7015 | 13.3136 | 14.7483 | 14.7483
4438 | 1.3867 | 0.65016 | 0.91723 | 0.74221 | 3.188 | 6.9901 | 7.0182 | 5.7958 | 3.1641 | 2.6771 | 18.651 | 16.0474 | 18.651
4439 | -0.58563 | -0.90368 | 0.27906 | 0.18308 | 3.4567 | 4.5736 | 4.0956 | 4.6391 | 3.8617 | 2.5198 | 15.1892 | 13.9338 | 15.1892
4440 | -1.0912 | -0.56814 | 0.13759 | 0.28497 | 4.2929 | 4.0777 | 6.2839 | 4.8432 | 5.261 | 1.5258 | 14.7396 | 17.3636 | 17.3636
4441 | 0.19195 | 1.0104 | 0.57611 | 0.84384 | 3.3824 | 5.4949 | 6.1867 | 6.1059 | 4.341 | 2.0097 | 16.9929 | 15.9198 | 16.9929
4442 | 0.4249 | 1.2419 | 0.66454 | 0.89287 | 3.6597 | 5.7918 | 5.9778 | 6.3024 | 3.6252 | 2.4685 | 18.2225 | 15.7313 | 18.2225
4443 | -0.68222 | -0.80376 | 0.24755 | 0.21077 | 3.3779 | 4.4713 | 5.9992 | 4.6965 | 3.2095 | 2.0832 | 14.6289 | 14.6698 | 14.6698
4444 | 0.282 | -0.18039 | 0.61103 | 0.42842 | 4.4706 | 5.6091 | 6.9752 | 5.1165 | 4.0263 | 1.7925 | 16.9887 | 17.2646 | 17.2646
4445 | -0.33282 | 0.90013 | 0.36963 | 0.81597 | 4.2599 | 4.8561 | 5.0561 | 6.0112 | 4.2546 | 1.9194 | 17.0465 | 15.49 | 17.0465
4446 | -0.58559 | 0.10382 | 0.27908 | 0.54134 | 2.7453 | 4.5736 | 6.135 | 5.3379 | 3.6985 | 2.5065 | 15.1633 | 15.0853 | 15.1633
4447 | 0.23927 | -0.98257 | 0.59455 | 0.16291 | 4.0115 | 5.5548 | 5.5453 | 4.5959 | 4.6784 | 1.6655 | 15.8277 | 15.9007 | 15.9007
4448 | 0.86578 | 1.1483 | 0.8067 | 0.87458 | 4.1099 | 6.3555 | 7.2702 | 6.2235 | 4.9139 | 1.945 | 18.6338 | 18.2389 | 18.6338
4449 | 1.2479 | 0.21388 | 0.89397 | 0.58468 | 4.8485 | 6.8267 | 6.8111 | 5.4274 | 3.8101 | 1.5439 | 18.6465 | 17.0137 | 18.6465
4450 | 0.65389 | 1.5468 | 0.74341 | 0.93904 | 3.3903 | 6.0856 | 5.1138 | 6.5523 | 4.6174 | 2.5854 | 18.6136 | 15.7069 | 18.6136
4451 | -0.31586 | -0.92663 | 0.37605 | 0.17706 | 3.1149 | 4.8757 | 4.3981 | 4.6264 | 5.8767 | 2.208 | 14.8251 | 15.5978 | 15.5978
4452 | 0.27484 | 0.18007 | 0.60828 | 0.57145 | 5.1246 | 5.6 | 5.5041 | 5.3997 | 5.3698 | 2.5109 | 18.6353 | 18.5094 | 18.6353
4453 | 0.98045 | -0.60672 | 0.83657 | 0.27202 | 3.7009 | 6.4995 | 4.6782 | 4.8181 | 4.9598 | 2.2429 | 17.2615 | 15.5819 | 17.2615
4454 | -0.24241 | -0.18191 | 0.40423 | 0.42783 | 2.6093 | 4.9617 | 7.225 | 5.1153 | 3.1787 | 2.2791 | 14.9654 | 15.2921 | 15.2921
4455 | -0.048534 | 0.93008 | 0.48065 | 0.82384 | 5.0445 | 5.1952 | 5.2938 | 6.037 | 4.8076 | 2.0596 | 18.3362 | 17.2054 | 18.3362
4456 | -0.68013 | -1.4777 | 0.24821 | 0.069738 | 3.9504 | 4.4734 | 7.6784 | 4.3669 | 3.9168 | 1.7163 | 14.507 | 17.2619 | 17.2619
4457 | -1.9295 | -0.070067 | 0.026834 | 0.47207 | 4.5716 | 3.4916 | 4.2038 | 5.2006 | 3.6588 | 1.9082 | 15.172 | 14.3424 | 15.172
4458 | -0.65306 | -0.1228 | 0.25686 | 0.45113 | 4.9866 | 4.5018 | 6.2147 | 5.16 | 3.6483 | 1.3285 | 15.977 | 16.1782 | 16.1782
4459 | -0.74893 | -1.9433 | 0.22695 | 0.025988 | 4.7463 | 4.4026 | 5.8509 | 4.2154 | 4.2974 | 2.071 | 15.4353 | 16.9656 | 16.9656
4460 | 1.5546 | 1.4958 | 0.93998 | 0.93265 | 5.065 | 7.1808 | 6.9148 | 6.5114 | 4.8215 | 1.6536 | 20.4108 | 18.4549 | 20.4108
4461 | -2.1304 | -1.2611 | 0.016569 | 0.10364 | 5.1669 | 3.3944 | 6.0292 | 4.4581 | 4.2093 | 1.9178 | 14.9373 | 17.3232 | 17.3232
4462 | -0.21682 | -0.62066 | 0.41418 | 0.26741 | 3.2488 | 4.992 | 4.8089 | 4.8091 | 4.1794 | 1.6627 | 14.7127 | 13.8998 | 14.7127
4463 | 0.06044 | 1.1464 | 0.5241 | 0.87418 | 4.8833 | 5.3298 | 4.4884 | 6.2218 | 4.4133 | 2.17 | 18.605 | 15.955 | 18.605
4464 | -1.4371 | -0.26653 | 0.075343 | 0.39491 | 3.2708 | 3.7993 | 6.6294 | 5.0526 | 3.1484 | 1.6093 | 13.732 | 14.6578 | 14.6578
4465 | 0.78061 | 1.2696 | 0.78248 | 0.89789 | 3.9713 | 6.2474 | 3.6307 | 6.3256 | 3.2984 | 2.5692 | 19.1135 | 13.4696 | 19.1135
4466 | -2.6472 | -0.83075 | 0.0040577 | 0.20306 | 3.8149 | 3.2104 | 4.3244 | 4.6807 | 4.6137 | 2.1069 | 13.813 | 14.86 | 14.86
4467 | -0.89838 | -0.14637 | 0.18449 | 0.44182 | 4.3375 | 4.255 | 3.4326 | 5.1421 | 4.8413 | 1.9799 | 15.7144 | 14.5912 | 15.7144
4468 | 0.51969 | 0.89354 | 0.69836 | 0.81422 | 3.9901 | 5.9134 | 6.8422 | 6.0055 | 3.4931 | 1.6366 | 17.5456 | 15.9619 | 17.5456
4469 | 0.028034 | 1.037 | 0.51118 | 0.85013 | 4.4185 | 5.2896 | 6.1931 | 6.1287 | 5.2727 | 2.1115 | 17.9483 | 17.9959 | 17.9959
4470 | 0.064673 | -0.018744 | 0.52578 | 0.49252 | 3.7701 | 5.3351 | 6.7846 | 5.2405 | 4.516 | 1.5162 | 15.862 | 16.587 | 16.587
4471 | 0.64084 | 1.0828 | 0.73919 | 0.86056 | 3.7511 | 6.0689 | 6.8844 | 6.1678 | 3.9251 | 1.6825 | 17.6703 | 16.2431 | 17.6703
4472 | 0.43784 | -0.34466 | 0.66925 | 0.36518 | 3.3547 | 5.8084 | 6.7722 | 4.9962 | 4.0459 | 1.8281 | 15.9873 | 16.0009 | 16.0009
4473 | 1.0229 | 1.178 | 0.84682 | 0.88059 | 4.6016 | 6.5523 | 7.6237 | 6.2486 | 4.1233 | 2.1032 | 19.5057 | 18.4518 | 19.5057
4474 | -0.3753 | 0.65299 | 0.35372 | 0.74312 | 3.3239 | 4.8072 | 6.1418 | 5.7982 | 5.0226 | 1.5687 | 15.4981 | 16.057 | 16.057
4475 | -0.14483 | -1.0189 | 0.44242 | 0.15412 | 4.7356 | 5.0781 | 4.7059 | 4.5766 | 3.6766 | 1.9645 | 16.3548 | 15.0826 | 16.3548
4476 | 0.12889 | -1.0466 | 0.55128 | 0.14765 | 5.6654 | 5.4154 | 5.2003 | 4.5622 | 5.1791 | 1.6151 | 17.2582 | 17.6599 | 17.6599
4477 | 1.184 | 0.67414 | 0.8818 | 0.74989 | 3.7137 | 6.7499 | 6.7711 | 5.8164 | 5.0206 | 2.5359 | 18.816 | 18.0414 | 18.816
4478 | -0.90477 | -0.32195 | 0.18279 | 0.37375 | 3.5367 | 4.2488 | 5.8685 | 5.0124 | 4.2019 | 2.1411 | 14.9391 | 15.7483 | 15.7483
4479 | 0.47796 | 0.21526 | 0.68366 | 0.58522 | 4.0232 | 5.8599 | 6.6948 | 5.4285 | 3.497 | 1.9124 | 17.2241 | 16.1274 | 17.2241
4480 | 1.5808 | 0.81945 | 0.94304 | 0.79373 | 4.6657 | 7.2098 | 4.5554 | 5.9416 | 3.0796 | 2.557 | 20.3741 | 14.8577 | 20.3741
4481 | -1.6128 | -2.9572 | 0.053396 | 0.0015523 | 5.2096 | 3.6778 | 6.7078 | 4.0505 | 4.6286 | 2.2582 | 15.196 | 18.8042 | 18.8042
4482 | -0.60013 | -0.3107 | 0.27421 | 0.37801 | 4.9968 | 4.558 | 6.9998 | 5.0205 | 3.3906 | 2.2371 | 16.8124 | 17.6242 | 17.6242
4483 | -0.49658 | -1.2246 | 0.30974 | 0.11037 | 5.0291 | 4.6707 | 6.9051 | 4.4749 | 4.4741 | 1.5264 | 15.7011 | 17.9347 | 17.9347
4484 | -0.023435 | -0.72756 | 0.49065 | 0.23344 | 3.488 | 5.226 | 7.2445 | 4.7422 | 5.2567 | 2.3501 | 15.8063 | 18.3394 | 18.3394
4485 | -0.87728 | -0.31311 | 0.19017 | 0.3771 | 4.1796 | 4.2753 | 5.0898 | 5.0188 | 3.5847 | 1.4939 | 14.9676 | 14.348 | 14.9676
4486 | -0.31978 | -0.036053 | 0.37457 | 0.48562 | 2.803 | 4.8712 | 5.0794 | 5.227 | 3.2882 | 2.3807 | 15.2819 | 13.5514 | 15.2819
4487 | -1.0296 | -0.43005 | 0.15161 | 0.33358 | 3.3571 | 4.1327 | 5.2412 | 4.9362 | 3.1534 | 2.1476 | 14.5736 | 13.8992 | 14.5736
4488 | -1.2178 | -0.59566 | 0.11166 | 0.2757 | 4.8636 | 3.9699 | 6.9822 | 4.8253 | 4.9628 | 1.6791 | 15.3379 | 18.4878 | 18.4878
4489 | 1.3819 | 0.83149 | 0.9165 | 0.79715 | 4.9427 | 6.9846 | 5.9492 | 5.952 | 3.5337 | 1.5726 | 19.4518 | 15.9982 | 19.4518
4490 | 0.59873 | 0.25525 | 0.72532 | 0.60073 | 4.7534 | 6.0149 | 3.9315 | 5.4615 | 3.1731 | 2.6009 | 18.8307 | 14.459 | 18.8307
4491 | 0.61127 | 2.3088 | 0.72949 | 0.98952 | 3.1321 | 6.031 | 7.4115 | 7.1007 | 3.5426 | 1.9573 | 18.221 | 16.0435 | 18.221
4492 | -0.34933 | 0.90717 | 0.36342 | 0.81784 | 4.993 | 4.837 | 6.1305 | 6.0172 | 3.778 | 2.4966 | 18.3438 | 17.3981 | 18.3438
4493 | 1.0667 | 1.6002 | 0.85695 | 0.94522 | 4.2615 | 6.6065 | 4.2777 | 6.5946 | 4.3785 | 1.2244 | 18.687 | 14.142 | 18.687
4494 | -0.57882 | 0.42524 | 0.28136 | 0.66467 | 3.9425 | 4.5809 | 6.5453 | 5.6038 | 3.3529 | 1.8243 | 15.9515 | 15.665 | 15.9515
4495 | -1.0638 | -2.5055 | 0.14371 | 0.0061146 | 2.9933 | 4.102 | 5.2118 | 4.1015 | 4.3468 | 1.8857 | 13.0825 | 14.4376 | 14.4376
4496 | 0.71337 | 0.42701 | 0.76219 | 0.66531 | 3.0121 | 6.1617 | 5.5737 | 5.6053 | 5.085 | 2.0206 | 16.7997 | 15.6914 | 16.7997
4497 | -0.78859 | 0.14399 | 0.21518 | 0.55725 | 5.4096 | 4.3626 | 4.1284 | 5.3704 | 4.3729 | 2.6149 | 17.7575 | 16.5259 | 17.7575
4498 | -0.66685 | 0.468 | 0.25243 | 0.68011 | 4.0315 | 4.4873 | 7.2381 | 5.64 | 3.3405 | 2.2017 | 16.3606 | 16.8119 | 16.8119
4499 | 0.5163 | 0.74558 | 0.69718 | 0.77204 | 5.5281 | 5.9091 | 4.1648 | 5.878 | 3.4548 | 1.847 | 19.1621 | 14.9946 | 19.1621
4500 | -0.77992 | -0.99481 | 0.21772 | 0.15991 | 3.1267 | 4.3713 | 3.6968 | 4.5894 | 4.1514 | 2.4243 | 14.5116 | 13.3992 | 14.5116
4501 | -0.46732 | -1.4382 | 0.32013 | 0.075184 | 3.6575 | 4.7032 | 4.2738 | 4.3825 | 4.629 | 1.984 | 14.7272 | 14.5443 | 14.7272
4502 | -0.5251 | -0.80138 | 0.29976 | 0.21145 | 4.0263 | 4.6393 | 5.7311 | 4.6979 | 5.3372 | 2.0627 | 15.4263 | 17.1573 | 17.1573
4503 | 0.46607 | 0.56747 | 0.67942 | 0.7148 | 3.379 | 5.8446 | 4.9837 | 5.7248 | 4.2435 | 2.0673 | 17.0157 | 14.6734 | 17.0157
4504 | 1.6379 | 1.2455 | 0.94928 | 0.89352 | 5.4233 | 7.2722 | 6.2354 | 6.3054 | 5.015 | 1.4071 | 20.408 | 18.0808 | 20.408
4505 | -0.85238 | -0.79262 | 0.197 | 0.214 | 4.53 | 4.2995 | 5.1267 | 4.7031 | 5.5253 | 2.239 | 15.7715 | 17.421 | 17.421
4506 | 0.67686 | 1.4809 | 0.75075 | 0.93069 | 4.0165 | 6.115 | 6.1416 | 6.4994 | 3.4917 | 1.2328 | 17.8637 | 14.8826 | 17.8637
4507 | 0.40145 | -0.40369 | 0.65595 | 0.34322 | 5.3582 | 5.7617 | 5.1103 | 4.9545 | 3.482 | 2.2551 | 18.3296 | 16.2056 | 18.3296
4508 | 0.036133 | 0.31302 | 0.51441 | 0.62287 | 3.9122 | 5.2996 | 6.2004 | 5.5095 | 5.5211 | 1.9345 | 16.6558 | 17.5681 | 17.5681
4509 | 0.15527 | 0.055818 | 0.5617 | 0.52226 | 3.9089 | 5.4486 | 6.345 | 5.2994 | 5.4568 | 1.5053 | 16.1622 | 17.216 | 17.216
4510 | -1.7747 | -1.8215 | 0.037974 | 0.034265 | 4.8263 | 3.5774 | 5.9456 | 4.2495 | 4.7924 | 1.8352 | 14.4883 | 17.3994 | 17.3994
4511 | 0.68387 | 1.2824 | 0.75297 | 0.90015 | 2.7164 | 6.124 | 6.9792 | 6.3363 | 4.4406 | 2.2732 | 17.4498 | 16.4094 | 17.4498
4512 | -0.3213 | 1.2679 | 0.37399 | 0.89759 | 4.473 | 4.8694 | 5.9423 | 6.3242 | 4.0689 | 1.6481 | 17.3147 | 16.1323 | 17.3147
4513 | -0.43432 | -0.7726 | 0.33203 | 0.21988 | 3.574 | 4.7402 | 6.0302 | 4.715 | 3.2003 | 2.3052 | 15.3344 | 15.1097 | 15.3344
4514 | 0.56152 | -0.28612 | 0.71278 | 0.38739 | 4.7036 | 5.9671 | 4.9997 | 5.0383 | 4.7499 | 2.0177 | 17.7267 | 16.4708 | 17.7267
4515 | 0.72798 | 0.23502 | 0.76669 | 0.5929 | 3.4536 | 6.1804 | 5.0133 | 5.4448 | 3.2217 | 1.9345 | 17.0133 | 13.6231 | 17.0133
4516 | 0.33395 | 0.21847 | 0.63079 | 0.58647 | 4.0463 | 5.6754 | 6.1464 | 5.4312 | 5.6329 | 1.719 | 16.8719 | 17.5446 | 17.5446
4517 | -0.50434 | -0.0055717 | 0.30701 | 0.49778 | 5.299 | 4.6622 | 7.2661 | 5.2509 | 4.3704 | 2.3359 | 17.5479 | 19.2714 | 19.2714
4518 | -0.28362 | 1.3921 | 0.38835 | 0.91805 | 3.2873 | 4.9133 | 5.1698 | 6.427 | 4.7996 | 2.1976 | 16.8252 | 15.4542 | 16.8252
4519 | 1.0479 | 0.65624 | 0.85265 | 0.74417 | 5.1857 | 6.5832 | 5.8326 | 5.801 | 3.9369 | 2.4111 | 19.9811 | 17.3663 | 19.9811
4520 | -0.30832 | -1.0639 | 0.37892 | 0.14368 | 2.9116 | 4.8845 | 6.4395 | 4.5533 | 5.0194 | 1.7498 | 14.0992 | 16.1202 | 16.1202
4521 | 0.6946 | 0.59958 | 0.75635 | 0.72561 | 3.4278 | 6.1377 | 6.8205 | 5.7524 | 4.8609 | 2.5652 | 17.8831 | 17.6745 | 17.8831
4522 | -0.19397 | -0.20401 | 0.4231 | 0.41917 | 3.1366 | 5.0192 | 4.2804 | 5.0988 | 4.1248 | 1.4977 | 14.7523 | 13.0395 | 14.7523
4523 | 1.1435 | 1.7193 | 0.87359 | 0.95722 | 3.2793 | 6.7007 | 6.5371 | 6.6872 | 3.1319 | 1.9555 | 18.6226 | 14.9038 | 18.6226
4524 | -0.033515 | 1.1838 | 0.48663 | 0.88176 | 3.8144 | 5.2136 | 6.5848 | 6.2535 | 3.7597 | 2.6585 | 17.94 | 16.8173 | 17.94
4525 | -0.78921 | -0.35298 | 0.21499 | 0.36205 | 4.4333 | 4.362 | 7.7385 | 4.9903 | 4.9445 | 1.6589 | 15.4444 | 18.7752 | 18.7752
4526 | -0.16144 | -0.73974 | 0.43587 | 0.22973 | 4.9482 | 5.0582 | 6.9274 | 4.7348 | 6.0252 | 2.5741 | 17.3153 | 20.4749 | 20.4749
4527 | -1.3133 | -2.0329 | 0.094535 | 0.021032 | 4.5534 | 3.893 | 6.3067 | 4.1926 | 4.1358 | 1.7391 | 14.3781 | 16.7349 | 16.7349
4528 | -1.7133 | -1.0325 | 0.043332 | 0.15092 | 4.2569 | 3.6142 | 3.6551 | 4.5695 | 3.9893 | 1.6289 | 14.0695 | 13.5302 | 14.0695
4529 | 1.2139 | 0.8942 | 0.8876 | 0.81439 | 4.1429 | 6.7858 | 7.7235 | 6.0061 | 3.6898 | 1.5779 | 18.5128 | 17.1341 | 18.5128
4530 | -1.211 | -0.42583 | 0.11295 | 0.33512 | 4.6455 | 3.9755 | 5.0575 | 4.9391 | 3.8639 | 1.8498 | 15.41 | 15.4168 | 15.4168
4531 | -0.13187 | 0.28473 | 0.44754 | 0.61208 | 4.2083 | 5.0938 | 5.6037 | 5.486 | 5.0008 | 2.3443 | 17.1323 | 17.1571 | 17.1571
4532 | 1.0736 | 0.8187 | 0.8585 | 0.79352 | 5.0062 | 6.615 | 5.9441 | 5.941 | 3.3585 | 1.3967 | 18.959 | 15.7054 | 18.959
4533 | -0.50883 | 0.30295 | 0.30544 | 0.61904 | 3.9884 | 4.6572 | 6.0239 | 5.5011 | 3.8138 | 1.7674 | 15.9142 | 15.5936 | 15.9142
4534 | -0.34406 | -0.20825 | 0.3654 | 0.41752 | 5.185 | 4.8431 | 6.3061 | 5.0956 | 4.0856 | 2.7548 | 17.8785 | 18.3314 | 18.3314
4535 | 0.20254 | -0.72451 | 0.58025 | 0.23437 | 3.7611 | 5.5083 | 5.3282 | 4.7441 | 3.6053 | 1.4833 | 15.4968 | 14.1778 | 15.4968
4536 | -0.68717 | -0.59487 | 0.24599 | 0.27597 | 5.2761 | 4.4661 | 3.974 | 4.8258 | 4.2661 | 1.5775 | 16.1455 | 15.0938 | 16.1455
4537 | -1.8431 | 0.00044697 | 0.032659 | 0.50018 | 3.885 | 3.5383 | 3.5026 | 5.2556 | 4.3612 | 1.8933 | 14.5721 | 13.6421 | 14.5721
4538 | 1.3788 | -0.39304 | 0.91602 | 0.34715 | 3.4824 | 6.9809 | 4.9582 | 4.962 | 3.6263 | 2.6768 | 18.1021 | 14.7438 | 18.1021
4539 | -0.73153 | 0.49661 | 0.23223 | 0.69027 | 5.2474 | 4.4204 | 4.7912 | 5.6643 | 3.9295 | 1.3879 | 16.7201 | 15.356 | 16.7201
4540 | -0.97089 | -0.14681 | 0.1658 | 0.44164 | 4.2839 | 4.1865 | 6.658 | 5.1418 | 3.3543 | 2.5061 | 16.1182 | 16.8023 | 16.8023
4541 | -0.81315 | -0.10876 | 0.20807 | 0.4567 | 5.278 | 4.3381 | 7.235 | 5.1708 | 3.1945 | 2.5379 | 17.3248 | 18.2454 | 18.2454
4542 | -0.67913 | 0.57957 | 0.24853 | 0.7189 | 3.2684 | 4.4745 | 6.0566 | 5.7352 | 4.4982 | 1.5867 | 15.0648 | 15.4099 | 15.4099
4543 | -0.030183 | -1.3138 | 0.48796 | 0.094451 | 3.6024 | 5.2177 | 6.8641 | 4.4347 | 3.8675 | 2.5583 | 15.8131 | 16.8924 | 16.8924
4544 | -0.17659 | -0.94745 | 0.42992 | 0.17171 | 4.5387 | 5.04 | 7.4029 | 4.6149 | 4.4289 | 1.52 | 15.7136 | 17.8904 | 17.8904
4545 | 0.69451 | 0.30158 | 0.75632 | 0.61851 | 4.151 | 6.1376 | 7.3601 | 5.5 | 4.0753 | 1.9799 | 17.7685 | 17.5663 | 17.7685
4546 | 2.2778 | 1.9458 | 0.98863 | 0.97416 | 3.5688 | 7.8916 | 5.8606 | 6.8555 | 4.9882 | 1.3193 | 19.6353 | 15.737 | 19.6353
4547 | 1.0229 | -0.077656 | 0.84681 | 0.46905 | 3.4159 | 6.5523 | 4.1509 | 5.1947 | 4.3762 | 2.0047 | 17.1677 | 13.9478 | 17.1677
4548 | -1.5446 | -1.4461 | 0.061225 | 0.074069 | 4.2378 | 3.7234 | 7.1232 | 4.3794 | 4.9729 | 1.8939 | 14.2344 | 18.2278 | 18.2278
4549 | -0.46951 | 0.97013 | 0.31935 | 0.83401 | 2.8593 | 4.7008 | 5.0387 | 6.0714 | 6.2404 | 2.2946 | 15.9261 | 16.433 | 16.433
4550 | -1.0955 | -0.26474 | 0.13666 | 0.39561 | 2.9717 | 4.074 | 6.5806 | 5.0539 | 5.0511 | 2.2711 | 14.3708 | 16.8746 | 16.8746
4551 | -1.955 | -1.0491 | 0.025291 | 0.14706 | 3.4917 | 3.4784 | 6.4477 | 4.5609 | 3.2306 | 2.218 | 13.749 | 15.388 | 15.388
4552 | 0.28185 | 0.40318 | 0.61097 | 0.65659 | 4.2274 | 5.6089 | 5.4378 | 5.5851 | 4.2454 | 2.6965 | 18.118 | 16.6071 | 18.118
4553 | 0.23327 | 0.81425 | 0.59223 | 0.79225 | 3.9264 | 5.5472 | 5.4219 | 5.9372 | 5.4754 | 1.723 | 17.1338 | 16.5467 | 17.1338
4554 | -1.2642 | -0.89524 | 0.10308 | 0.18533 | 4.6152 | 3.9321 | 6.1567 | 4.6439 | 3.628 | 1.2636 | 14.4548 | 15.6636 | 15.6636
4555 | -1.013 | 1.0308 | 0.15554 | 0.84869 | 4.6663 | 4.1478 | 5.1992 | 6.1234 | 4.9378 | 1.7659 | 16.7035 | 16.5692 | 16.7035
4556 | -0.57678 | -1.8105 | 0.28204 | 0.035111 | 4.2924 | 4.5831 | 4.9294 | 4.2527 | 5.4119 | 2.1507 | 15.2789 | 16.7844 | 16.7844
4557 | 0.18408 | 0.62194 | 0.57302 | 0.73301 | 4.2779 | 5.4849 | 6.5035 | 5.7715 | 5.2125 | 2.0359 | 17.5703 | 18.0298 | 18.0298
4558 | -0.083441 | -2.4427 | 0.46675 | 0.007289 | 3.5731 | 5.1525 | 4.9021 | 4.1111 | 3.9012 | 1.935 | 14.7716 | 14.3113 | 14.7716
4559 | -0.81828 | 0.49576 | 0.2066 | 0.68997 | 2.753 | 4.333 | 3.9022 | 5.6636 | 3.5801 | 2.2769 | 15.0265 | 12.5122 | 15.0265
4560 | 0.074211 | 0.12205 | 0.52958 | 0.54857 | 5.4357 | 5.347 | 6.4299 | 5.3526 | 5.1908 | 1.6651 | 17.8004 | 18.7216 | 18.7216
4561 | 0.31773 | -0.95286 | 0.62465 | 0.17033 | 3.0588 | 5.6547 | 5.569 | 4.612 | 3.2789 | 2.14 | 15.4655 | 14.0467 | 15.4655
4562 | 0.247 | 0.32582 | 0.59754 | 0.62772 | 3.9054 | 5.5646 | 5.0683 | 5.5202 | 5.5389 | 1.2419 | 16.2321 | 15.7544 | 16.2321
4563 | 0.63727 | -1.3433 | 0.73803 | 0.089582 | 3.8163 | 6.0643 | 4.4705 | 4.4219 | 4.5007 | 2.275 | 16.5775 | 15.0624 | 16.5775
4564 | 1.0914 | 0.65839 | 0.86245 | 0.74486 | 4.368 | 6.6369 | 6.3794 | 5.8029 | 4.0668 | 2.4798 | 19.2876 | 17.2941 | 19.2876
4565 | 0.64434 | 0.45311 | 0.74032 | 0.67477 | 3.0283 | 6.0734 | 6.6326 | 5.6274 | 4.6769 | 1.9824 | 16.7114 | 16.3202 | 16.7114
4566 | -0.99016 | -0.12386 | 0.16105 | 0.45071 | 3.141 | 4.1687 | 6.2819 | 5.1592 | 4.0411 | 2.6194 | 15.0883 | 16.0834 | 16.0834
4567 | 0.31668 | 0.12005 | 0.62426 | 0.54778 | 3.3323 | 5.6533 | 6.7727 | 5.351 | 6.1252 | 1.8637 | 16.2003 | 18.0939 | 18.0939
4568 | -2.1309 | -1.4148 | 0.016549 | 0.078557 | 4.9352 | 3.3942 | 5.1317 | 4.392 | 3.5097 | 1.4385 | 14.1599 | 15.0151 | 15.0151
4569 | -0.51885 | -0.74282 | 0.30193 | 0.22879 | 2.9014 | 4.6462 | 5.7237 | 4.7329 | 5.3775 | 2.0303 | 14.3109 | 16.033 | 16.033
4570 | -1.1961 | -0.85202 | 0.11584 | 0.1971 | 2.4717 | 3.9879 | 4.0609 | 4.6684 | 3.9323 | 2.2016 | 13.3297 | 12.6665 | 13.3297
4571 | 1.275 | 1.0392 | 0.89885 | 0.85064 | 3.0355 | 6.859 | 5.4526 | 6.1306 | 3.1245 | 2.3544 | 18.3794 | 13.967 | 18.3794
4572 | -0.4236 | -0.16784 | 0.33593 | 0.43336 | 4.8766 | 4.7523 | 6.5595 | 5.1259 | 4.8 | 2.5034 | 17.2582 | 18.7394 | 18.7394
4573 | -1.1178 | -1.0905 | 0.13182 | 0.13775 | 2.6053 | 4.0545 | 5.8967 | 4.5398 | 5.2677 | 2.7789 | 13.9785 | 16.5486 | 16.5486
4574 | -0.71961 | -1.8266 | 0.23588 | 0.033882 | 4.1978 | 4.4326 | 4.777 | 4.248 | 5.1249 | 1.8923 | 14.7707 | 15.9921 | 15.9921
4575 | -0.53536 | -1.019 | 0.2962 | 0.1541 | 4.0068 | 4.6281 | 3.3993 | 4.5766 | 5.4198 | 1.9117 | 15.1232 | 14.7376 | 15.1232
4576 | 0.2374 | -1.9086 | 0.59383 | 0.028159 | 4.3768 | 5.5524 | 4.055 | 4.2247 | 4.1568 | 1.3853 | 15.5392 | 13.9739 | 15.5392
4577 | 0.52928 | 0.54621 | 0.70169 | 0.70754 | 3.26 | 5.9257 | 5.4289 | 5.7067 | 5.0116 | 2.6177 | 17.5101 | 16.3183 | 17.5101
4578 | -2.8531 | -0.13026 | 0.002165 | 0.44818 | 5.1791 | 3.1597 | 5.8907 | 5.1544 | 5.6993 | 2.1608 | 15.6539 | 18.9299 | 18.9299
4579 | 0.20937 | -0.69484 | 0.58292 | 0.24358 | 3.8159 | 5.5169 | 4.8761 | 4.7624 | 5.2719 | 2.171 | 16.2663 | 16.135 | 16.2663
4580 | 1.1688 | 0.71976 | 0.87875 | 0.76416 | 4.4281 | 6.7314 | 6.0095 | 5.8557 | 4.6015 | 2.2109 | 19.226 | 17.25 | 19.226
4581 | 0.6947 | 0.36637 | 0.75638 | 0.64296 | 5.2372 | 6.1378 | 4.1083 | 5.5542 | 5.2448 | 2.2877 | 19.2169 | 16.878 | 19.2169
4582 | -1.5299 | -1.3118 | 0.063019 | 0.094791 | 4.9195 | 3.7335 | 7.4867 | 4.4355 | 3.3359 | 2.2989 | 15.3875 | 18.0411 | 18.0411
4583 | 0.75875 | 1.7763 | 0.776 | 0.96216 | 2.7261 | 6.2196 | 7.6089 | 6.7306 | 4.2782 | 1.3061 | 16.9823 | 15.9193 | 16.9823
4584 | -0.31696 | 1.1619 | 0.37564 | 0.87736 | 4.6156 | 4.8744 | 5.0668 | 6.235 | 3.6006 | 1.6219 | 17.3469 | 14.9048 | 17.3469
4585 | -0.63262 | -1.667 | 0.26349 | 0.047753 | 3.7378 | 4.5234 | 5.6162 | 4.2982 | 5.2701 | 1.2641 | 13.8234 | 15.8881 | 15.8881
4586 | 0.48575 | 0.77169 | 0.68643 | 0.77985 | 4.8927 | 5.8699 | 4.6519 | 5.9005 | 5.1874 | 2.0376 | 18.7006 | 16.7696 | 18.7006
4587 | 0.94477 | 1.3784 | 0.82761 | 0.91597 | 2.9046 | 6.4549 | 6.2663 | 6.4158 | 3.624 | 2.4247 | 18.2 | 15.2196 | 18.2
4588 | 1.1578 | 1.9802 | 0.87652 | 0.97616 | 4.6183 | 6.718 | 3.4726 | 6.8801 | 4.2071 | 1.5615 | 19.7779 | 13.8596 | 19.7779
4589 | 0.8893 | -0.56221 | 0.81308 | 0.28699 | 4.0279 | 6.3851 | 4.4036 | 4.8471 | 3.5424 | 1.7823 | 17.0424 | 13.7563 | 17.0424
4590 | 0.35113 | 0.77683 | 0.63726 | 0.78137 | 3.8478 | 5.6973 | 5.7402 | 5.9049 | 4.2346 | 1.9032 | 17.3532 | 15.7258 | 17.3532
4591 | 0.15768 | -0.45445 | 0.56265 | 0.32475 | 4.1233 | 5.4516 | 5.0297 | 4.9194 | 3.978 | 1.9089 | 16.4032 | 15.0399 | 16.4032
4592 | -0.73588 | -0.49827 | 0.2309 | 0.30915 | 2.8992 | 4.4159 | 4.6279 | 4.8896 | 4.9172 | 2.5583 | 14.7631 | 15.0027 | 15.0027
4593 | 1.0217 | 1.5202 | 0.84655 | 0.93577 | 3.6865 | 6.5509 | 6.2958 | 6.531 | 4.5117 | 2.1849 | 18.9533 | 16.6789 | 18.9533
4594 | 2.1563 | 0.40899 | 0.98447 | 0.65873 | 3.6179 | 7.7861 | 4.1042 | 5.59 | 4.3496 | 2.504 | 19.498 | 14.5756 | 19.498
4595 | 1.9818 | -0.073233 | 0.97625 | 0.47081 | 4.0277 | 7.6243 | 4.2512 | 5.1981 | 3.5945 | 2.438 | 19.2881 | 14.3115 | 19.2881
4596 | 0.33038 | 0.21958 | 0.62944 | 0.5869 | 4.0319 | 5.6708 | 6.0659 | 5.4321 | 4.0149 | 1.8903 | 17.0251 | 16.0029 | 17.0251
4597 | -1.0315 | -0.42949 | 0.15115 | 0.33378 | 4.8467 | 4.131 | 6.4337 | 4.9366 | 4.0782 | 2.3127 | 16.227 | 17.6713 | 17.6713
4598 | -1.2722 | 0.9652 | 0.10164 | 0.83278 | 5.3275 | 3.9256 | 6.3613 | 6.0671 | 3.4692 | 1.8306 | 17.1509 | 16.9886 | 17.1509
4599 | -1.6499 | -0.24376 | 0.049479 | 0.40371 | 5.1059 | 3.6537 | 3.752 | 5.0693 | 5.4613 | 1.8251 | 15.6541 | 16.1443 | 16.1443
4600 | 0.18916 | 2.2064 | 0.57502 | 0.98632 | 2.9379 | 5.4914 | 5.4249 | 7.0348 | 4.762 | 1.966 | 17.4301 | 15.0908 | 17.4301
4601 | -3.2787 | -1.6214 | 0.0005214 | 0.052464 | 4.1414 | 3.0859 | 6.9572 | 4.3139 | 5.1402 | 2.3038 | 13.8449 | 18.5426 | 18.5426
4602 | 0.77944 | 0.63335 | 0.78214 | 0.73675 | 4.3925 | 6.246 | 6.846 | 5.7814 | 5.1634 | 2.1155 | 18.5353 | 18.5174 | 18.5353
4603 | -0.55181 | 0.16142 | 0.29054 | 0.56412 | 4.3802 | 4.6102 | 7.1587 | 5.3845 | 4.1552 | 2.4484 | 16.8233 | 18.1425 | 18.1425
4604 | -1.7756 | -1.3096 | 0.037899 | 0.095167 | 4.1916 | 3.5768 | 5.8178 | 4.4365 | 5.0395 | 2.1117 | 14.3167 | 17.1606 | 17.1606
4605 | 0.28901 | 1.148 | 0.61371 | 0.87451 | 4.0381 | 5.6181 | 6.1769 | 6.2232 | 4.5259 | 1.5756 | 17.4549 | 16.3164 | 17.4549
4606 | -0.51094 | 0.57556 | 0.3047 | 0.71754 | 4.225 | 4.6549 | 4.9472 | 5.7318 | 5.0837 | 2.1786 | 16.7903 | 16.4345 | 16.7903
4607 | -1.7093 | -1.1995 | 0.043699 | 0.11518 | 3.3342 | 3.6166 | 5.5099 | 4.4866 | 3.7401 | 1.9181 | 13.3556 | 14.5024 | 14.5024
4608 | -0.010784 | -0.11365 | 0.4957 | 0.45476 | 3.9519 | 5.2416 | 5.9135 | 5.167 | 4.1221 | 2.0099 | 16.3704 | 15.9974 | 16.3704
4609 | -0.9292 | -0.48623 | 0.17639 | 0.3134 | 4.1557 | 4.2256 | 7.2552 | 4.8978 | 4.4228 | 2.4613 | 15.7404 | 18.295 | 18.295
4610 | 0.95207 | 2.0532 | 0.82947 | 0.97997 | 3.85 | 6.464 | 4.5278 | 6.9314 | 3.158 | 2.346 | 19.5914 | 13.8819 | 19.5914
4611 | 0.70996 | -0.96547 | 0.76114 | 0.16716 | 4.609 | 6.1574 | 5.4287 | 4.6051 | 4.2305 | 1.8395 | 17.2109 | 16.1077 | 17.2109
4612 | -0.98155 | -0.69369 | 0.16316 | 0.24394 | 5.4742 | 4.1766 | 4.0794 | 4.7631 | 4.1554 | 2.4792 | 16.8931 | 16.1882 | 16.8931
4613 | -1.8964 | 0.16631 | 0.028952 | 0.56605 | 5.0082 | 3.5091 | 4.2072 | 5.3885 | 4.5347 | 1.9304 | 15.8362 | 15.6805 | 15.8362
4614 | 0.65121 | -1.1722 | 0.74255 | 0.12055 | 4.074 | 6.0822 | 7.2363 | 4.4996 | 4.2942 | 2.0523 | 16.7081 | 17.6568 | 17.6568
4615 | -0.52584 | -0.25158 | 0.2995 | 0.40068 | 3.4819 | 4.6385 | 5.9854 | 5.0636 | 4.0487 | 2.4636 | 15.6476 | 15.9795 | 15.9795
4616 | 0.46973 | -0.074918 | 0.68073 | 0.47014 | 4.0402 | 5.8493 | 3.5708 | 5.1968 | 5.7512 | 1.6649 | 16.7512 | 15.0271 | 16.7512
4617 | -0.48212 | 0.75016 | 0.31486 | 0.77342 | 2.9884 | 4.6868 | 4.7187 | 5.8819 | 4.6794 | 2.7117 | 16.2687 | 15.0981 | 16.2687
4618 | 1.1104 | 1.4786 | 0.86659 | 0.93037 | 3.1021 | 6.6603 | 6.3971 | 6.4975 | 3.4275 | 2.4795 | 18.7393 | 15.4062 | 18.7393
4619 | -0.81031 | -1.4969 | 0.20888 | 0.067209 | 4.386 | 4.3409 | 6.6769 | 4.3595 | 3.7477 | 1.28 | 14.3664 | 16.0905 | 16.0905
4620 | 2.0357 | 1.7588 | 0.97911 | 0.9607 | 2.4165 | 7.6755 | 5.8592 | 6.7173 | 4.4093 | 2.2099 | 19.0192 | 14.8949 | 19.0192
4621 | -0.32263 | -0.70813 | 0.37349 | 0.23943 | 4.34 | 4.8679 | 4.3748 | 4.7542 | 4.5067 | 1.8319 | 15.7939 | 15.0534 | 15.7939
4622 | 0.95915 | 1.6404 | 0.83126 | 0.94954 | 4.0701 | 6.4729 | 6.0039 | 6.6262 | 3.342 | 1.7126 | 18.8818 | 15.1286 | 18.8818
4623 | -1.3626 | 0.091141 | 0.086499 | 0.53631 | 4.8308 | 3.8549 | 6.7863 | 5.3277 | 4.6283 | 2.3219 | 16.3354 | 18.5673 | 18.5673
4624 | -0.25769 | -0.37243 | 0.39832 | 0.35479 | 3.2004 | 4.9437 | 7.2991 | 4.9765 | 4.7349 | 2.5588 | 15.6794 | 17.7933 | 17.7933
4625 | 0.86001 | 0.98401 | 0.80511 | 0.83744 | 3.7241 | 6.3482 | 5.5586 | 6.0833 | 5.1537 | 1.9298 | 18.0853 | 16.3661 | 18.0853
4626 | -0.84601 | -0.33052 | 0.19877 | 0.3705 | 5.0295 | 4.3057 | 6.8717 | 5.0063 | 3.8587 | 2.2916 | 16.6332 | 18.0516 | 18.0516
4627 | 0.26995 | -0.24602 | 0.6064 | 0.40283 | 2.8449 | 5.5938 | 6.5324 | 5.0677 | 3.6058 | 2.0261 | 15.5324 | 15.0092 | 15.5324
4628 | -0.41806 | 0.12542 | 0.33795 | 0.54991 | 3.1104 | 4.7586 | 7.5191 | 5.3553 | 3.726 | 2.2614 | 15.4857 | 16.6169 | 16.6169
4629 | 1.2636 | 1.9033 | 0.89682 | 0.9715 | 3.9946 | 6.8454 | 5.1228 | 6.8248 | 4.7213 | 1.5188 | 19.1837 | 15.3575 | 19.1837
4630 | -1.4956 | -1.0458 | 0.067382 | 0.14783 | 3.66 | 3.7574 | 4.9089 | 4.5626 | 4.197 | 2.2876 | 14.2676 | 15.0534 | 15.0534
4631 | -1.6895 | -0.7973 | 0.045562 | 0.21264 | 3.2394 | 3.6288 | 3.6223 | 4.7003 | 4.6284 | 1.7166 | 13.2852 | 13.2067 | 13.2852
4632 | -0.74809 | -0.43465 | 0.2272 | 0.33191 | 3.7393 | 4.4035 | 3.8534 | 4.933 | 3.9118 | 1.8496 | 14.9255 | 13.3542 | 14.9255
4633 | 0.055711 | -0.8253 | 0.52221 | 0.2046 | 3.1974 | 5.3239 | 3.8818 | 4.6839 | 5.1616 | 2.1327 | 15.3379 | 14.3735 | 15.3379
4634 | -0.18742 | -1.5702 | 0.42566 | 0.058184 | 2.3274 | 5.027 | 5.8917 | 4.3321 | 4.4845 | 1.6143 | 13.3009 | 14.3179 | 14.3179
4635 | -0.020436 | -0.73892 | 0.49185 | 0.22998 | 2.986 | 5.2297 | 5.422 | 4.7353 | 4.3149 | 2.7556 | 15.7066 | 15.4785 | 15.7066
4636 | 1.0867 | 0.28483 | 0.86142 | 0.61211 | 5.0436 | 6.6312 | 6.1628 | 5.486 | 4.4602 | 1.9754 | 19.1362 | 17.6419 | 19.1362
4637 | 1.7013 | -0.13386 | 0.95556 | 0.44675 | 4.5074 | 7.3402 | 6.1169 | 5.1516 | 3.7859 | 1.8458 | 18.845 | 16.256 | 18.845
4638 | -0.67966 | 0.2932 | 0.24836 | 0.61532 | 3.0709 | 4.4739 | 7.47 | 5.493 | 3.7898 | 1.5122 | 14.55 | 15.8429 | 15.8429
4639 | 0.2872 | -0.38487 | 0.61302 | 0.35017 | 3.2161 | 5.6158 | 2.6061 | 4.9677 | 4.4583 | 1.9029 | 15.7025 | 12.1834 | 15.7025
4640 | 1.6206 | -0.024529 | 0.94745 | 0.49022 | 4.2505 | 7.2534 | 7.1169 | 5.236 | 4.3022 | 1.4103 | 18.1502 | 17.0799 | 18.1502
4641 | -0.090015 | -0.37267 | 0.46414 | 0.3547 | 3.8464 | 5.1445 | 4.9289 | 4.9763 | 4.1669 | 1.6153 | 15.5825 | 14.5574 | 15.5825
4642 | -0.68714 | -0.96542 | 0.246 | 0.16717 | 3.2589 | 4.4661 | 5.3597 | 4.6052 | 3.9094 | 2.7034 | 15.0337 | 15.2315 | 15.2315
4643 | 0.33527 | 0.41169 | 0.63129 | 0.65972 | 3.509 | 5.6771 | 6.3446 | 5.5923 | 4.6497 | 1.7987 | 16.5771 | 16.302 | 16.5771
4644 | -2.1029 | -2.4758 | 0.017739 | 0.0066461 | 3.0176 | 3.4068 | 6.5538 | 4.1059 | 6.41 | 1.5925 | 12.1228 | 17.5739 | 17.5739
4645 | -0.36574 | 0.022732 | 0.35728 | 0.50907 | 4.779 | 4.8182 | 5.047 | 5.2732 | 5.0021 | 1.9261 | 16.7964 | 16.7542 | 16.7964
4646 | -0.65463 | -0.80031 | 0.25635 | 0.21176 | 2.5626 | 4.5002 | 6.1389 | 4.6986 | 4.4332 | 1.9497 | 13.7109 | 15.0843 | 15.0843
4647 | -1.3687 | 0.047944 | 0.085549 | 0.51912 | 4.5736 | 3.8503 | 3.5515 | 5.2932 | 5.0376 | 2.0857 | 15.8029 | 15.2485 | 15.8029
4648 | -0.59185 | -0.7322 | 0.27698 | 0.23202 | 4.6075 | 4.5669 | 6.6237 | 4.7394 | 3.6791 | 1.7701 | 15.6839 | 16.6804 | 16.6804
4649 | -0.64808 | 0.64117 | 0.25847 | 0.73929 | 4.8812 | 4.507 | 6.7815 | 5.7881 | 5.0826 | 2.4426 | 17.6189 | 19.188 | 19.188
4650 | 0.26408 | 0.35543 | 0.60414 | 0.63887 | 4.4922 | 5.5863 | 7.5634 | 5.545 | 6.2565 | 2.1383 | 17.7618 | 20.4503 | 20.4503
4651 | -0.0036629 | -1.2785 | 0.49854 | 0.10053 | 3.4359 | 5.2504 | 3.3615 | 4.4503 | 4.0121 | 1.589 | 14.7255 | 12.3984 | 14.7255
4652 | 0.10425 | 0.92913 | 0.54151 | 0.82359 | 5.1718 | 5.3845 | 7.645 | 6.0361 | 4.4456 | 1.3954 | 17.9878 | 18.6578 | 18.6578
4653 | 0.86762 | 1.2102 | 0.8072 | 0.8869 | 4.8543 | 6.3578 | 4.2625 | 6.2758 | 4.1359 | 2.2615 | 19.7494 | 15.5142 | 19.7494
4654 | -0.59402 | -1.0685 | 0.27625 | 0.14265 | 3.0708 | 4.5645 | 7.4459 | 4.5509 | 3.8244 | 1.9733 | 14.1596 | 16.3144 | 16.3144
4655 | 0.26929 | 0.80214 | 0.60615 | 0.78876 | 3.6845 | 5.593 | 6.4955 | 5.9267 | 4.5218 | 1.4279 | 16.632 | 16.1296 | 16.632
4656 | 0.50525 | -0.33059 | 0.69331 | 0.37048 | 3.8841 | 5.8949 | 5.4948 | 5.0062 | 4.7066 | 2.319 | 17.1042 | 16.4044 | 17.1042
4657 | 0.2811 | -0.13188 | 0.61068 | 0.44754 | 4.1187 | 5.608 | 4.6449 | 5.1531 | 3.0817 | 1.5921 | 16.4718 | 13.4373 | 16.4718
4658 | 0.1753 | 1.0289 | 0.56958 | 0.84823 | 4.4356 | 5.4739 | 7.2101 | 6.1217 | 3.7543 | 2.4683 | 18.4995 | 17.8682 | 18.4995
4659 | -2.0177 | 0.19132 | 0.021809 | 0.57586 | 3.9981 | 3.447 | 5.1116 | 5.4089 | 4.6486 | 1.6982 | 14.5522 | 15.4566 | 15.4566
4660 | -1.1702 | -1.7996 | 0.12096 | 0.035958 | 4.0091 | 4.0097 | 5.3997 | 4.256 | 5.294 | 1.887 | 14.1617 | 16.5898 | 16.5898
4661 | 0.79867 | 0.71708 | 0.78776 | 0.76334 | 4.9578 | 6.2704 | 5.1526 | 5.8534 | 3.5686 | 1.6687 | 18.7504 | 15.3478 | 18.7504
4662 | 0.56374 | 0.29326 | 0.71353 | 0.61534 | 5.8437 | 5.97 | 4.2143 | 5.493 | 3.7643 | 2.3731 | 19.6799 | 16.1954 | 19.6799
4663 | 0.83762 | -0.30945 | 0.79888 | 0.37849 | 3.3283 | 6.3198 | 2.7648 | 5.0214 | 5.4811 | 1.6197 | 16.2892 | 13.1939 | 16.2892
4664 | 1.4182 | 2.0857 | 0.92194 | 0.9815 | 4.5162 | 7.0266 | 5.3523 | 6.9538 | 3.8993 | 2.2855 | 20.782 | 16.0532 | 20.782
4665 | -0.1466 | -0.5503 | 0.44172 | 0.29106 | 3.2236 | 5.076 | 5.8076 | 4.8549 | 3.4653 | 2.2629 | 15.4175 | 14.7594 | 15.4175
4666 | 0.41251 | 0.9937 | 0.66002 | 0.83982 | 4.3843 | 5.7759 | 5.4978 | 6.0916 | 3.472 | 2.7575 | 19.0093 | 16.1116 | 19.0093
4667 | 0.98074 | -0.57718 | 0.83664 | 0.28191 | 3.6381 | 6.4999 | 4.4327 | 4.8373 | 4.0498 | 2.3327 | 17.308 | 14.4534 | 17.308
4668 | -0.1191 | 0.2865 | 0.4526 | 0.61275 | 4.4458 | 5.1092 | 4.6031 | 5.4874 | 4.2 | 1.5969 | 16.6393 | 14.8458 | 16.6393
4669 | -0.11758 | -0.24266 | 0.4532 | 0.40413 | 4.6651 | 5.1111 | 5.0418 | 5.0701 | 3.2711 | 1.5374 | 16.3837 | 14.5154 | 16.3837
4670 | 2.4357 | 1.3234 | 0.99257 | 0.90716 | 4.4408 | 8.0199 | 5.7909 | 6.3704 | 5.5831 | 2.3992 | 21.2303 | 18.214 | 21.2303
4671 | -0.4825 | -0.056168 | 0.31473 | 0.4776 | 3.6436 | 4.6863 | 6.2744 | 5.2113 | 4.93 | 1.4046 | 14.9459 | 16.2526 | 16.2526
4672 | 0.015004 | 0.076187 | 0.50599 | 0.53037 | 4.7119 | 5.2734 | 5.6834 | 5.3157 | 4.2676 | 1.5066 | 16.8076 | 16.1694 | 16.8076
4673 | 0.3225 | -0.67974 | 0.62646 | 0.24833 | 2.903 | 5.6608 | 5.4643 | 4.7718 | 4.562 | 2.3402 | 15.6757 | 15.2695 | 15.6757
4674 | 0.036467 | 0.15034 | 0.51454 | 0.55975 | 5.2889 | 5.3 | 5.1893 | 5.3755 | 3.4637 | 1.4525 | 17.417 | 15.3945 | 17.417
4675 | -1.1527 | -0.90829 | 0.12451 | 0.18186 | 3.0342 | 4.0245 | 6.8649 | 4.6366 | 4.138 | 1.6083 | 13.3035 | 15.6455 | 15.6455
4676 | -0.38178 | 0.37973 | 0.35131 | 0.64793 | 4.4078 | 4.7998 | 7.689 | 5.5654 | 4.3541 | 1.3829 | 16.1559 | 17.8338 | 17.8338
4677 | -0.070124 | 0.55651 | 0.47205 | 0.71107 | 5.3561 | 5.1688 | 7.046 | 5.7155 | 4.4813 | 1.6493 | 17.8897 | 18.5328 | 18.5328
4678 | -0.34154 | -0.48515 | 0.36635 | 0.31378 | 4.586 | 4.846 | 5.7583 | 4.8985 | 3.92 | 2.0229 | 16.3534 | 16.2872 | 16.3534
4679 | 0.518 | 0.088314 | 0.69777 | 0.53519 | 2.7339 | 5.9113 | 4.2144 | 5.3254 | 3.6226 | 2.6101 | 16.5806 | 13.181 | 16.5806
4680 | -0.67898 | -1.1648 | 0.24857 | 0.12205 | 5.4174 | 4.4746 | 7.2425 | 4.5031 | 4.7576 | 1.7883 | 16.1834 | 19.2058 | 19.2058
4681 | 2.2327 | 2.9365 | 0.98722 | 0.99834 | 5.1648 | 7.8531 | 3.4714 | 7.4439 | 4.891 | 1.4856 | 21.9475 | 15.0128 | 21.9475
4682 | 0.85925 | 1.0887 | 0.8049 | 0.86186 | 3.3532 | 6.3472 | 5.2349 | 6.1728 | 3.3272 | 2.0036 | 17.8769 | 13.919 | 17.8769
4683 | -0.45717 | 0.9897 | 0.32377 | 0.83884 | 3.3554 | 4.7146 | 6.5166 | 6.0882 | 4.6123 | 1.4383 | 15.5965 | 15.9226 | 15.9226
4684 | -0.88903 | -1.4622 | 0.18699 | 0.071841 | 5.4589 | 4.2639 | 6.3505 | 4.373 | 4.293 | 1.4971 | 15.5929 | 17.5994 | 17.5994
4685 | -0.38878 | -1.4001 | 0.34872 | 0.080739 | 5.6843 | 4.7918 | 4.4044 | 4.398 | 4.1276 | 1.3963 | 16.2704 | 15.6126 | 16.2704
4686 | -0.51331 | 0.18367 | 0.30387 | 0.57286 | 4.9457 | 4.6523 | 3.7897 | 5.4027 | 3.8345 | 2.181 | 17.1816 | 14.7509 | 17.1816
4687 | -0.68817 | 0.066218 | 0.24567 | 0.5264 | 4.9325 | 4.4651 | 7.0725 | 5.3077 | 3.5638 | 1.7497 | 16.455 | 17.3186 | 17.3186
4688 | 0.19623 | -0.51155 | 0.57778 | 0.30448 | 2.32 | 5.5003 | 5.4184 | 4.8807 | 3.3677 | 1.8788 | 14.5797 | 12.9848 | 14.5797
4689 | -1.2598 | -1.189 | 0.10387 | 0.11722 | 3.6299 | 3.9356 | 7.1205 | 4.4916 | 4.8224 | 1.4527 | 13.5098 | 17.0255 | 17.0255
4690 | 0.46797 | 0.59926 | 0.6801 | 0.7255 | 3.6043 | 5.847 | 5.7269 | 5.7521 | 3.8676 | 2.1747 | 17.3782 | 15.3736 | 17.3782
4691 | -0.68968 | -0.3856 | 0.2452 | 0.3499 | 2.6471 | 4.4635 | 3.5968 | 4.9672 | 4.2206 | 2.4818 | 14.5596 | 12.9463 | 14.5596
4692 | -1.6968 | -1.7338 | 0.044871 | 0.041481 | 3.5595 | 3.6243 | 5.5132 | 4.2764 | 3.2597 | 2.13 | 13.5903 | 14.4624 | 14.4624
4693 | -0.82917 | -0.040152 | 0.2035 | 0.48399 | 4.4494 | 4.3222 | 6.5296 | 5.2238 | 3.3662 | 1.4638 | 15.4593 | 15.809 | 15.809
4694 | 0.69504 | 1.1453 | 0.75648 | 0.87396 | 4.991 | 6.1383 | 3.4305 | 6.2209 | 4.9634 | 2.6622 | 20.0124 | 16.0471 | 20.0124
4695 | -0.62819 | -1.3209 | 0.26494 | 0.093265 | 3.9116 | 4.5281 | 5.8422 | 4.4316 | 4.774 | 2.4748 | 15.3461 | 17.0026 | 17.0026
4696 | -0.33135 | 0.4573 | 0.37019 | 0.67627 | 3.704 | 4.8578 | 6.1663 | 5.6309 | 3.7256 | 2.1606 | 16.3533 | 15.7565 | 16.3533
4697 | -0.22908 | 0.0004383 | 0.4094 | 0.50017 | 4.1042 | 4.9775 | 3.3298 | 5.2556 | 3.7599 | 2.2424 | 16.5797 | 13.4363 | 16.5797
4698 | 1.0679 | 1.2708 | 0.85722 | 0.8981 | 3.3056 | 6.608 | 6.1358 | 6.3266 | 3.8641 | 1.8167 | 18.0569 | 15.1222 | 18.0569
4699 | -1.2649 | -0.85986 | 0.10296 | 0.19493 | 3.8667 | 3.9315 | 6.7161 | 4.6639 | 4.9499 | 2.1387 | 14.6009 | 17.6714 | 17.6714
4700 | 0.18126 | 0.5325 | 0.57192 | 0.70281 | 4.2732 | 5.4814 | 5.888 | 5.6949 | 3.5145 | 2.2867 | 17.7362 | 15.9624 | 17.7362
4701 | 0.27296 | -0.64432 | 0.60756 | 0.25968 | 3.6719 | 5.5976 | 5.8901 | 4.7941 | 3.9288 | 2.0487 | 16.1122 | 15.5394 | 16.1122
4702 | -2.1848 | -0.69493 | 0.01445 | 0.24355 | 5.3618 | 3.3708 | 6.0118 | 4.7623 | 4.2248 | 1.7194 | 15.2143 | 17.3179 | 17.3179
4703 | 0.012872 | -0.28379 | 0.50514 | 0.38829 | 3.9617 | 5.2708 | 5.9195 | 5.04 | 4.0412 | 1.794 | 16.0665 | 15.7164 | 16.0665
4704 | -0.85944 | 0.37542 | 0.19505 | 0.64633 | 4.9054 | 4.2926 | 6.9366 | 5.5618 | 3.9386 | 1.7469 | 16.5067 | 17.5276 | 17.5276
4705 | -1.4035 | 0.03839 | 0.080236 | 0.51531 | 5.1819 | 3.8241 | 3.7006 | 5.2856 | 3.7719 | 2.7104 | 17.002 | 15.3648 | 17.002
4706 | 0.29641 | -1.1944 | 0.61654 | 0.11616 | 2.7766 | 5.6275 | 5.1222 | 4.489 | 5.716 | 2.1916 | 15.0847 | 15.8064 | 15.8064
4707 | 2.0722 | 1.4558 | 0.98088 | 0.92727 | 3.2928 | 7.7096 | 6.3573 | 6.479 | 3.1675 | 1.7342 | 19.2156 | 14.5518 | 19.2156
4708 | -1.6116 | -1.7245 | 0.053523 | 0.042307 | 3.5985 | 3.6785 | 7.4275 | 4.2793 | 3.3885 | 1.9671 | 13.5235 | 16.3816 | 16.3816
4709 | 1.1067 | 0.59598 | 0.86579 | 0.72441 | 2.8552 | 6.6557 | 5.6967 | 5.7493 | 5.1616 | 1.6967 | 16.9569 | 15.4103 | 16.9569
4710 | 1.5246 | 0.67814 | 0.93632 | 0.75116 | 4.0257 | 7.1474 | 6.7182 | 5.8199 | 4.8263 | 1.6352 | 18.6282 | 17.2055 | 18.6282
4711 | -0.47921 | -0.3314 | 0.31589 | 0.37017 | 3.7367 | 4.69 | 7.064 | 5.0057 | 5.1668 | 2.5471 | 15.9795 | 18.5146 | 18.5146
4712 | 0.15257 | -0.15665 | 0.56063 | 0.43776 | 3.171 | 5.4452 | 5.3104 | 5.1343 | 4.6034 | 1.8004 | 15.551 | 14.8853 | 15.551
4713 | 0.81953 | -0.3509 | 0.79376 | 0.36283 | 4.7576 | 6.2969 | 5.2128 | 4.9917 | 4.3034 | 1.6461 | 17.6923 | 15.9199 | 17.6923
4714 | 0.013708 | 1.0031 | 0.50547 | 0.84208 | 3.8982 | 5.2718 | 5.1914 | 6.0996 | 4.141 | 2.7048 | 17.9744 | 15.9354 | 17.9744
4715 | 1.937 | 1.4642 | 0.97363 | 0.92843 | 3.5695 | 7.5809 | 6.8142 | 6.4858 | 4.0445 | 2.3396 | 19.9758 | 16.7678 | 19.9758
4716 | -0.032596 | 0.897 | 0.487 | 0.81514 | 5.2332 | 5.2147 | 2.495 | 6.0085 | 3.0203 | 1.5237 | 17.9801 | 12.2722 | 17.9801
4717 | -0.17868 | 0.57045 | 0.4291 | 0.71581 | 4.6258 | 5.0375 | 6.3666 | 5.7274 | 6.0202 | 1.3738 | 16.7645 | 18.3864 | 18.3864
4718 | -0.67681 | -0.7386 | 0.24926 | 0.23007 | 4.6183 | 4.4769 | 3.6321 | 4.7355 | 4.3605 | 1.9258 | 15.7565 | 14.5367 | 15.7565
4719 | 2.6767 | 1.9319 | 0.99628 | 0.97331 | 3.6624 | 8.1963 | 3.8877 | 6.8455 | 3.6204 | 1.2995 | 20.0036 | 12.47 | 20.0036
4720 | -0.1328 | -0.84763 | 0.44718 | 0.19832 | 4.3036 | 5.0927 | 5.6687 | 4.671 | 5.171 | 1.2783 | 15.3456 | 16.4217 | 16.4217
4721 | 0.20536 | 0.49863 | 0.58136 | 0.69098 | 4.6882 | 5.5118 | 4.7462 | 5.6661 | 3.8911 | 2.3551 | 18.2212 | 15.6806 | 18.2212
4722 | 0.39969 | -0.74509 | 0.65531 | 0.22811 | 4.2262 | 5.7595 | 6.3375 | 4.7316 | 3.922 | 2.5437 | 17.261 | 17.0294 | 17.261
4723 | -0.20305 | 0.5396 | 0.41955 | 0.70526 | 3.2415 | 5.0084 | 6.4619 | 5.701 | 3.283 | 1.4688 | 15.4197 | 14.4552 | 15.4197
4724 | -0.71656 | 1.0992 | 0.23682 | 0.86416 | 3.9578 | 4.4357 | 4.7118 | 6.1818 | 4.0152 | 1.4676 | 16.0429 | 14.1524 | 16.0429
4725 | -0.83795 | -0.91838 | 0.20103 | 0.17921 | 4.91 | 4.3136 | 6.0221 | 4.6309 | 5.5374 | 1.5159 | 15.3704 | 17.9854 | 17.9854
4726 | 2.3491 | 1.4877 | 0.99059 | 0.93159 | 4.0265 | 7.9508 | 5.0074 | 6.5049 | 5.5786 | 2.6915 | 21.1737 | 17.304 | 21.1737
4727 | 1.0336 | -0.24411 | 0.84933 | 0.40357 | 3.875 | 6.5655 | 5.1678 | 5.0691 | 4.5463 | 1.5194 | 17.029 | 15.1085 | 17.029
4728 | -1.084 | -1.0716 | 0.13917 | 0.14194 | 3.783 | 4.0841 | 3.9522 | 4.5493 | 4.155 | 1.8638 | 14.2802 | 13.754 | 14.2802
4729 | -0.13236 | 0.67225 | 0.44735 | 0.74929 | 3.4855 | 5.0932 | 2.9343 | 5.8148 | 4.7013 | 2.2878 | 16.6813 | 13.4089 | 16.6813
4730 | 1.3005 | 0.86704 | 0.90329 | 0.80704 | 4.7174 | 6.8892 | 6.121 | 5.9827 | 4.4053 | 1.357 | 18.9463 | 16.6007 | 18.9463
4731 | -0.62678 | -0.59934 | 0.2654 | 0.27447 | 3.1558 | 4.5296 | 5.3905 | 4.8229 | 4.3504 | 1.5621 | 14.0703 | 14.4588 | 14.4588
4732 | 1.691 | 1.162 | 0.95458 | 0.87737 | 3.5727 | 7.3293 | 5.903 | 6.235 | 3.5877 | 1.6143 | 18.7513 | 14.6778 | 18.7513
4733 | -0.039105 | 0.17881 | 0.4844 | 0.57096 | 5.349 | 5.2067 | 6.4457 | 5.3987 | 3.5225 | 2.3044 | 18.2589 | 17.6217 | 18.2589
4734 | 0.056357 | -0.16026 | 0.52247 | 0.43634 | 3.4391 | 5.3247 | 5.4706 | 5.1316 | 3.5846 | 1.816 | 15.7114 | 14.3103 | 15.7114
4735 | 1.1873 | -0.10974 | 0.88245 | 0.45631 | 4.3948 | 6.7539 | 5.5122 | 5.17 | 3.5313 | 2.2427 | 18.5613 | 15.681 | 18.5613
4736 | -0.37574 | 0.5141 | 0.35356 | 0.69641 | 4.4623 | 4.8067 | 6.4093 | 5.6792 | 5.3711 | 2.1144 | 17.0627 | 18.3572 | 18.3572
4737 | -1.3427 | -0.20935 | 0.08968 | 0.41709 | 4.2379 | 3.8702 | 5.6109 | 5.0948 | 5.9023 | 1.7318 | 14.9348 | 17.4829 | 17.4829
4738 | 0.97815 | 0.59128 | 0.836 | 0.72284 | 4.3403 | 6.4966 | 5.982 | 5.7452 | 3.8148 | 1.4608 | 18.043 | 15.598 | 18.043
4739 | -0.2347 | -0.40259 | 0.40722 | 0.34362 | 4.7907 | 4.9708 | 5.1412 | 4.9553 | 3.7776 | 2.5987 | 17.3156 | 16.3082 | 17.3156
4740 | -0.43271 | 1.4408 | 0.33261 | 0.92517 | 3.7412 | 4.742 | 4.0735 | 6.4668 | 3.3015 | 1.4767 | 16.4267 | 12.5928 | 16.4267
4741 | -0.087339 | 0.98551 | 0.4652 | 0.83781 | 3.9115 | 5.1478 | 3.9042 | 6.0846 | 4.2758 | 1.4976 | 16.6414 | 13.5891 | 16.6414
4742 | -0.032037 | 0.44656 | 0.48722 | 0.6724 | 4.7096 | 5.2154 | 5.1788 | 5.6218 | 4.1043 | 2.6238 | 18.1706 | 16.6165 | 18.1706
4743 | -0.2232 | -0.42416 | 0.41169 | 0.33573 | 5.077 | 4.9845 | 4.6217 | 4.9403 | 4.8403 | 2.2641 | 17.2658 | 16.8031 | 17.2658
4744 | 1.2645 | 0.72435 | 0.89697 | 0.76558 | 3.2831 | 6.8464 | 7.0085 | 5.8597 | 3.574 | 1.4491 | 17.4384 | 15.3148 | 17.4384
4745 | -1.0204 | -1.1164 | 0.15376 | 0.13212 | 4.7448 | 4.141 | 7.6756 | 4.5268 | 3.7752 | 2.1551 | 15.5677 | 18.3507 | 18.3507
4746 | 0.0024348 | 0.46556 | 0.50097 | 0.67923 | 2.7716 | 5.2579 | 6.2637 | 5.6379 | 4.3766 | 1.7165 | 15.3839 | 15.1283 | 15.3839
4747 | 1.1219 | 0.33766 | 0.86904 | 0.63219 | 3.303 | 6.6742 | 5.4527 | 5.5301 | 4.5792 | 1.3425 | 16.8499 | 14.6774 | 16.8499
4748 | -0.078591 | 0.77583 | 0.46868 | 0.78108 | 4.604 | 5.1584 | 6.0812 | 5.904 | 4.7566 | 1.5343 | 17.2008 | 16.9762 | 17.2008
4749 | -0.47287 | 0.56312 | 0.31815 | 0.71332 | 5.6977 | 4.6971 | 4.0304 | 5.7211 | 4.6458 | 1.7141 | 17.83 | 16.088 | 17.83
4750 | -0.51897 | -0.98837 | 0.30189 | 0.16149 | 5.1319 | 4.6461 | 5.8843 | 4.5928 | 3.4902 | 1.2259 | 15.5966 | 15.7323 | 15.7323
4751 | -0.13034 | -0.79746 | 0.44815 | 0.21259 | 4.744 | 5.0956 | 5.9055 | 4.7002 | 3.6418 | 2.2418 | 16.7816 | 16.5331 | 16.7816
4752 | -0.38167 | -0.30022 | 0.35135 | 0.382 | 4.1988 | 4.7999 | 5.6978 | 5.0281 | 4.1996 | 1.5391 | 15.566 | 15.6354 | 15.6354
4753 | -1.0129 | -0.87505 | 0.15555 | 0.19077 | 4.413 | 4.1478 | 6.6138 | 4.6553 | 5.1987 | 2.3203 | 15.5364 | 18.5458 | 18.5458
4754 | 0.084809 | 1.4136 | 0.53379 | 0.92126 | 3.4511 | 5.3602 | 5.5943 | 6.4447 | 5.6263 | 2.2877 | 17.5437 | 16.9594 | 17.5437
4755 | -1.1509 | 0.53663 | 0.12488 | 0.70424 | 3.8989 | 4.026 | 5.8132 | 5.6985 | 3.7754 | 1.5183 | 15.1417 | 15.0058 | 15.1417
4756 | -1.0283 | -0.12732 | 0.15191 | 0.44934 | 3.1015 | 4.1339 | 6.7556 | 5.1566 | 4.6991 | 2.3222 | 14.7142 | 16.8785 | 16.8785
4757 | -2.6034 | -1.9815 | 0.0046158 | 0.023769 | 2.9894 | 3.2228 | 6.2004 | 4.2054 | 3.4055 | 1.6606 | 12.0782 | 14.2558 | 14.2558
4758 | 0.4777 | -0.48806 | 0.68357 | 0.31275 | 3.7709 | 5.8595 | 5.4415 | 4.8965 | 3.6778 | 2.3799 | 16.9068 | 15.2701 | 16.9068
4759 | 0.46101 | 0.97228 | 0.6776 | 0.83454 | 5.5695 | 5.8381 | 5.9572 | 6.0732 | 5.1405 | 1.4217 | 18.9026 | 18.0889 | 18.9026
4760 | 0.73932 | -0.14339 | 0.77014 | 0.44299 | 3.7493 | 6.1948 | 5.1841 | 5.1444 | 4.1032 | 2.2256 | 17.314 | 15.2622 | 17.314
4761 | -1.6574 | -0.37312 | 0.048723 | 0.35453 | 5.2598 | 3.649 | 7.1027 | 4.976 | 4.984 | 2.5 | 16.3849 | 19.8466 | 19.8466
4762 | 2.7925 | 0.7615 | 0.99738 | 0.77682 | 3.6985 | 8.2727 | 3.7723 | 5.8917 | 3.7375 | 1.8668 | 19.7297 | 13.0751 | 19.7297
4763 | 0.56011 | -0.19745 | 0.7123 | 0.42174 | 3.7828 | 5.9653 | 5.7977 | 5.1037 | 4.0236 | 2.6761 | 17.5279 | 16.2803 | 17.5279
4764 | -0.72307 | -0.57682 | 0.23482 | 0.28203 | 5.2905 | 4.429 | 5.3552 | 4.8375 | 5.2032 | 2.4128 | 16.9699 | 18.2617 | 18.2617
4765 | 1.0002 | 1.0211 | 0.84138 | 0.84641 | 3.9556 | 6.5241 | 3.9158 | 6.1151 | 3.2249 | 2.0432 | 18.638 | 13.1395 | 18.638
4766 | -0.0010037 | -0.28569 | 0.4996 | 0.38756 | 5.2322 | 5.2536 | 4.934 | 5.0386 | 5.2685 | 1.8063 | 17.3308 | 17.241 | 17.3308
4767 | -1.5843 | -0.13959 | 0.056562 | 0.44449 | 5.4174 | 3.6966 | 7.103 | 5.1473 | 4.607 | 2.0956 | 16.3568 | 19.223 | 19.223
4768 | -0.653 | -1.0821 | 0.25688 | 0.1396 | 4.6168 | 4.5019 | 2.9258 | 4.544 | 3.4323 | 1.6023 | 15.265 | 12.5772 | 15.265
4769 | 0.07123 | -0.1438 | 0.52839 | 0.44283 | 3.8719 | 5.3433 | 4.5213 | 5.1441 | 3.9041 | 2.4604 | 16.8196 | 14.7577 | 16.8196
4770 | -0.113 | 0.071222 | 0.45501 | 0.52839 | 3.8736 | 5.1166 | 6.1794 | 5.3117 | 4.8323 | 2.3234 | 16.6253 | 17.2086 | 17.2086
4771 | -1.0062 | -0.73595 | 0.15716 | 0.23088 | 3.9417 | 4.154 | 6.5182 | 4.7371 | 5.1123 | 1.4529 | 14.2857 | 17.0251 | 17.0251
4772 | 0.44449 | 1.3021 | 0.67165 | 0.90355 | 2.4074 | 5.8169 | 7.469 | 6.3527 | 3.8162 | 1.9664 | 16.5433 | 15.6589 | 16.5433
4773 | -0.64313 | -0.80303 | 0.26007 | 0.21098 | 5.2756 | 4.5123 | 5.5279 | 4.697 | 4.0152 | 2.385 | 16.8698 | 17.2038 | 17.2038
4774 | 0.052515 | 0.69751 | 0.52094 | 0.75726 | 3.7849 | 5.32 | 5.4456 | 5.8365 | 3.6106 | 1.5857 | 16.527 | 14.4267 | 16.527
4775 | 0.1507 | 0.91585 | 0.55989 | 0.82013 | 3.5891 | 5.4428 | 6.8962 | 6.0247 | 3.5095 | 1.7166 | 16.7732 | 15.7113 | 16.7732
4776 | -0.47142 | 0.34825 | 0.31867 | 0.63618 | 3.7055 | 4.6987 | 6.5022 | 5.539 | 4.4631 | 2.585 | 16.5281 | 17.2558 | 17.2558
4777 | -1.0117 | 0.0073691 | 0.15583 | 0.50294 | 3.859 | 4.1489 | 4.5457 | 5.261 | 4.5631 | 2.2427 | 15.5116 | 15.2105 | 15.5116
4778 | 0.28968 | -0.14392 | 0.61397 | 0.44278 | 4.2975 | 5.6189 | 5.6892 | 5.144 | 4.3965 | 2.1228 | 17.1833 | 16.5061 | 17.1833
4779 | -0.23988 | -0.69973 | 0.40521 | 0.24205 | 3.888 | 4.9647 | 5.6162 | 4.7593 | 3.6507 | 2.0044 | 15.6165 | 15.1593 | 15.6165
4780 | -1.5705 | -2.4364 | 0.058151 | 0.0074175 | 2.3869 | 3.7058 | 7.4345 | 4.1121 | 3.8748 | 1.6112 | 11.8161 | 15.3075 | 15.3075
4781 | -0.49126 | -0.47806 | 0.31162 | 0.3163 | 4.6854 | 4.6766 | 6.3563 | 4.9033 | 4.031 | 2.0873 | 16.3527 | 17.1601 | 17.1601
4782 | -0.29893 | -2.2839 | 0.3825 | 0.01119 | 4.457 | 4.8954 | 6.1224 | 4.1386 | 5.5826 | 1.8289 | 15.3199 | 17.991 | 17.991
4783 | -0.23893 | 0.024312 | 0.40558 | 0.5097 | 4.3636 | 4.9658 | 7.0792 | 5.2744 | 3.9342 | 2.2752 | 16.879 | 17.6521 | 17.6521
4784 | -1.2585 | -0.32478 | 0.1041 | 0.37267 | 3.9374 | 3.9366 | 3.0953 | 5.0104 | 4.8903 | 2.1 | 14.9845 | 14.023 | 14.9845
4785 | -0.35693 | -0.01908 | 0.36057 | 0.49239 | 3.5082 | 4.8283 | 6.366 | 5.2403 | 4.4044 | 1.5309 | 15.1076 | 15.8095 | 15.8095
4786 | 0.24368 | -0.5755 | 0.59626 | 0.28248 | 3.6163 | 5.5604 | 4.3379 | 4.8384 | 4.1077 | 1.666 | 15.6811 | 13.728 | 15.6811
4787 | -1.564 | -1.1094 | 0.058908 | 0.13362 | 4.1609 | 3.7102 | 6.7442 | 4.5303 | 4.5301 | 2.2477 | 14.6491 | 17.6829 | 17.6829
4788 | 0.70311 | -0.86596 | 0.75901 | 0.19326 | 2.7065 | 6.1486 | 6.32 | 4.6605 | 5.0868 | 1.3702 | 14.8858 | 15.4836 | 15.4836
4789 | 0.4345 | 1.3569 | 0.66804 | 0.91259 | 3.3667 | 5.8041 | 4.9263 | 6.3981 | 3.4548 | 2.614 | 18.1829 | 14.3618 | 18.1829
4790 | -1.8675 | -1.0731 | 0.030915 | 0.14161 | 3.18 | 3.5248 | 6.3498 | 4.5486 | 3.8488 | 2.0977 | 13.3511 | 15.4763 | 15.4763
4791 | -1.2181 | 0.45022 | 0.1116 | 0.67372 | 3.1712 | 3.9697 | 7.2801 | 5.6249 | 4.9522 | 1.6378 | 14.4036 | 17.0414 | 17.0414
4792 | -0.38715 | -0.35611 | 0.34932 | 0.36088 | 4.2012 | 4.7937 | 6.709 | 4.988 | 4.3713 | 2.2146 | 16.1975 | 17.496 | 17.496
4793 | -0.31096 | -0.66501 | 0.37792 | 0.25302 | 4.4936 | 4.8814 | 4.912 | 4.781 | 4.6483 | 1.3345 | 15.4905 | 15.3884 | 15.4905
4794 | -1.2539 | -0.45934 | 0.10494 | 0.323 | 3.7461 | 3.9404 | 6.6454 | 4.9161 | 4.4521 | 1.712 | 14.3146 | 16.5556 | 16.5556
4795 | 2.0337 | -0.11648 | 0.97901 | 0.45363 | 3.841 | 7.6736 | 5.5265 | 5.1649 | 5.4033 | 2.1265 | 18.8061 | 16.8974 | 18.8061
4796 | 0.59772 | -0.77157 | 0.72499 | 0.22018 | 2.8656 | 6.0136 | 5.7663 | 4.7156 | 3.4404 | 2.6886 | 16.2834 | 14.7609 | 16.2834
4797 | 1.023 | 1.9817 | 0.84685 | 0.97624 | 4.2098 | 6.5525 | 5.9592 | 6.8812 | 5.0116 | 1.3732 | 19.0166 | 16.5538 | 19.0166
4798 | -0.49948 | 0.88077 | 0.30872 | 0.81078 | 2.6455 | 4.6675 | 5.9545 | 5.9945 | 4.2923 | 2.4852 | 15.7927 | 15.3775 | 15.7927
4799 | 0.62821 | 1.1157 | 0.73507 | 0.86773 | 2.7261 | 6.0527 | 7.2583 | 6.1958 | 4.412 | 1.6341 | 16.6087 | 16.0304 | 16.6087
4800 | 0.18193 | 0.24852 | 0.57218 | 0.59813 | 4.3062 | 5.4822 | 5.4074 | 5.456 | 3.2626 | 1.317 | 16.5614 | 14.2933 | 16.5614
4801 | -1.486 | -0.32943 | 0.068634 | 0.37092 | 3.9705 | 3.7641 | 6.2822 | 5.0071 | 3.9946 | 2.1698 | 14.9115 | 16.4171 | 16.4171
4802 | 0.26441 | -0.89985 | 0.60427 | 0.1841 | 4.1002 | 5.5867 | 5.2521 | 4.6413 | 4.8335 | 1.9855 | 16.3137 | 16.1713 | 16.3137
4803 | 0.20424 | 1.1457 | 0.58092 | 0.87404 | 3.5778 | 5.5104 | 5.0941 | 6.2212 | 3.2741 | 2.1231 | 17.4325 | 14.0691 | 17.4325
4804 | 1.0199 | -0.12615 | 0.84611 | 0.44981 | 3.9266 | 6.5486 | 6.8669 | 5.1575 | 4.6953 | 2.5049 | 18.1376 | 17.9938 | 18.1376
4805 | 0.15765 | -0.084117 | 0.56263 | 0.46648 | 3.5604 | 5.4516 | 5.8469 | 5.1897 | 6.0302 | 2.5577 | 16.7593 | 17.9952 | 17.9952
4806 | 1.5474 | -0.47825 | 0.93911 | 0.31624 | 4.4221 | 7.1728 | 6.8604 | 4.9032 | 6.3627 | 2.1457 | 18.6437 | 19.7908 | 19.7908
4807 | 0.0086283 | -0.89187 | 0.50344 | 0.18623 | 4.0412 | 5.2655 | 7.0529 | 4.6458 | 4.9617 | 1.5283 | 15.4807 | 17.5841 | 17.5841
4808 | 1.2457 | -0.068416 | 0.89357 | 0.47273 | 3.7694 | 6.8241 | 3.3902 | 5.2018 | 4.8186 | 2.6236 | 18.419 | 14.6018 | 18.419
4809 | 0.70345 | -0.12225 | 0.75911 | 0.45135 | 2.7531 | 6.149 | 4.7863 | 5.1605 | 3.5027 | 2.5485 | 16.6111 | 13.5906 | 16.6111
4810 | -0.61011 | -0.21137 | 0.27089 | 0.4163 | 2.9087 | 4.5473 | 6.7179 | 5.0933 | 5.7178 | 1.3587 | 13.908 | 16.703 | 16.703
4811 | -1.5616 | -0.84456 | 0.059186 | 0.19918 | 4.6258 | 3.7118 | 6.1462 | 4.6727 | 5.0592 | 2.0999 | 15.1102 | 17.9312 | 17.9312
4812 | 0.44077 | 0.56071 | 0.67031 | 0.7125 | 4.1595 | 5.8121 | 5.5901 | 5.7191 | 4.1015 | 2.2356 | 17.9263 | 16.0867 | 17.9263
4813 | -1.2752 | -1.0646 | 0.10113 | 0.14353 | 3.8556 | 3.9233 | 6.6899 | 4.5529 | 3.9926 | 1.2909 | 13.6228 | 15.8291 | 15.8291
4814 | 0.71907 | 0.54415 | 0.76395 | 0.70683 | 4.2332 | 6.169 | 4.6676 | 5.7049 | 4.0654 | 1.9214 | 18.0285 | 14.8876 | 18.0285
4815 | 0.73817 | 0.5146 | 0.76979 | 0.69658 | 2.8821 | 6.1934 | 5.0666 | 5.6797 | 3.4192 | 2.4833 | 17.2384 | 13.8511 | 17.2384
4816 | -0.29024 | -0.4659 | 0.38582 | 0.32064 | 5.0344 | 4.9056 | 3.9731 | 4.9116 | 4.9531 | 1.7809 | 16.6324 | 15.7414 | 16.6324
4817 | 1.0149 | 0.66982 | 0.84491 | 0.74851 | 2.6788 | 6.5423 | 5.8161 | 5.8127 | 3.4936 | 2.3716 | 17.4054 | 14.3601 | 17.4054
4818 | 1.1616 | 0.69477 | 0.8773 | 0.7564 | 4.3756 | 6.7227 | 4.5469 | 5.8342 | 4.0672 | 1.4249 | 18.3573 | 14.4146 | 18.3573
4819 | 0.23942 | -0.0023239 | 0.59461 | 0.49907 | 4.6791 | 5.555 | 5.9052 | 5.2534 | 5.1341 | 1.7023 | 17.1898 | 17.4207 | 17.4207
4820 | -0.98012 | -1.0923 | 0.16351 | 0.13736 | 3.9352 | 4.178 | 5.8776 | 4.5389 | 4.7602 | 1.7597 | 14.4117 | 16.3326 | 16.3326
4821 | -1.1639 | -1.0808 | 0.12222 | 0.1399 | 3.6186 | 4.0149 | 4.2391 | 4.5447 | 4.2468 | 1.8612 | 14.0395 | 13.9658 | 14.0395
4822 | 0.79967 | 1.065 | 0.78805 | 0.85656 | 4.7681 | 6.2717 | 5.4211 | 6.1526 | 4.8846 | 1.7265 | 18.9188 | 16.8003 | 18.9188
4823 | -0.70019 | 1.3682 | 0.2419 | 0.91437 | 4.2087 | 4.4526 | 5.533 | 6.4074 | 4.8219 | 1.4738 | 16.5425 | 16.0374 | 16.5425
4824 | 0.74159 | -0.89359 | 0.77083 | 0.18577 | 5.036 | 6.1977 | 7.5166 | 4.6448 | 3.5827 | 2.1279 | 18.0064 | 18.2631 | 18.2631
4825 | 0.11292 | 1.999 | 0.54495 | 0.9772 | 4.6352 | 5.3954 | 5.242 | 6.8934 | 4.5077 | 2.462 | 19.386 | 16.8468 | 19.386
4826 | -0.015352 | -0.16128 | 0.49388 | 0.43593 | 4.4706 | 5.2359 | 6.9024 | 5.1308 | 5.3187 | 2.7029 | 17.5402 | 19.3946 | 19.3946
4827 | 1.5278 | -0.93004 | 0.93671 | 0.17618 | 4.2304 | 7.1509 | 5.6269 | 4.6245 | 3.744 | 1.9402 | 17.946 | 15.5415 | 17.946
4828 | 0.040009 | -1.5149 | 0.51596 | 0.064899 | 3.9386 | 5.3044 | 7.4259 | 4.3526 | 6.0752 | 2.53 | 16.1256 | 19.9696 | 19.9696
4829 | 0.20406 | 1.0117 | 0.58085 | 0.84416 | 3.6568 | 5.5102 | 4.3329 | 6.107 | 4.3758 | 1.9052 | 17.1792 | 14.2707 | 17.1792
4830 | -0.25775 | -2.1026 | 0.3983 | 0.01775 | 4.2504 | 4.9436 | 5.3648 | 4.1762 | 4.501 | 1.5568 | 14.927 | 15.6729 | 15.6729
4831 | 0.69378 | 1.6088 | 0.75609 | 0.94617 | 2.8523 | 6.1367 | 6.0766 | 6.6014 | 4.181 | 2.3641 | 17.9545 | 15.4741 | 17.9545
4832 | 0.22743 | 0.068234 | 0.58996 | 0.5272 | 4.4294 | 5.5398 | 5.9222 | 5.3094 | 3.4454 | 1.7951 | 17.0737 | 15.5921 | 17.0737
4833 | 2.3932 | 1.2682 | 0.99165 | 0.89764 | 4.0699 | 7.9864 | 4.5273 | 6.3244 | 4.2134 | 1.5458 | 19.9265 | 14.3564 | 19.9265
4834 | -0.29689 | -0.49476 | 0.38328 | 0.31039 | 3.9325 | 4.8978 | 5.7866 | 4.892 | 4.4557 | 2.558 | 16.2803 | 16.7328 | 16.7328
4835 | 0.049753 | -0.19505 | 0.51984 | 0.42268 | 4.7488 | 5.3165 | 7.679 | 5.1055 | 3.7719 | 2.1228 | 17.2936 | 18.3226 | 18.3226
4836 | 1.2703 | 1.1779 | 0.89802 | 0.88059 | 3.2035 | 6.8534 | 5.8994 | 6.2485 | 4.6651 | 1.8432 | 18.1486 | 15.6111 | 18.1486
4837 | -0.31632 | -1.211 | 0.37588 | 0.11295 | 3.5049 | 4.8752 | 5.8467 | 4.4812 | 3.8005 | 2.0339 | 14.8952 | 15.186 | 15.186
4838 | 0.62215 | 0.42224 | 0.73308 | 0.66357 | 4.7657 | 6.0449 | 3.7642 | 5.6012 | 3.5687 | 2.2045 | 18.6163 | 14.303 | 18.6163
4839 | -0.02486 | -1.2573 | 0.49008 | 0.10432 | 3.7335 | 5.2242 | 4.4053 | 4.4599 | 5.3898 | 2.2278 | 15.6454 | 15.7564 | 15.7564
4840 | -0.23559 | 0.32757 | 0.40688 | 0.62838 | 4.0114 | 4.9698 | 4.379 | 5.5216 | 4.133 | 1.6848 | 16.1877 | 14.2083 | 16.1877
4841 | 0.11938 | 0.53573 | 0.54751 | 0.70393 | 4.2085 | 5.4035 | 6.0163 | 5.6977 | 4.6196 | 1.4235 | 16.7332 | 16.2678 | 16.7332
4842 | -1.175 | -0.41925 | 0.11999 | 0.33752 | 4.1184 | 4.0056 | 4.1463 | 4.9437 | 3.61 | 2.2604 | 15.328 | 14.135 | 15.328
4843 | -1.3556 | -0.18679 | 0.087605 | 0.42591 | 3.2478 | 3.8603 | 6.0084 | 5.1117 | 3.3286 | 1.686 | 13.9057 | 14.2707 | 14.2707
4844 | 0.77397 | 3.1621 | 0.78053 | 0.99922 | 2.9884 | 6.239 | 6.0316 | 7.5416 | 5.0242 | 1.9606 | 18.7296 | 16.0048 | 18.7296
4845 | 3.2411 | 2.8109 | 0.9994 | 0.99753 | 3.8756 | 8.5204 | 5.7263 | 7.3837 | 5.8367 | 1.8106 | 21.5903 | 17.2492 | 21.5903
4846 | 0.23677 | 0.7224 | 0.59358 | 0.76498 | 3.2513 | 5.5516 | 7.4307 | 5.858 | 4.7478 | 1.7661 | 16.427 | 17.1959 | 17.1959
4847 | 0.87594 | -0.10798 | 0.80947 | 0.45701 | 4.2638 | 6.3683 | 6.0744 | 5.1714 | 3.9012 | 1.5621 | 17.3657 | 15.8016 | 17.3657
4848 | 0.51207 | 0.21696 | 0.6957 | 0.58588 | 3.9825 | 5.9036 | 6.5898 | 5.4299 | 4.3559 | 2.086 | 17.4021 | 17.0142 | 17.4021
4849 | -0.3141 | -0.48147 | 0.37672 | 0.31509 | 4.9446 | 4.8778 | 4.7359 | 4.901 | 3.9764 | 1.9789 | 16.7022 | 15.6357 | 16.7022
4850 | -0.73366 | 0.20927 | 0.23158 | 0.58288 | 4.5447 | 4.4182 | 7.4304 | 5.4236 | 5.6396 | 1.8143 | 16.2008 | 19.4289 | 19.4289
4851 | -0.12401 | -0.21227 | 0.45065 | 0.41595 | 4.7464 | 5.1033 | 6.3808 | 5.0926 | 4.4737 | 1.3673 | 16.3096 | 16.9682 | 16.9682
4852 | 1.0526 | 0.82517 | 0.85374 | 0.79536 | 4.9131 | 6.5891 | 7.3719 | 5.9466 | 4.9995 | 1.9565 | 19.4053 | 19.2409 | 19.4053
4853 | 1.5963 | 1.0287 | 0.94479 | 0.84818 | 3.0949 | 7.2268 | 5.2198 | 6.1216 | 5.5151 | 2.1098 | 18.5531 | 15.9396 | 18.5531
4854 | -0.46042 | 0.79852 | 0.32261 | 0.78772 | 3.2412 | 4.7109 | 6.054 | 5.9236 | 3.2999 | 1.7086 | 15.5844 | 14.3038 | 15.5844
4855 | 0.55047 | -0.1843 | 0.709 | 0.42689 | 3.1977 | 5.9529 | 4.4012 | 5.1135 | 4.3529 | 2.0026 | 16.2668 | 13.9544 | 16.2668
4856 | -0.16579 | -0.16325 | 0.43416 | 0.43516 | 3.4337 | 5.0529 | 4.9494 | 5.1294 | 3.4979 | 1.4583 | 15.0743 | 13.3393 | 15.0743
4857 | 0.15582 | -1.7794 | 0.56191 | 0.037591 | 3.0995 | 5.4493 | 4.9714 | 4.2621 | 4.8233 | 1.7868 | 14.5977 | 14.681 | 14.681
4858 | -0.3165 | -0.76243 | 0.37581 | 0.2229 | 3.9254 | 4.875 | 4.2777 | 4.7211 | 3.683 | 2.0043 | 15.5258 | 13.8905 | 15.5258
4859 | -0.10865 | 0.34841 | 0.45674 | 0.63623 | 4.3689 | 5.1219 | 6.8122 | 5.5391 | 4.7995 | 1.5021 | 16.5319 | 17.4827 | 17.4827
4860 | -0.8961 | -0.37403 | 0.1851 | 0.35419 | 3.8599 | 4.2572 | 7.4337 | 4.9754 | 4.4324 | 2.1335 | 15.2259 | 17.8594 | 17.8594
4861 | 0.7542 | -0.25177 | 0.77464 | 0.40061 | 3.471 | 6.2138 | 5.6903 | 5.0634 | 3.1931 | 2.1227 | 16.8709 | 14.4771 | 16.8709
4862 | -0.55347 | -0.21918 | 0.28997 | 0.41325 | 3.906 | 4.6083 | 7.1404 | 5.0875 | 4.3571 | 1.8398 | 15.4417 | 17.2434 | 17.2434
4863 | 1.7414 | 0.74453 | 0.95919 | 0.77172 | 4.1458 | 7.3826 | 5.5271 | 5.8771 | 3.5721 | 1.7535 | 19.159 | 14.9986 | 19.159
4864 | 0.85253 | -0.3821 | 0.80304 | 0.35119 | 3.9502 | 6.3387 | 7.1185 | 4.9697 | 3.1879 | 2.5912 | 17.8498 | 16.8479 | 17.8498
4865 | -0.21556 | 1.2927 | 0.41466 | 0.90194 | 3.9609 | 4.9935 | 5.1701 | 6.3448 | 3.8476 | 2.1838 | 17.4831 | 15.1625 | 17.4831
4866 | 1.3855 | 1.7298 | 0.91705 | 0.95817 | 3.9349 | 6.9887 | 5.9189 | 6.6953 | 5.2843 | 2.0868 | 19.7058 | 17.2249 | 19.7058
4867 | -0.34101 | 0.15838 | 0.36655 | 0.56292 | 3.8288 | 4.8466 | 4.6684 | 5.382 | 5.5713 | 1.9694 | 16.0268 | 16.0378 | 16.0378
4868 | -0.28048 | -0.41807 | 0.38955 | 0.33795 | 3.7945 | 4.917 | 5.527 | 4.9445 | 4.6408 | 2.4596 | 16.1156 | 16.422 | 16.422
4869 | -1.5871 | -1.5483 | 0.056242 | 0.060775 | 4.7183 | 3.6947 | 6.7223 | 4.3401 | 5.2047 | 2.0775 | 14.8306 | 18.7228 | 18.7228
4870 | -0.12694 | -0.24443 | 0.4495 | 0.40345 | 4.5083 | 5.0997 | 6.9174 | 5.0688 | 4.3632 | 2.2916 | 16.9685 | 18.0806 | 18.0806
4871 | 0.62409 | 0.72436 | 0.73372 | 0.76558 | 3.4371 | 6.0474 | 5.732 | 5.8597 | 3.6708 | 2.0726 | 17.4167 | 14.9124 | 17.4167
4872 | 1.9568 | 1.4653 | 0.97481 | 0.92858 | 2.7032 | 7.6001 | 4.3311 | 6.4867 | 4.6014 | 2.378 | 19.1681 | 14.0138 | 19.1681
4873 | 0.99324 | -0.44875 | 0.8397 | 0.32681 | 3.0083 | 6.5154 | 5.0247 | 4.9233 | 5.2194 | 2.2778 | 16.7248 | 15.5301 | 16.7248
4874 | -0.46865 | -0.94166 | 0.31966 | 0.17318 | 4.7115 | 4.7018 | 7.2542 | 4.6181 | 4.3453 | 2.1237 | 16.155 | 18.4347 | 18.4347
4875 | 0.17338 | 0.63159 | 0.56882 | 0.73617 | 4.4387 | 5.4714 | 5.2714 | 5.7798 | 4.1857 | 2.3593 | 18.0493 | 16.2552 | 18.0493
4876 | 0.57058 | 1.9645 | 0.71586 | 0.97527 | 4.6959 | 5.9788 | 6.3547 | 6.8689 | 3.7684 | 2.3368 | 19.8804 | 17.1558 | 19.8804
4877 | -0.47063 | -2.2738 | 0.31895 | 0.01149 | 3.5257 | 4.6996 | 3.7743 | 4.1405 | 3.4214 | 2.6236 | 14.9894 | 13.3451 | 14.9894
4878 | -0.27434 | 0.43708 | 0.39191 | 0.66897 | 3.4637 | 4.9242 | 7.0481 | 5.6138 | 4.7105 | 2.2341 | 16.2358 | 17.4564 | 17.4564
4879 | -1.3733 | -0.7039 | 0.084828 | 0.24075 | 4.0896 | 3.8468 | 7.4468 | 4.7568 | 4.2268 | 1.4311 | 14.1243 | 17.1943 | 17.1943
4880 | 0.64067 | 0.050946 | 0.73913 | 0.52032 | 3.2138 | 6.0687 | 5.6632 | 5.2956 | 3.9613 | 2.2388 | 16.8168 | 15.0771 | 16.8168
4881 | -0.32076 | -0.90266 | 0.3742 | 0.18335 | 4.0464 | 4.87 | 5.9373 | 4.6397 | 5.8463 | 2.0182 | 15.5744 | 17.8483 | 17.8483
4882 | -0.44953 | 0.4617 | 0.32652 | 0.67785 | 3.9722 | 4.7231 | 4.5566 | 5.6347 | 4.1845 | 1.3866 | 15.7166 | 14.0999 | 15.7166
4883 | -0.63397 | 0.54177 | 0.26305 | 0.70601 | 4.1629 | 4.522 | 3.6359 | 5.7029 | 4.3596 | 2.1324 | 16.5201 | 14.2908 | 16.5201
4884 | 0.019595 | 0.85246 | 0.50782 | 0.80302 | 5.1131 | 5.2791 | 7.4239 | 5.9701 | 3.9492 | 2.0876 | 18.4499 | 18.5737 | 18.5737
4885 | 0.36236 | -0.74757 | 0.64146 | 0.22736 | 5.4221 | 5.7117 | 5.4468 | 4.7301 | 4.0654 | 1.1059 | 16.9697 | 16.0402 | 16.9697
4886 | -0.72315 | 1.1006 | 0.23479 | 0.86446 | 4.2734 | 4.4289 | 6.8072 | 6.183 | 5.2725 | 2.0264 | 16.9117 | 18.3795 | 18.3795
4887 | -0.51724 | 0.30657 | 0.30249 | 0.62041 | 4.4946 | 4.648 | 5.7229 | 5.5041 | 3.4228 | 1.7603 | 16.407 | 15.4006 | 16.407
4888 | 0.53624 | -0.95375 | 0.7041 | 0.17011 | 3.5609 | 5.9347 | 6.096 | 4.6115 | 5.3743 | 1.5641 | 15.6712 | 16.5953 | 16.5953
4889 | -1.8147 | -2.3334 | 0.034784 | 0.0098146 | 2.7266 | 3.5543 | 6.2141 | 4.1295 | 5.3118 | 1.5852 | 11.9955 | 15.8376 | 15.8376
4890 | 1.3504 | 0.4809 | 0.91155 | 0.68471 | 4.4258 | 6.9478 | 6.3617 | 5.651 | 4.2461 | 2.5559 | 19.5805 | 17.5895 | 19.5805
4891 | 0.2607 | -0.9479 | 0.60284 | 0.17159 | 2.7606 | 5.582 | 7.285 | 4.6147 | 4.8614 | 1.9526 | 14.9099 | 16.8596 | 16.8596
4892 | 0.53723 | -0.55441 | 0.70445 | 0.28965 | 3.7443 | 5.9359 | 7.5356 | 4.8522 | 3.0863 | 1.213 | 15.7455 | 15.5792 | 15.7455
4893 | -0.58418 | -1.3246 | 0.27955 | 0.092655 | 5.542 | 4.5751 | 6.151 | 4.43 | 3.2251 | 2.2094 | 16.7565 | 17.1276 | 17.1276
4894 | 0.39553 | 2.324 | 0.65378 | 0.98994 | 4.6015 | 5.7542 | 7.1139 | 7.1103 | 3.9864 | 1.8164 | 19.2824 | 17.5182 | 19.2824
4895 | 0.44906 | 2.0698 | 0.67331 | 0.98076 | 3.2275 | 5.8228 | 6.3986 | 6.9429 | 4.8063 | 2.4406 | 18.4337 | 16.8729 | 18.4337
4896 | 1.1743 | -0.26977 | 0.87987 | 0.39367 | 4.0125 | 6.7381 | 5.2578 | 5.0502 | 4.0726 | 1.8226 | 17.6235 | 15.1656 | 17.6235
4897 | 1.4375 | 0.5319 | 0.92471 | 0.7026 | 4.7502 | 7.0487 | 7.3079 | 5.6944 | 4.5484 | 2.2737 | 19.767 | 18.8802 | 19.767
4898 | 0.28943 | -1.3718 | 0.61387 | 0.08507 | 4.2862 | 5.6186 | 5.9862 | 4.4098 | 3.171 | 1.9143 | 16.2289 | 15.3577 | 16.2289
4899 | 0.038469 | 0.5058 | 0.51534 | 0.6935 | 4.8013 | 5.3025 | 2.889 | 5.6722 | 5.423 | 2.1967 | 17.9727 | 15.31 | 17.9727
4900 | -0.081687 | 0.2696 | 0.46745 | 0.60627 | 3.81 | 5.1547 | 3.7801 | 5.4734 | 3.8671 | 2.2341 | 16.6721 | 13.6913 | 16.6721
4901 | -1.473 | -0.72836 | 0.070381 | 0.2332 | 4.0521 | 3.7735 | 4.4531 | 4.7417 | 3.683 | 1.9186 | 14.4859 | 14.1068 | 14.4859
4902 | -1.1742 | -0.76596 | 0.12015 | 0.22185 | 4.5088 | 4.0062 | 7.6628 | 4.719 | 4.5728 | 1.73 | 14.964 | 18.4744 | 18.4744
4903 | 0.12067 | 0.7518 | 0.54803 | 0.77391 | 4.4467 | 5.4051 | 3.5176 | 5.8833 | 4.5361 | 2.3976 | 18.1328 | 14.898 | 18.1328
4904 | -0.26942 | -0.61321 | 0.3938 | 0.26987 | 3.0933 | 4.9299 | 7.0875 | 4.8139 | 3.8929 | 1.7763 | 14.6135 | 15.85 | 15.85
4905 | 0.32046 | 0.41389 | 0.62569 | 0.66052 | 4.5608 | 5.6582 | 4.408 | 5.5942 | 3.8587 | 1.907 | 17.7201 | 14.7344 | 17.7201
4906 | 1.6661 | 1.2166 | 0.95215 | 0.88813 | 4.0857 | 7.3026 | 4.3422 | 6.2812 | 4.1527 | 2.1801 | 19.8496 | 14.7608 | 19.8496
4907 | 0.12581 | 0.37261 | 0.55006 | 0.64528 | 4.7501 | 5.4116 | 4.5612 | 5.5594 | 4.336 | 2.0218 | 17.7428 | 15.6691 | 17.7428
4908 | 0.43332 | 0.12982 | 0.66761 | 0.55164 | 3.0458 | 5.8026 | 5.2874 | 5.3589 | 3.752 | 2.312 | 16.5192 | 14.3971 | 16.5192
4909 | -0.56395 | -1.3031 | 0.28639 | 0.096275 | 2.7649 | 4.597 | 7.5451 | 4.4394 | 4.6863 | 2.4987 | 14.2999 | 17.495 | 17.495
4910 | 0.52927 | 1.6606 | 0.70169 | 0.9516 | 2.6359 | 5.9257 | 4.5969 | 6.6419 | 4.1786 | 2.7792 | 17.9828 | 14.1907 | 17.9828
4911 | -1.5072 | -1.6448 | 0.065885 | 0.050005 | 3.6027 | 3.7493 | 7.079 | 4.3058 | 3.5145 | 2.3173 | 13.9751 | 16.5136 | 16.5136
4912 | 0.29077 | 0.26889 | 0.61439 | 0.60599 | 3.7402 | 5.6203 | 4.1293 | 5.4728 | 4.0655 | 2.0618 | 16.8951 | 13.9968 | 16.8951
4913 | 0.084741 | 0.88426 | 0.53377 | 0.81172 | 3.8446 | 5.3601 | 5.6969 | 5.9975 | 6.1417 | 2.2337 | 17.4359 | 17.9169 | 17.9169
4914 | -0.80834 | -1.6059 | 0.20945 | 0.054151 | 2.4341 | 4.3429 | 3.5929 | 4.3193 | 5.0527 | 2.0125 | 13.1087 | 13.0922 | 13.1087
4915 | -0.32105 | -0.062951 | 0.37409 | 0.4749 | 4.9668 | 4.8697 | 4.8599 | 5.2061 | 5.3487 | 2.2004 | 17.2429 | 17.3757 | 17.3757
4916 | -1.8786 | -1.63 | 0.030153 | 0.05155 | 4.2714 | 3.5187 | 5.0475 | 4.3109 | 4.1059 | 2.6189 | 14.7199 | 16.0437 | 16.0437
4917 | -0.51036 | -0.34252 | 0.3049 | 0.36598 | 4.5471 | 4.6555 | 3.2365 | 4.9977 | 5.8621 | 2.0114 | 16.2117 | 15.6571 | 16.2117
4918 | 0.78159 | 0.67335 | 0.78277 | 0.74964 | 4.2405 | 6.2487 | 2.8328 | 5.8157 | 4.4106 | 2.3638 | 18.6687 | 13.8477 | 18.6687
4919 | -0.19409 | 0.11504 | 0.42305 | 0.54579 | 4.4862 | 5.0191 | 6.2199 | 5.3469 | 3.5087 | 1.9359 | 16.7881 | 16.1506 | 16.7881
4920 | -0.035103 | -0.61821 | 0.486 | 0.26822 | 4.8368 | 5.2116 | 6.7548 | 4.8107 | 4.1517 | 1.7073 | 16.5665 | 17.4506 | 17.4506
4921 | 0.48603 | 0.36903 | 0.68653 | 0.64395 | 2.7434 | 5.8702 | 6.3189 | 5.5564 | 4.4448 | 2.3014 | 16.4713 | 15.8084 | 16.4713
4922 | -0.80099 | -0.94223 | 0.21157 | 0.17304 | 4.5185 | 4.3502 | 5.5286 | 4.6178 | 3.661 | 1.6686 | 15.1551 | 15.3768 | 15.3768
4923 | -0.3192 | 0.19484 | 0.37479 | 0.57724 | 3.8637 | 4.8718 | 5.9487 | 5.4118 | 3.6771 | 1.5613 | 15.7087 | 15.0508 | 15.7087
4924 | 1.3368 | 1.0652 | 0.90935 | 0.85661 | 3.9243 | 6.9319 | 6.9588 | 6.1528 | 4.8381 | 1.3324 | 18.3414 | 17.0537 | 18.3414
4925 | -0.39154 | -0.38189 | 0.3477 | 0.35127 | 2.941 | 4.7887 | 6.0009 | 4.9698 | 3.2145 | 1.5834 | 14.2828 | 13.7397 | 14.2828
4926 | -1.1768 | 0.3641 | 0.11963 | 0.64211 | 2.9651 | 4.004 | 3.8488 | 5.5522 | 4.0847 | 1.6441 | 14.1655 | 12.5427 | 14.1655
4927 | 0.31759 | 0.19284 | 0.6246 | 0.57646 | 5.1706 | 5.6545 | 5.5395 | 5.4102 | 4.6299 | 1.5245 | 17.7598 | 16.8645 | 17.7598
4928 | -2.8813 | -1.305 | 0.0019801 | 0.09595 | 3.1948 | 3.1535 | 3.5666 | 4.4385 | 3.1998 | 2.722 | 13.5088 | 12.6832 | 13.5088
4929 | -0.38445 | 1.5191 | 0.35032 | 0.93563 | 2.6658 | 4.7968 | 5.0442 | 6.5301 | 3.8355 | 2.106 | 16.0987 | 13.6516 | 16.0987
4930 | -1.2731 | 0.1185 | 0.10149 | 0.54716 | 3.6855 | 3.9249 | 5.7304 | 5.3497 | 3.8535 | 1.774 | 14.7341 | 15.0434 | 15.0434
4931 | -0.62264 | 1.0672 | 0.26676 | 0.85705 | 4.5002 | 4.534 | 5.6665 | 6.1545 | 5.0309 | 2.1504 | 17.339 | 17.348 | 17.348
4932 | -0.34433 | -0.31219 | 0.3653 | 0.37745 | 5.333 | 4.8428 | 4.2191 | 5.0195 | 3.218 | 2.3328 | 17.5281 | 15.1029 | 17.5281
4933 | 1.3937 | 0.3856 | 0.9183 | 0.65011 | 5.1203 | 6.9982 | 6.8977 | 5.5703 | 3.4268 | 1.2706 | 18.9595 | 16.7154 | 18.9595
4934 | -0.31337 | 0.19036 | 0.377 | 0.57549 | 4.1537 | 4.8786 | 6.504 | 5.4081 | 5.6348 | 1.9615 | 16.4019 | 18.254 | 18.254
4935 | 0.46709 | 1.0516 | 0.67978 | 0.8535 | 5.3604 | 5.8459 | 4.8859 | 6.1411 | 5.1531 | 1.8265 | 19.1739 | 17.2259 | 19.1739
4936 | 1.7439 | 1.2475 | 0.95941 | 0.8939 | 5.4724 | 7.3852 | 4.4165 | 6.3071 | 4.7761 | 2.6219 | 21.7866 | 17.2869 | 21.7866
4937 | 0.34898 | -0.12944 | 0.63645 | 0.4485 | 4.9822 | 5.6946 | 6.5512 | 5.155 | 4.8878 | 1.6344 | 17.4661 | 18.0556 | 18.0556
4938 | -0.14896 | 0.47448 | 0.44079 | 0.68242 | 4.3556 | 5.0732 | 6.1663 | 5.6455 | 4.4411 | 1.8658 | 16.9401 | 16.8288 | 16.9401
4939 | -0.44505 | -1.3702 | 0.32814 | 0.085306 | 4.1567 | 4.7282 | 4.221 | 4.4105 | 5.2123 | 1.5966 | 14.892 | 15.1866 | 15.1866
4940 | 0.8285 | 0.13504 | 0.79631 | 0.55371 | 3.0344 | 6.3083 | 5.6047 | 5.3631 | 4.6421 | 1.8432 | 16.549 | 15.1245 | 16.549
4941 | -2.1077 | -0.40576 | 0.017528 | 0.34246 | 5.0608 | 3.4046 | 5.6186 | 4.9531 | 4.6903 | 2.0811 | 15.4996 | 17.4508 | 17.4508
4942 | -0.17511 | -0.98253 | 0.4305 | 0.16292 | 3.7192 | 5.0418 | 6.3752 | 4.5959 | 3.1844 | 2.0673 | 15.4242 | 15.3461 | 15.4242
4943 | 1.7512 | 1.6374 | 0.96005 | 0.94923 | 4.0976 | 7.3928 | 6.2835 | 6.6238 | 4.956 | 1.9806 | 20.0948 | 17.3176 | 20.0948
4944 | 1.5272 | 0.73506 | 0.93665 | 0.76885 | 4.3838 | 7.1503 | 2.9208 | 5.8689 | 4.4387 | 1.8893 | 19.2923 | 13.6326 | 19.2923
4945 | -0.92179 | -0.31731 | 0.17832 | 0.37551 | 3.4367 | 4.2326 | 7.2623 | 5.0158 | 3.4274 | 2.2684 | 14.9534 | 16.3947 | 16.3947
4946 | 0.5359 | -0.27394 | 0.70399 | 0.39207 | 4.4347 | 5.9342 | 6.1511 | 5.0472 | 4.8257 | 2.0978 | 17.5139 | 17.5093 | 17.5139
4947 | 0.68125 | 0.82052 | 0.75214 | 0.79404 | 3.0432 | 6.1206 | 6.2877 | 5.9426 | 4.6939 | 1.3137 | 16.4202 | 15.3386 | 16.4202
4948 | -0.22173 | -0.54013 | 0.41226 | 0.29455 | 3.6716 | 4.9862 | 5.5952 | 4.8616 | 4.7605 | 2.3709 | 15.8904 | 16.3982 | 16.3982
4949 | -1.9895 | -0.84261 | 0.023323 | 0.19972 | 3.3827 | 3.4609 | 6.5127 | 4.6739 | 4.2619 | 2.4933 | 14.0108 | 16.6506 | 16.6506
4950 | 1.1836 | 0.58983 | 0.88172 | 0.72235 | 4.4952 | 6.7494 | 4.5615 | 5.744 | 5.6972 | 2.1033 | 19.0919 | 16.8572 | 19.0919
4951 | -1.5457 | -0.75686 | 0.06109 | 0.22457 | 5.2025 | 3.7226 | 6.6347 | 4.7245 | 3.8397 | 1.4964 | 15.1459 | 17.1732 | 17.1732
4952 | 0.1313 | -0.17985 | 0.55223 | 0.42864 | 3.1873 | 5.4185 | 4.8479 | 5.1169 | 5.6418 | 1.8806 | 15.6032 | 15.5577 | 15.6032
4953 | -0.76804 | 1.0995 | 0.22123 | 0.86422 | 4.2585 | 4.3832 | 4.25 | 6.182 | 4.5991 | 1.7829 | 16.6066 | 14.8905 | 16.6066
4954 | 0.36774 | 0.41561 | 0.64347 | 0.66115 | 3.7196 | 5.7186 | 7.3638 | 5.5956 | 3.5893 | 1.6569 | 16.6908 | 16.3297 | 16.6908
4955 | 0.61188 | 0.29944 | 0.72969 | 0.6177 | 4.9935 | 6.0317 | 5.9331 | 5.4982 | 3.661 | 1.9851 | 18.5085 | 16.5727 | 18.5085
4956 | -0.60321 | -1.4555 | 0.27318 | 0.072765 | 4.4417 | 4.5547 | 5.211 | 4.3756 | 4.3323 | 1.7781 | 15.1501 | 15.763 | 15.763
4957 | -1.1114 | -2.5536 | 0.1332 | 0.0053305 | 3.7418 | 4.0601 | 6.0935 | 4.0946 | 5.0664 | 2.0586 | 13.9551 | 16.9603 | 16.9603
4958 | 0.31176 | 0.57941 | 0.62239 | 0.71884 | 2.9254 | 5.6471 | 5.9673 | 5.7351 | 4.0469 | 1.5976 | 15.9052 | 14.5372 | 15.9052
4959 | 1.054 | 1.0743 | 0.85407 | 0.85865 | 4.5149 | 6.5909 | 5.7137 | 6.1605 | 4.1825 | 2.2132 | 19.4795 | 16.6242 | 19.4795
4960 | 0.062871 | 0.64098 | 0.52507 | 0.73923 | 3.299 | 5.3329 | 4.4378 | 5.7879 | 3.9029 | 2.3878 | 16.8075 | 14.0275 | 16.8075
4961 | 0.30402 | -0.28994 | 0.61944 | 0.38593 | 3.2262 | 5.6372 | 6.4162 | 5.0356 | 4.6951 | 1.9664 | 15.8654 | 16.3038 | 16.3038
4962 | -0.095578 | -0.38079 | 0.46193 | 0.35168 | 3.2442 | 5.1377 | 6.2702 | 4.9706 | 3.8924 | 1.5773 | 14.9297 | 14.984 | 14.984
4963 | 0.86822 | 0.61332 | 0.80736 | 0.73017 | 2.9884 | 6.3586 | 7.7991 | 5.7642 | 4.1594 | 1.5886 | 16.6997 | 16.5355 | 16.6997
4964 | -0.216 | -0.24386 | 0.41449 | 0.40367 | 4.3772 | 4.993 | 6.2867 | 5.0693 | 4.2133 | 2.1652 | 16.6047 | 17.0424 | 17.0424
4965 | 0.055278 | -0.092199 | 0.52204 | 0.46327 | 3.5798 | 5.3234 | 6.4462 | 5.1835 | 4.0377 | 1.9747 | 16.0614 | 16.0384 | 16.0614
4966 | -0.73389 | -0.75334 | 0.23151 | 0.22562 | 3.4835 | 4.4179 | 7.0265 | 4.7266 | 4.8389 | 2.5473 | 15.1753 | 17.8962 | 17.8962
4967 | -1.2497 | 0.20674 | 0.1057 | 0.58189 | 4.8065 | 3.9437 | 6.9438 | 5.4215 | 3.7369 | 1.5199 | 15.6917 | 17.0072 | 17.0072
4968 | 1.1412 | -0.081037 | 0.87311 | 0.46771 | 3.3681 | 6.6979 | 6.7373 | 5.1921 | 3.902 | 1.3189 | 16.577 | 15.3263 | 16.577
4969 | -0.22077 | 0.58144 | 0.41264 | 0.71953 | 4.3273 | 4.9873 | 3.9189 | 5.7368 | 5.1904 | 1.8982 | 16.9497 | 15.3348 | 16.9497
4970 | 0.58982 | 2.0052 | 0.72234 | 0.97753 | 4.5444 | 6.0034 | 7.3117 | 6.8978 | 5.9739 | 2.2125 | 19.6583 | 20.0425 | 20.0425
4971 | 1.2982 | 1.3749 | 0.90289 | 0.91543 | 4.7509 | 6.8865 | 7.6043 | 6.413 | 3.5166 | 2.185 | 20.2353 | 18.0567 | 20.2353
4972 | 1.0127 | 0.40002 | 0.8444 | 0.65543 | 4.7276 | 6.5397 | 5.6334 | 5.5825 | 3.9572 | 1.9366 | 18.7864 | 16.2548 | 18.7864
4973 | 1.2546 | -0.21307 | 0.89518 | 0.41564 | 4.0497 | 6.8346 | 5.6943 | 5.092 | 4.6151 | 1.7337 | 17.7101 | 16.0929 | 17.7101
4974 | 1.8215 | 0.59762 | 0.96574 | 0.72495 | 3.2203 | 7.4655 | 7.1955 | 5.7507 | 3.8473 | 2.5393 | 18.9757 | 16.8023 | 18.9757
4975 | -0.48769 | -0.44189 | 0.31288 | 0.32929 | 5.6396 | 4.6806 | 3.7549 | 4.928 | 5.0087 | 1.8683 | 17.1166 | 16.2716 | 17.1166
4976 | -2.4799 | -1.4021 | 0.0065709 | 0.080444 | 3.4744 | 3.2605 | 7.0448 | 4.3972 | 4.3274 | 2.2148 | 13.3469 | 17.0614 | 17.0614
4977 | -0.12098 | 0.56805 | 0.45186 | 0.715 | 4.727 | 5.1069 | 5.7574 | 5.7253 | 5.5904 | 2.7073 | 18.2666 | 18.7821 | 18.7821
4978 | -1.042 | -0.51471 | 0.14871 | 0.30338 | 4.9419 | 4.1215 | 4.2238 | 4.8786 | 4.3525 | 2.0363 | 15.9782 | 15.5544 | 15.9782
4979 | 0.24795 | 0.81093 | 0.59791 | 0.7913 | 3.9891 | 5.5658 | 5.8265 | 5.9343 | 3.3969 | 1.5756 | 17.0648 | 14.7881 | 17.0648
4980 | 2.8935 | 1.7508 | 0.9981 | 0.96001 | 2.9897 | 8.3351 | 5.4379 | 6.7112 | 5.1117 | 1.545 | 19.5811 | 15.0843 | 19.5811
4981 | 1.0922 | 0.05434 | 0.86264 | 0.52167 | 4.8966 | 6.638 | 4.8689 | 5.2983 | 3.9816 | 1.8389 | 18.6717 | 15.5861 | 18.6717
4982 | -1.707 | 0.91716 | 0.043907 | 0.82047 | 3.3908 | 3.618 | 4.7486 | 6.0258 | 4.2707 | 1.9554 | 14.99 | 14.3655 | 14.99
4983 | 1.1406 | 0.37472 | 0.87297 | 0.64606 | 4.1127 | 6.6971 | 6.3053 | 5.5612 | 4.2307 | 1.5418 | 17.9128 | 16.1905 | 17.9128
4984 | 1.0164 | 1.4903 | 0.84528 | 0.93192 | 3.8495 | 6.5443 | 5.8981 | 6.5069 | 3.5596 | 1.9193 | 18.82 | 15.2264 | 18.82
4985 | -1.4817 | -0.73778 | 0.069216 | 0.23032 | 4.0376 | 3.7673 | 4.5472 | 4.736 | 4.2091 | 2.3461 | 14.887 | 15.14 | 15.14
4986 | 0.49889 | 0.50624 | 0.69107 | 0.69366 | 4.9406 | 5.8867 | 4.2328 | 5.6725 | 4.0207 | 2.2093 | 18.7091 | 15.4034 | 18.7091
4987 | 0.47054 | -0.5787 | 0.68102 | 0.2814 | 3.5691 | 5.8503 | 4.8989 | 4.8363 | 4.8137 | 1.782 | 16.0377 | 15.0637 | 16.0377
4988 | 0.95318 | 1.0401 | 0.82975 | 0.85085 | 4.1932 | 6.4654 | 6.262 | 6.1313 | 3.3263 | 2.1236 | 18.9136 | 15.9051 | 18.9136
4989 | -1.3906 | -1.4824 | 0.08218 | 0.069123 | 2.8424 | 3.8338 | 3.3247 | 4.3651 | 3.6135 | 2.5784 | 13.6198 | 12.3591 | 13.6198
4990 | -0.065453 | -0.94758 | 0.47391 | 0.17167 | 4.7807 | 5.1745 | 6.5855 | 4.6149 | 5.4564 | 2.3164 | 16.8864 | 19.1389 | 19.1389
4991 | -1.1636 | -1.9123 | 0.12229 | 0.027921 | 3.8675 | 4.0152 | 7.4356 | 4.2237 | 3.5132 | 1.9396 | 14.046 | 16.7559 | 16.7559
4992 | 0.37963 | -0.21976 | 0.64789 | 0.41303 | 4.0583 | 5.7338 | 6.9236 | 5.0871 | 3.1616 | 2.2934 | 17.1726 | 16.4369 | 17.1726
4993 | -1.3628 | -0.47218 | 0.08647 | 0.3184 | 3.4024 | 3.8548 | 5.3234 | 4.9073 | 3.3837 | 2.243 | 14.4075 | 14.3525 | 14.4075
4994 | -1.9812 | -2.7393 | 0.023786 | 0.003078 | 4.0811 | 3.4651 | 6.1951 | 4.0714 | 4.5063 | 2.0495 | 13.6672 | 16.832 | 16.832
4995 | 0.65857 | 0.97561 | 0.74491 | 0.83537 | 4.6195 | 6.0916 | 7.3662 | 6.0761 | 5.4152 | 2.3558 | 19.1429 | 19.7567 | 19.7567
4996 | 1.6084 | 1.4964 | 0.94613 | 0.93272 | 4.6461 | 7.2401 | 6.4014 | 6.5118 | 4.6206 | 1.5785 | 19.9765 | 17.2466 | 19.9765
4997 | -2.4738 | -0.45877 | 0.0066848 | 0.3232 | 3.3835 | 3.2625 | 4.895 | 4.9165 | 3.7588 | 2.2803 | 13.8428 | 14.3176 | 14.3176
4998 | -1.7048 | -0.69473 | 0.044111 | 0.24361 | 3.749 | 3.6193 | 6.3313 | 4.7624 | 4.3647 | 1.1706 | 13.3014 | 15.6156 | 15.6156
4999 | -1.216 | -1.0464 | 0.11199 | 0.14768 | 4.7917 | 3.9713 | 5.7116 | 4.5623 | 5.1651 | 1.9307 | 15.256 | 17.599 | 17.599
5000 | -0.054456 | 0.13412 | 0.47829 | 0.55335 | 3.0475 | 5.1879 | 6.0209 | 5.3624 | 3.4672 | 1.6012 | 15.1989 | 14.1368 | 15.1989

## Fin_Inputs
Finance inputs
Must equal data/finance_inputs.json in the tool. Yellow = paste your verified values.
Key | Description | Value | Unit
land_cost_lakh | Land cost, paid at month 0 by equity | 2500 | Rs lakh
approvals_cost_lakh | Approvals, paid at month 0 | 150 | Rs lakh
saleable_area_sqft | Saleable area | 95000 | sq ft
sale_price_per_sqft_inr | Sale price | 9000 | Rs/sq ft
presale_share | Share sold before completion, paid with construction progress | 0.3 | fraction
months_to_sell_after_completion | Months to sell the rest after completion | 12 | months
brokerage_pct | Brokerage, share of collections | 0.02 | fraction
debt_share | Loan share of each month's funding gap | 0.6 | fraction
interest_rate_annual | Loan interest rate | 0.105 | per year
discount_rate_annual | Discount rate for project NPV | 0.12 | per year
equity_discount_rate_annual | Cost of equity, for equity NPV | 0.16 | per year
overhead_per_month_lakh | Site overheads | 12 | Rs lakh/month
rera_delay_interest_annual | Compensation to buyers for late possession (0 = off) | 0 | per year
rera_grace_months | Grace months before compensation starts | 0 | months
Scenario settings (for T20 and T21)
cost_multiplier | 1 = plan; 1.10 = flat 10% test (T20) | 1 | x
delay_activity | Activity to delay for the delay test | A28 | id
delay_days | 0 = plan; 60 = delay test (T21) | 0 | days
Derived
im | Monthly loan rate | 0.0083552
rm | Monthly discount rate (project) | 0.0094888
rme | Monthly discount rate (equity) | 0.012445
revenue | Total revenue (Rs lakh) = area x price / 100000 | 8550

## Fin_Activities
Activities and plan schedule (most-likely durations)
Paste id, name, predecessors, dur_m, cost_m_lakh, daily_cost_lakh from your verified CSV into the yellow columns. Keep activities in order (predecessors above) with no blank rows between them.
id | name | predecessors | dur_m | cost_m_lakh | daily_cost_lakh | Duration used | Cost used (Rs lakh) | ES | EF | Duration (no delay) | ES (no delay) | EF (no delay) | Preds listed | Preds found above | Check
A01 | Mobilisation and site setup |  | 20 | 40 | 0.05 | 20 | 41 | 0 | 20 | 20 | 0 | 20 | 0 | 0 | OK
A02 | Site clearance and survey | A01 | 10 | 10 | 0.02 | 10 | 10.2 | 20 | 30 | 10 | 20 | 30 | 1 | 1 | OK
A03 | Piling (bored cast-in-situ) | A02 | 45 | 220 | 0.8 | 45 | 256 | 30 | 75 | 45 | 30 | 75 | 1 | 1 | OK
A04 | Excavation for pile caps and raft | A03 | 15 | 45 | 0.3 | 15 | 49.5 | 75 | 90 | 15 | 75 | 90 | 1 | 1 | OK
A05 | Pile caps, raft and foundation | A04 | 30 | 180 | 0.1 | 30 | 183 | 90 | 120 | 30 | 90 | 120 | 1 | 1 | OK
A06 | Plinth beams and ground floor slab | A05 | 20 | 70 | 0.1 | 20 | 72 | 120 | 140 | 20 | 120 | 140 | 1 | 1 | OK
A07 | RCC frame floors 1-5 | A06 | 90 | 380 | 0.6 | 90 | 434 | 140 | 230 | 90 | 140 | 230 | 1 | 1 | OK
A08 | RCC frame floors 6-10 and terrace | A07 | 85 | 380 | 0.6 | 85 | 431 | 230 | 315 | 85 | 230 | 315 | 1 | 1 | OK
A09 | Masonry floors 1-5 | A07 | 60 | 110 | 0.05 | 60 | 113 | 230 | 290 | 60 | 230 | 290 | 1 | 1 | OK
A10 | Masonry floors 6-10 | A08;A09 | 55 | 110 | 0.05 | 55 | 112.75 | 315 | 370 | 55 | 315 | 370 | 2 | 2 | OK
A11 | Electrical conduit and plumbing rough-in floors 1-5 | A09 | 45 | 60 | 0.03 | 45 | 61.35 | 290 | 335 | 45 | 290 | 335 | 1 | 1 | OK
A12 | Electrical conduit and plumbing rough-in floors 6-10 | A10;A11 | 45 | 60 | 0.03 | 45 | 61.35 | 370 | 415 | 45 | 370 | 415 | 2 | 2 | OK
A13 | Internal plastering floors 1-5 | A11 | 45 | 75 | 0.03 | 45 | 76.35 | 335 | 380 | 45 | 335 | 380 | 1 | 1 | OK
A14 | Internal plastering floors 6-10 | A12;A13 | 45 | 75 | 0.03 | 45 | 76.35 | 415 | 460 | 45 | 415 | 460 | 2 | 2 | OK
A15 | External plaster and facade | A10 | 75 | 140 | 0.15 | 75 | 151.25 | 370 | 445 | 75 | 370 | 445 | 1 | 1 | OK
A16 | Waterproofing (terrace and toilets) | A08;A12 | 25 | 45 | 0.02 | 25 | 45.5 | 415 | 440 | 25 | 415 | 440 | 2 | 2 | OK
A17 | Flooring and wall tiling | A14;A16 | 75 | 260 | 0.05 | 75 | 263.75 | 460 | 535 | 75 | 460 | 535 | 2 | 2 | OK
A18 | Doors, windows and grills | A14 | 50 | 150 | 0.03 | 50 | 151.5 | 460 | 510 | 50 | 460 | 510 | 1 | 1 | OK
A19 | Lift supply and installation | A08 | 75 | 120 | 0.03 | 75 | 122.25 | 315 | 390 | 75 | 315 | 390 | 1 | 1 | OK
A20 | Electrical wiring and fixtures | A17 | 50 | 140 | 0.03 | 50 | 141.5 | 535 | 585 | 50 | 535 | 585 | 1 | 1 | OK
A21 | Plumbing and sanitary fixtures | A17 | 45 | 120 | 0.03 | 45 | 121.35 | 535 | 580 | 45 | 535 | 580 | 1 | 1 | OK
A22 | Fire fighting system | A12 | 55 | 90 | 0.03 | 55 | 91.65 | 415 | 470 | 55 | 415 | 470 | 1 | 1 | OK
A23 | Internal painting | A18;A20;A21 | 50 | 70 | 0.03 | 50 | 71.5 | 585 | 635 | 50 | 585 | 635 | 3 | 3 | OK
A24 | External painting | A15 | 35 | 40 | 0.05 | 35 | 41.75 | 445 | 480 | 35 | 445 | 480 | 1 | 1 | OK
A25 | External development (roads, drains, landscaping) | A15 | 60 | 110 | 0.1 | 60 | 116 | 445 | 505 | 60 | 445 | 505 | 1 | 1 | OK
A26 | Utilities: substation, STP, water tanks | A08 | 75 | 160 | 0.05 | 75 | 163.75 | 315 | 390 | 75 | 315 | 390 | 1 | 1 | OK
A27 | Testing and commissioning | A19;A22;A23;A26 | 20 | 15 | 0.05 | 20 | 16 | 635 | 655 | 20 | 635 | 655 | 4 | 4 | OK
A28 | Occupancy certificate and handover | A24;A25;A27 | 45 | 20 | 0.05 | 45 | 22.25 | 655 | 700 | 45 | 655 | 700 | 3 | 3 | OK
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
| Project duration (days) | 700
| Plan duration without delay (days) | 700
| Completion month | 24
| Promised month (plan + grace) | 24
| Total activity cost (Rs lakh) | 3497.85
| Rows with problems | 0

## Fin_Spread
Construction spend by month
Each activity's cost spread evenly over its days: overlap of the activity with the month / duration x cost.
id | ES | Duration | EF | Cost | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
A01 | 0 | 20 | 20 | 41 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A02 | 20 | 10 | 30 | 10.2 | 10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A03 | 30 | 45 | 75 | 256 | 0 | 170.6667 | 85.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A04 | 75 | 15 | 90 | 49.5 | 0 | 0 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A05 | 90 | 30 | 120 | 183 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A06 | 120 | 20 | 140 | 72 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A07 | 140 | 90 | 230 | 434 | 0 | 0 | 0 | 0 | 48.2222 | 144.6667 | 144.6667 | 96.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A08 | 230 | 85 | 315 | 431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.7059 | 152.1176 | 152.1176 | 76.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A09 | 230 | 60 | 290 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.8333 | 56.5 | 37.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A10 | 315 | 55 | 370 | 112.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.75 | 61.5 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A11 | 290 | 45 | 335 | 61.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6333 | 40.9 | 6.8167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A12 | 370 | 45 | 415 | 61.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2667 | 34.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A13 | 335 | 45 | 380 | 76.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.4167 | 33.9333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A14 | 415 | 45 | 460 | 76.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4833 | 50.9 | 16.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A15 | 370 | 75 | 445 | 151.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.3333 | 60.5 | 50.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A16 | 415 | 25 | 440 | 45.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 36.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A17 | 460 | 75 | 535 | 263.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.3333 | 105.5 | 87.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A18 | 460 | 50 | 510 | 151.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.6 | 90.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A19 | 315 | 75 | 390 | 122.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.45 | 48.9 | 48.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A20 | 535 | 50 | 585 | 141.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.15 | 84.9 | 42.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A21 | 535 | 45 | 580 | 121.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4833 | 80.9 | 26.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A22 | 415 | 55 | 470 | 91.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3318 | 49.9909 | 33.3273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A23 | 585 | 50 | 635 | 71.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.45 | 42.9 | 7.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A24 | 445 | 35 | 480 | 41.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9643 | 35.7857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A25 | 445 | 60 | 505 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6667 | 58 | 48.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A26 | 315 | 75 | 390 | 163.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.75 | 65.5 | 65.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A27 | 635 | 20 | 655 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A28 | 655 | 45 | 700 | 22.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4722 | 14.8333 | 4.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 51.2 | 170.6667 | 134.8333 | 183 | 120.2222 | 144.6667 | 144.6667 | 165.9837 | 208.6176 | 203.4176 | 204.9088 | 225.1333 | 236.4333 | 120.4985 | 203.3385 | 275.013 | 244.7333 | 115.55 | 165.8 | 90.8667 | 42.9 | 25.6222 | 14.8333 | 4.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Fin_CashFlow
T15-T21: Monthly cash flow, debt, NPV and IRR
Month 0 = start (land). Month k = days (k-1)*30 to k*30. Rules match docs/NEW_FEATURES_GUIDE.md section 2.
Month | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Upfront (land + approvals) | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction spend | 0 | 51.2 | 170.6667 | 134.8333 | 183 | 120.2222 | 144.6667 | 144.6667 | 165.9837 | 208.6176 | 203.4176 | 204.9088 | 225.1333 | 236.4333 | 120.4985 | 203.3385 | 275.013 | 244.7333 | 115.55 | 165.8 | 90.8667 | 42.9 | 25.6222 | 14.8333 | 4.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overheads | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Progress share | 0 | 0.014638 | 0.048792 | 0.038547 | 0.052318 | 0.03437 | 0.041359 | 0.041359 | 0.047453 | 0.059642 | 0.058155 | 0.058581 | 0.064363 | 0.067594 | 0.034449 | 0.058132 | 0.078623 | 0.069967 | 0.033035 | 0.047401 | 0.025978 | 0.012265 | 0.0073251 | 0.0042407 | 0.0014136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presale collections | 0 | 37.5453 | 125.1512 | 98.8743 | 134.1953 | 88.1599 | 106.0852 | 106.0852 | 121.7171 | 152.9809 | 149.1677 | 150.2612 | 165.092 | 173.3784 | 88.3625 | 149.1097 | 201.6691 | 179.4648 | 84.7337 | 121.5824 | 66.6332 | 31.4589 | 18.789 | 10.8774 | 3.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Later collections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total collections | 0 | 37.5453 | 125.1512 | 98.8743 | 134.1953 | 88.1599 | 106.0852 | 106.0852 | 121.7171 | 152.9809 | 149.1677 | 150.2612 | 165.092 | 173.3784 | 88.3625 | 149.1097 | 201.6691 | 179.4648 | 84.7337 | 121.5824 | 66.6332 | 31.4589 | 18.789 | 10.8774 | 3.6258 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 498.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brokerage | 0 | 0.75091 | 2.503 | 1.9775 | 2.6839 | 1.7632 | 2.1217 | 2.1217 | 2.4343 | 3.0596 | 2.9834 | 3.0052 | 3.3018 | 3.4676 | 1.7672 | 2.9822 | 4.0334 | 3.5893 | 1.6947 | 2.4316 | 1.3327 | 0.62918 | 0.37578 | 0.21755 | 0.072516 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 9.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Buyers' payments before this month | 0 | 0 | 37.5453 | 162.6965 | 261.5708 | 395.7661 | 483.926 | 590.0111 | 696.0963 | 817.8134 | 970.7943 | 1119.962 | 1270.2232 | 1435.3152 | 1608.6936 | 1697.056 | 1846.1657 | 2047.8348 | 2227.2996 | 2312.0333 | 2433.6157 | 2500.2489 | 2531.7078 | 2550.4968 | 2561.3742 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565
Compensation to buyers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project cash flow | -2650 | -26.4056 | -60.0185 | -49.9365 | -63.4886 | -45.8255 | -52.7032 | -52.7032 | -58.7009 | -70.6964 | -69.2333 | -69.6528 | -75.3432 | -78.5225 | -45.9033 | -69.211 | -89.3773 | -80.8578 | -44.511 | -58.6492 | -37.5661 | -24.0703 | -19.209 | -16.1735 | -5.3912 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debt opening | 0 | 0 | 15.8433 | 51.9868 | 82.3831 | 121.1646 | 149.6723 | 182.5447 | 215.6918 | 252.7145 | 297.2438 | 341.2673 | 385.9103 | 434.3406 | 485.0831 | 516.678 | 562.5216 | 620.8479 | 674.5498 | 706.8924 | 747.9881 | 776.7774 | 797.7096 | 815.9 | 832.4211 | 842.6108 | 360.876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest | 0 | 0 | 0.13237 | 0.43436 | 0.68832 | 1.0123 | 1.2505 | 1.5252 | 1.8021 | 2.1115 | 2.4835 | 2.8513 | 3.2243 | 3.629 | 4.0529 | 4.3169 | 4.7 | 5.1873 | 5.636 | 5.9062 | 6.2496 | 6.4901 | 6.665 | 6.817 | 6.955 | 7.0401 | 3.0152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding need | 2650 | 26.4056 | 60.0185 | 49.9365 | 63.4886 | 45.8255 | 52.7032 | 52.7032 | 58.7009 | 70.6964 | 69.2333 | 69.6528 | 75.3432 | 78.5225 | 45.9033 | 69.211 | 89.3773 | 80.8578 | 44.511 | 58.6492 | 37.5661 | 24.0703 | 19.209 | 16.1735 | 5.3912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debt draw | 0 | 15.8433 | 36.0111 | 29.9619 | 38.0932 | 27.4953 | 31.6219 | 31.6219 | 35.2206 | 42.4178 | 41.54 | 41.7917 | 45.2059 | 47.1135 | 27.542 | 41.5266 | 53.6264 | 48.5147 | 26.7066 | 35.1895 | 22.5397 | 14.4422 | 11.5254 | 9.7041 | 3.2347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surplus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488.775 | 363.8911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debt closing | 0 | 15.8433 | 51.9868 | 82.3831 | 121.1646 | 149.6723 | 182.5447 | 215.6918 | 252.7145 | 297.2438 | 341.2673 | 385.9103 | 434.3406 | 485.0831 | 516.678 | 562.5216 | 620.8479 | 674.5498 | 706.8924 | 747.9881 | 776.7774 | 797.7096 | 815.9 | 832.4211 | 842.6108 | 360.876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity cash flow | -2650 | -10.5622 | -24.0074 | -19.9746 | -25.3954 | -18.3302 | -21.0813 | -21.0813 | -23.4804 | -28.2785 | -27.6933 | -27.8611 | -30.1373 | -31.409 | -18.3613 | -27.6844 | -35.7509 | -32.3431 | -17.8044 | -23.4597 | -15.0264 | -9.6281 | -7.6836 | -6.4694 | -2.1565 | 0 | 124.8839 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 488.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Results | Current scenario: | Plan | [5 empty] | Tool delay activity: | A28
Measure | Excel | Tool: Plan | Tool: Flat10 | Tool: Delay60 | Tool (current scenario) | Difference | Tolerance | Result
Project duration (days) | 700 | 700 | 700 | 760 | 700 | 0 | 0.0001 | Pass
Construction cost incl. overheads (Rs lakh) | 3777.85 | 3777.85 | 4155.635 | 3804.85 | 3777.85 | 0 | 0.01 | Pass
Project NPV (Rs lakh) | 613.9657 | 613.9657 | 274.1776 | 510.0943 | 613.9657 | 0 | 0.01 | Pass
Equity NPV (Rs lakh) | 313.4826 | 313.4826 | -3.5417 | 200.2647 | 313.4826 | 0 | 0.01 | Pass
Project IRR (annual) | 0.19708 | 0.19708 | 0.1532 | 0.17987 | 0.19708 | 3.0809e-15 | 0.0001 | Pass
Equity IRR (annual) | 0.2062 | 0.2062 | 0.15948 | 0.18787 | 0.2062 | 0 | 0.0001 | Pass
Interest during construction (Rs lakh) | 84.1208 | 84.1208 | 109.5065 | 98.547 | 84.1208 | 0 | 0.01 | Pass
Total interest (Rs lakh) | 94.1761 | 94.1761 | 124.8892 | 109.1162 | 94.1761 | 0 | 0.01 | Pass
Peak debt (Rs lakh) | 842.6108 | 842.6108 | 1094.6675 | 873.237 | 842.6108 | 0 | 0.01 | Pass
Compensation to buyers (Rs lakh) | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | Pass
Undiscounted profit (Rs lakh) | 1951.15 | 1951.15 | 1573.365 | 1924.15 | 1951.15 | 0 | 0.01 | Pass
Horizon check | OK
Hand checks by calculator (fill yellow, do not copy from Excel)
Item | Excel | Your hand value | Difference
Equity cash flow in month 0 = -(land + approvals) | -2650
Overheads in month 1 = overheads per month | 12
Construction spend in month 1 (sum of cost x days in month 1 / duration) | 51.2
Presale collections in month 1 = presale share x revenue x month-1 share | 37.5453
Interest in month 3 = month-3 opening debt x monthly rate | 0.43436
Completion month = CEILING(project duration / 30) | 24